## 400kV 22-23 captlz
ANNEXURE-I
Scheme wise details of Actual Capitalisation for FY 2022-23 - 400KV SCHEMES
FY: 2022-23
Sl No | Name of the project | Investment approval date | Start Date |  | Completion Date (400kV works) |  | Approved cost as per Investment approval | Capitalization upto previous years (As per audited Financial Statements) (from FY 2016-17) | Capitalization claimed for the current year | Means of Finance ( % ) |  |  | Date of Capitalization | Addition to Transmission Network (only 400kV wing data ) |  |  | Reasons for cost overrun | Reasons for time overrun | Whether part or Full Capitalization | Physical Completion Certificate (400kV works only) | Financial Completion Certificate (400kV works only) | Electrical Inspector Certificate
|  |  | Schedule | Actual | Schedule | Actual | (Rs.in Crs) | (Rs.in Crs) | (Rs.in Crs) | Debt | Equity | Grants |  | Lines (CkM) | Capacity (MVA) | Bays (No.)
I | System Improvement Schemes
1 | Suryapet System Improvement Scheme (S-14-02) | 21.01.2015 (Revised) | Jul' 2013 | Sep' 2013 | Mar' 2017 | Apr' 2018 | 1738.03 | 649.735 | 0.305 |  |  | - | 23.06.2021 | 0 | 0 | 0 | NA | Delay in land acquistion and ROW issues | Part | 2019000039 2019000404 | 0202000198 0202001824 | Exempted by GoTS as per Energy (PR.II) Department, GO Ms No. 10 Date 09-05-2022
2 | 765kV Wardha-Hyderabad Link Transmission Scheme (S-15-13) | 19.12.2017 (revised) | Jan' 2016 | Feb' 2016 | Mar' 2019 | Feb' 2021 | 1178.97 | 927.17 | 1.142 |  |  | - | 30.07.2021 | 0 | 0 | 0 | NA | severe ROW in the vicinity of Hyderabad | Part | 2019000043 2020000523 2021000352 2021000353 | 0202000157 0202000332 0202100149 0202100148
3 | Rayadurg System Improvement Scheme (S-17-08) | 24.05.2018 | May' 2018 | Sep' 2018 | May' 2020 | April 2022 | 1786.4 | 1567.516 | 151.467 |  |  | - | 31.03.2023 | 0 | 0 | 0 | NA | Delayed due to RoW & COVID | Part | 2020000013 2022000085 2022000094 2022000104 2022000120 2022000129 2022000141 2022000151 2022000181 2023000684 2023000843 | 0202200511 2023000609 0202200163 0202200162 0202200172 0202200170 0202200167 0202200165 0202200168 2023000696 2023000714
4 | Reactor Scheme-III (S-19-02) | 09.12.2019 | Jan' 2020 | Jan' 2020 | Mar' 2023 | ongoing | 249.79 | 0 | 3.629 | - | - | 90% | 10.02.2023 | 0 | 0 | 1 | NA | - | Part | 2023001150 | 2023000712
5 | HVWS at 500MVA ICTs of 400kV Substations (S-21-05) | - | - | Dec' 2021 | - | May' 2022 | - | 0 | 0.805 | - | - | - | 27.06.2022 | 0 | 0 | 0 | NA | - | Part | 2023000444 2023000445 2023000448 | 2023000697 2023000618 2023000713
II | Augmentation Schemes
1 | 400kV Augmentation Scheme ( PTRs at Veltoor&Dichpally & Gajwel) (A-15-11& A-15-10) | 04.05.2017 (Revised) | Feb' 2016 | Feb' 2016 | Oct' 2017 | May' 2018 | 95.59 | 45.27 | 0.021 |  |  | - | 17.12.2020 | 0 | 0 | 0 | NA | upgradation to SAS | Part | 2019000044 | 0202000043
III | Power evacuation schemes
1 | Telangana STPP-I Power Evacuation Scheme (P-16-01) | 23.08.2017 | Apr' 2017 | Oct' 2017 | Apr' 2020 | Aug' 2021 | 1151.6 | 452.24 | 408.936 |  |  | - | 03.06.2021 | 0 | 0 | 0 | NA | Delayed due to RoW | Part | 2020000559 2023000472 2023000473 | 0202000364 2023000426 2023000425
2 | Yadradri Thermal Power Evacuation (P-19-02) | 27.01.2020 | Jan. 2020 | Dec' 2021 | May' 2022 | On-going | 2354.35 | 0 | 385.524 | - | - | - | 15.03.2023 | 43.24 | 1500 | 0 | NA | - | Part | 2023000422 2023001148 2023001134 2023001136 2023001151 | 2023000674 2023000663 2023000710 2023000711 2023000671
IV | DC Works | [18 empty] | - | -
1 | Diversion of 400kV Julurupadu-KTPS & KTPS-PGCIL Line) (D-20-03) | - | - | Aug' 2020 | - | Aug' 2021 | - | 21.88 | 0.0385 | - | - | - | 16.10.2021 | 0 | 0 | 0 | NA | - | - | 2022000288 2022000291 | 0202200154 0202200155
| Total | [5 empty] | 8554.73 | 3663.811 | 951.8675
NA:Not applicable as the investment is within the approved scheme cost.

## Schemes-22-23_Capitlza
ANNEXURE-I
Scheme wise details of Actual Capitalisation for FY 2022-23 - System Improvement Schemes
FY: 2022-23 | [24 empty] | (Figures in Rs Crore)
Sl. No. | Scheme ID | Name of the Project | Investment Approval Date | Start Date |  | Completion Date (Charging date) |  | Approved Cost as per Investment Approval | Capitalisation Upto Previous Year (n-1) (as per Audited Financial Statements) (up to 2022) (As per ARR) | Expenditure/ Capitalisation claimed for the Current year (2022-23) | Loan Source | Means of finance |  |  | Funding tie up | Loan Amount in Crores | Date of Capitalization | Addition to Transmission Network |  |  | Reasons for Low expenditure | Reasons for cost overrun | Reasons for time overrun | Whether Part Capitalization or Full Capitalisation | Physical Completion Certificate | Financial Completion Certificate | Electrical Inspector Certificate
|  |  |  | Schedule | Actual | Schedule | Actual | Rs. Crore | Rs. Crore | Rs. Crore |  | Debt | Equity | Grants (Rs. Crore) |  |  | Date | Lines (ckt km) | Capacity (MVA) | Bays (No.)
I |  | System Improvement schemes
1 | S-07-03 | Erragadda and O.U GIS &Cables scheme | 10.2009 | 29-09-2011 | 27.12.2011 | 31.03.2020 | E-27.05.2015 OU-14.10.2015 | 525.25 | 77 | 0.12 | PFC | 75% | 25% | 0 | PFC | 415 | __ | 44.8 | 960 | 6 |  | __ | __ | Full | 2019000183 2019000186 2019000196 2019000554 2020000328 | 202001409 202000318 202001636 202001435 202000378 | *
2 | - | Erection of various 220 kV & 132 kV GIS substations and connecting XLPE UG cable lines in and around Hyderabad metropolitan city with JBIC funding | [6 empty] | 89.33 | -1.17 | JICA | [6 empty] | 308 | 1621.5 | 42
| S-07-04.24 | A) Hayatnagar 220 kV SS |  | 2013-02-01 | 8.2.2013 | March'2017 | 03.05.2017 | 17.36 |  |  |  | 75% | 25% | 0 |  |  | __ |  |  | 0 |  | __ | __ | Full | 2019000506 | 202000615 | *
| S-07-04.23 | B) Imlibun 220 kV SS |  | 2013-06-01 | 10.5.2013 | March'2017 | 31.01.2017 02.02.2017 | 328.2 |  |  |  | 75% | 25% | 0 |  |  | __ |  |  | 0 |  | __ | __ | Full | 2019000200 | 0202001681 | *
| S-07-04.17 | C) Moosarambagh 132 kV SS |  | Mar-15 | 19.03.2015 | Mar'2017 | 26.10.2016 | 95 |  |  |  | 75% | 25% | 0 |  |  | __ |  |  | 0 |  | __ | __ | Full | 2021000096 | 202000078 | *
| S-07-04.14 | D) Balkampet 132 kV SS |  | Mar-15 | 16.11.2010 | Mar'2017 | 29.09.2016 | 77 |  |  |  | 75% | 25% | 0 |  |  | __ |  |  | 0 |  | __ | __ | Full | 2020000298 2019000506 2019000192 | 202000046 202000615 202001630 | *
| S-07-04-13 | E) Fever Hospital 132 kV SS |  | Nov-10 | 16.11.2010 | March'2017 | 02.01.2017 07.01.2017 | 69.15 |  |  |  | 75% | 25% | 0 |  |  | __ |  |  |  |  | __ | __ | Full | 2019000194 2020000294 2019000198 | 202001677 202001678 202001506 | *
| S-07-04.16 | F)NIMS |  | 24.09.2010 | 26.03.2015 | 16.02.2017 | 19.09.2018 | 85.36 |  |  |  | 75% | 25% | 0 |  |  | __ |  |  |  |  | __ | __ | Full | 2019000179 2019000181 | 202001706 202001509 | *
| S-07-04-15 | G) Pattigadda 132 kV SS |  | Apr-15 | 26.03.2015 | March'2017 | 29.12.2016 | 66.3 |  |  |  | 75% | 25% | 0 |  |  | __ |  |  |  |  | __ | __ | Full | 2019000184 2019000193 | 202001680 202001675 | *
3 | S-08-08 | 132/33 KV Narayanaguda GIS Sub-station | 13.10.2016 | 13.10.2016 | 31.05.2013 | 31.03.2020 | 08.12.2017 | 56.9 | 7.54 | 0.11 | PFC | 75% | 25% | 0 | PFC | 31.19 | __ | 3 | 47.5 | 2 |  | __ | __ | Full | 2019000195 | 202001682 | *
4 | S-08-11 | 132 kV SS Mamidipally & connected lines | 2016-08-01 | 31.10.2008 | 31.12.2008 | 31.03.2020 | 31.03.2016 20.08.2016 | 21.92 | 0.27 | -0.31 | PFC | 75% | 25% | 0 |  |  | __ | 20 | 81.5 | 4 |  | __ | __ | Full | 2019000522 2019000523 | 202000278 202000277 | *
5 | S-10-05 | 132/33kv SS Aitipamula | 15.09.2010 | 28.04.2010 | 20.10.2010 | 19.04.2012 | 21.03.2013 | 12.94 | 0.02 | 0.09 | UCO Bank | 75% | 25% | 0 |  |  | __ | 21 | 47.5 | 2 |  | __ | __ | Full | 2022000449 2023000522 | 202200455 2023000965 | *
6 | S-10-13 | Erection of 132/33KV SS LGM Pet | 08.08.2011 | 31.06.2011 | 16.09.2011 | 31.03.2020 | 18.08.2016 | 31.9 | 0.63 | 0.13 | UCO Bank | 75% | 25% | 0 |  |  | __ | 19.581 | 47.5 | 2 |  | __ | __ | Full | 2019000346 2019000397 2023000971 | 202000488 202000492 202000489 | *
7 | S-10-17 | 132/33 KV Substation at N V Puram in Khammam District | 06.05.2013 | 07.03.2014 | 17.08.2016 | 31.03.2020 | 24.06.2019 | 18.01 | 26.75 | 0 | REC | 75% | 25% | 0 | REC | 10.55 | __ | 10 | 32 | 2 |  | RC pile foundations casted in Godavari river. | __ | Full | 2020000530 2020000532, 2020000310, 2020000313 2020000333 | 202000034 202000036 202000037 202000033 202001647 | *
8 | S-10-20 | 220 kV Switching Station at Thimmajipeta & connected lines | 2017-12-01 | 05.07.2013 | 30.09.2013 | 31.03.2020 | 07.06.2017 | 29.32 | 2.02 | 0 | PFC | 75% | 25% | 0 |  |  | __ | 94 | 0 | 8 |  | __ | __ | Full | 2019000486 2019000487 2019000492 20190000488 2021000184 | 202100291 202000833 202100290 202000232 202100380 | *
9 | S-10-22 | Erection of 33KV features at Vikarabad | 23.06.2010 | 23.06.2010 | 04.12.2012 | 31.03.2020 | 01.03.2016 | 4.47 | 0.08 | 0.02 |  | 75% | 25% | 0 |  |  | __ | -- | 32 | -- |  | __ | __ | Full | 2019000416 | 202000496 | *
10 | S-10-23 | 132/33 KVSS at water works in Karimnagar District | 2013 | 10.05.2013 | 12.07.2013 | 11.04.2014 | 06.09.2014 | 47.5 | 0 | 0.04 | Oriental Bank of Commerce | 75% | 25% | 0 |  |  | __ | 6.5 | 47.5 | 1 |  | __ | __ | Full | 2023000746 | 202001260 202001262 | *
11 | S-11-01 | 132/33 kv ss At Gudur | 22.12.11 | 16.06.2015 | 07.07.2015 | 06.04.2016 | 28.07.2016 | 13.29 | 0.13 | 0.03 | PFC | 75% | 25% | 0 |  |  | __ | 20 | 47.5 | 2 |  | __ | __ | Full | 2019000407 2023001050 2023001049 2019000406 | 202001471 2023000351 2023000352 202000216 | *
12 | S-11-07 | 132/33KVSS- GANGANPALLI (ALWALPAD)LINES | 27.04.2011 | 27.04.2011 | 26.10.2015 | 31.03.2020 | 23.08.2018 | 14.7 | 0.79 | 0 | PFC | 75% | 25% | 0 |  |  | __ | 14 | 47.5 | 1 |  | __ | __ | Full | 2019000074 2019000073 2019000071 2019000818 | 202000845 202000846 202100293 202000155 | *
13 | S-11-11 | 132KV parigi dmsagar line | 15.09.2018 | 18.04.2018 | 13.12.2016 | 31.03.2020 | work in progress (expected -31.03.2024) | 30.8 | 1.23 | 0.16 | REC | 75% | 25% | 0 |  |  | __ | 70 | -- | 4 |  | __ | __ | Full | NO | NO | *
14 | S-11-12 | 132/33 KV SS at Dornakal in Warangal District | 2014 | 2014-05-01 | 10.06.2015 | 2015-05-01 | 22.07.2016 | 17.32 | 0.01 | 0 | REC | 75% | 25% | 0 |  |  | __ | 20 | 47.5 | 2 |  | __ | __ | Full | 2019000274 2019000275 2019000276 2019000740 | 202001633 202001631 202000264 202000267 | *
15 | S-11-13 | 132 kV SS Doulthabad & connected lines | APT/TS/132kV SS-Doulthabad/F-INVST-38/2013 | 21.06.2013 | 21.6.2013 | 2014-03-01 | 10.02.2017 | 21.8 | 0.018 | 1.1 | REC | 75% | 25% | 0 |  |  | __ | 32.7 | 47.5 | 2 |  | __ | __ | Full | 2022000425 2023000828 2023000784 | 202001236 202001234 202001235 | *
16 | S-11-16 | 220/132/33 kV substation at Huzurnagar in Nalgonda District | 02.04.2013 | 21.06.2013 | 18.02.2016 | 31.03.2020 | 10.12.2018 | 52.49 | 65.36 | 0.02 | PFC | 75% | 25% | 0 | PFC | 62.65 | __ | 100 | 263 | 10 |  | __ | __ | Full | 2020000545 2020000546 2020000547 2020000548 2019000924 2019000925 2019000926 2019000810 2019000812 2019000927 2019000811 | 202001036 202001040 202001019 202001039 202001037 202001016 202001013 2020010130 202001010 202001034 202001041 | *
17 | S-11-27 | 132/33 kV Substation at Nellikuduru in Warangal district along with connected 132 kV & 33 kV lines | 24.05.2013 | 06.04.2011 | 21.07.2016 | 31.03.2020 | 04.01.2018 | 21.21 | 0.96 | 0.02 | REC | 75% | 25% | 0 | REC | 17.847 | __ | 30 | 47.5 | 2 |  | __ | __ | Full | 2019000295 2019000296 2019000297 | 0202000289 0202000288 0202001634 | *
18 | S-11-28 | 132kV SS Nimmapally & connected lines | APT/TS/132 kV SS -Nimmapalli/ F-INVST -06/2014 | 2015-04-01 | 23.3.2018 | 2016-04-01 | work in progres | 25.35 | 15.9 | 0.19 | REC | 75% | 25% | 0 |  |  | __ | 21 | 32 | 2 |  | __ | __ | Full | 2021000275 2023000534 2023000535 | 202200384 202100077 202001277 | *
19 | S-11-30 | erection of 220/132 kV substation at Parigi in Ranga Reddy district | 11.05.2012 | 09.08.2011 | 19.10.2013 | 31.03.2020 | 04.03.2016 | 60.35 | 1.24 | 0.04 | REC | 75% | 25% | 0 | REC | 54.3164 | __ | 110 | 200 | 8 |  | __ | __ | Full | 2019000418, 2019000419, 2019000420 2019000412 | 202000500 202000501 202000502 202000503 | *
20 | S-11-35 | Shifting of 132 kV SS at Wadapally by erection of 132 kV SS at Wadapally (New) in place of existing Wadapally SS and 132 kV LILO arrangements to 132/33 kV SS Wadapally (NEW) in Nalgonda district. | TOO / CE/Trans/ MS No.106 Dated 17.06.2015 (As per APREC Proceedings No: 725/2013, dt.06.05.2013) | 22.04.2013 | 22.4.2013 | 2014-01-01 | 26.11.2016 | 4.99 | 0.63 | 0.24 | REC | 75% | 25% | 0 |  |  | __ | - | 47.5 | - |  | __ | __ | Full | 2021000070 2021000071 | 202001056 202001057 | *
21 | S-12-05 | erection of 33 kV features at Jankampet 132/11 kV Lift irrigation substation in Nizamabad district | 20.12.2012 | 20.09.2016 | 01.11.2016 | 31.03.2020 | 16.02.2018 | 4.18 | 0.29 | 0.17 | REC | 75% | 25% | 0 |  |  | __ | 0 | 32 | 0 |  | __ | __ | Full | 2019000254 2019000255 2019000140 2019000141 | 202000041 202000355 202001053 202001139 | *
22 | S-12-06 | Erection of 2nd circuit stringing on existing 220 kV DC/SC line from 220 kV Ramagundam Sub-Station to 220 kV Mandamarri (Bellampally) Sub-Station | 31.01.2013 | 28.11.2012 | 06.10.2012 | 31.03.2020 | 20.10.2015 | 10.67 | 0.2 | 0.01 | REC | 75% | 25% | 0 |  |  | __ | 34 | -- | 2 |  | __ | __ | Full |  | 202001290 202001292 202001722 | *
23 | S-12-09 | 132 kV DC/SC line from 220/132 kV substation Yeddumailaram to 132/33 kV SS Pashamailaram –Accorded. | 2013 | 27.12.2020 | 27.12.2020 | 26.04.2021 | 27.09.2022 | 9.31 | - | 10.51 | NABARD | 75% | 25% | 0 |  |  | __ | 7 | -- | 2 |  | __ | __ | Full | 2023001117 2023001118 2023001114 | 2023000470 2023000471 2023000472 | *
24 | S-12-13 | of 132/33 kV Substation at Palakurthy in Warangal district along with connected 132 kV & 33 kV lines |  | 09.11.2015 | 09.11.2015 | 09.08.2016 | 29.07.2016 | 19.63 | - | 0.09 |  | 75% | 25% | 0 |  |  | __ | 29 | 32 | 1 |  | __ | __ | Full | 2019000689 2019000690 2019000691 2023000999 2023001000 202300998 | 202000307 202000308 202000309 2023000317 2023000318 2023000319 | *
25 | S-13-02 | 220/132 kV SS at Ayyagaripally in Mahaboobabad in Warangal district | 09.05.2016 | 05.01.2016 | 02.03.2016 | 31.03.2020 | 29.01.2018 | 78.33 | -0.29 | 0.26 | REC | 75% | 25% | 0 |  |  | __ | 94 | 200 | 9 |  | __ | __ | Full | 2019000282 2019000305 2019000306 2019000308 2019000519 2019000737 2020000597 2019000739 | 202001637 202000310 202001635 202000320 202000317 202000316 202000319 202000315 | *
26 | S-13-03 | 220/132/33KV SS at Bonguloor in RR District | 28.02.2014 | 30.05.2014 | 05.09.2013 | 31.03.2020 | 23.05.2020 | 63.4 | 48.06 | 0.15 | NABARD | 75% | 25% | 0 | NABARD | 36.75 | __ | 20 | 300 | 6 |  | __ | ROW issues | Full | 2019000540 2019000541 2020000357 2021000144 2022000053 | 202000284 202200054 202100152 202000619 202000622 | *
27 | S-13-06 | 132/33 kV Sub-Station at Dommarapochampally in Rangareddy district with connected 132 KV lines | 03.09.2014 | 15.05.2018 | 24.12.2016 | 31.03.2020 | 16.07.2018 | 36.32 | 22.29 | 0 | REC | 75% | 25% | 0 |  |  | __ | 7.2 | 63 | 2 |  | __ | __ | Full | 2019000392 2019000394 | 202000504 202000505
28 | S-13-10 | 132/33kV SS Kachapur & connected lines | 26.2.2016 | 07.10.2015 | 22.09.2015 | 31.03.2020 | 04.05.2018 | 21.53 | 12.82 | 0.47 | REC | 75% | 25% | 0 | REC | 21.53 | __ | 37.5 | 48 | 2 |  | __ | __ | Full | 2023000749 2023000750 2023000751 | 202001280 202001281 202001283 202001286 202001289 202001288 | *
29 | S-13-14 | 220/132 kV SS at Sircilla in Karimnagar District | 08.10.2015 | 03.08.2015 | 22.12.2015 | 31.03.2020 | 15.12.2016 | 87.3 | 4.49 | 0.13 | REC | 75% | 25% | 0 |  |  | __ | 134 | 300 | 8 |  | __ | __ | Full | 2023001099 2023001100 | 202001293 202001298 202001300 202001301 202001304 | *
30 | S-14-12 | 132 KV substation Khaithalapur aong with connected lines | 01.09.2015 | 10.09.2014 | 04.07.2016 | 31.08.2020 | 27.08.2019 | 66.04 | 55.51 | 0.05 | REC | 75% | 25% | 0 | REC | 59.09 | __ | 15 | 63 | 4 |  | __ | __ | Full | 2020000006, 2020000007 2020000008 2021000240 2021000242 | 202000507 202000508 202000509 202100302 202100303 | *
31 | S-15-01 | Providing second source of supply to 132/33 kV Sub-Station, Lalgadi Malakpet in Shameerpet Mandal of Ranga Reddy District | 06.05.2013 | 19.08.2015 | 20.10.2015 | 31.03.2020 | 18.10.2019 | 7.31 | 10.13 | 0.04 | PFC | 75% | 25% | 0 | PFC | 6.2 | __ | 16 | - | 2 |  | Additional towers erected due to ROW | Severe ROW issues. Some of the locations got completed with police protection | Full | 2020000010, 2020000009 | 202001129 202001134 | *
32 | S-15-02 | Up-Gradation of 132/33 kV SS Aswaraopet to 220/132 kV SS | 05.10.2015 | 24.08.2015 | 18.01.2017 | 31.03.2020 | 28.04.2018 | 52.82 | 39.96 | 0.23 | PFC | 75% | 25% | 0 | PFC | 42.55 | __ | 100 | 200 | 8 |  | __ | __ | Full | 2020000136, 2019000093& 2019000613 2020000522 | 202000027 202000035 202001650 202000023 | *
33 | S-15-03 | 132/33 kV Substation at Chandulapur Village of Chinnakodur Mandal in Medak District along with connected lines | 04.02.2015. | 04.02.2015. | 27.04.2015 | 31.03.2020 | 06.10.2017 | 18.25 | 0.38 | 0 | REC | 75% | 25% | 0 | REC | 30.5565 | __ | 8 | 63 | 4 |  | __ | __ | Full | 2019000605 2019000343 | 202000584 202000585 | *
34 | S-15-11 | 220 kV 2nd circuit stringing on 220 kV RSS - Jagityal and 220 kV RSS - Nirmal | 17.12.2015 | 06.11.2017 | 19.11.2016 | 31.03.2020 | N-30.12.2016 J-02.11.2016 | 46.4 | 18.86 | 0.01 | PFC | 75% | 25% | 0 |  |  | __ | 208 | __ | 4 |  | __ | __ | Full | 2023001162 2023000538 | 202001323 202001326 202001334 202001338 202001345 | *
35 | S-15-29 | 132KV DC line from 220KV HSBD. LISS, BAY | 27.07.2015 | 27.07.2015 | 11.11.2016 | 31.03.2020 | 29.12.2017 | 18 | 2.17 | 0.53 | REC | 75% | 25% | 0 |  |  | __ | 17 | 100 | 6 |  | __ | __ | Full | 2023000538 2023000539 | 202001357 202001353 202001356 202001359 202001361 | *
36 | S-15-31 | erection of 2nd circuit from 220kV Shivarampally SS to 132kV Asifnagar SS for providing 2nd source of supply to 132kV Asifnagar substation | 05.10.2015 | 25.03.2015 | 16.02.2018 | 31.03.2020 | 31.05.2019 | 45.97 | 35.97 | -0.12 | REC | 75% | 25% | 0 | REC | 41.3635 | __ | 4 | -- | 2 |  | __ | __ | Full | 2020000354 2019000006 2019000005 2020000356 | 202000287 202000290 202000291 202000292 | *
37 | S-15-32 | Erection of 220/132/33 kV SS at Pedagopati in Khammam district | 22.03.2016 | 07.11.2015 | 27.02.2017 | 31.03.2020 | 01.12.2018 | 124.44 | 45.51 | 0.04 | REC | 75% | 25% | 0 | REC | 121.2483 | __ | 220 | 263 | 4 |  | __ | __ | Full | 2019000088 2019000103 | 202000025 202000029 | *
38 | S-15-33 | 132/33 kV SS at Sarangapur in Adilabad District | 06.05.2013 | 21-12-2015 | 04.04.2018 | 31.01.2020 | 11.12.2019 | 19.93 | 15.09 | 1.61 | REC | 75% | 25% | 0 | REC | 17.66 | __ | 28 | 48 | 2 |  | __ | __ | Full | 2020000621 2020000620 | 202001545 202001544 | *
39 | S-15-34 | 220 kV DC line on Galvanised Towers with Moose ACSR from 400/220/132 kV SS Gajwel to 220/132 kv SS Siddipet | 2.07.2017 | 4.12.2017 | 4.12.2017 | 3.12.2018 | 19.11.2022 | 63.28 | - | 53.73 | REC | 75% | 25% | 0 |  |  | __ | 80 | __ | 4 |  | __ | __ | Full | 2023001110 2023001111 2023001112 | 2023000465 2023000467 2023000468 | *
40 | S-15-37 | 132 kV line from 220 kV Jurala Sub-Station to 132 kV Ieeza Sub-Station | 06.05.2013 | 29.07.2015 | 12.03.2018 | 11.03.2019 | 07.08.2019 | 16.54 | 16.64 | 0 | REC | 75% | 25% | 0 |  |  | __ | 35 | __ | 2 |  | __ | __ | Full | 2020000637 2020000640 2020000641 | 202000206 202000212 202000213 | *
41 | S-16-08 | 33 kV Features at existing 220/11 kV LI Sub-Station, Bheemghanpur Warangal District. | 25.04.2016 | 25.04.2016 | 05.05.2017 | 31.03.2020 | 08.07.2020 | 5.73 | 15.72 | 0.56 | PFC | 75% | 25% | 0 | PFC | 16.31 | __ | -- | 50 | -- |  | __ | Delay in PTR supply | Full | 2020000505 | 202100143 | *
42 | S-16-11 | 132/33 kV Substation at Bachannapet in Warangal District | 25.05.2016 | 25.05.2016 | 06.06.2018 | 31.03.2020 | 31.10.2019 | 19.38 | 18.09 | 0.1 | PFC | 75% | 25% | 0 | PFC | 16.71 | __ | 18 | 48 | 2 |  | __ | __ | Full | 2020000506 2020000507 | 202000017 202000368 | *
43 | S-16-12 | 132/33 kV Substation at Kotagiri in Nizamabad District | 30.06.2016 | 28.06.2019 | 28.06.2019 | 31.03.2020 | 11.05.2022 | 15.05 | __ | 16.95 | PFC | 75% | 25% | 0 |  |  | __ | 12 | 48 | 1 |  | __ | __ | Full | 2023000284 2023000283 2023000282 | 2023000156 2023000157 2023000158 | *
44 | S-17-01 | Erection of 220/33 kV Sub-Station at Chanchalguda | CRN TS/TST/220/33 KV, GIS, Chanchaguda/Invest.Approval No.7/17-2017-18 | 27.02.2017 | 28.02.2018 | 31.03.2021 | 20.03.2021 | 89.12 | 77.57 | -0.02 | REC | 75% | 25% | 0 |  |  | __ | 2 | 150 | -- |  | __ | __ | Full | 2021000035 | 202100160 | *
45 | S-17-03 | 132/33 kV Sub-Station at Moulali ZTS in Medchal-Malkajgiri District | 2017-18 | 04.05.2019 | 04.05.2019 | 03.02.2020 | 30.07.2021 | 49.78 | __ | 43.85 | REC | 75% | 25% | 0 |  |  | __ | 7 | 100 | 2 |  | __ | __ | Full | 2022000496 2022000497 2022000498 | 2023000065 2023000066 2023000067 | *
46 | S-17-04 | 132/33kV SS Gachibowli in Ranga Reddy district | 27.02.2017 | 27.02.2017 | 11.06.2019 | 10.12.2020 | 22.09.2021 | 18.73 | 20.42 | 0.69 | REC | 75% | 25% | 0 |  |  | __ | 2 | 160 | -- |  | __ | __ | Full | 2022000374 2022000375 2022000376 | 202200406 202200407 202200408 | *
47 | S-17-09 | 220/132/33 kV Substation at Toopran(meenaji pet) in Medak District along with connected lines | 09.04.2015 | 27.05.2017 | 23.12.2016 | 31.03.2021 | 06.02.2020 | 76.78 | 52.46 | 0.17 | REC | 75% | 25% | 0 | REC | 68.43 | __ | 110 | 263 | 12 |  | __ | __ | Full | 2020000000 2020000001 | 202000576 202000577 | *
48 | S-17-13 | erection of 132/33 kV Sub-Station at Yadagirigutta Temple with connected line Town of Yadadri (erstwhile Nalgonda) .District | 09.05.2017 | 09.05.2017 | 16.07.2018 | 31.03.2020 | 11.12.2019 | 15.06 | 17.11 | 0.04 | PFC | 75% | 25% | 0 | PFC | 13.16 | __ | 4 | 63 | 2 |  | __ | __ | Full | 2019000921 2019000922 | 202000883 202000886 | *
49 | S-17-14 | 33kV features at 220kV SS mahabubabad | 16.11.2017 | 16.11.2017 | 20.02.2020 | 19.08.2021 | 26.05.2021 | 8.54 | 2.88 | -0.01 | REC | 75% | 25% | 0 |  |  | __ | -- | 32 | -- |  | __ | __ | Full | 2021000061 | 202200369 | *
50 | S-17-15 | Erection of 132/33 kV Sub-Station at Chinna Shankarampet in Medak District | 06.05.2013 | 19.08.2017 | 01.04.2018 | 31.03.2021 | 23.01.2021 | 16 | 9.17 | 0.23 | REC | 75% | 25% | 0 |  |  | __ | 12 | 32 | -- |  | __ | __ | Full | 2021000138 2021000140 | 202100228 202100229 | *
51 | S-17-16 | 132kv 2nd Circuit stringing from waddekothapally to peddanagaram | 09.10.2017 | 09.10.2017 | 22.02.2020 | 21.08.2021 | 06.11.2021 | 7.02 | 3.21 | 0.09 | REC | 75% | 25% | 0 |  |  | __ | 30 | -- | 2 |  | __ | __ | Full | 2022000382 2022000383 2022000384 | 202200374 202200376 202200375 | *
52 | S-17-18 | feeding 132/33 kV SS Ghanpur through Ring Mains | 09.05.2017 | 09.05.2017 | 23.10.2018 | 31.03.2020 | 26.06.2019 | 5.8 | 8.01 | 0.38 | PFC | 75% | 25% | 0 | PFC | 5.07 | __ | 4 | -- | 8 |  | __ | __ | Full | 2020000516 2020000517 2023001048 2023001047 | 202000372 202000373 2023000354 2023000355 | *
53 | S-17-20 | 132 KV DC/SC line from 220KVSS Chegur (Kothur) to existing 132KVSS Kothur | 30-11-2017 | 30-11-2017 | 12.03.2019 | 31.03.2020 | 24.07.2020 | 5.68 | 10.37 | 0.11 | REC | 75% | 25% | 0 | REC | 5.11 | __ | 6 | -- | 2 |  | Narrow based towers erected due to RoW | RoW | Full | 2021000366 2021000367 | 202100306 202100305 | *
54 | S-17-23 | 132 kV features at 220 kV Thimmajipet Switching Station in Mahaboobnagar District and extending connectivity to 132 kV Jadcherla Sub-Station from Thimmajipet | 2017-12-01 | 07.03.2020 | 07.03.2020 | 06.12.2020 | 22.07.2022 | 29.32 | __ | 7.34 | REC | 75% | 25% | 0 |  |  | __ | 36 | -- | 2 |  | __ | __ | Full | 2023001163 | 2023000825 | *
55 | S-18-02 | 220/132 kV Sub-Station at Ammavaripet, Kazipet (M) in Warangal Urban District and connected lines and bays along with downstream works | 10.08.2018 | 26.02.2021 | 26.02.2021 | 19.05.2022 | 31.03.2024(expected) | 111.84 | __ | 17.28 | PFC | 75% | 25% | 0 |  |  | __ | 133.55 | -- | 4 |  | __ | __ | Full | 2023000369 2023000306 2023000368 2023000303 | 2023000320 2023000321 2023000322 2023000323 | *
56 | S-18-04 | 132/33kV SS Nagaram in Suryapet District | 12.12.2018 | 30.08.2018 | 27.10.2020 | 26.04.2022 | 27.03.2022 | 33.97 | 10.91 | 0.92 | PFC | 75% | 25% | 0 |  |  | __ | 32 | 47.5 | -- |  | __ | __ | Full | 2022000074 2022000076 | 202200171 202200173 | *
57 | S-19-03 | 132/33 KV Sub-Station at Patancheru in Sangareddy District | 22.11.2019 | 06.07.2020 | 06.07.2020 | 5.11.2021 | 30.11.2022 | 23.64 | 0 | 14.13 | REC | 75% | 25% | 0 |  |  | __ | 4.7 | 63 | -- |  | __ | __ | Full | 2023001114 2023001115 | 2023000466 2023000469 | *
58 | S-19-05 | 132/33 kV Gas Insulated Sub-Station (GIS) at Manikonda in Ranga Reddy District along with connected line with 132 KV XLPE UG cable | 29.12.2019 | 18.03.2021 | 18.03.2021 | 17.03.2022 | 15.09.2022 | 66.56 | 0 | 85.55 | REC | 75% | 25% | 0 |  |  | __ | __ | 160 | -- |  | __ | __ | Full | 202300002 202300003 202300004 | 2023000277 2023000278 2023000279 | *
59 | S-21-01 | 132/33kV SS Pasra at mulugu District | 30.06.2021 | 30.06.2021 | 25.10.2021 | 31.12.2022 | 31.01.2022 | 12.8 | 6.23 | 1.73 | Transco funds | 75% | 25% | 0 |  |  | __ | 3.8 | 32 | -- |  | __ | __ | Full | 2022000264 2022000381 | 202200373 202200274 | *
60 | P-19-01 | 400/220 kV, 1X315 MVA ICT at Bhadradri Thermal Power Station (BTPS) switch yard, Manuguru, TSGENCO and erection of 220 KV DC line from 220/132/33 KV Manuguru SS to 400 KV BTPS switch yard | 22.11.2019 | 08.07.2019 | 31.09.2019 | 31.03.2021 | 12.03.2021 | 66.56 | 26.03 | 0.56 | REC | 75% | 25% | 0 |  |  | __ | 46 | 315 | 4 |  | __ | __ | Full | 2021000006 2021000007 | 202100047 202100080 | *
61 | S-02-03 | EREC 132KV BAY AT NIRMAL-KHANPUR FEEDER | [7 empty] | 0.33
62 | P-12-02 | Nirmal Power Transmission Scheme | [7 empty] | 3.95
63 | P-15-01 | Dindi System Improvement Scheme | [7 empty] | 0.97
64 | P-15-03 | Bhadradri Thermal Power Transmission scheme | [7 empty] | 25.74
65 | P-15-04 | KTPS (Stage-VII-1X800MW) -Scheme | [7 empty] | 0.32
66 | P-16-01 | Telangana STPP-I( 2 X 800MW) Power Evacuation scheme | [7 empty] | 0
| P-19-02 | Yadadri Thermal Power (5X 800MW) evacuation scheme | [7 empty] | 66.31
357.01
*Note: Electrical Inspector Certification is exempted as per the G.O. Ms.No.10, Dt:09.05.2022

## Schemes-22-23_Capitlz DCworks
ANNEXURE-I
Scheme wise details of Actual Capitalisation for FY 2022-23 -Depository contribution works (DC Works)
FY: 2022-23 | [24 empty] | (Figures in Rs Crore)
Sl. No. | Scheme ID-SAP | Name of the Project | Investment Approval Date | Start Date |  | Completion Date |  | Approved Cost as per Investment Approval/ Scheme cost | Capitalisation Upto Previous Year (n-1) (as per Audited Financial Statements) (up to 2021) (As per ARR) | Capitalisation claimed for the Current year (2022-23) | Loan Source | Means of finance |  |  | Funding tie up | Loan Amount in Crores | Date of Capitalization | Addition to Transmission Network |  |  | Reasons for Low expenditure | Reasons for cost overrun | Reasons for time overrun | Whether Part Capitalization or Full Capitalisation | Physical Completion Certificate | Financial Completion Certificate | Electrical Inspector Certificate
|  |  |  | Schedule | Actual | Schedule | Actual | Rs. Crore | Rs. Crore | Rs. Crore |  | Debt (Rs. Crore) | Equity (Rs. Crore) | Grants (Rs. Crore) |  |  | Date | Lines (ckt km) | Capacity (MVA) | Bays (No.)
|  | Brought Forward (BF) | [7 empty] | 357.01
1 | D-13-02 | SWICHYARDSTATION NTPC SOLAR EVACUATION |  | 01.09.2012 | 07.08.2014 | 13.05.2015 | 05.05.2016 | 10.17 | 0.14 | 0.06 | Consumer contribution
2 | D-15-08 | 220KV YELLURU & GOURIDEVIPALLY SS |  | 24.02.2016 | 24.02.2016 | 23.11.2016 | Y-03.11.17 G-08.12.17 |  | 4.34 | -0.02 | Consumer contribution
3 | D-16-08 | 132KV DC Mandamarry-Bellampally line from Loc.No.132 to 136 and Loc No. 141 to 145 for a length of 5.938 |  | 28.10.2025 | 28.10.2015 | 27.02.2016 | 26.02.2017 | 8.51 | - | -0.15 | Consumer contribution
4 | D-16-14 | Providing open Access metering systemsViz., Main,Check and Stand by Metering to the existing 132KV HT Cinsumer. M/s CCI at 220/132/33KV SS Tandur(TSTRANSCO-Executing) |  | 21.06.2018 | 21.06.2018 | 30.08.2019 | 11.08.2020 | 1.78 | 1.17 | 0.05 | Consumer contribution
5 | D-17-04 | 132KV DC/SC line from Gangadhara LIS to proposed 132/25 KV Kothapally Railway Traction Substation |  | 06.04.2018 | 06.04.2018 | 05.10.2018 | 09.02.2019 | 1291.31 | 0.56 | -0.01 | Consumer contribution
6 | D-17-11 | 132 KV lne 4m Miryalaguda to RTSS and Ramannapet to Ramannapet |  | 02.06.2018 (Miryalaguda line) | 02.06.2018 (Miryalaguda line) | 01.12.2018 (Miryalaguda line) | 27.09.2019 | 8.374 | 5.54 | 0.15 | Consumer contribution | [7 empty] | - | -
|  |  |  | 02.06.2018 (Ramannapet line) | 02.06.2018 (Ramannapet line) | 01.12.2018 (Ramannapetline) | 06.12.2018 | 7.0374 |  |  | Consumer contribution | [7 empty] | - | -
7 | D-18-10 | Divrsn of Gajwl-Kndapka etc Komrveli mal |  | 26.09.2018 | 26.09.2018 | 25.03.2019 | 09.12.2020 | 17.599 | 12.14 | -0.02 | Consumer contribution | [6 empty] | - | - | -
8 | D-18-12 | Extnsion of power supply to RTSS Manoharabad |  | 15.04.2019 | 15.04.2019 | 14.10.2019 | 25.11.2020 | 1.05 | 7.66 | 0.28 | Consumer contribution | [6 empty] | - | - | -
9 | D-18-13 | pwr sply 2 132KV RTSS Divitipally(RVNL) |  | PO.Issued Dt:10.01.2019 DoH Bay-21.01.2020 Line- 29.04.2019 Metering Bay 28.09.2021 | - | Bay-20.10.2020 Line-28.01.2020 Metering Bay- 27.06.2022 | 22.07.2022 | 9.76 | - | 6.58 | Consumer contribution
10 | D-18-15 | Extn of 132KV lne 4 kamrdy 2 tlamdla Ra |  | 24.03.2021 | 24.03.2021 | 23.12.2021 | 31.03.2023 | 14.55 | - | 7.48 | Consumer contribution
11 | D-18-17 | Erection of metering bay at 132KV Parigi SS and Laying of 132KV XLPE UG Cable between existing TSTRANSCO 132KV Bus to wind power 132KV Bus including Outdoor Tewrminations (DC-Supervision work) |  | DC_Supevision work |  |  | 24.03.2016 | 0.41 |  | -0.05 | Consumer contribution
12 | D-18-21 | 220KV DC line Dindi-Bonguluru |  | 07.05.2019 | 07.05.2019 | 06.11.2019 | 05.02.2020 | 7.91 | 4.57 | 0.08 | Consumer contribution | [6 empty] | - | - | -
13 | D-18-22 | Shift of 132KV Makthal-Krishna RTSS DC line between Loc. No.29A to 29B Near Maganooru Village in Mahaboobnagar District |  | 07.03.2019 | 07.03.2019 | 28.07.2019 | 23.12.2019 | 4.14 | 1.6 | 0.01 | Consumer contribution
14 | D-19-02 | Shift Gachibowli-Madapur-I&II DC lines crossing at Botonical garden junction hyderabad(TSTRANSCO-Executing) |  | 29.11.2019 | 29.11.2019 | 28.05.2020 | 28.06.2022 | 13.02 | - | 4.77 | Consumer contribution
15 | D-19-03 | Sft 220KV Gachibowli -S.nagar-Erragadda line |  | 29.11.2019 | 29.11.2019 | 28.05.2020 | 31.08.2021 | 19.61 | 9.16 | -1.03 | Consumer contribution | [6 empty] | - | - | -
16 | D-19-04 | Shifting 132kV lines from Road number 45 Durgam Cheruvu |  | 30.01.2019 | 22.03.2019 | 21.09.2019 | 13.06.2020 | 18.8 | 8.92 | 0.46 | Consumer contribution | [6 empty] | - | - | -
17 | D-20-06 | 132KV DC/Sc line 4m 132/33kv ss morthad |  | 15.04.2021 | 15.04.2021 | 14.01.2021 | 29.04.2022 | 5.81 | - | 1.02 | Consumer contribution
18 | D-20-07 | Modifictn ofbpower lne of Bhadrachalam Sattupally Railway track in bhadradrikothagudem |  | 20.10.2020 | 20.10.2020 | 19.04.2021 | 28.07.2021 | 61.16 |  | 14.51 | Consumer contribution
19 | D-20-09 | Gajwel-Chegunta for manoharabad to Kothapally |  | 29.01.2021 | 29.01.2021 | 23.04.2021 | 03.07.2021 | 2.69 | 1.54 | 0.11 | Consumer contribution | [6 empty] | - | - | -
20 | D-21-18 | Shifting of 220KV Miryalaguda-KTPS SC line |  | __ | __ | __ | __ | __ | 0.46 | 0.35 | Consumer contribution | [6 empty] | - | - | -
21 | D-21-24 | 132kV DC.SC line Ganganpally-RTSS Pandur |  | P.O.:11.10.2021 DOH: Bays and 132KV Line 29.09.2021. 2nd Ckt: profile:11.10.2021 | __ | 10.04.2022 | 132kV Line: 28.10.2022 2nd Ckt 10.04.2023 | 14.55 | - | 2.27 | Consumer contribution
22 | D-21-37 | Shifting of 1No.220KV DC line of Regumanugadda-Wanaparthy & Singotam of length 2KM |  | 22.12.2021 | 22.12.2021 | 21.09.2022 | 19.08.2022 & 26.08.2022 | 9.56 | - | 7.35 | Consumer contribution
23 | D-21-44 | M/s. Mahalakshmi Profiles Pvt Ltd- Medak |  | Supervision work |  |  |  | 1.26 | - | 0.28 | Consumer contribution
24 | D-22-18 | Erection of (i) 1No. 132KV bay at 220/132KV Chandanvally SS (M/s.TSIIC) |  | Supervision work |  |  | 18.01.2023 | 2.49 |  | 0.28 | Consumer contribution
25 | L-12-02 | 2Nos 132kV Bays at Jaipur for SCCL |  | __ | __ | __ | __ | __ | 0.25 | 0.07 | Consumer contribution | [6 empty] | - | - | -
26 | D-20-10 | Extn of cntrl room bal works at 20KV SS |  | __ | __ | __ | 31.03.2024 |  | - | 0.53 | Consumer contribution
27 | D-21-30 | Industrial park at Chandanvally(V) | [7 empty] | 37.84 | Consumer contribution
| Total | [8 empty] | 440.26

## Schemes-22-23_Capitlz Non Plan
ANNEXURE-I
Scheme wise detail of Actual Capitalisation for FY 2022-23-Non Plan Capital Works
FY: 2022-23 | [24 empty] | (Figures in Rs Crore)
Sl. No. | Scheme ID-SAP | Name of the Project | Investment Approval Date | Start Date |  | Completion Date |  | Approved Cost as per Investment Approval/ Scheme cost | Capitalisation Upto Previous Year (n-1) (as per Audited Financial Statements) (up to 2021) (As per ARR) | Capitalisation claimed for the Current year (2021-22) | Loan Source | Means of finance |  |  | Funding tie up | Loan Amount in Crores | Date of Capitalization | Addition to Transmission Network |  |  | Reasons for Low expenditure | Reasons for cost overrun | Reasons for time overrun | Whether Part Capitalization or Full Capitalisation | Physical Completion Certificate | Financial Completion Certificate | Electrical Inspector Certificate
|  |  |  | Schedule | Actual | Schedule | Actual | Rs. Crore | Rs. Crore | Rs. Crore |  | Debt (Rs. Crore) | Equity (Rs. Crore) | Grants (Rs. Crore) |  |  | Date | Lines (ckt km) | Capacity (MVA) | Bays (No.)
|  | Brought Forword (BF) | [7 empty] | 440.26
1 | N-17-01 | Other Non Planned Project Str 2017-18 | [7 empty] | 0.01
2 | N-18-01 | Other Non Planned Project Str 2018-19 | [7 empty] | 0.73
3 | N-19-01 | Non Plan Capital Works for FY 2019-20 | [7 empty] | 0.82
4 | N-21-01 | Non Plan Capital Works for FY 2021-22 | [7 empty] | 4.57
5 | N-22-01 | Non Plan Capital Works for FY 2022-23 | [7 empty] | 0.03
| Grand Total | [8 empty] | 446.42

## Tr, RMI__22-23 CAPITLZ
ANNEXURE-I
Details of Actual Capitalization for FY:2022-23 of Augmentation of PTRs, Lines & RMI Schemes
FY:2022-23
Sl. No. | L1 WBS Element | Name of the Project | Investment Approval Date | Start Date |  | Completion Date |  | Approved Cost as per Investment Approval | Capitalisation upto previous year as per Audited Financial Statements | Capitalisation claimed for the Current Year (Rs. Crores) | Means of Finance |  |  | Date of Capitali- sation | Addition to Transmission Network |  |  | Reason for Cost Overrun | Reason for Time Overrun | Whether Part Capitalisation (or) Full Capitalisation | Physical Completion Certificate | Financial Completion Certificate | Electricial Inspector Certificate
|  |  |  | Scheduled | Actual | Scheduled | Actual |  |  |  | Debt | Equity | Grant |  | Lines (CKT KM) | Capacity (MVA) | Bays (Nos.)
1 | A-17-01 | 24 Hrs. Agl. supply works in WGL ZONE | No.13/17, 2017-18 | 01.05.15 | 01.05.15 | 01.05.21 | 2019-12-11 |  |  | 0.35652 | 75% | 25% | - | 2023-07-14 |  |  |  | No cost overrun | No Time Overrun |  | 2023001170 |  | *
2 | [6 empty] | 2018-04-21 | [6 empty] | 2019-06-14 |  |  |  | No cost overrun |  |  | 2019000694 |  | *
3 | [6 empty] | 2018-04-30 | [6 empty] | 2023-06-09 |  |  |  | No cost overrun |  |  | 2023000536 |  | *
4 | [6 empty] | 2021-08-07 | [6 empty] | 2023-07-05 |  |  |  | No cost overrun |  |  | 2023001159 |  | *
5 | [6 empty] | 2016-03-05 | [6 empty] | 2023-07-03 |  |  |  | No cost overrun |  |  | 2023001135 |  | *
6 | [6 empty] | 2018-07-11 | [6 empty] | 2021-07-06 |  |  |  | No cost overrun |  |  | 2021000154 |  | *
2 | A-17-02 | Aug Sys Stren & 24 Hrs Agl METRO & RURAL | No.13/17, 2017-18 | 01.05.15 | 01.05.15 | 01.05.21 | 2019-02-05 |  |  | 0.00095068 | 75% | 25% | - | 2020-07-01 |  |  |  | No cost overrun | No Time Overrun |  | 2020000431 |  | *
3 | A-18-02 | Aug of PTR cap.at YWGI |  | 18.07.18 | 18.07.18 | 18.07.21 | 2021-02-19 |  |  | 0.31729 | 75% | 25% | - | 2022-06-20 |  |  |  | No cost overrun | No Time Overrun |  | 2022000380 |  | *
9 |  | Aug of PTR cap.at YWGI |  |  |  |  | 2021-02-19 | [6 empty] | 2023-06-30 |  |  |  | No cost overrun |  |  | 2023001104 |  | *
4 | A-19-01 | Aug of 4th 160 MVA at 220KV Gachibowli |  | 03.07.19 | 03.07.19 | 02.07.21 | 2020-01-25 |  |  | 0.092242 | 75% | 25% | - | 2023-06-26 |  |  |  | No cost overrun | No Time Overrun |  | 2023001041 |  | *
5 | A-19-03 | Augmentation of 80 MVA at 132 KV IDPL SS |  | 07.03.20 | 07.03.20 | 06.03.22 | 2020-12-28 |  |  | 0.11248 | 75% | 25% | - | 2023-06-19 |  |  |  | No cost overrun | No Time Overrun |  | 2023000760 |  | *
12 |  | Augmentation of 80 MVA at 132 KV IDPL SS |  |  |  |  | 2020-12-28 | [6 empty] | 2023-06-19 |  |  |  | No cost overrun |  |  | 2023000759 |  | *
6 | A-19-04 | Augmentation of PTRs at 220 KV Hayathnag |  | 18.03.20 | 18.03.20 | 17.03.22 | 2021-08-26 |  |  | 0.0016751 | 75% | 25% | - | 2022-06-01 |  |  |  | No cost overrun | No Time Overrun |  | 2022000132 |  | *
7 | A-20-03 | Aug of PTR at Warangal & Karimnagar Circ |  | 03.10.20 | 03.10.20 | 02.10.23 | 2021-03-19 |  |  | 0.15109 | 75% | 25% | - | 2022-11-02 |  |  |  | No cost overrun | No Time Overrun |  | 2022000489 |  | *
16 |  | Aug of PTR at Warangal & Karimnagar Circ |  |  |  |  | 2021-01-18 | [6 empty] | 2023-06-16 |  |  |  | No cost overrun |  |  | 2023000682 |  | *
17 |  | Aug of PTR at Warangal & Karimnagar Circ |  |  |  |  | 2021-01-18 | [6 empty] | 2023-06-16 |  |  |  | No cost overrun |  |  | 2023000683 |  | *
18 |  | Aug of PTR at Warangal & Karimnagar Circ |  |  |  |  | 2021-02-04 | [6 empty] | 2023-06-16 |  |  |  | No cost overrun |  |  | 2023000685 |  | *
8 | A-20-06 | Aug of 3rd PTR at 132KV MDPally SS |  | 05.02.21 | 05.02.21 | 04.02.23 | 2022-09-08 |  |  | 3.8297 | 75% | 25% | - | 2022-11-03 |  |  |  | No cost overrun | No Time Overrun |  | 2022000495 |  | *
9 | A-20-07 | Aug of 4rd PTR at 132KV Pashmailaram SS |  | 30.03.21 | 30.03.21 | 29.03.23 | 2021-12-26 |  |  | 0.06925 | 75% | 25% | - | 2022-06-10 |  |  |  | No cost overrun | No Time Overrun |  | 2022000273 |  | *
10 | A-21-01 | Aug of 160 MVA PTR at 400KV Suryapet SS |  | 12.04.21 | 12.04.21 | 11.04.23 | 2023-01-13 |  |  | 3.1532 | 75% | 25% | - | 2023-02-03 |  |  |  | No cost overrun | No Time Overrun |  | 2022000501 |  | *
23 |  | Aug of 160 MVA PTR at 400KV Suryapet SS |  |  |  |  | 2023-01-13 | [6 empty] | 2023-06-13 |  |  |  | No cost overrun |  |  | 2023000612 |  | *
11 | A-21-02 | Aug of 132/33 KV PTRs at Mamidipally & 4 |  | 07.05.21 | 07.05.21 | 06.05.23 | 2022-04-27 |  |  | 0.025844 | 75% | 25% | - | 2023-06-23 |  |  |  | No cost overrun | No Time Overrun |  | 2023000955 |  | *
12 | A-21-05 | Augmentations of 220KV PTRs at 5Nos Subs |  | 04.10.21 | 04.10.21 | 03.10.23 | 2022-09-07 |  |  | 1.4208 | 75% | 25% | - | 2023-06-24 |  |  |  | No cost overrun | No Time Overrun |  | 2023000997 |  | *
26 |  | Augmentations of 220KV PTRs at 5Nos Subs |  |  |  |  | 2022-08-22 | [6 empty] | 2023-06-12 |  |  |  | No cost overrun |  |  | 2023000570 |  | *
27 |  | Augmentations of 220KV PTRs at 5Nos Subs |  |  |  |  | 2022-08-26 | [6 empty] | 2023-06-17 |  |  |  | No cost overrun |  |  | 2023000738 |  | *
28 |  | Augmentations of 220KV PTRs at 5Nos Subs |  |  |  |  | 2022-08-26 | [6 empty] | 2023-06-17 |  |  |  | No cost overrun |  |  | 2023000737 |  | *
29 |  | Augmentations of 220KV PTRs at 5Nos Subs |  |  |  |  | 2022-09-13 | [6 empty] | 2023-06-27 |  |  |  | No cost overrun |  |  | 2023001068 |  | *
13 | A-21-06 | Augmentations of 132KV PTRs at 24Nos Sub |  | 07.10.21 | 07.10.21 | 06.10.23 | 2023-03-13 |  |  | 6.0692 | 75% | 25% | - | 2023-06-12 |  |  |  | No cost overrun | No Time Overrun |  | 2023000582 |  | *
31 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2022-09-28 | [6 empty] | 2023-06-13 |  |  |  | No cost overrun |  |  | 2023000609 |  | *
32 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2022-12-24 | [6 empty] | 2023-06-12 |  |  |  | No cost overrun |  |  | 2023000583 |  | *
33 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2022-12-22 | [6 empty] | 2023-05-23 |  |  |  | No cost overrun |  |  | 2023000333 |  | *
34 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2022-11-11 | [6 empty] | 2023-06-15 |  |  |  | No cost overrun |  |  | 2023000664 |  | *
35 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2022-10-13 | [6 empty] | 2023-06-27 |  |  |  | No cost overrun |  |  | 2023001074 |  | *
36 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2022-09-28 | [6 empty] | 2023-06-17 |  |  |  | No cost overrun |  |  | 2023000740 |  | *
37 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2021-12-27 | [6 empty] | 2022-06-17 |  |  |  | No cost overrun |  |  | 2022000358 |  | *
38 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2022-05-10 | [6 empty] | 2023-06-23 |  |  |  | No cost overrun |  |  | 2023000905 |  | *
39 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2022-07-13 | [6 empty] | 2023-06-15 |  |  |  | No cost overrun |  |  | 2023000650 |  | *
40 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2022-06-09 | [6 empty] | 2023-06-23 |  |  |  | No cost overrun |  |  | 2023000856 |  | *
41 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2022-10-23 | [6 empty] | 2023-06-10 |  |  |  | No cost overrun |  |  | 2023000555 |  | *
42 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2022-10-23 | [6 empty] | 2023-05-20 |  |  |  | No cost overrun |  |  | 2023000228 |  | *
43 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2022-10-23 | [6 empty] | 2023-06-10 |  |  |  | No cost overrun |  |  | 2023000556 |  | *
44 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2022-09-28 | [6 empty] | 2023-06-23 |  |  |  | No cost overrun |  |  | 2023000851 |  | *
45 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2023-03-29 | [6 empty] | 2023-06-13 |  |  |  | No cost overrun |  |  | 2023000584 |  | *
46 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2022-12-24 | [6 empty] | 2023-06-23 |  |  |  | No cost overrun |  |  | 2023000850 |  | *
47 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2023-02-03 | [6 empty] | 2023-06-23 |  |  |  | No cost overrun |  |  | 2023000849 |  | *
48 |  | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2023-03-01 | [6 empty] | 2023-05-20 |  |  |  | No cost overrun |  |  | 2023000234 |  | *
14 | A-22-01 | Augmentation of PTR at 132 KV Medchal SS |  | 06.06.22 | 06.06.22 | 05.06.24 | 2023-01-08 |  |  | 0.19714 | 75% | 25% | - | 2023-06-23 |  |  |  | No cost overrun | No Time Overrun |  | 2023000896 |  | *
50 |  | Augmentation of PTR at 132 KV Medchal SS |  |  |  |  | 2023-01-08 | [6 empty] | 2023-06-23 |  |  |  | No cost overrun |  |  | 2023000894 |  | *
51 |  | Augmentation of PTR at 132 KV Medchal SS |  |  |  |  | 2023-01-08 | [6 empty] | 2023-06-23 |  |  |  | No cost overrun |  |  | 2023000882 |  | *
52 |  | Augmentation of PTR at 132 KV Medchal SS |  |  |  |  | 2023-01-04 | [6 empty] | 2023-06-23 |  |  |  | No cost overrun |  |  | 2023000881 |  | *
15 | A-22-02 | Augmentation of PTR at 132KV Balanagar S |  | 11.10.22 | 11.10.22 | 10.10.24 | 2022-12-06 |  |  | 0.039916 | 75% | 25% | - | 2023-06-23 |  |  |  | No cost overrun | No Time Overrun |  | 2023000936 |  | *
54 |  | Augmentation of PTR at 132KV Balanagar S |  |  |  |  | 2022-12-06 | [6 empty] | 2023-06-23 |  |  |  | No cost overrun |  |  | 2023000932 |  | *
16 | A-22-03 | Aug. of PTR at Kaithalapur & Bhongir |  | 21.12.22 | 21.12.22 | 20.12.24 | 2023-03-01 |  |  | 0.095991 | 75% | 25% | - | 2023-05-20 |  |  |  | No cost overrun | No Time Overrun |  | 2023000241 |  | *
56 |  | Aug. of PTR at Kaithalapur & Bhongir |  |  |  |  | 2023-03-01 | [6 empty] | 2023-06-26 |  |  |  | No cost overrun |  |  | 2023001013 |  | *
17 | D-16-06 | Erection 33KV Bays TSNPDCL |  |  |  |  | 2016-07-26 |  |  | 0.33543 | 100 % customer contribution |  |  | 2023-06-15 |  |  |  | No cost overrun | No Time Overrun |  | 2023000654 |  | *
58 |  | Erection 33KV Bays TSNPDCL |  |  |  |  | 2017-03-09 | [6 empty] | 2023-06-16 |  |  |  | No cost overrun |  |  | 2023000701 |  | *
18 | D-18-20 | Providing of ABT Meters for all Traction |  |  |  |  | 2019-09-04 |  |  | 1.7171 | 100 % customer contribution |  |  | 2023-06-27 |  |  | 1 | No cost overrun | No Time Overrun |  | 2023001082 |  | *
60 |  | Providing of ABT Meters for all Traction |  |  |  |  | 2020-03-03 | [6 empty] | 2023-06-27 |  |  |  | No cost overrun |  |  | 2023001083 |  | *
61 |  | Providing of ABT Meters for all Traction |  |  |  |  | 2020-10-10 | [6 empty] | 2023-03-01 |  |  | 1 | No cost overrun |  |  | 2022000503 |  | *
62 |  | Providing of ABT Meters for all Traction |  |  |  |  | 2020-08-24 | [6 empty] | 2023-05-15 |  |  |  | No cost overrun |  |  | 2023000024 |  | *
63 |  | Providing of ABT Meters for all Traction |  |  |  |  | 2020-10-10 | [6 empty] | 2023-05-15 |  |  | 1 | No cost overrun |  |  | 2023000019 |  | *
64 |  | Providing of ABT Meters for all Traction |  |  |  |  | 2021-01-05 | [6 empty] | 2023-02-20 |  |  |  | No cost overrun |  |  | 2022000502 |  | *
19 | D-19-07 | ABT Metering at 132 KV Manuguru & Kothag |  |  |  |  | 2021-03-28 |  |  | 0.15445 | 100 % customer contribution |  |  | 2023-06-27 |  |  | 1 | No cost overrun | No Time Overrun |  | 2023001062 |  | *
66 |  | ABT Metering at 132 KV Manuguru & Kothag |  |  |  |  | 2021-04-11 | [6 empty] | 2023-06-26 |  |  |  | No cost overrun |  |  | 2023001017 |  | *
20 | D-19-08 | ABT Metering at 132KV OCM & Mandamarry S |  |  |  |  | 2022-02-20 |  |  | 3.6509 | 100 % customer contribution |  |  | 2022-07-07 |  |  | 2 | No cost overrun | No Time Overrun |  | 2022000430 |  | *
68 |  | ABT Metering at 132KV OCM & Mandamarry S |  |  |  |  | 2020-11-19 | [6 empty] | 2023-06-08 |  |  |  | No cost overrun |  |  | 2023000531 |  | *
69 |  | ABT Metering at 132KV OCM & Mandamarry S |  |  |  |  | 2022-02-20 | [6 empty] | 2022-07-07 |  |  |  | No cost overrun |  |  | 2022000429 |  | *
70 |  | ABT Metering at 132KV OCM & Mandamarry S |  |  |  |  | 2022-02-20 | [6 empty] | 2022-07-07 |  |  |  | No cost overrun |  |  | 2022000431 |  | *
21 | D-19-14 | 33 KV Bay extension at 220KV SS Manguru |  |  |  |  | 2022-06-27 |  |  | 0.16949 | 100 % customer contribution |  |  | 2023-06-24 |  |  | 1 | No cost overrun | No Time Overrun |  | 2023000977 |  | *
72 |  | 33 KV Bay extension at 220KV SS Manguru |  |  |  |  | 2022-06-27 | [6 empty] | 2023-06-27 |  |  |  | No cost overrun |  |  | 2023001060 |  | *
22 | D-20-16 | Erection of 4Nos 33KV Bays for M/s Amazo |  |  |  |  | 2021-05-24 |  |  | 0.0013755 | 100 % customer contribution |  |  | 2021-07-01 |  |  | 1 | No cost overrun | No Time Overrun |  | 2021000083 |  | *
74 |  | Erection of 4Nos 33KV Bays for M/s Amazo |  |  |  |  | 2021-05-24 | [6 empty] | 2021-07-01 |  |  |  | No cost overrun |  |  | 2021000085 |  | *
23 | D-20-21 | 33KV bay for SCCL,Bittupally at 132KV Ma |  |  |  |  | 2022-07-09 |  |  | 0.16576 | 100 % customer contribution |  |  | 2023-06-12 |  |  | 1 | No cost overrun | No Time Overrun |  | 2023000558 |  | *
77 |  | 33KV bay for SCCL,Bittupally at 132KV Ma |  |  |  |  | 2022-09-07 | [6 empty] | 2023-06-12 |  |  |  | No cost overrun |  |  | 2023000560 |  | *
78 |  | 33KV bay for SCCL,Bittupally at 132KV Ma |  |  |  |  | 2022-09-07 | [6 empty] | 2023-06-12 |  |  |  | No cost overrun |  |  | 2023000559 |  | *
24 | D-20-43 | 33 KV Bay for TSNPDCL at 132KV Dasnagar |  |  |  |  | 2018-05-21 |  |  | 0.21971 | 100 % customer contribution |  |  | 2023-06-01 |  |  | 1 | No cost overrun | No Time Overrun |  | 2023000471 |  | *
25 | D-21-16 | 4Nos 33KV Bays in substation in OMC Wara |  |  |  |  | 2021-11-18 |  |  | 0.39769 | 100 % customer contribution |  |  | 2023-05-25 |  |  | 2 | No cost overrun | No Time Overrun |  | 2023000375 |  | *
82 |  | 4Nos 33KV Bays in substation in OMC Wara |  |  |  |  | 2022-03-05 | [6 empty] | 2022-06-18 |  |  |  | No cost overrun |  |  | 2022000364 |  | *
83 |  | 4Nos 33KV Bays in substation in OMC Wara |  |  |  |  | 2021-11-18 | [6 empty] | 2023-06-16 |  |  |  | No cost overrun |  |  | 2023000703 |  | *
84 |  | 4Nos 33KV Bays in substation in OMC Wara |  |  |  |  | 2022-03-05 | [6 empty] | 2023-06-07 |  |  |  | No cost overrun |  |  | 2023000512 |  | *
85 |  | 4Nos 33KV Bays in substation in OMC Wara |  |  |  |  | 2021-09-15 | [6 empty] | 2023-05-24 |  |  |  | No cost overrun |  |  | 2023000362 |  | *
86 |  | 4Nos 33KV Bays in substation in OMC Wara |  |  |  |  | 2021-11-27 | [6 empty] | 2023-05-27 |  |  |  | No cost overrun |  |  | 2023000434 |  | *
87 |  | 4Nos 33KV Bays in substation in OMC Wara |  |  |  |  | 2021-11-27 | [6 empty] | 2023-05-27 |  |  |  | No cost overrun |  |  | 2023000435 |  | *
88 |  | 4Nos 33KV Bays in substation in OMC Wara |  |  |  |  | 2021-09-15 | [6 empty] | 2023-05-23 |  |  |  | No cost overrun |  |  | 2023000330 |  | *
89 |  | 4Nos 33KV Bays in substation in OMC Wara |  |  |  |  | 2021-11-27 | [6 empty] | 2023-05-27 |  |  |  | No cost overrun |  |  | 2023000436 |  | *
90 |  | 4Nos 33KV Bays in substation in OMC Wara |  |  |  |  | 2021-09-15 | [6 empty] | 2023-05-23 |  |  |  | No cost overrun |  |  | 2023000331 |  | *
91 |  | 4Nos 33KV Bays in substation in OMC Wara |  |  |  |  | 2021-09-15 | [6 empty] | 2023-05-23 |  |  |  | No cost overrun |  |  | 2023000332 |  | *
92 |  | 4Nos 33KV Bays in substation in OMC Wara |  |  |  |  | 2021-11-27 | [6 empty] | 2023-05-27 |  |  |  | No cost overrun |  |  | 2023000433 |  | *
93 |  | 4Nos 33KV Bays in substation in OMC Wara |  |  |  |  | 2022-03-05 | [6 empty] | 2023-06-07 |  |  |  | No cost overrun |  |  | 2023000513 |  | *
94 |  | 4Nos 33KV Bays in substation in OMC Wara |  |  |  |  | 2021-09-15 | [6 empty] | 2023-05-23 |  |  |  | No cost overrun |  |  | 2023000334 |  | *
26 | D-21-20 | 33KV Bay for Raghuram at 132KV Suglampal |  |  |  |  | 2021-03-14 |  |  | 0.11542 | 100 % customer contribution |  |  | 2022-11-01 |  |  | 1 | No cost overrun | No Time Overrun |  | 2022000479 |  | *
96 |  | 33KV Bay for Raghuram at 132KV Suglampal |  |  |  |  | 2021-03-14 | [6 empty] | 2022-11-01 |  |  |  | No cost overrun |  |  | 2022000482 |  | *
97 |  | 33KV Bay for Raghuram at 132KV Suglampal |  |  |  |  | 2021-03-14 | [6 empty] | 2022-11-01 |  |  |  | No cost overrun |  |  | 2022000483 |  | *
98 |  | 33KV Bay for Raghuram at 132KV Suglampal |  |  |  |  | 2022-03-14 | [6 empty] | 2022-11-01 |  |  |  | No cost overrun |  |  | 2022000484 |  | *
27 | D-21-26 | 33KV Bay for singareni at 132KV Penuball |  |  |  |  | 2021-12-02 |  |  | 0.085823 | 100 % customer contribution |  |  | 2023-06-24 |  |  | 1 | No cost overrun | No Time Overrun |  | 2023000970 |  | *
100 |  | 33KV Bay for singareni at 132KV Penuball |  |  |  |  | 2021-12-02 | [6 empty] | 2023-06-28 |  |  |  | No cost overrun |  |  | 2023001089 |  | *
28 | D-21-46 | 33KV Bay at 132KV B.Gangaram for diverio |  |  |  |  | 2023-01-23 |  |  | 0.10937 | 100 % customer contribution |  |  | 2023-06-26 |  |  | 1 | No cost overrun | No Time Overrun |  | 2023001008 |  | *
29 | D-22-03 | Replacement of 132KV metering CT&PTs at |  |  |  |  | 2022-04-03 |  |  | 0.028447 | 100 % customer contribution |  |  | 2023-06-17 |  |  | 0 | No cost overrun | No Time Overrun |  | 2023000723 |  | *
103 |  | Replacement of 132KV metering CT&PTs at |  |  |  |  | 2022-04-28 | [6 empty] | 2023-06-17 |  |  |  | No cost overrun |  |  | 2023000726 |  | *
30 | N-18-OMCP | Cap.Material Drawl in O&M for FY:2018-19 |  |  |  |  | 2018-10-23 |  |  | 0.036946 | 75% | 25% |  | 2023-06-26 |  |  |  | No cost overrun | No Time Overrun |  | 2023001037 |  | *
31 | N-19-02 | Non Planned Capital works (O&M) 2019-20 |  | 01.04.19 |  | 31.03.22 | 2019-11-29 |  |  | 0.10156 | 75% | 25% |  | 2023-06-23 |  |  |  | No cost overrun | No Time Overrun |  | 2023000877 |  | *
106 |  | Non Planned Capital works (O&M) 2019-20 |  |  |  |  | 2019-11-29 | [6 empty] | 2023-06-23 |  |  |  | No cost overrun |  |  | 2023000880 |  | *
107 |  | Non Planned Capital works (O&M) 2019-20 |  |  |  |  | 2021-12-22 | [6 empty] | 2023-06-15 |  |  |  | No cost overrun |  |  | 2023000663 |  | *
108 |  | Non Planned Capital works (O&M) 2019-20 |  |  |  |  | 2020-03-17 | [6 empty] | 2021-07-15 |  |  |  | No cost overrun |  |  | 2021000282 |  | *
109 |  | Non Planned Capital works (O&M) 2019-20 |  |  |  |  | 2019-11-25 | [6 empty] | 2023-06-23 |  |  |  | No cost overrun |  |  | 2023000887 |  | *
32 | N-19-OMCP | Cap.Material Drawl in O&M for FY:2019-20 |  |  |  |  | 2020-09-23 |  |  | 0.078508 | 75% | 25% |  | 2023-06-27 |  |  |  | No cost overrun | No Time Overrun |  | 2023001069 |  | *
111 |  | Cap.Material Drawl in O&M for FY:2019-20 |  |  |  |  | 2020-08-03 | [6 empty] | 2021-07-16 |  |  |  | No cost overrun |  |  | 2021000309 |  | *
33 | N-20-02 | Non Planned Capital works (O&M) 2020-21 |  | 01.04.20 | 01.04.20 | 31.03.2023 | 2022-04-20 |  |  | 0.33924 | 75% | 25% |  | 2023-06-12 |  |  |  | No cost overrun | No Time Overrun |  | 2023000580 |  | *
113 |  | Non Planned Capital works (O&M) 2020-21 |  |  |  |  | 2022-06-20 | [6 empty] | 2023-06-12 |  |  |  | No cost overrun |  |  | 2023000581 |  | *
114 |  | Non Planned Capital works (O&M) 2020-21 |  |  |  |  | 2022-07-20 | [6 empty] | 2023-06-12 |  |  |  | No cost overrun |  |  | 2023000557 |  | *
115 |  | Non Planned Capital works (O&M) 2020-21 |  |  |  |  | 2022-07-26 | [6 empty] | 2023-06-26 |  |  |  | No cost overrun |  |  | 2023001040 |  | *
34 | N-21-02 | Non Planned Capital works (O&M) 2021-22 |  | 01.04.21 | 01.04.21 | 31.03.2024 | 2021-10-30 |  |  | 4.9122 | 75% | 25% |  | 2022-06-01 |  |  |  | No cost overrun | No Time Overrun |  | 2022000137 |  | *
117 |  | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2022-09-17 | [6 empty] | 2023-05-15 |  |  |  | No cost overrun |  |  | 2023000022 |  | *
118 |  | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2023-05-23 | [6 empty] | 2023-06-13 |  |  |  | No cost overrun |  |  | 2023000586 |  | *
119 |  | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2023-01-10 | [6 empty] | 2023-05-22 |  |  |  | No cost overrun |  |  | 2023000271 |  | *
120 |  | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2023-02-04 | [6 empty] | 2023-05-18 |  |  |  | No cost overrun |  |  | 2023000145 |  | *
121 |  | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2023-02-10 | [6 empty] | 2023-05-18 |  |  |  | No cost overrun |  |  | 2023000141 |  | *
122 |  | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2023-01-12 | [6 empty] | 2023-05-16 |  |  |  | No cost overrun |  |  | 2023000058 |  | *
123 |  | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2023-01-11 | [6 empty] | 2023-05-22 |  |  |  | No cost overrun |  |  | 2023000261 |  | *
124 |  | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2023-01-18 | [6 empty] | 2023-05-26 |  |  |  | No cost overrun |  |  | 2023000416 |  | *
125 |  | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2023-02-07 | [6 empty] | 2023-05-18 |  |  |  | No cost overrun |  |  | 2023000137 |  | *
126 |  | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2023-02-21 | [6 empty] | 2023-06-09 |  |  |  | No cost overrun |  |  | 2023000545 |  | *
127 |  | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2023-01-19 | [6 empty] | 2023-05-30 |  |  |  | No cost overrun |  |  | 2023000451 |  | *
128 |  | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2023-01-18 | [6 empty] | 2023-05-16 |  |  |  | No cost overrun |  |  | 2023000059 |  | *
129 |  | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2022-12-24 | [6 empty] | 2023-06-23 |  |  |  | No cost overrun |  |  | 2023000889 |  | *
130 |  | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2023-03-16 | [6 empty] | 2023-05-22 |  |  |  | No cost overrun |  |  | 2023000264 |  | *
131 |  | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2022-12-28 | [6 empty] | 2023-05-15 |  |  |  | No cost overrun |  |  | 2023000017 |  | *
132 |  | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2023-02-28 | [6 empty] | 2023-05-22 |  |  |  | No cost overrun |  |  | 2023000269 |  | *
133 |  | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2022-03-31 | [6 empty] | 2023-05-25 |  |  |  | No cost overrun |  |  | 2023000378 |  | *
35 | N-22-02 | Non Planned Capital works (O&M) 2022-23 |  | 01.04.22 | 01.04.22 | 31.03.2025 | 2022-12-05 |  |  | 0.092427 | 75% | 25% |  | 2023-05-24 |  |  |  | No cost overrun | No Time Overrun |  | 2023000371 |  | *
36 | S-22-01 | Const. of 33KV bays at 132/33KV Substati |  | 01.04.22 | 01.04.22 | 31.03.2024 | 2022-12-22 |  |  | 0.23338 | 75% | 25% |  | 2023-06-26 |  |  | 2 | No cost overrun | No Time Overrun |  | 2023001019 |  | *
136 |  | Const. of 33KV bays at 132/33KV Substati |  |  |  |  | 2022-09-26 | [6 empty] | 2023-05-27 |  |  |  | No cost overrun |  |  | 2023000432 |  | *
137 |  | Const. of 33KV bays at 132/33KV Substati |  |  |  |  | 2022-09-26 | [6 empty] | 2023-05-27 |  |  |  | No cost overrun |  |  | 2023000431 |  | *
138 |  | Const. of 33KV bays at 132/33KV Substati |  |  |  |  | 2022-12-22 | [6 empty] | 2023-06-09 |  |  |  | No cost overrun |  |  | 2023000553 |  | *
139 |  | Const. of 33KV bays at 132/33KV Substati |  |  |  |  | 2022-12-22 | [6 empty] | 2023-06-09 |  |  |  | No cost overrun |  |  | 2023000554 |  | *
37 | O-16-01 | Rolling stock for FY 2016-2017 | - | 11.01.2017 | 11.01.2017 | 11.01.2018 | 31.03.2023 | 39.53 | - | 0.323 | [8 empty] | Procurement Delay due to poor response of Bidders |  | - | - | *
37 | R-16-02 | PSDF | - | 11.01.2017 | 11.01.2017 | 11.01.2018 | 31.03.2023 | 59.97 | - | 0.519 | - | - | - |  | - | - | - |  | Procurement Delay due to poor response of Bidders |  | - | - | *
38 | R-15-01 | RMI for the year 2015 | APERC in its Tariff Order dt.09.05.2014 has approved Rs.98.50 Crores for combined state of Andhra Pradesh under Renovation & Modernization Scheme for the year 2015-16.After careful consideration, TSTRANSCO accords approval for Rs.53.08 Crores (53.89% of 98.50 Crores. | 16.09.2015 | 16.09.2015 | 15.09.2016 | 31.03.2023 | 53.08 |  | 0.172 | - | - | - |  | - | - | - |  | Repeated Tendering |  | - | - | *
39 | R-17-01 | RMI for FY:2017-18 & 2018-19 | TSERC in its tariff order dt.01.05.2017 has approved for investment of Rs.50.11Crs under RMI during each of F.Y:2017-18,2018-19 | 07.10.2017 | 07.10.2017 | 06.10.2018 | 31.03.2023 | 100.22 | - | 5.024 | - | - | - |  | - | - | - |  | Repeated Tendering |  | - | - | *
40 | R-20-01 | RMI for the F.Y:2020-21 | TSERC in its tariff order dt.20.03.2020 has approved for investment of Rs.75.67Crs under RMI during each of F.Y:2020-21 | 16.09.2020 | 16.09.2020 | 15.09.2021 | 31.03.2023 | 75.6 |  | 7.879 | [8 empty] | Repeated Tendering |  |  |  | *
41 | R-21-01 | RMI for the F.Y:202-22 | TSERC in its tariff order dt.20.03.2020 has approved for investment of Rs.59.70Crs under RMI during each of F.Y:2021-22 | 14.03.2022 | 13.03.2023 | 13.03.2023 | 31.03.2023 | 59.7 |  | 1.51 | [8 empty] | Repeated Tendering |  |  |  | *
42 | Z-21-01 | Rolling stock for the F.Y:2021-22 | - | 17.07.2021 |  | 31.03.2022 |  |  |  | 14.575 | [8 empty] | Repeated Tendering |  |  |  | *
43 | Z-99-01 | Rolling stock for the major Sub-Station equipment | - | 23.09.2022 |  | 31.03.2023 |  |  |  | 1.982 | [8 empty] | Repeated Tendering |  |  |  | *
44 | D-21-22 | Shifting of 132KV Nandipet-Nizamabad line(DC Work) (Railway) |  | 23.07.2021 | 02.10.2021 | 12.01.2022 | 12.01.2022 | 2.93 | NA | 0.23 | NA | NA | DC work | 12.1.22 | [6 empty] | 2022000046 | 2022000420 | *
45 | R-17-02 | R-17-02.01 : 132 KV Bellampally-Sirpurkhagaznagar tower replacement works |  | 23.04.2018 | 28.01.2019 | 29.03.2021 | 29.03.2021 | 4.9 | NA | 0.78 | NA | NA | RMI funds | [7 empty] | Not completed | NA | *
|  | Total | [5 empty] | 395.93 |  | 61.8726
Note : * Electrical Inspector Certification is exempted by the Govt. of TS, as per the G.O. Ms.No.10, Dt:09.05.2022 issued by Energy
14 | A-19-05 | Augmentation of PTRs at gesukonda & Tiru |  |  |  |  | 2022-01-26 |  |  |  | (PR-II) Department | 25% | - | 2022-06-20 |  |  |  | No cost overrun |  |  | 2022000385
19 | A-20-05 | Augmentation of PTR at 132KV Khaithalapu |  |  |  |  | 2021-08-25 |  |  |  | 75% | 25% | - | 2022-06-17 |  |  |  | No cost overrun |  |  | 2022000336
75 | D-20-20 | 33KV Bay at 220KV FABCITY SS for chirpa |  |  |  |  | 2021-05-24 |  |  |  | 100 % customer contribution |  |  | 2021-07-01 |  |  |  | No cost overrun |  |  | 2021000084
79 | D-20-22 | CT Replacement for Kesoram at Malyalapal |  |  |  |  | 2022-03-03 |  |  |  | 100 % customer contribution |  |  | 2023-06-21 |  |  |  | No cost overrun |  |  | 2023000815
1 | A-13-05 | Aug of PTR at 132KV SS Ichoda |  | 18.01.13 | 18.01.13 | 17.01.15 | 2020-02-03 | 0.61 |  | 0 | 75% | 25% |  | 2022-07-15 | - | - | - | No cost overrun |  |  | 2022000446 | - | NA
2 | A-15-05 | AUGof PTR@EHT SS for extending 9Hrs |  | 01.05.15 | 01.05.15 | 01.05.17 | 2016-03-05 | 283.03 |  | 0 | 75% | 25% |  | 2019-05-07 | - | 31.5 | 2 | No cost overrun | No Time Over Run |  | 2019000120 | 202000704 | NA
3 | A-15-05 | AUGof PTR@EHT SS for extending 9Hrs |  |  |  |  | 2016-04-07 | [6 empty] | 2019-05-07 | - | 31.5 | 2 |  |  |  | 2019000119 | 202000708
4 | A-15-05 | AUGof PTR@EHT SS for extending 9Hrs |  |  |  |  | 2016-03-12 | [6 empty] | 2022-06-22 | - | 31.5 | 2 | No cost overrun |  |  | 2022000400 | -
5 | A-15-05 | AUGof PTR@EHT SS for extending 9Hrs |  |  |  |  | 2016-03-06 | [6 empty] | 2019-06-10 | - | 18.5 | - |  |  |  | 2019000624 | -
6 | A-15-05 | AUGof PTR@EHT SS for extending 9Hrs |  |  |  |  | 2016-12-30 | [6 empty] | 2019-05-22 | - | 47.5 | - |  |  |  | 2019000345 | 202001687
7 | A-15-05 | AUGof PTR@EHT SS for extending 9Hrs |  |  |  |  | 2016-03-31 | [6 empty] | 2019-05-29 | - | 31.5 | 2 |  |  |  | 2019000503 | 202000723
8 | A-15-05 | AUGof PTR@EHT SS for extending 9Hrs |  |  |  |  | 2016-05-23 | [6 empty] | 2019-06-22 | - | 80 | 2 |  |  |  | 2019000816 | 202001003
9 | A-15-05 | AUGof PTR@EHT SS for extending 9Hrs |  |  |  |  | 2016-05-27 | [6 empty] | 2021-06-25 | - | 64 | - |  |  |  | 2021000068 | 202001006
10 | A-15-06 | Augmentation of PTR capacities at variou |  | 01.05.16 | 01.05.16 | 01.05.18 | 2016-03-04 | 233.75 |  | 0 | 75% | 25% |  | 2019-06-13 | - | 16.5 | - | No cost overrun | No Time Over Run |  | 2019000686 | 202001331 | NA
11 | A-15-07 | Augmentation of PTR capacities at 220kV |  | 02.07.15 | 02.07.15 | 02.07.17 | 2016-05-13 | 11.35 |  | 0.019 | 75% | 25% |  | 2019-06-22 | - | 100 | 2 | No cost overrun | No Time Over Run |  | 2019000817 | 202100091 | NA
12 | A-15-07 | Augmentation of PTR capacities at 220kV |  |  |  |  | 2016-04-26 | [6 empty] | 2019-06-22 | - | 100 | 2 |  | No Time Over Run |  | 2019000806 | 202100090
13 | A-15-08 | ERECTION OF 31.5 MVA PTR IN PLACE OF 10/ |  | 01.05.15 | 01.05.15 | 01.05.17 | 2016-03-31 | - |  | 0 | 75% | 25% |  | 2022-06-24 | - | 15.5 | - | No cost overrun | No Time Over Run |  | 2022000409 | 202200321 | NA
14 | A-15-19 | Dismatling of 10/16MVAPTR-II & Erect.of |  | 01.05.15 | 01.05.15 | 01.05.17 | 2016-03-31 | - |  | 0 | 75% | 25% |  | 2022-06-24 | - | - | - | No cost overrun | No Time Over Run |  | 2022000408 | 202200320 | NA
15 | A-16-01 | 3rd 31.5MVA PTR at Adilabad SS |  | 01.03.16 | 01.03.16 | 01.03.16 | 2020-02-06 | 3.06 |  | 0 | 75% | 25% |  | 2022-07-15 | - | 31.5 | 2 | No cost overrun | No Time Over Run |  | 2022000447 | - | NA
16 | A-16-01 | 3rd 31.5MVA PTR at Adilabad SS |  |  |  |  | 2017-03-03 | [6 empty] | 2021-07-13 | [6 empty] | 2021000237 | 202001422
17 | A-16-10 | Aug. at 220KV SS Gunrock & Ghanapur 160M |  | 03.09.16 | 03.09.16 | 03.09.18 | 2020-01-25 | 14.05 |  | 0 | 75% | 25% |  | 2020-07-01 | - | - | - | No cost overrun | No Time Over Run |  | 2020000437 | 202000454 | NA
18 | A-17-01 | 24 Hrs. Agl. supply works in WGL ZONE | No.13/17, 2017-18 | 02.05.17 | 02.05.17 | 02.05.19 | 2020-04-30 | 72.23 |  | 0 | 75% | 25% |  | 2022-06-18 | - | 18.5 | - | No cost overrun | No Time Over Run |  | 2022000361 | 202200233 | NA
19 | A-18-02 | Aug of PTR cap.at YWGI |  | 18.07.18 | 18.07.18 | 18.07.20 | 2021-02-19 | 6.68 |  | 0 | 75% | 25% |  | 2022-06-20 | - | 31.5 | 2 | No cost overrun | No Time Over Run |  | 2022000380 | 202200372 | NA
20 | A-18-05 | PSDF STRENGTHENING-7NO'S 220KV EHT LINES | No.8/18 2018-19 | 18.09.18 | 18.09.18 | 17.09.19 | 2019-01-31 | 100.55 |  | 0 |  | 25% | 75% | 2019-01-31 | - | - | - | No cost overrun | No Time Over Run |  | 2019000153 | 202000608 | NA
21 | A-18-05 | PSDF STRENGTHENING-7NO'S 220KV EHT LINES |  |  |  |  | 2019-02-11 | [6 empty] | 2019-02-11 | - | - | - |  |  |  | 2019000152 | 202000603
22 | A-19-04 | Augmentation of PTRs at 220 KV Hayathnag |  | 18.03.20 | 18.03.20 | 18.03.22 | 2021-08-26 | 14.4 |  | 0 | 75% | 25% |  | 2022-06-01 | - | 100 | - | No cost overrun | No Time Over Run |  | 2022000132 | 202200048 | NA
23 | A-19-04 | Augmentation of PTRs at 220 KV Hayathnag |  |  |  |  | 2021-08-26 | [6 empty] | 2022-02-14 | [6 empty] | 2021000378 | 202200080
24 | A-19-04 | Augmentation of PTRs at 220 KV Hayathnag |  |  |  |  | 2021-08-26 | [6 empty] | 2022-06-01 | [6 empty] | 2022000143 | 202200057
25 | A-19-05 | Augmentation of PTRs at gesukonda & Tiru |  | 18.03.20 | 18.03.20 | 18.03.22 | 2022-01-26 | 1.47 |  | 0 | 75% | 25% |  | 2022-06-20 | - | 31.5 | 2 | No cost overrun | No Time Over Run |  | 2022000385 | 202200377 | NA
26 | A-20-03 | Aug of PTR at Warangal & Karimnagar Circ |  | 03.10.20 | 03.10.20 | 03.10.22 | 2020-12-23 | 8.26 |  | 0 | 75% | 25% |  | 2021-06-22 | - | 18.5 | - | No cost overrun | No Time Over Run |  | 2021000022 | 202100257 | NA
27 | A-20-04 | Augmentation of PTR at 132KV Donthanpall |  | 03.11.20 | 03.11.20 | 03.11.22 | 2021-02-26 | 3.3 |  | 0 | 75% | 25% |  | 2022-06-13 | - | 47.5 | - | No cost overrun | No Time Over Run |  | 2022000287 | 202200388 | NA
28 | A-20-04 | Augmentation of PTR at 132KV Donthanpall |  |  |  |  | 2021-02-26 | [6 empty] | 2022-06-13 | [6 empty] | 2022000289 | 202200390
29 | A-20-04 | Augmentation of PTR at 132KV Donthanpall |  |  |  |  | 2021-02-26 | [6 empty] | 2022-06-13 | [6 empty] | 2022000290 | 202200392
30 | A-20-04 | Augmentation of PTR at 132KV Donthanpall |  |  |  |  | 2021-08-25 | [6 empty] | 2022-06-16 | [6 empty] | 2022000319 | 202200401
31 | A-20-05 | Augmentation of PTR at 132KV Khaithalapu |  | 18.11.20 | 18.11.20 | 18.11.21 | 2021-08-25 | 0.55 |  | 0 | 75% | 25% |  | 2022-06-16 | - | 47.5 | - | No cost overrun | No Time Over Run |  | 2022000324 | 202200387 | NA
32 | A-20-05 | Augmentation of PTR at 132KV Khaithalapu |  |  |  |  | 2021-08-25 | [6 empty] | 2022-06-16 | [6 empty] | 2022000320 | 202200389
33 | A-20-05 | Augmentation of PTR at 132KV Khaithalapu |  |  |  |  | 2021-08-25 | [6 empty] | 2022-06-17 | [6 empty] | 2022000336 | 202200391
34 | A-20-05 | Augmentation of PTR at 132KV Khaithalapu |  |  |  |  | 2022-03-11 | [6 empty] | 2022-06-17 | [6 empty] | 2022000341 | -
35 | A-20-07 | Aug of 4rd PTR at 132KV Pashmailaram SS |  | 30.03.21 | 30.03.21 | 30.03.22 | 2021-12-30 | 1.56 |  | 0 | 75% | 25% |  | 2022-06-10 | - | 50 | 2 | No cost overrun | No Time Over Run |  | 2022000273 | 202200195 | NA
36 | A-20-07 | Aug of 4rd PTR at 132KV Pashmailaram SS |  |  |  |  | 2021-12-30 | [6 empty] | 2022-06-10 | [6 empty] | 2022000276 | 202200196
37 | A-21-02 | Aug of 132/33 KV PTRs at Mamidipally & 4 |  | 07.05.21 | 07.05.21 | 07.05.22 | 2021-08-21 | 11.47 |  | 0 | 75% | 25% |  | 2022-07-13 | - | 15.5 | - | No cost overrun | No Time Over Run |  | 2022000441 | - | NA
38 | A-21-02 | Aug of 132/33 KV PTRs at Mamidipally & 4 |  |  |  |  | 2021-12-02 | [6 empty] | 2022-07-13 | - | 15.5 | - |  |  |  | 2022000440 | -
39 | A-21-02 | Aug of 132/33 KV PTRs at Mamidipally & 4 |  |  |  |  | 2022-02-08 | [6 empty] | 2022-05-31 | - | 18.5 | - |  |  |  | 2022000103 | -
40 | A-21-04 | Aug. of PTR capacity at 220KV Huzurabad |  | 18.08.21 | 18.08.21 | 18.08.22 |  | 6.03 |  | 0 | 75% | 25% |  |  | - | 160 | - | No cost overrun | No Time Over Run | Part |  | - | NA
41 | A-21-06 | Augmentations of 132KV PTRs at 24Nos Sub | 03/2021-22 | 7.10.21 | 7.10.21 | 7.10.21 | 2021-12-27 | 48.75 |  | 0 | 75% | 25% |  | 2022-06-17 | - | 30 | - | No cost overrun | No Time Over Run |  | 2022000356 | 202200317 | NA
42 | A-21-06 | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2021-12-27 | [6 empty] | 2022-06-17 | [6 empty] | 2022000357 | 202200318
43 | A-21-06 | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2021-12-22 | [6 empty] | 2022-06-18 | [6 empty] | 2022000367 | -
44 | A-21-06 | Augmentations of 132KV PTRs at 24Nos Sub |  |  |  |  | 2021-12-27 | [6 empty] | 2022-06-17 | [6 empty] | 2022000358 | 202200319
45 | D-18-03 | Implementation of DAS for RTSS |  | 11.01.18 | 11.01.18 | 11.01.19 | 2019-03-26 |  |  | 0 | 100 % customer contribution |  |  | 2020-06-15 | - | - | - | No Cost Overrun | No Time Over Run |  | 2020000267 | 202000989 | NA
46 | D-18-03 | Implementation of DAS for RTSS |  |  |  |  | 2019-09-21 | [6 empty] | 2021-07-07 | - | - | - | No Cost Overrun |  |  | 2021000161 | 202100184
47 | D-18-03 | Implementation of DAS for RTSS |  |  |  |  | 2022-03-25 | [6 empty] | 2022-06-22 | - | - | - | No Cost Overrun |  |  | 2022000399 | 202200352
48 | D-18-03 | Implementation of DAS for RTSS |  |  |  |  | 2019-12-04 | [6 empty] | 2020-06-18 | - | - | - | No Cost Overrun |  |  | 2020000302 | 202001721
49 | D-18-03 | Implementation of DAS for RTSS |  |  |  |  | 2019-02-25 | [6 empty] | 2020-06-10 | - | - | - | No Cost Overrun |  |  | 2020000101 | 202001720
50 | D-18-03 | Implementation of DAS for RTSS |  |  |  |  | 2019-02-26 | [6 empty] | 2019-05-21 | - | - | - | No Cost Overrun |  |  | 2019000335 | 202001719
51 | D-18-03 | Implementation of DAS for RTSS |  |  |  |  | 2019-06-14 | [6 empty] | 2020-06-11 | - | - | - | No Cost Overrun |  |  | 2020000187 | 202001718
52 | D-18-03 | Implementation of DAS for RTSS |  |  |  |  | 2022-01-31 | [6 empty] | 2022-05-28 | - | - | - | No Cost Overrun |  |  | 2022000017 | 202200129
53 | D-18-03 | Implementation of DAS for RTSS |  |  |  |  | 2019-08-31 | [6 empty] | 2019-05-16 | - | - | - | No Cost Overrun |  |  | 2019000252 | 202001709
54 | D-19-08 | ABT Metering at 132KV OCM & Mandamarry S |  | 01.04.20 | 01.04.20 | 01.04.21 | 2022-02-20 |  |  | 0 | 100 % customer contribution |  |  | 2022-07-07 | - | - | - | No Cost Overrun | No Time Over Run |  | 2022000430 | - | NA
55 | D-19-08 | ABT Metering at 132KV OCM & Mandamarry S |  |  |  |  | 2022-02-20 | [6 empty] | 2022-07-07 | - | - | - |  |  |  | 2022000429 | 202200416
56 | D-19-08 | ABT Metering at 132KV OCM & Mandamarry S |  |  |  |  | 2022-02-20 | [6 empty] | 2022-07-07 | - | - | - |  |  |  | 2022000431 | 202200417
57 | D-20-16 | Erection of 4Nos 33KV Bays for M/s Amazo |  | 17.04.20 | 17.04.20 | 17.04.21 | 2021-05-24 |  |  | 0 | 100 % customer contribution |  |  | 2021-07-01 | - | - | 1 | No Cost Overrun | No Time Over Run |  | 2021000083 | 202200044 | NA
58 | D-20-16 | Erection of 4Nos 33KV Bays for M/s Amazo |  |  |  |  | 2021-05-24 | [6 empty] | 2021-07-01 | - | - | 1 |  |  |  | 2021000085 | 202200043
59 | D-20-20 | 33KV Bay at 220KV FABCITY SS for chirpa |  | 08.05.20 | 08.05.20 | 08.05.21 | 2021-05-24 |  |  | 0 | 100 % customer contribution |  |  | 2021-07-01 | - | - | 1 | No Cost Overrun | No Time Over Run |  | 2021000084 | 202200045 | NA
60 | D-20-23 | 33KV Bay for Textile Park at Geesukonda |  | 12.06.20 | 12.06.20 | 12.06.21 | 2021-07-09 |  |  | 0 | 100 % customer contribution |  |  | 2021-07-16 | - | - | 1 | No Cost Overrun | No Time Over Run |  | 2021000308 | 202200251 | NA
61 | D-20-23 | 33KV Bay for Textile Park at Geesukonda |  |  |  |  | 2021-05-13 | [6 empty] | 2022-06-16 | - | - |  |  |  |  | 2022000328 | 202200229
62 | D-20-23 | 33KV Bay for Textile Park at Geesukonda |  |  |  |  | 2021-08-26 | [6 empty] | 2022-06-17 | - | - |  |  |  |  | 2022000333 | 202200226
63 | D-20-23 | 33KV Bay for Textile Park at Geesukonda |  |  |  |  | 2021-08-26 | [6 empty] | 2022-06-17 | - | - |  |  |  |  | 2022000334 | 202200227
64 | D-20-27 | 33KV Bays for Amazon at Mahabubnagar Cir |  | 08.07.20 | 08.07.20 | 08.07.21 | 2020-11-17 |  |  | 0 | 100 % customer contribution |  |  | 2021-07-14 | - | - | 1 | No Cost Overrun | No Time Over Run |  | 2021000253 | 202100271 | NA
65 | D-20-31 | Intermediate towers for gajwel ring road |  | 12.11.20 | 12.11.20 | 12.11.21 | 2021-02-20 |  |  | 0 | 100 % customer contribution |  |  | 2021-02-20 | - | - | - | No Cost Overrun | No Time Over Run |  | 2021000143 | 202100230 | NA
66 | D-20-31 | Intermediate towers for gajwel ring road |  |  |  |  | 2021-03-10 | [6 empty] | 2021-03-10 | - | - | - |  |  |  | 2021000142 | 202100231
67 | D-20-31 | Intermediate towers for gajwel ring road |  |  |  |  | 2021-03-04 | [6 empty] | 2021-03-04 | - | - | - |  |  |  | 2021000141 | 202100233
68 | D-20-31 | Intermediate towers for gajwel ring road |  |  |  |  | 2021-02-26 | [6 empty] | 2021-02-26 | - | - | - |  |  |  | 2021000137 | 202100234
69 | D-21-16 | 4Nos 33KV Bays in substation in OMC Wara |  | 25.02.22 | 25.02.22 | 25.02.23 | 2022-03-05 |  |  | 0 | 100 % customer contribution |  |  | 2022-06-18 | - | - | 1 | No Cost Overrun | No Time Over Run |  | 2022000364 | 202200237 | NA
70 | D-21-22 | Shifting of 132KV Nandipet - Nizamabad S |  | 02.10.21 | 02.10.21 | 01.10.22 | 12.01.22 |  |  | 0 | 100 % customer contribution |  |  | 12.1.22 | - | - | - | No Cost Overrun | No Time Over Run |  | 2022000046 | 202200420 | NA
71 | N-18-OMCP | Cap.Material Drawl in O&M for FY:2018-19 |  | 01.04.18 | 01.04.18 | 31.03.22 | 2021-07-26 |  |  | 0 | 75% | 25% |  | 2021-07-28 | - | - | - |  |  |  | 2021000349 | 202200385 | NA
72 | N-18-OMCP | Cap.Material Drawl in O&M for FY:2018-19 |  |  |  |  | 2022-02-14 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000079 | 202200269
73 | N-19-02 | Non Planned Capital works (O&M) 2019-20 |  | 01.04.20 | 01.04.20 | 31.03.22 | 2020-09-28 |  |  | 0 | 75% | 25% |  | 2021-07-15 | - | - | - |  |  |  | 2021000291 | 202100269 | NA
74 | N-19-02 | Non Planned Capital works (O&M) 2019-20 |  |  |  |  | 2021-07-09 | [6 empty] | 2021-07-26 | - | - | - |  |  |  | 2021000347 | 202200370
75 | N-19-02 | Non Planned Capital works (O&M) 2019-20 |  |  |  |  | 2022-03-31 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000354 | 202200249
76 | N-19-OMCP | Cap.Material Drawl in O&M for FY:2019-20 |  | 01.04.20 | 01.04.20 | 31.03.22 | 2020-03-10 |  |  | 0 | 75% | 25% |  | 2022-03-29 | - | - | - |  |  |  | 2021000379 | - | NA
77 | N-20-02 | Non Planned Capital works (O&M) 2020-21 |  | 01.04.20 | 01.04.20 | 31.03.22 | 2019-11-20 |  |  | 0 | 75% | 25% |  | 2021-07-03 | - | - | - |  |  |  | 2021000117 | 202100128 | NA
78 | N-20-02 | Non Planned Capital works (O&M) 2020-21 |  |  |  |  | 2020-10-02 | [6 empty] | 2021-07-05 | - | - | - |  |  |  | 2021000123 | 202100130
79 | N-20-02 | Non Planned Capital works (O&M) 2020-21 |  |  |  |  | 2020-09-23 | [6 empty] | 2022-06-23 | - | - | - |  |  |  | 2022000405 | 202200347
80 | N-20-02 | Non Planned Capital works (O&M) 2020-21 |  |  |  |  | 2021-09-02 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000265 | 202200330
81 | N-21-02 | Non Planned Capital works (O&M) 2021-22 |  | 01.04.21 | 01.04.21 | 31.03.22 | 2021-10-30 |  |  | 0 | 75% | 25% |  | 2022-06-01 | - | - | - |  |  |  | 2022000137 | 202200279 | NA
82 | N-21-02 | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2021-06-15 | [6 empty] | 2022-06-09 | - | - | - |  |  |  | 2022000256 | 202200332
83 | N-21-02 | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2021-08-23 | [6 empty] | 2022-06-15 | - | - | - |  |  |  | 2022000309 | 202200086
84 | N-21-02 | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2022-01-04 | [6 empty] | 2022-06-25 | - | - | - |  |  |  | 2022000415 | 202200381
85 | N-21-02 | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2021-08-23 | [6 empty] | 2022-06-14 | - | - | - |  |  |  | 2022000295 | 202200187
86 | N-21-02 | Non Planned Capital works (O&M) 2021-22 |  |  |  |  | 2021-10-31 | [6 empty] | 2022-06-25 | - | - | - |  |  |  | 2022000414 | 202200380
87 | O-16-01 | Rolling stock for FY 2016-2017 |  | 11.01.2017 | 11.01.2017 | 11.01.2018 | 2017-09-18 | 39.53 |  | 2.68 | 75% | 25% |  | 2022-05-30 | - | - | - |  | Procurement Delay due to poor response of Bidders |  | 2022000055 | 202200359 | NA
88 | O-16-01 | Rolling stock for FY 2016-2017 |  |  |  |  | 2021-11-19 | [6 empty] | 2022-07-21 | - | - | - |  |  |  | 2022000454 | -
89 | O-16-01 | Rolling stock for FY 2016-2017 |  |  |  |  | 2021-11-19 | [6 empty] | 2022-07-21 | - | - | - |  |  |  | 2022000455 | -
90 | O-18-01 | Procure of Major SS equip under rolling |  | 3.4.2018 | 03.04.2018 | 02.04.2019 | 2021-06-07 | 26.43 |  | 0.03 | 75% | 25% |  | 2022-06-17 | - | - | - |  |  |  | 2022000335 | 202200344
91 | R-15-01 | RMI for the year 2015 | APERC in its Tariff Order dt.09.05.2014 has approved Rs.98.50 Crores for combined state of Andhra Pradesh under Renovation & Modernization Scheme for the year 2015-16.After careful consideration, TSTRANSCO accords approval for Rs.53.08 Crores (53.89% of 98.50 Crores. | 16.09.2015 | 16.09.2015 | 15.09.2016 | 2020-11-11 | 53.08 |  | 0.15 | 75% | 25% |  | 2021-07-08 | - | - | - |  | Repeated Tendering |  | 2021000182 | 202100117 | NA
92 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2020-11-11 | [6 empty] | 2022-06-08 | - | - | - |  |  |  | 2022000251 | -
93 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2020-10-31 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000228 | -
94 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2021-07-15 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000152 | 202200149
95 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-09-06 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000118 | 202200005
96 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-09-07 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000122 | 202200006
97 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-08-21 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000124 | 202200007
98 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-09-11 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000125 | 202200008
99 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-09-21 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000126 | 202200009
100 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-08-22 | [6 empty] | 2022-08-03 | - | - | - |  |  |  | 2022000476 | -
101 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-05-25 | [6 empty] | 2022-06-15 | - | - | - |  |  |  | 2022000307 | 202200349
102 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-05-25 | [6 empty] | 2022-06-15 | - | - | - |  |  |  | 2022000308 | 202200350
103 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-09-21 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000127 | 202200010
104 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-08-07 | [6 empty] | 2022-06-04 | - | - | - |  |  |  | 2022000180 | 202200011
105 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-07-10 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000164 | 202200030
106 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-08-05 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000165 | 202200031
107 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-08-27 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000166 | 202200027
108 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-08-09 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000167 | 202200026
109 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-07-10 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000168 | 202200025
110 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-04-08 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000170 | 202200029
111 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-08-06 | [6 empty] | 2021-07-03 | - | - | - |  |  |  | 2021000108 | 202100344
112 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-04-03 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000171 | 202200028
113 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-03-16 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000153 | 202200022
114 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2020-03-05 | [6 empty] | 2022-06-04 | - | - | - |  |  |  | 2022000176 | 202200013
115 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-02-28 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000154 | 202200024
116 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-02-14 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000155 | 202200015
117 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-03-16 | [6 empty] | 2022-06-04 | - | - | - |  |  |  | 2022000177 | 202200014
118 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2020-01-04 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000156 | 202200023
119 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2020-01-11 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000157 | 202200018
120 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2020-01-04 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000158 | 202200021
121 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2020-01-04 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000159 | 202200016
122 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2020-01-04 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000160 | 202200020
123 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2020-02-06 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000161 | 202200017
124 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-04-23 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000037 | 202200127
125 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-04-27 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000039 | 202200128
126 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-09-10 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000014 | 202200130
127 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2019-09-10 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000013 | 202200131
128 | R-15-01 | RMI for the year 2015 |  |  |  |  | 2021-11-16 | [6 empty] | 2022-06-18 | - | - | - |  |  |  | 2022000369 | 202200220
129 | R-16-02 | PSDF |  | 28.10.2015 | 08.02.2016 | 31.03.21 | 2019-07-02 |  |  | 0.062 |  | 10% | 90% | 2022-06-07 | - | - | - | No Cost Overrun | No Time Over Run |  | 2022000208 | 202200164
130 | R-16-02 | PSDF |  |  |  |  | 2019-07-03 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000211 | 202200180
131 | R-16-02 | PSDF |  |  |  |  | 2019-07-05 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000214 | 202200177
132 | R-16-02 | PSDF |  |  |  |  | 2019-12-31 | [6 empty] | 2021-07-13 | - | - | - |  |  |  | 2021000236 | 202100256
133 | R-16-02 | PSDF |  |  |  |  | 2021-11-09 | [6 empty] | 2022-06-15 | - | - | - |  |  |  | 2022000311 | 202200313
134 | R-17-01 | RMI for FY:2017-18 & 2018-19 | TSERC in its tariff order dt.01.05.2017 has approved for investment of Rs.50.11Crs under RMI during each of F.Y:2017-18,2018-19 | 07.10.2017 | 07.10.2017 | 06.10.2018 | 2019-04-16 | 100.22 |  | 2.31 | 75% | 25% |  | 2022-05-28 | - | - | - |  | Repeated Tendering |  | 2022000011 | 202200000 | NA
135 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2020-03-05 | [6 empty] | 2022-06-23 | - | - | - |  |  |  | 2022000401 | 202200351
136 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-04-09 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000005 | 202200032
137 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-04-10 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000012 | 202200106
138 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-05-20 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000006 | 202200107
139 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-04-17 | [6 empty] | 2022-05-29 | - | - | - |  |  |  | 2022000041 | 202200108
140 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-05-03 | [6 empty] | 2022-05-29 | - | - | - |  |  |  | 2022000042 | 202200109
141 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-05-20 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000007 | 202200110
142 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2020-01-04 | [6 empty] | 2021-06-24 | - | - | - |  |  |  | 2021000052 | 202100045
143 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-07-05 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000010 | 202200004
144 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-10-30 | [6 empty] | 2022-06-16 | - | - | - |  |  |  | 2022000322 | 202200181
145 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-11-27 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000062 | 202200256
146 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2020-01-04 | [6 empty] | 2021-06-24 | - | - | - |  |  |  | 2021000053 | 202100046
147 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-08-10 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000002 | 202200111
148 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-09-07 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000001 | 202200112
149 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-05-08 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000000 | 202200114
150 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-06-26 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000003 | 202200115
151 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-05-02 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000004 | 202200116
152 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-04-24 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000016 | 202200117
153 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-04-30 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000018 | 202200118
154 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-04-25 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000020 | 202200119
155 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-04-12 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000025 | 202200120
156 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-04-17 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000031 | 202200122
157 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-04-23 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000032 | 202200123
158 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-04-16 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000015 | 202200124
159 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-04-15 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000034 | 202200125
160 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-04-15 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000035 | 202200126
161 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2018-04-17 | [6 empty] | 2019-06-18 | - | - | - |  |  |  | 2019000730 | -
162 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2021-08-02 | [6 empty] | 2022-06-30 | - | - | - |  |  |  | 2022000426 | 202200353
163 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2021-08-02 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000198 | -
164 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2021-08-02 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000199 | -
165 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2022-05-30 | [6 empty] | 2022-06-22 | - | - | - |  |  |  | 2022000395 | -
166 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2021-03-16 | [6 empty] | 2022-07-21 | - | - | - |  |  |  | 2022000460 | -
167 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-01-05 | [6 empty] | 2020-09-01 | - | - | - |  |  |  | 2020000586 | -
168 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-06-12 | [6 empty] | 2020-09-09 | - | - | - |  |  |  | 2020000613 | 202001670
169 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-04-25 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000216 | 202200188
170 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-11-30 | [6 empty] | 2021-07-14 | - | - | - |  |  |  | 2021000249 | 202100037
171 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-09-03 | [6 empty] | 2020-09-08 | - | - | - |  |  |  | 2020000611 | 202000693
172 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2021-08-13 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000173 | 202200421
173 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-12-20 | [6 empty] | 2021-07-15 | - | - | - |  |  |  | 2021000295 | 202100029
174 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2021-06-30 | [6 empty] | 2022-06-01 | - | - | - |  |  |  | 2022000133 | 202200282
175 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2021-05-31 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000095 | 202200078
176 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2020-12-23 | [6 empty] | 2021-07-19 | - | - | - |  |  |  | 2021000318 | 202100270
177 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2021-07-21 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000229 | 202200189
178 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2021-10-25 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000230 | 202200193
179 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2022-02-02 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000069 | 202200071
180 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2021-11-15 | [6 empty] | 2022-07-27 | - | - | - |  |  |  | 2022000472 | -
181 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-01-04 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000338 | 202200386
182 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2020-08-17 | [6 empty] | 2021-08-03 | - | - | - |  |  |  | 2021000356 | 202100255
183 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-03-16 | [6 empty] | 2020-07-09 | - | - | - |  |  |  | 2020000472 | 202000253
184 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-12-05 | [6 empty] | 2021-07-19 | - | - | - |  |  |  | 2021000317 | 202100261
185 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2020-12-13 | [6 empty] | 2022-06-18 | - | - | - |  |  |  | 2022000359 | 202200217
186 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2019-12-23 | [6 empty] | 2022-06-28 | - | - | - |  |  |  | 2022000419 | 202200354
187 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2020-12-09 | [6 empty] | 2021-07-05 | - | - | - |  |  |  | 2021000127 | 202100214
188 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2020-06-15 | [6 empty] | 2022-06-28 | - | - | - |  |  |  | 2022000420 | 202200355
189 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2021-04-18 | [6 empty] | 2022-06-02 | - | - | - |  |  |  | 2022000147 | 202200214
190 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2020-07-25 | [6 empty] | 2021-06-24 | - | - | - |  |  |  | 2021000042 | 202100202
191 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2020-06-15 | [6 empty] | 2022-06-25 | - | - | - |  |  |  | 2022000416 | 202200357
192 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2021-07-28 | [6 empty] | 2022-06-04 | - | - | - |  |  |  | 2022000175 | 202200133
193 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2020-08-20 | [6 empty] | 2022-07-16 | - | - | - |  |  |  | 2022000450 | -
194 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2015-10-19 | [6 empty] | 2021-07-15 | - | - | - |  |  |  | 2021000270 | 202100084
195 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2022-02-19 | [6 empty] | 2022-06-04 | - | - | - |  |  |  | 2022000174 | 202200134
196 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2021-04-18 | [6 empty] | 2022-06-02 | - | - | - |  |  |  | 2022000148 | 202200213
197 | R-17-01 | RMI for FY:2017-18 & 2018-19 |  |  |  |  | 2022-03-28 | [6 empty] | 2022-06-18 | - | - | - |  |  |  | 2022000360 | 202200235
198 | R-20-01 | Renovation & Modernization Scheme - 2020 | TSERC in its tariff order dt.20.03.2020 has approved for investment of Rs.75.67Crs under RMI during each of F.Y:2020-21 | 16.09.2020 | 16.09.2020 | 15.09.2020 | 2021-03-06 | 75.6 |  | 5.39 | 75% | 25% |  | 2021-07-06 | - | - | - |  | Repeated Tendering |  | 2021000136 | 202100131 | NA
199 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-02-20 | [6 empty] | 2022-06-24 | - | - | - |  |  |  | 2022000407 | 202200348
200 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-12-04 | [6 empty] | 2022-06-15 | - | - | - |  |  |  | 2022000305 | 202200300
201 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-03-23 | [6 empty] | 2022-06-01 | - | - | - |  |  |  | 2022000134 | 202200281
202 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-02-03 | [6 empty] | 2022-06-02 | - | - | - |  |  |  | 2022000150 | 202200285
203 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-03-20 | [6 empty] | 2021-07-03 | - | - | - |  |  |  | 2021000107 | 202100121
204 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2020-12-15 | [6 empty] | 2021-07-03 | - | - | - |  |  |  | 2021000112 | 202100138
205 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-04-24 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000066 | 202200073
206 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-03-23 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000068 | 202200072
207 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-03-25 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000213 | 202200079
208 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-05-29 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000084 | 202200077
209 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-12-16 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000077 | 202200070
210 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-11-24 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000163 | 202200058
211 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-09-03 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000339 | 202200394
212 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-02-20 | [6 empty] | 2022-06-22 | - | - | - |  |  |  | 2022000397 | 202200395
213 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-03-11 | [6 empty] | 2022-06-22 | - | - | - |  |  |  | 2022000396 | 202200398
214 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-09-14 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000048 | 202200211
215 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-10-10 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000275 | 202200194
216 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-09-16 | [6 empty] | 2022-06-20 | - | - | - |  |  |  | 2022000377 | 202200223
217 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-11-22 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000067 | 202200252
218 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-04-03 | [6 empty] | 2021-07-12 | - | - | - |  |  |  | 2021000216 | 202200202
219 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-05-31 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000105 | 202200267
220 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-06-12 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000078 | 202200270
221 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-01-05 | [6 empty] | 2022-06-01 | - | - | - |  |  |  | 2022000142 | 202200263
222 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-07-15 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000107 | 202200271
223 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-06-26 | [6 empty] | 2022-06-02 | - | - | - |  |  |  | 2022000146 | 202200215
224 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-07-13 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000130 | 202200272
225 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2019-12-16 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000269 | 202200206
226 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-06-27 | [6 empty] | 2022-06-08 | - | - | - |  |  |  | 2022000243 | 202200198
227 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2020-10-30 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000070 | 202200250
228 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-06-05 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000058 | 202200325
229 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-06-06 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000064 | 202200253
230 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2020-12-15 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000054 | 202200203
231 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-07-07 | [6 empty] | 2022-06-01 | - | - | - |  |  |  | 2022000144 | 202200261
232 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-12-16 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000266 | 202200205
233 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-08-12 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000057 | 202200326
234 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-10-23 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000052 | 202200255
235 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-10-27 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000056 | 202200327
236 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-01-30 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000277 | 202200197
237 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-03-31 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000051 | 202200329
238 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-03-27 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000063 | 202200254
239 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-03-19 | [6 empty] | 2022-07-27 | - | - | - |  |  |  | 2022000464 | -
240 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-12-03 | [6 empty] | 2022-07-27 | - | - | - |  |  |  | 2022000465 | -
241 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-03-19 | [6 empty] | 2022-07-21 | - | - | - |  |  |  | 2022000459 | -
242 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-10-02 | [6 empty] | 2022-07-27 | - | - | - |  |  |  | 2022000466 | -
243 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-02-08 | [6 empty] | 2021-07-14 | - | - | - |  |  |  | 2021000254 | 202100274
244 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-01-04 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000233 | 202200305
245 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-10-14 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000206 | 202200297
246 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-04-05 | [6 empty] | 2021-07-15 | - | - | - |  |  |  | 2021000265 | -
247 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-04-05 | [6 empty] | 2021-07-15 | - | - | - |  |  |  | 2021000266 | 202200286
248 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-04-05 | [6 empty] | 2021-07-15 | - | - | - |  |  |  | 2021000267 | 202200287
249 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-04-05 | [6 empty] | 2021-07-15 | - | - | - |  |  |  | 2021000269 | 202200288
250 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2020-12-19 | [6 empty] | 2021-07-19 | - | - | - |  |  |  | 2021000320 | 202100278
251 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-04-05 | [6 empty] | 2022-06-30 | - | - | - |  |  |  | 2022000427 | -
252 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-03-22 | [6 empty] | 2022-06-08 | - | - | - |  |  |  | 2022000239 | 202200307
253 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-05-12 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000204 | 202200295
254 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-01-05 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000205 | 202200296
255 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-12-31 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000210 | 202200298
256 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-09-03 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000212 | 202200299
257 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-03-16 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000189 | 202200291
258 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-04-30 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000185 | -
259 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2020-11-19 | [6 empty] | 2022-06-20 | - | - | - |  |  |  | 2022000370 | 202200218
260 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-12-29 | [6 empty] | 2022-06-08 | - | - | - |  |  |  | 2022000246 | 202200182
261 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-11-05 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000343 | 202200241
262 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-10-22 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000347 | 202200242
263 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-11-07 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000349 | 202200243
264 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-11-05 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000350 | 202200244
265 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-07-14 | [6 empty] | 2022-06-23 | - | - | - |  |  |  | 2022000403 | 202200275
266 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-06-05 | [6 empty] | 2022-06-23 | - | - | - |  |  |  | 2022000402 | 202200276
267 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-03-29 | [6 empty] | 2022-06-23 | - | - | - |  |  |  | 2022000404 | 202200277
268 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-10-30 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000351 | 202200246
269 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-11-03 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000352 | 202200247
270 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-10-25 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000353 | 202200248
271 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2019-06-10 | [6 empty] | 2022-06-25 | - | - | - |  |  |  | 2022000411 | 202200356
272 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-02-25 | [6 empty] | 2022-06-20 | - | - | - |  |  |  | 2022000371 | 202200219
273 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-09-12 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000331 | 202200236
274 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-11-21 | [6 empty] | 2022-06-16 | - | - | - |  |  |  | 2022000326 | 202200239
275 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-07-24 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000337 | 202200230
276 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-11-16 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000215 | 202200176
277 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-01-07 | [6 empty] | 2022-06-08 | - | - | - |  |  |  | 2022000247 | 202200183
278 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2022-02-09 | [6 empty] | 2022-06-18 | - | - | - |  |  |  | 2022000362 | 202200234
279 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-11-29 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000234 | 202200192
280 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-06-08 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000236 | 202200190
281 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-09-04 | [6 empty] | 2022-06-09 | - | - | - |  |  |  | 2022000257 | 202200191
282 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-09-03 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000278 | 202200184
283 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-10-24 | [6 empty] | 2022-06-04 | - | - | - |  |  |  | 2022000179 | 202200135
284 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2020-12-10 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000201 | 202200150
285 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-09-18 | [6 empty] | 2022-08-03 | - | - | - |  |  |  | 2022000477 | -
286 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-08-18 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000110 | 202200002
287 | R-20-01 | Renovation & Modernization Scheme - 2020 |  |  |  |  | 2021-09-21 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000109 | 202200001
288 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  | 17.07.2021 | 17.07.2021 | 31.03.2022 | 2021-05-31 | - |  | 6.07 | 75% | 25% |  | 2022-05-31 | - | - | - |  | Repeated Tendering |  | 2022000106 | 202200257 | NA
289 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-04-28 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000169 | 202200059
290 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-05-24 | [6 empty] | 2022-06-08 | - | - | - |  |  |  | 2022000238 | 202200342
291 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-06-17 | [6 empty] | 2022-06-13 | - | - | - |  |  |  | 2022000292 | 202200335
292 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-05-07 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000286 | 202200337
293 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-06-01 | [6 empty] | 2022-06-14 | - | - | - |  |  |  | 2022000294 | 202200312
294 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-05-11 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000100 | -
295 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-09-04 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000207 | 202200340
296 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-08-07 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000340 | 202200346
297 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-06-09 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000192 | 202200292
298 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-06-29 | [6 empty] | 2022-06-16 | - | - | - |  |  |  | 2022000325 | 202200240
299 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-06-20 | [6 empty] | 2022-06-15 | - | - | - |  |  |  | 2022000310 | 202200085
300 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-08-25 | [6 empty] | 2022-07-28 | - | - | - |  |  |  | 2022000473 | -
301 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-07-08 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000267 | 202200207
302 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-06-30 | [6 empty] | 2022-07-20 | - | - | - |  |  |  | 2022000453 | -
303 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-07-01 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000190 | -
304 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-06-23 | [6 empty] | 2022-06-15 | - | - | - |  |  |  | 2022000312 | 202200084
305 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-06-24 | [6 empty] | 2022-06-15 | - | - | - |  |  |  | 2022000314 | 202200083
306 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-09-30 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000090 | 202200039
307 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-07-01 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000217 | 202200166
308 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-07-08 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000082 | 202200065
309 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-10-20 | [6 empty] | 2022-06-21 | - | - | - |  |  |  | 2022000387 | 202200393
310 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-07-17 | [6 empty] | 2022-06-08 | - | - | - |  |  |  | 2022000245 | 202200309
311 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-07-12 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000080 | 202200042
312 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-07-06 | [6 empty] | 2022-06-14 | - | - | - |  |  |  | 2022000298 | 202200047
313 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-07-19 | [6 empty] | 2022-06-09 | - | - | - |  |  |  | 2022000258 | 202200343
314 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-12-09 | [6 empty] | 2022-07-13 | - | - | - |  |  |  | 2022000439 | -
315 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-02-15 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000281 | 202200090
316 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-08 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000280 | -
317 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-05-02 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000283 | -
318 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-08-09 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000209 | 202200341
319 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-07-24 | [6 empty] | 2022-06-20 | - | - | - |  |  |  | 2022000373 | 202200222
320 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-08-02 | [6 empty] | 2022-06-14 | - | - | - |  |  |  | 2022000297 | 202200088
321 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-08-25 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000187 | 202200146
322 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-12-20 | [6 empty] | 2022-07-13 | - | - | - |  |  |  | 2022000438 | -
323 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-11-19 | [6 empty] | 2022-07-21 | - | - | - |  |  |  | 2022000456 | -
324 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-08-07 | [6 empty] | 2022-06-15 | - | - | - |  |  |  | 2022000315 | 202200082
325 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-07-17 | [6 empty] | 2022-06-08 | - | - | - |  |  |  | 2022000244 | 202200308
326 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-09-17 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000218 | 202200034
327 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-08-12 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000019 | 202200074
328 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-01-05 | [6 empty] | 2022-07-27 | - | - | - |  |  |  | 2022000467 | -
329 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-12-05 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000193 | 202200293
330 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-09-02 | [6 empty] | 2022-06-09 | - | - | - |  |  |  | 2022000261 | 202200333
331 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-11-29 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000344 | 202200396
332 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-11-10 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000075 | 202200259
333 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-11-20 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000073 | 202200268
334 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-02-09 | [6 empty] | 2022-06-01 | - | - | - |  |  |  | 2022000145 | 202200262
335 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-08-24 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000097 | 202200266
336 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-12-03 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000227 | 202200303
337 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-01-05 | [6 empty] | 2022-07-27 | - | - | - |  |  |  | 2022000468 | -
338 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-05-02 | [6 empty] | 2022-07-23 | - | - | - |  |  |  | 2022000463 | -
339 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2020-07-29 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000332 | 202200397
340 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-11-02 | [6 empty] | 2022-06-15 | - | - | - |  |  |  | 2022000317 | 202200315
341 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-07-27 | [6 empty] | 2022-06-15 | - | - | - |  |  |  | 2022000318 | 202200316
342 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-09-10 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000091 | 202200064
343 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-10-21 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000021 | 202200076
344 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-01-28 | [6 empty] | 2022-06-09 | - | - | - |  |  |  | 2022000260 | 202200334
345 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-02-02 | [6 empty] | 2022-07-27 | - | - | - |  |  |  | 2022000469 | -
346 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-09-29 | [6 empty] | 2022-07-22 | - | - | - |  |  |  | 2022000461 | -
347 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-10-01 | [6 empty] | 2022-06-18 | - | - | - |  |  |  | 2022000365 | 202200238
348 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-11-23 | [6 empty] | 2022-06-16 | - | - | - |  |  |  | 2022000327 | 202200231
349 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-10-01 | [6 empty] | 2022-07-21 | - | - | - |  |  |  | 2022000457 | -
350 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-06-12 | [6 empty] | 2022-06-14 | - | - | - |  |  |  | 2022000303 | -
351 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-12-17 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000279 | 202200185
352 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-11-12 | [6 empty] | 2022-06-14 | - | - | - |  |  |  | 2022000299 | 202200089
353 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-10-20 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000086 | 202200067
354 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-10-18 | [6 empty] | 2022-06-15 | - | - | - |  |  |  | 2022000316 | 202200081
355 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-08-30 | [6 empty] | 2022-06-08 | - | - | - |  |  |  | 2022000248 | 202200310
356 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-10-29 | [6 empty] | 2022-06-15 | - | - | - |  |  |  | 2022000313 | 202200314
357 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-11-03 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000222 | 202200301
358 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-04 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000235 | -
359 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-11-02 | [6 empty] | 2022-06-14 | - | - | - |  |  |  | 2022000301 | 202200087
360 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-05-03 | [6 empty] | 2022-06-14 | - | - | - |  |  |  | 2022000302 | -
361 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-02-03 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000285 | 202200336
362 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-02-12 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000040 | 202200051
363 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-11-17 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000202 | 202200294
364 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-01-08 | [6 empty] | 2022-06-08 | - | - | - |  |  |  | 2022000240 | 202200179
365 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-01-08 | [6 empty] | 2022-06-08 | - | - | - |  |  |  | 2022000241 | 202200178
366 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-12-16 | [6 empty] | 2022-07-21 | - | - | - |  |  |  | 2022000458 | -
367 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-12-28 | [6 empty] | 2022-07-27 | - | - | - |  |  |  | 2022000470 | -
368 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-06 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000117 | 202200200
369 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-01-13 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000072 | 202200260
370 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-08-17 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000197 | 202200147
371 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-12-06 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000219 | 202200035
372 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-11-21 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000348 | 202200399
373 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-12-04 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000271 | 202200208
374 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-11-29 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000081 | 202000704
375 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-12-06 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000101 | 202200258
376 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-12-04 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000270 | 202200204
377 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-01-04 | [6 empty] | 2022-07-27 | - | - | - |  |  |  | 2022000471 | -
378 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-11-20 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000345 | 202200345
379 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-13 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000045 | -
380 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-12-15 | [6 empty] | 2022-06-22 | - | - | - |  |  |  | 2022000398 | 202200400
381 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-28 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000282 | -
382 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-12-13 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000231 | 202200304
383 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-05 | [6 empty] | 2022-06-09 | - | - | - |  |  |  | 2022000263 | 202200060
384 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-29 | [6 empty] | 2022-07-28 | - | - | - |  |  |  | 2022000475 | -
385 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-03-16 | [6 empty] | 2022-07-16 | - | - | - |  |  |  | 2022000451 | -
386 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-12-24 | [6 empty] | 2022-06-09 | - | - | - |  |  |  | 2022000252 | 202200063
387 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-12-29 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000123 | 202200199
388 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-10-29 | [6 empty] | 2022-06-09 | - | - | - |  |  |  | 2022000253 | 202200062
389 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-01-13 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000098 | 202200265
390 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-01-22 | [6 empty] | 2022-06-08 | - | - | - |  |  |  | 2022000242 | 202200161
391 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-01-28 | [6 empty] | 2022-06-08 | - | - | - |  |  |  | 2022000249 | 202200311
392 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-01-25 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000092 | 202200038
393 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-04-18 | [6 empty] | 2022-06-02 | - | - | - |  |  |  | 2022000149 | 202200212
394 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-01-24 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000099 | 202200264
395 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-02-19 | [6 empty] | 2022-06-20 | - | - | - |  |  |  | 2022000379 | 202200221
396 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-01-28 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000089 | 202200040
397 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-07-14 | [6 empty] | 2022-06-16 | - | - | - |  |  |  | 2022000329 | 202200232
398 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-06-23 | [6 empty] | 2022-07-14 | - | - | - |  |  |  | 2022000443 | -
399 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-21 | [6 empty] | 2022-06-09 | - | - | - |  |  |  | 2022000262 | 202200061
400 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-22 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000274 | 202200209
401 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-02-09 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000272 | 202200210
402 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-11 | [6 empty] | 2022-07-14 | - | - | - |  |  |  | 2022000445 | -
403 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-26 | [6 empty] | 2022-06-01 | - | - | - |  |  |  | 2022000140 | 202200056
404 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-02-18 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000096 | 202200216
405 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-11 | [6 empty] | 2022-05-29 | - | - | - |  |  |  | 2022000043 | 202200245
406 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-11 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000342 | -
407 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-15 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000088 | 202200066
408 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-02 | [6 empty] | 2022-06-01 | - | - | - |  |  |  | 2022000139 | 202200055
409 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-05-01 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000102 | -
410 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-04 | [6 empty] | 2022-06-20 | - | - | - |  |  |  | 2022000378 | 202200371
411 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-11 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000330 | 202200228
412 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-31 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000047 | 202200052
413 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-10 | [6 empty] | 2022-06-08 | - | - | - |  |  |  | 2022000237 | 202200338
414 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-10 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000232 | 202200339
415 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-17 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000226 | 202200302
416 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-10 | [6 empty] | 2022-06-18 | - | - | - |  |  |  | 2022000368 | 202200224
417 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-10 | [6 empty] | 2022-06-20 | - | - | - |  |  |  | 2022000372 | 202200225
418 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-14 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000049 | 202200053
419 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-06-26 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000182 | 202200148
420 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-25 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000060 | 202200068
421 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-03-22 | [6 empty] | 2022-06-10 | - | - | - |  |  |  | 2022000284 | 202200186
422 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-16 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000026 | 202200050
423 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-07-22 | [6 empty] | 2022-07-23 | - | - | - |  |  |  | 2022000462 | -
424 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2019-08-11 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000191 | 202200151
425 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-12 | [6 empty] | 2022-07-28 | - | - | - |  |  |  | 2022000474 | -
426 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-03-25 | [6 empty] | 2022-06-16 | - | - | - |  |  |  | 2022000321 | 202200402
427 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-24 | [6 empty] | 2022-05-28 | - | - | - |  |  |  | 2022000028 | 202200075
428 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-29 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000196 | -
429 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-16 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000195 | -
430 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-01 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000050 | -
431 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-04 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000071 | -
432 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-30 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000194 | -
433 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-11 | [6 empty] | 2022-06-17 | - | - | - |  |  |  | 2022000346 | -
434 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-07-14 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000220 | 202200036
435 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-08-16 | [6 empty] | 2022-06-07 | - | - | - |  |  |  | 2022000221 | 202200037
436 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-01-13 | [6 empty] | 2022-06-03 | - | - | - |  |  |  | 2022000172 | 202200049
437 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-19 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000200 | -
438 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-03-30 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000083 | 202200046
439 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-06 | [6 empty] | 2022-05-31 | - | - | - |  |  |  | 2022000114 | -
440 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2021-07-06 | [6 empty] | 2022-06-06 | - | - | - |  |  |  | 2022000184 | 202200152
441 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION |  |  |  |  | 2022-04-04 | [6 empty] | 2022-05-30 | - | - | - |  |  |  | 2022000044 | -
[9 empty] | Total | 16.711 | [5 empty] | 1184 | 28
Chief Engineer/ Transmission
Abstract
| Sl.No | Description | Amount Capitalization
| 1 | RMI | 7.84
| 2 | Schemes & Non plan and other capital works | 36.84
44.68
91 | R-12-02 | Capacitor banks T.O.O 355, Dt:16.02.2013 |  |  |  |  | 2017-02-11 | [6 empty] | 2019-07-10 | [6 empty] | 2019000903 | 0

## CE-400kV LIS capitlza
ANNEXURE-I
Scheme wise Actual Capitalization for FY 2022-23 (400kV Lift Irrigation Schemes)
FY: 2022-23
Sl No | Name of the project | Invest-ment approval date | Start Date |  | Completion Date (400kV works) |  | Approved cost as per Investment approval | Capitalization upto previous years (As per audited Financial Statements) (from FY 2016-17) | Capitalization claimed for the current year | Means of Finance ( % ) |  |  | Date of Capitalization | Addition to Transmission Network (only 400kV wing data ) |  |  | Reasons for cost overrun | Reasons for time overrun | Whether part or Full Capitalization | Physical Completion Certificate (400kV works only) | Financial Completion Certificate (400kV works only) | Electrical Inspector Certificate
|  |  | Schedule | Actual | Schedule | Actual | (Rs.in Crs) | (Rs.in Crs) | (Rs.in Crs) | Debt | Equity | Grants |  | Lines (CkM) | Capacity (MVA) | Bays (No.)
1 | Indira Sagar Rudrammakota LI scheme (L-13-01) | - | - | Mar' 2014 | - | Aug' 2017 | - | 109.18 | 0.01 | - | - | 100 | 10.08.2017 | 0 | 0 | 0 | NA | - | - | 2019000432 2022000442 | 0202000780 0202001837 | Exempted by GoTS as per Energy (PR.II) Department, G.O.Ms.No.10, Dt.09.05.2022 | EE400C3WGL
2 | Sita Rama LI Scheme (L-18-04) | - | - | Sep' 2018 | - | May, 2023 | - | 99.07 | 164.65 | - | - | 100 | 30.06.2022 | 0 | 0 | 0 | NA | - | Part | 2020000587 2021000024 2021000025 2021000026 2021000177 2022000392 2023000327 2023000328 2023000329 2023000354 | 0202000375 0202100164 0202100163 0202100165 0202100166 0202200361 2023000423 2023000421 2023000422 2023000420
| Total | [6 empty] | 208.25 | 164.66
NA:Not applicable as the investment is within the approved scheme cost.
CHIEF ENGINEER/400kV

## CE-LIS 22-23 capitiliz
ANNEXURE-I
Lift Irrigation Schemes -- Actual Capitalisation for FY 2022-23
FY : 2022-23
Sl. No. | L1 WBS Element | Name of the Project | Start Date |  | Completion Date |  | Approved Cost as per Investment Approval | Capitalisation upto previous year as per Audited Financial Statements | Capitalisation claimed for the Current Year(FY 2022-23) (Rs. Crores) | Means of Finance |  |  | Date of Capitalisation | Addition to Transmission Network |  |  | Reason for Cost Overrun | Reason for Time Overrun | Whether Part Capitalisation (or) Full Capitalisation | Physical Completion Certificate | Financial Completion Certificate | Electricial Inspector Certificate
|  |  | Scheduled | Actual | Scheduled | Actual |  |  |  | Debt | Equity | Grant |  | Lines (CKT KM) | Capacity (MVA) | Bays (Nos.)
1 | D-15-03 (revised) | 400kV Supply to Myadaram SS /Ramadugu SS/tippapur SS | Sep'16 |  | Jul'19 | Jan'20 | 889.99 | 771.62 | 23.26 | Grant |  |  | 31.03.2019 | [5 empty] | Part Capitalisation | 2019000619 2019000618 2020000420 2020000425 | 0202001108, 0202001113 0202000738, 0202000743 0202000755, 0202001108 0202001113, 0202000738 0202000743, 0202000755 | Exempted by GoTS as per Energy (PR.II) Department, GO Ms No. 10 Date 09-05-2022
2 | L-05-02 | Extn of 220&132kV Supply to Godavari LIS (Gandiramaram,Bommakur,Rangaraopally,Dharmasagar,Salivagu SS,Connected Lines and Bays) | Apr'17 |  | Jul'21 | Oct'19 | 119.59 | 57.485 | 0.08 | Grant |  |  | 05.02.2018, 25.10.2019, 20.08.2018, 05.02.2018, 06.11.2017, 06.11.2017, 10.01.2018, 10.01.2018, 25.10.2019, 10.01.2018, 27.04.2011, 30.03.2022 | [6 empty] | 2019000431 2019000435 2019000438 2019000439 2019000440 2019000443 2019000528 2019000531 | 0202000171, 0202001456 0202001461, 0202000064 0202000056, 0202000095 0202000083, 0202000089
3 | L-11-01 (revised) | Extn of Supply@132kV Thotpaly-Gourvly LI (Huzurabad to Regonda Line, LILO to Huzurabad,Huzurabad SS) | Nov'14 |  | Dec'16 | Sep'19 | 43.733 | 36.83 | -0.03 | Grant |  |  | 31.03.2020, 31.03.2017, 19.07.2017 | [5 empty] | Part Capitalisation | 2020000368 | 0202000760 0202001146
4 | L-14-01 | Lift Irrigation Scheme at Jogapur | Apr'17 |  | Jul'18 | May'18 | 45.1209 | 12.17 | 0.03 | Grant |  |  | 31.03.2019 | [5 empty] | Part Capitalisation | 2019000451 2019000449 2019000447 | `0202000769
5 | L-15-01 (new) | Extn of Supply @ 220kV to AMRP LLC LIS | Jan'16 |  | Apr'16 | Jan'18 | 7.99 | 2.5281 | -0.035 | Grant |  |  | 23.01.2018 , 17.01.2018, 03.10.2016,17.01.2018 | [6 empty] | 2019000849 2019000824 2021000038 2019000823 | 202000962 202000963 202000965 202000966
6 | L-15-02 | 400 kV Supply to Tippapur (Ramadugu to Tippapur Line) | Jun'17 |  | Sep'18 | Apr'19 | 158.28 | 155.09 | -1.42 | Grant |  |  | 31.03.2020 | [6 empty] | 2019000474 | `0202000788
7 | L-15-03 (revised) | 400kV Supply to Myadaram (Ramadugu to Medaram Line) | Aug'16 |  | Aug'17 | Nov'18 | 66.48 | 54.7 | 0 | Grant |  |  | 31.03.2019 | [5 empty] | Part Capitalisation | 2019000607 2019000619 | `020200079
8 | L-15-04 | 400kV Supply to Ramadugu Mandal (LILO of Both SCCL -Gajwel CKTS to Ramadugu) | Aug'16 |  | Dec'17 | May'18 | 113.96 | 88.35 | -0.24 | Grant |  |  | 31.03.20219 | [5 empty] | Part Capitalisation | 2019000615 | `0202000793
9 | L-16-04 | Extn of 132 kV Supply to Kanakapur PCLI | May'17 |  | May'18 | Nov'18 | 31.73 | 19.23 | 0.01 | Grant |  |  | 31.03.2019 | [5 empty] | Part Capitalisation | 2020000367 2019000658 2019000663 2019000367 | 0202001153 0202001154 020200079 0202000802 0202000801
10 | L-16-05 | Kaleshwaram Lift Irrigation Project (Tukkapur SS & Bays,Chandulapur SS & LILO of Gajwel -Bplapally to Chandulapur SS and Sundilla, Annaram,Medigadda, Malakpet SS, Connected Lines and Bays) | Mar'17 |  | Dec'18 | Jun'20 | 1336.07 | 1134.38 | 10.6737 | Grant |  |  | 31.03.2019 | [5 empty] | Part Capitalisation | 2019000480 2019000482 2019000472 2019000483 2019000469 2019000444 2019000478 2019000481 2020000450 2021000363 2021000359 2020000124 2019000536 | 0202100330, 0202100370 0202000787, 0202000783 0202100068, 0202000771 0202000766, 0202000761 0202000758, 0202000750 0202000732
11 | L-17-01 (revised) | Chanaka - Korata Lift Irrigation Scheme | Mar'17 |  | Jun'18 | May'19 | 43.49 | 24.48 | 0.09 | Grant |  |  | 31.03.2019 | [5 empty] | Part Capitalisation | 2019000659 2019000661 2020000375 2019000662 | 0202001164 0202001167 0202000727 0202000716 0202000705 0202000700
12 | L-17-03 | FFC | Feb'18 |  | Nov'18 | Jun'20 | 186.89 | 101.32 | 0.29 | Grant |  |  | 31.03.2020, 31.03.2021 | [5 empty] | Part Capitalisation | 2021000073 2021000036 2020000633 2020000632 2021000044 2020000631 | 0202100072 0202000690 0202000695 0202000688 0202100073 0202100075
13 | L-16-03 | Erection of bulk load works of 400/11KV Tukkapur LI(Package 12) under Kaleshwaram Lift Irrigation Project (Dr.B.R.P.C.L.I.S) (Chandulapur to Tukkapur Line, Narsapur to Tukkapur Line, Tippapur to Chandulapur Line) | Jun'17 |  | Dec'18 | Mar'20 | 219.28 | 183.57 | 1.2 | Grant |  |  | 31.03.2020 | [5 empty] | Part Capitalisation | 2020000134 2020000135 2020000495 2020000134 2020000577 2019000433 | `0202001724
14 | L-18-02 | 220/11 kv SS at Bheemghanpur | Jun'18 |  | Dec'18 | Aug'19 | 23.99 | 10.87 | 0.05 | Grant |  |  | 14.08.2019 | [6 empty] | 2012000534 | `0202000397
15 | L-18-03 | Thumilla LIS | Jul'18 |  | Dec'18 | Nov'18 | 28.17 | 16.8501 | 0.16756 | Grant |  |  | 19.11.2018, 31.08.2019 | [5 empty] | Part Capitalisation | 2020000473 2019000923 2021000362 | `0202001656 0202001654
16 | L-13-02 | Kaleshwaram Lift Irrigation Scheme OLD(kannepalli) | Jan'18 |  | Jun'20 | Jun'20 | 28.78 | 17.35 | 0.51 | Grant |  |  | 31.03.2021 | [6 empty] | 2021000346 2021000345 2021000351
17 | L-17-04 | Akkaram and Markook | Aug'18 |  | May'19 | Apr'20 | 197.66 | 116.775 | 1.4336 | Grant |  |  | 26.04.2020, 16.05.2020 | [6 empty] | 2021000361 2021000358 2021000360 2021000302 2021000301 2021000299
18 | L-14-02 | Dr B.R.Ambedkar Pranahitha LIS Pkg-20,21,22 (Manchippa,Sarangapur,Yacharam Thanda SS, Connected Lines and Bays) | Apr'19 |  | May'22 | Dec'23 | 266.47 | 67.74 | -0.38 | Grant |  |  | 31.03.2022 |  | 120 | 3
19 | D-17-04 (new) | 132 kV DC/SC line from Gangadhara LIS | Dec'09 |  | Dec'10 | July'12 | 7.99 | 0.56 | -0.01 | Grant |  |  | 09.02.2019
20 | l-17-05 | Diversion of 3 No's 220 kV Lines-Anjanagiri | May'18 |  | Nov'18 | Dec'20 | 18.23 | 1.1089 | -0.071348 | Grant |  |  | 09.12.2020
21 | l-19-02 | 132/11 kV RS Ghanpur | Mar'20 |  | Sep'20 | Mar'22 | 22.43 | 0.89 | 16.2 | Grant |  |  | 30.03.2022 , 07.02.2022 , 25.05.2022 |  | 32 | 2
22 | D-11-05 | 132/11 kV SS at Gouavelli | Nov'15 |  | Mar'22 | Mar'22 | 25.97 | 0 | 20.69 | Grant |  |  | 31.03.2023 | [6 empty] | 2020000833
23 | L-19-01 | Mentrajpally | Mar'20 |  | Feb'21 | Mar'22 | 37.4 | 0 | 17.05 | Grant |  |  | 31.03.2023
24 | L-18-01 | Devannapeta | Sep'20 |  | Sep'21 | Jun'23 | 138.67 | 0 | 0 | Grant | [5 empty] | 2
25 | L-16-01 | Extn of 132kv Dubbathanda BRLI | [6 empty] | 0.002 | Grant
26 | L-13-01 | C.M.D of 220 MVA @ IND SAGAR RUDRA LIS | [6 empty] | 0.01 | Grant
|  | Total: |  |  |  |  | 4058.3639 | 2873.8972 | 89.5955 |  |  |  |  | 0 | 152 | 7