## 400kV_22-23-1.1d
ANNEXURE- II
Format 1.1(d) 1.1(D) ABSTRACT OF ACTUAL INVESTMENT INCURRED (True Up) DURING FY: 2022-23 OF 400KV SCHEMES
| FY 2022-23 | [27 empty] | (Amount Rs. in Crores)
Sl No. | Project Code | Project Title | Project Purpose | Projrct Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [5 empty] | SOURCE OF FINANCING | [6 empty] | Investments proposed for the year |  |  |  | Investments incurred in the year |  |  |  | Cumulative progress (year on year) |  |  |  | Remarks
[6 empty] | Base Cost | Contigency | IDC | TAXES | Expence Capatalised | Total Cost | Internal Accrual Component of capex in year | Equity Component of capex in year | Loan Amount | Interest Rate | Moratorium period | Repayment period | Loan source | Proposed investment in the year | Proposed IDC | Proposed other expence | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation
1 | APT/TS/400kV Suryapet/ F-INVST-28/2014 dated 21.01.2015 | Suryapet Power Transmission Scheme (S-14-02) | System Improvement | Jul' 2013 | Mar' 2021 | 1426.53 | 42.796 | 144.8 |  | 153.35 | 1767.476 |  |  | 1317.27 |  |  |  | REC | 0 |  |  |  | 0.305 |  |  |  | 11.855 |  |  | 100
2 | TST/TS/765kV Wardha– Hyderabad Link Transmission Scheme- Investment proposal Revised Approval No.16/17-2017-18, dated 19.12.2017 | 765kV Wardha– Hyderabad Link Transmission scheme (S-15-13) | System Improvement | Nov' 2015 | Mar'2022 | 1037.6982 | 30.82 | 100.08 |  | 110.45 | 1279.0482 |  |  | 1001.65 |  |  |  | PFC | 0 |  |  |  | 1.142 |  |  |  | 460.702
3 | TST/TS/Rayadurg System Improvement Scheme Approval No.02/2018-19, dated 24.05.2018 | Rayadurg System Improvement Scheme (S-17-08) | System Improvement | Sep'2018 | Apr'2022 | 1469.0147 | 43.63 | 117.4 |  | 156.36 | 1786.4047 |  |  | 1778.26 |  |  |  | PFC | 0 |  |  |  | 49.967 |  |  |  | 1742.867
4 | TST/TS/KTPP SIS/ Approval No.03/2019-20 | KTPP System Improvement Scheme (S-19-01) | System Improvement | Jan'2020 | Mar' 2024 | 372.58 | 11.07 | 30.92 |  | 39.66 | 454.23 |  |  | 405 |  |  |  | PFC | 0 |  |  |  | 44.641 |  |  |  | 208.591
5 | TST/TS/Reactor Scheme-III/ Approval No.04/2019-20 | Reactor Scheme -III (S-19-02) | System Improvement | Jan'2020 | Mar'2023 | 201.44 | 5.98 | 20.92 |  | 21.44 | 249.78 |  |  | 158.72 |  |  |  | PSDF | 0 |  |  |  | 29.412 |  |  |  | 57.422
6 | - - | HVWS at 500MVA ICTs of 400kV SS (S-21-05) | System Improvement | Dec'2021 | May'2022 | 0.8999 | 0.0267 | 0 |  | 0.0957 | 1.0223 | 1.0223 | [5 empty] | TSTRANSCO | 0 |  |  |  | 0.162 |  |  |  | 0.64
7 | TS/TST/Investment Approval/Telangana STPP-1 (2x800MW) No.10/2017, dt.23.08.2017 | Telangana STPP-I Power Evacuation (P-16-01) | Power Evacuation | Oct'2017 | Mar'2022 | 1013.6087 | 30.107 | 105.26 |  | 107.88 | 1256.8557 |  |  | 1131.17 |  |  |  | REC | 0 |  |  |  | 0.258 |  |  |  | 854.298
8 | TST/TS/Yadradri Thermal Power Evacuation/ Approval No.09/2019-20, dated 27.01.2020 | Yadradri Thermal Power Evacuation (P-19-02) | Power Evacuation | Jan'2020 | Mar' 2024 | 1887.67 | 56.07 | 209.7 |  | 200.91 | 2354.35 |  |  | 2212.91 |  |  |  | REC & PFC | 0 |  |  |  | 303.925 |  |  |  | 1338.445
9 | TST/TS/315 MVA PTR,Augmentation/DICHPALLY,VELTOOR,Gajwel/revised APPROVAL NO 03/17,2017-18 dated 04.05.2017 | Augmentation Scheme (A-15-11, A-15-10) | System Improvement | Feb'2016 | Mar' 2020 | 95.5909 | -- | -- | -- | -- | 95.5909 |  |  | 79.84 |  |  |  | PFC | 0 |  |  |  | 0.021 |  |  |  | 4.591 |  |  | 100
10 | TST/TS/Augmentation Scheme-IV/ Erection of 315/500MVA ICT's at 400kV Suryapet, Asupaka, Veltoor, Dichpally & Gajwel Substations. Approval No.01/2022-23 | 400kV Augmentation Scheme-IV (A-21-07) | System Improvement | Dec.' 2020 | Sept., 2023 | 154.45 | 4.59 | 12 |  | 16.44 | 187.48 | 187.48 | [5 empty] | PFC | 0 |  |  |  | 73.191 |  |  |  | 73.191
DC Works
1 | - - | Diversion of 400kV Julurupadu-KTPS & KTPS-PGCIL Line) (D-20-03) | DC work | Aug' 2020 | Aug'2021 | 17.58 | -- | -- | -- | -- | 17.58 |  |  | NA | NA | NA | NA | Consumer contribution | 0 |  |  |  | 0.038 | NA |  |  | 21.92 | NA |  | 100
Non-Plan Capital Works :
1 | Other Non-planned Project 2018-19 (N-18-01) | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -0.04 | - | - | - | 0 | - | - | -
2 | Non-plan Capital works (N-19-01) | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -0.427 | - | - | - | 0 | - | - | -
| Total | [9 empty] | 9449.8179 | [7 empty] | 0 |  |  |  | 502.595 |  |  |  | 4774.522
NA:Not applicable

## Schemes-2022-23
|  |  | 1.1(D) ABSTRACT OF ACTUAL INVESTMENT INCURRED DURING FY: 2022-23 OF 220KV & 132KV SCHEMES. | [27 empty] | ANNEXURE- II
Financial Year 2022-23 | [28 empty] | (Amount Rs. in Crores)
Sl No. | TOO NO. | Scheme IDs | Project Code (ERC Approval) | Project Title | Project Purpose | Project Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [5 empty] | SOURCE OF FINANCING | [6 empty] | Actual Expenditure from 01.04.2022 to 31.03.2023 | Investments proposed for the year FY 2022-23 |  |  |  | Investments incurred in the year | Cumulative expenditure as on 31.03.2022 |  |  |  | Cumulative progress upto 31.03.2023 |  |  |  | Remarks
Internal Accrual Component of capex in year
[8 empty] | Base Cost (in Rs.Crores) | Contigency | IDC | TAXES | Expence Capatalised | Total Cost (in Rs.Crores) |  | Equity Component of capex in year | Loan Amount | Interest Rate | Moratorium period | Repayment period | Loan source |  | Proposed investment in the year(Rs. Crores) | Proposed IDC | Proposed other expense | % Capatalisation | OPENING BALANCE | Actual investment in the year | IDC incurred | Other expense incurred | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation
1 | T.O.O (CE-Construction) Ms. No. 277 Dated: 26.02.2009 | S-02-03 | CRN:APT/TS/ 132/33kV SS / F.INVST - 37/2003 | Erection of 132/33 kV substation at Khanapur along with connected line from Akkapur to proposed 132/33 kV Khanapur substation in Adilabad district | System Improvement | 26.02.2009 | 09.09.2013 | 17.62 | -- | -- | -- | -- | 17.62 |  |  | 17.62 |  |  |  | TSTransco funds | 0.06 | -- |  |  |  |  | 0.27 |  |  |  | 0.33
2 | TOO (CE-construction) MS.NO.245 dt:29-09-2011 | S-07-03 | - | Erragadda and O.U GIS &Cables scheme | System Improvement | 27.12.2011 | 31.03.2020 | 437.7 | 13.131 | 43.77 | 26.262 | 47.0527 | 567.9157 |  |  | 415 |  |  |  | PFC | 0.12 | -- |  |  |  |  | 5.91 |  |  |  | 6.03
3 | T.O.O (CE-Construction-1) Ms. No. 07 Dated: 18.12.2013 SI10NIM132 | S-07-04 | - | TWIN CITIES TRANSMISSION SYSTEM & 132 kV SS NIMS & connected lines & erection of 220/132 kV substations at Gunrock, Imlibun (GIS) & Hayatnagar and 132 kV GIS Substations at Moosarambagh, Miralam Filter bed, Patigadda, Balkampet and with connected Under Ground XLPE Cables – Under Modernization and Strengthening of Hyderabad Metropolitan area | System Improvement | 01.08.2014 | 31.03.2022 | 76.8437 | 2.3009 | 8.825 | 0.6132 | 8.4922 | 97.075 |  |  | 85.36 |  |  |  | JICA | -0.67 | -- |  |  |  |  | 4.8 |  |  |  | 4.13
| TOO (CE-Construction) MS NO.379, Dt:17.01.2012 |  |  |  |  | 01.08.2014 | 31.03.2022 | 11.75 | 0.3525 | 1.175 | 0.705 | 1.2631 | 15.2456 |  |  | 11.4 | [5 empty] | --
4 | T.O.O. (CE-Transmission) Ms. No. 140 Dated. 13.10.2016 (Revised) | S-08-08 | CRN.No./TST/TS/220-132 KV GIS-Hyd/F.Invst./99/2019, Dt:20.02.2009 | 132/33 KV Narayanaguda GIS Sub-station | System Improvement | 31.05.2013 | 08.12.2017 | 130.1917 | 3.9058 | 13.0192 | 7.8115 | 13.9956 | 168.9237 |  |  | 31.19 |  |  |  | PFC | 0.11 | -- |  |  |  |  | 6.99 |  |  |  | 7.1
5 | T.O.O (CE-Transmission) Ms. No. 59 Dated:19.04.2016 | S-08-11 | APT/TS/132 kV SS-Mamidipalli/ F-INVST - 12/2013 | 132 kV SS Mamidipally & connected lines | System Improvement | 26.06.2009 | 31.03.2016 | 21.92 | -- | -- | -- | -- | 21.92 |  |  | 19.72 |  |  |  | PFC | -0.31 | -- |  |  |  |  | 2.62 |  |  |  | 2.31
6 | T.O.O (CE-Construction) Ms. No.37, Dt:28.04.2010 | S-10-05 | CRN: APT/TS/ 132kV SS Aitipamula/ F. INVST - 13/2011 | Erection of 132/33 kV Substation at Aitipamula (V) / Nakrekal, Kattanguru(M) in Nalgonda district | System Improvement | 28.04.2010 | 21.03.2013 | 12.93 | -- | -- | -- | -- | 12.93 |  |  | 11.64 |  |  |  | UCO Bank | 0.09 | -- |  |  |  |  | 0.02 |  |  |  | 0.11
7 | T.O.O (CE-Construction-I) Ms. No. 506 Dated: 15.03.2011 | S-10-13 | APT/TS/132kv SS- LGM Peta/F-INVST-17/2012 (Revised approval awaited) | Erection of 132/33KV SS LGM Pet | System Improvement | 16.09.2011 | 18.08.2016 | 35.51 | -- | -- | -- | -- | 35.51 |  |  | 14.79 |  |  |  | UCO Bank | 0.13 | -- |  |  |  |  | 36.59 |  |  |  | 36.72
8 | T.O.O MS.NO.11 dt:07.03.2014 | S-10-17 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 KV Substation at N V Puram in Khammam District | System Improvement | 07.08.2016 | 24.06.2019 | 19.9462 | 0.59838 | 1.9946 | 1.2466 | 2.1442 | 25.93 |  |  | 10.55 |  |  |  | REC | 0 | -- |  |  |  |  | 26.91 |  |  |  | 26.91
9 | T.O.O (CE-Construction) MS. No.319 Dated: 06.11.2010 | S-10-20 | APT/TS/220 kV - SW.Stn / F-INVST - 2/2013 | 220 kV Switching Station at Thimmajipeta & connected lines | System Improvement | 30.09.2013 | 01.03.2016 | 74.76 | -- | -- | -- | -- | 74.76 |  |  | 67.46 |  |  |  | PFC | 0 | -- |  |  |  |  | 79.5 |  |  |  | 79.5
10 | T.O.O (CE-Construction) Ms. No. 107 Dated: 23.06.2010 | S-10-22 | - | Erection of 33KV features at Vikarabad | System Improvement | 01.05.2014 | 01.03.2022 | 4.47 | -- | -- | -- | -- | 4.47 |  |  | 4.47 |  |  |  | TSTransco funds | 0.02 | -- |  |  |  |  | 0.1 |  |  |  | 0.12
11 | T.O.O (CE-Construction-I) Ms. No. 185 Dated: 11.08.2011 | S-10-23 | APT/TS/132KV SS/Water works (Karimnagar)/F-INVST-47/2013 | 132/33 KV Substation at water works in Karimnagar District | System Improvement | 12.07.2013 | 06.09.2014 | 18.55 | -- | -- | -- | -- | 18.55 |  |  | 17.85 |  |  |  | Oriental Bank of Commerce | 0.04 | -- |  |  |  |  | 0 |  |  |  | 0.04
12 | T.O.O (CE-Construction-I) Ms. No. 34 Dated: 27.04.2011 SI11ALWALP | S-11-07 | APT/TS/132kV SS-Alwalpad/F-INVST-41/2013 | 132 kV SS Ganganpalli (Alwalpadu) & connected lines | System Improvement | 26.10.2015 | 23.08.2018 | 13.5862 | 0.24382 | 1.47 | 0.0012 | 0.8688 | 16.17 |  |  | 12.95 |  |  |  | PFC | 0 | -- |  |  |  | 10.97 | 0.87 |  |  |  | 0.87
13 | T.O.O (CE-Construction) MS.No .82 Dated:18.04.2018 | S-11-11 | CRN.No.TST/TS132 kV SSt Donthanpalli /F-INVST-06 /2013/Dt:08.10.2014 | 132 kV DC line from the proposed 220/132/33 kV SS Parigi to 132/33 kV SS Dharmasagar (132/33 kV Substation at Donthanpalli ) | System Improvement | 13.12.2016 | 31.03.2023 | 15.9462 | 0.47838 | 1.5946 | 0.99663 | 1.7142 | 20.73 |  |  | 19.2627 |  |  |  | REC | 1.07 | 2 |  |  |  |  | 20.11 |  |  |  | 21.18
14 | T.O.O (CE-Construction-I) Ms. No. 04 Dt: 06.04.2011 | S-11-13 | APT/TS/132kV SS-Doulthabad/F-INVST-38/2013 | erection of 132/33 kV Substation at Doulthabad in Medak district along with connected 132 kV & 33 kV lines | System Improvement | 10.06.2011 | 10.02.2017 | 18.17 | 0.5451 | 2.18 | 1.1356 | 1.9533 | 23.984 |  |  | 18.77 |  |  |  | REC | 1.1 | -- |  |  |  | 0 | 0.02 |  |  |  | 1.12
15 | TOO (CE-Construction) MS NO.83, Dt:21.06.2013 | S-11-16 | CRN.No.APT/TS/220/132 kV SS-Huzurnagar/F-INVST-01/2014/Dt:20.04.2013 | 220/132/33 kV substation at Huzurnagar in Nalgonda District | System Improvement | 31.10.2013 | 10.12.2018 | 45.75 | 1.37 | 5.49 | 2.86 | 4.92 | 60.39 |  |  | 62.65 |  |  |  | PFC | 0.02 | -- |  |  |  |  | 14.34 |  |  |  | 14.36
16 | T.O.O (CE-Construction-I) Ms. No.8 Dated: 6.04.2011 | S-11-27 | CRN.No.TST/TS/132 KVSS/Nellikoduru/F.Invest. 07/2014 | 132/33 kV Substation at Nellikuduru in Warangal district along with connected 132 kV & 33 kV lines | System Improvement | 21.07.2016 | 04.01.2018 | 17.675 | 0.53025 | 1.7675 | 1.0605 | 1.9001 | 22.9333 |  |  | 17.847 |  |  |  | REC | 0.02 | -- |  |  |  |  | 0.63 |  |  |  | 0.65
17 | TOO (CE-Transmission) MS.NO.161 dt:26-08-2015 | S-11-28 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV SS at Nimmapalli with connected line in Karimnagar Dist | System Improvement | 23.03.2018 | 29.04.2021 | 18.4688 | 0.2546 | 1.97 | 0.0644 | 0.9122 | 21.67 |  |  | 17.73 |  |  |  | REC | 0.19 | -- |  |  |  |  | 15.74 |  |  |  | 15.93
18 | T.O.O (CE-Construction–I) MS. No.180 Dated: 09.08.2011 | S-11-30 | CRN:APT/TS/220/132kV Parigi/ F.INVST-1/2013 Dt:11.05.2012 | 220/132 kV substation at Parigi in Ranga Reddy district | System Improvement | 09.08.2011 | 04.03.2016 | 40 | 1.2 | 3.6 | 11.2 | 4.3 | 60.3 |  |  | 54.27 |  |  |  | REC | 0.04 | -- |  |  |  |  | 0.05 |  |  |  | 0.09
19 | T.O.O (CE-Construction–I) MS. No.180 Dated: 09.08.2011 | S-11-32 | - | 132/33 kV Substation at Rampur (Palamakula) in Medak District | System Improvement | 21.06.2013 | 28.11.2014 | 20.14 | - | - | - | - | 20.14 |  |  | 19.71 |  |  |  | PFC | 0 | [5 empty] | 0 |  |  |  | 0
20 | T.O.O (CE-Construction) Ms.No. 106 Dated:17 .06.2015 | S-11-35 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | shifting of 132kV SS Wadapally by erection of 132/33 kV SS at Wadapally(New) in place of existing Wadapally SS and 132kV LILO arrangements to 132/33kV SS Wadapally(New) in Nalgonda district | System Improvement | 17.06.2015 | 18.06.2016 | 7.6 | 0.228 | 0.684 | 2.128 | 0.817 | 11.457 |  |  | 4.4 |  |  |  | REC | 0.24 | -- |  |  |  |  | 0.42 |  |  |  | 0.66
21 | T.O.O (CE-Construction-I) Ms. No. 283 Dated: 20.12.2012 | S-12-05 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 33 kV features at Jankampet 132/11 kV Lift irrigation substation in Nizamabad district | System Improvement | 01.11.2016 | 06.12.2018 | 4.18 | -- | -- | -- | -- | 4.18 |  |  | 7.54 |  |  |  | REC | 0.17 | -- |  |  |  |  | 4.61 |  |  |  | 4.78
22 | TOO 61, Dt:25.05.2012 | S-12-09 | APT/TS/132/Yeddumailram/F-INVST-27/2013 | 132 KV DC/SC inter linking lines between substations 220 KV Yeddumailram-132 KV Pashmailaram | System Improvement | 01.12.2018 | 27.09.2022 | 9.086 | 0.0462 | 0.931 | 0.0012 | 0.1766 | 10.241 |  |  | 9.22 |  |  |  | NABARD | 1.84 | 2.5 |  |  |  |  | 8.67 |  |  |  | 10.51
23 | T.O.O (CE-Construction) Ms.No.27 Dated: 12 .02.2015 SI12MDPALL | S-12-10 | TST/TS/132kV / MD Pally, Kattedan /F-INVST- 03/2016 | 132 kV SS MD Pally (Kattedan) & connected lines | System Improvement | 05.08.2015 | 25.09.2017 | 52.6715 | 0.7587 | 5.79 | 1.7015 | 2.7683 | 63.69 |  |  | 33.864 |  |  |  | PFC | 0 | -- |  |  |  |  | 0.26 |  |  |  | 0.26
24 | T.O.O (CE-Transmission)MS.No. 5 Dated:11.01.2016 | S-13-02 | TST/TS / 220/132 kV SS Ayyagaripally, Mahabubabad /F-INVST- 03/16 - 2016-17 | 220/132 kV SS at Ayyagaripally in Mahaboobabad in Warangal district | System Improvement | 02.03.2016 | 29.01.2018 | 78.33 | -- | -- | -- | -- | 78.33 |  |  | 68.9 |  |  |  | REC | 0.26 | -- |  |  |  |  | 25.38 |  |  |  | 25.64
25 | TOO (CE-Construction-I) MS NO.117, Dt:30.05.2014 | S-13-03 | CRN.No. APT/TS/220 KVSS -Bonguluru/F.Invest-27/2014 | 220/132/33KV SS at Bonguloor in RR District | System Improvement | 01.06.2014 | 31.10.2015 | 56.8088 | 2.1343 | 6.34 | 0.04328 | 4.4136 | 69.74 |  |  | -- |  |  |  | NABARD | 0.15 | -- |  |  |  |  | 27.85 |  |  |  | 28
26 | T.O.O (CE-Construction) MS.No .109 Dated:17.05.2018 (Revised) | S-13-06 | TST/TS/132kV SS/ Dommarapochampalli /F-INVST- 04/2015 | 132KV Dommarapochampally & connected lines | System Improvement | 24.12.2016 | 16.07.2018 | 35.9609 | 0.4336 | 4.031 | 2.3413 | 1.5742 | 44.341 |  |  | 32.3488 |  |  |  | REC | 0 | [5 empty] | 1.23 |  |  |  | 1.23
27 | T.O.O (CE-Transmission) Ms.No.193 Dated:07.10.2015 (Revised) | S-13-10 | TST/TS/132kV / Kachapur SS/F-INVST- 17/2016 | 132/33kV SS Kachapur & connected lines | System Improvement | 22.09.2015 | 04.05.2018 | 19.9182 | 0.3337 | 1.8946 | 0.0827 | 1.1954 | 23.4246 |  |  | 21.53 |  |  |  | REC | 0.47 | -- |  |  |  |  | 1.11 |  |  |  | 1.58
28 | T.O.O (CE-Construction-I) Ms.No. 347 Dated: 13.02.2013 SI13KANDUK | S-13-11 | TST/TS/132 kV SS-Kandukuru/ F-INVST-05/2015 | 132 kV SS Kandukuru & connected lines | System Improvement | 09.09.2016 | 31.03.2024 (expected) | 21.4405 | 0.27755 | 2.275 | 0.0024 | 1.0296 | 25.025 |  |  | 20.0578 |  |  |  | REC | 1.89 | 2.3 |  |  |  |  | 17.72 |  |  |  | 19.61
29 | T.O.O (CE-Construction) MS.No. 144 Dated:03.08.2015 | S-13-14 | CRN.No./TST/TS/220/132KV Substation /Sircilla /F.Invst./ App./08/2015 | 220/132 kV SS at Sircilla in Karimnagar District | System Improvement | 22.12.2015 | 15.12.2016 | 72.7583 | 2.1827 | 7.2758 | 4.3655 | 7.8215 | 94.4039 |  |  | 59.9992 |  |  |  | REC | 0.13 | -- |  |  |  |  | 2.22 |  |  |  | 2.35
30 | TOO 22 Dt:10.09.2014 | S-14-12 | APT/TS/132 KV SS Kaithlapur/F-INVST-4/2014 | 132 KV substation Khaithalapur aong with connected lines | System Improvement | 05.07.2016 | 27.08.2019 | 63.5174 | 0.50461 | 5.0851 | 0.1489 | 1.8691 | 71.1251 |  |  | 59.09 |  |  |  | REC | 0.01 | -- |  |  |  |  | 55.02 |  |  |  | 55.03
31 | TOO / CE/Trans/ MS No. 156 Dated 19.08.2015 | S-15-01 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Providing second source of supply to 132/33 kV Sub-Station, Lalgadi Malakpet in Shameerpet Mandal of Ranga Reddy District | System Improvement | 20.10.2015 | 18.10.2019 | 7.0327 | 0.0559 | 0.731 | 0.0212 | 0.2002 | 8.041 |  |  | 6.2 |  |  |  | PFC | 0.04 | -- |  |  |  |  | 10.09 |  |  |  | 10.13
32 | T.O.O (CE-Transmisssion) MS.No. 159 Dated: 24.08.2015 SI15ASWARA | S-15-02 | TST/TS/ 132/33 kV Aswaraopet SS Up-Gradation to 220/132 kV / F-INVST- 7/2015 | Up-Gradation of 132/33 kV SS Aswaraopet to 220/132 kV SS | System Improvement | 18.01.2017 | 28.04.2018 | 50.2217 | 0.5249 | 4.65 | 0.1926 | 1.8808 | 57.47 |  |  | 42.55 |  |  |  | PFC | 0.23 | -- |  |  |  |  | 3.59 |  |  |  | 3.82
33 | T.O.O (CE-Construction) Ms. No. 02 `Dated: 04.02.2015. | S-15-03 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV Substation at Chandulapur Village of Chinnakodur Mandal in Medak District along with connected lines | System Improvement | 27.04.2016 | 06.10.2017 | 15.2083 | 0.45625 | 1.5208 | 0.9125 | 1.6349 | 19.7328 |  |  | 30.5565 |  |  |  | REC | 0 | -- |  |  |  |  | 0.14 |  |  |  | 0.14
34 | TOO / CE/Trans/ MS No. 210 Dated 6.11.2015 SI15L2CNKT | S-15-06 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Providing of alternate supply to 132 /33 kV SS Chennur and 132/33 kV SS Kataram from 220/132 kV SS, Manthani under the program for providing 9.00 Hrs Day Time Supply for Agriculture. | System Improvement | 07.02.2018 | 31.03.2024(expected) | 11.9197 | 0.0421 | 1.213 | 0.0178 | 0.1504 | 13.343 |  |  | 10.917 |  |  |  | REC | 3.82 | 2.6 |  |  |  |  | 7.63 |  |  |  | 11.45
35 | T.O.O (CE-Transmission) MS.No. 164 Dated: 06.11.2017 (Revised) | S-15-11 | TST/TS/ 220 kV 2nd circuit / RSS to Nirmal SS and RSS to Jagityal SS / F-INVST- 15/2015 | 220 kV 2nd circuit stringing on 220 kV RSS - Jagityal and 220 kV RSS - Nirmal | System Improvement | 27.11.2015 | RSS- Nirmal - 30.12.2016 RSS-Jagityal-02.11.2018 | 65.6314 | 0.0511 | 6.614 | 0.2699 | 0.1876 | 72.754 |  |  | 38.06 |  |  |  | PFC | 0.01 | -- |  |  |  |  | 0.84 |  |  |  | 0.85
36 | TOO / CE/Trans/ MS No. 136 Dated 27.07.2015 SI15LNHZRB | S-15-29 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Erection of 132 kV line for making LILO of both of the circuits of existing 132 KV Husnabad-Huzurabad DC line at 220/132 kV LI Substation Huzurabad and Erection of 1 No. 100 MVA additional PTR at 220/132 kV LI SS, Huzurabad with equipment totalling to 2 X 100 MVA. | System Improvement | 11.11.2016 | RSS-Jagityal-02.11.2018 | 17.1691 | 0.16 | 1.8 | 0.0978 | 0.5731 | 19.8 |  |  | 0 |  |  |  | REC | 0.53 | -- |  |  |  | 1.89 | 0.73 |  |  |  | 1.26
37 | TOO (CE-Construction-I) MS NO.55, Dt:25.03.2015 | S-15-31 | CRN.No.TST/TSAsifnagar SS alternatesource of supply/Invest.App.06/2015 | erection of 2nd circuit from 220kV Shivarampally SS to 132kV Asifnagar SS for providing 2nd source of supply to 132kV Asifnagar substation | System Improvement | 16.02.2018 | 31.05.2019 | 43.7987 | 0.4071 | 4.0454 | 0.2972 | 1.467 | 50.0154 |  |  | 41.3635 |  |  |  | REC | -0.12 | -- |  |  |  |  | 21.05 |  |  |  | 20.93
38 | T.O.O (CE-Transmisssion) MS.No. 211 Dated: 07.11.2015 | S-15-32 | TST/TS/ 220 kV Pedagopati SS / Investment approval No. 19/16-2016 | Erection of 220/132/33 kV SS at Pedagopati in Khammam district | System Improvement | 27.02.2017 | 01.12.2018 | 120.2411 | 0.8479 | 10.9507 | 0.3131 | 3.0383 | 135.3911 |  |  | 121.2483 |  |  |  | REC | 0.04 | -- |  |  |  |  | 3.4 |  |  |  | 3.44
39 | TOO (CE-Transmission) MS.NO.231 dt:21-12-2015 | S-15-33 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV SS at Sarangapur in Adilabad District | System Improvement | 04.04.2018 | 11.12.2019 | 18.4173 | 0.3138 | 1.8685 | 0.0749 | 1.1242 | 21.7987 |  |  | 17.66 |  |  |  | REC | 1.61 | -- |  |  |  |  | 14.06 |  |  |  | 15.67
40 | TOO (CE-Tr) MS NO.225, Dt:10.12.2015 | S-15-34 | CRN.No.TST/TS/Erection of 220 KV DC line Gajwel/Siddipet/Invest.App.04/17-2017-18 | 220 KV D/C Line from 400KV GAJWEL-SIDDIPET | System Improvement | 05.12.2017 | 19.11.2022 | 37.8541 | 0.0515 | 3.8117 | 0.0198 | 0.1846 | 41.9217 |  |  | 74.97 |  |  |  | REC | 1.95 | 1.5 |  |  |  |  | 51.93 |  |  |  | 53.88
41 | TOO (CE-Construction) Ms.No.137, Dated:29.07.2015 | S-15-37 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection 132 kV line from 220 kV Jurala Sub-Station to 132 kV Ieeza Sub-Station under the program of providing 9.00 Hrs agricultural supply during day time | System Improvement | 12.03.2018 | 07.08.2019 | 16.38 | 0.03 | 1.64 | 0.013 | 0.11 | 18.18 |  |  | 30.56 |  |  |  | REC | 0 | [5 empty] | 16.12 |  |  |  | 16.12
42 | TOO / CE/Trans/ MS No.62 Dated 25.04.2016 | S-16-08 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 33 kV Features at existing 220/11 kV LI Sub-Station, Bheemghanpur Warangal District. | System Improvement | 05.05.2017 | 08.07.2020 | 4.775 | 0.14325 | 0.573 | 0.29844 | 0.51331 | 6.303 |  |  | 16.31 |  |  |  | PFC | 0.56 | -- |  |  |  |  | 9.48 |  |  |  | 10.04
43 | TOO / CE/Trans/ MS No.76 Dated 25.05.2016 | S-16-11 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV Substation at Bachannapet in Warangal District | System Improvement | 20.04.2017 | 31.10.2019 | 18.1064 | 0.2639 | 1.938 | 0.0642 | 0.9455 | 21.318 |  |  | 16.71 |  |  |  | PFC | 0.1 | -- |  |  |  | 5.82 | 11.47 |  |  |  | 11.57
44 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | S-16-12 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132/33 kV SS at Kotagiri with connected line & Bay in Nizamabad District | System Improvement | 06.06.2018 | 12.05.2022 | 13.8496 | 0.2419 | 1.505 | 0.0842 | 0.8743 | 16.555 |  |  | 12.98 |  |  |  | PFC | 3.03 | -- |  |  |  |  | 13.93 |  |  |  | 16.96
45 | TOO No.72 Dt:13.05.2016 | S-16-14 | TST/TS/ 220132/33 kV / Substation, Borampet RR District/ INVST- No. 07/16 - 2016-17 | 220/132/33 kV Substation at Borampet in Ranga Reddy district | System Improvement | 28.11.2016 | 31.03.2024 (expected) | 196.487 | 3.3449 | 20.3712 | 0.3778 | 11.9859 | 232.5668 |  |  | 182.98 |  |  |  | PFC | 39.37 | 45 |  |  |  | 56.88 | 128.13 |  |  |  | 167.5
46 | T.O.O (CE-Transmission) Ms. No. 26, Dated: 27.02.2017. | S-17-01 | CRN TS/TST/220/33 KV, GIS, Chanchaguda/Invest.Approval No.7/17-2017-18 | Erection of 220/33 kV Sub-Station at Chanchalguda | System Improvement | 28.02.2018 | 31.03.2021 | 78.651 | 2.2842 | 8.192 | - | 8.1849 | 97.3121 |  |  | 80.208 |  |  |  | REC | -0.02 | -- |  |  |  |  | 82.14 |  |  |  | 82.12
47 | TOO (CE-Transmission) MS.NO.31 dt:27-02-2017 | S-17-03 | CRN TS/TST/132/33 KV, Moulali-ZTS SS, Investment Approval No.17/17, 2017-18 | 132/33 KV Sub-station at Moulali ZTS with connected UG cable & bay in Medchal-Malkajgiri District | System Improvement | 01.04.2019 | 30.07.2021 | 44.124 | 1.2338 | 4.9779 | 0.1599 | 4.2615 | 54.7571 |  |  | 44.47 |  |  |  | REC | 0.12 | -- |  |  |  |  | 44.03 |  |  |  | 44.15
48 | TOO (CE-Transmission) MS.NO.27 dt:27-02-2017 | S-17-04 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Administrative approval for erection of 132/33 KVSS Gachibowli in Ranga Reddy District. | System Improvement | 01.04.2019 | 22.09.2021 | 16.7357 | 0.3993 | 1.872 | 0.1636 | 1.4307 | 20.6013 |  |  | 16.52 |  |  |  | REC | 0.69 | [5 empty] | 20.42 |  |  |  | 21.11
49 | TOO (CE-Transmission) MS.NO.28 dt:27-02-2017 | S-17-05 | CRN TS/TST/132/33 KV, GIS, Seetharambagh/Invest.Approval No.6/17-2017-18 | 132/33 KV Gas Insulated Sub-station (GIS) at Seetharambagh with connected UG cable & bay in Hyderabad District and connectivity from Asifnagar SS. | System Improvement | 01.04.2019 | 31.03.2023 (expected) | 56.3096 | 1.5947 | 6.362 | 0.0104 | 5.7146 | 69.9913 |  |  | 57.27 |  |  |  | REC | 38.23 | 35 |  |  |  |  | 1.22 |  |  |  | 39.45
50 | T.O.O (CE-Transmission) Ms. No.84, Dated: 27.05.2017 | S-17-09 | TST/TS/132 kV SS- 220 kV Toopran, 132 kV Ganeshpally & 132 kV Duddeda SS / F-INVST-07/2015 | 220/132/33 kV Substation at Toopran(meenaji pet) in Medak District along with connected lines | System Improvement | 27.01.2016 | 06.02.2020 132 KV connected line works are in progress | 60.8 | 1.824 | 6.08 | 3.8 | 6.536 | 79.04 |  |  | 68.43 |  |  |  | REC | 0.17 | -- |  |  |  | 44.79 | 52.01 |  |  |  | 52.18
51 | TOO (CE-construction) MS.NO.86 dt:29-05-2017 | S-17-12 | CRN TST/TS/132/33KV, Choppadandi, SS /Invest,Approval No.20/18-2017-18 | 132/33 kV SS with connected line at Choppadandi in Karimnagar Dist. | System Improvement | 06.06.2018 | 31.03.2024 (Expected) | 21.1755 | 0.3375 | 2.5135 | 0.1282 | 1.2093 | 25.364 |  |  | 19.97 |  |  |  | PFC | 0 | -- |  |  |  |  | 0.12 |  |  |  | 0.12
52 | TOO (CE_Transmission)Ms.No.69 Dt:09.05.2017 | S-17-13 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 132/33 kV Sub-Station at Yadagirigutta Temple with connected line Town of Yadadri (erstwhile Nalgonda) .District | System Improvement | 01.10.2018 | 11.12.2019 | 13.9285 | 0.2154 | 1.6566 | 0.1312 | 0.7851 | 16.7168 |  |  | 13.16 |  |  |  | PFC | 0.04 | -- |  |  |  |  | 12.11 |  |  |  | 12.15
53 | T.O.O (CE-Construction) Ms. No.170 Dt;16.11.2017 | S-17-14 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Providing of 33 kV Features at upcoming 220/132 KV Sub-Station, Mahabubabad in Mahabubabad District | System Improvement | 31.10.2018 | 26.05.2021 | 6.6281 | 0.1807 | 0.854 | 1.0839 | 0.6473 | 9.394 |  |  | 7.44 |  |  |  | REC | -0.01 | -- |  |  |  |  | 2.94 |  |  |  | 2.93
54 | T.O.O (CE-Construction) Ms. No. 124, Dated: 19.08.2017 | S-17-15 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | erection of 132/33 kV Sub-Station at Chinna Shankarampet in Medak District | System Improvement | 01.04.2018 | 23.01.2021 | 13.3134 | 0.2482 | 1.76 | 1.4891 | 0.8893 | 17.7 |  |  | 13.96 |  |  |  | REC | 0.23 | -- |  |  |  |  | 9.2 |  |  |  | 9.43
55 | TOO (CE-construction) MS.NO.149 dt:09-10-2017 | S-17-16 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 2nd CKT (30KM) on 132KV DC/SC line from existing 220/132KV SS Waddekothapally to existing 132/33KV SS Peddanagaram with Panther ACSR Conductor with connected bays | System Improvement | 01.04.2019 | 06.11.2021 | 6.7387 | 0.0316 | 0.7019 | 0.1328 | 0.1167 | 7.7217 |  |  | 6.32 |  |  |  | REC | 0.09 | -- |  |  |  |  | 3.24 |  |  |  | 3.33
56 | TOO (CE-construction) MS.NO.13 dt:20-01-2018 | S-17-19 | CRN No. TST/TS/Erection of 132/33 KV SS at Pitlam in Khammam Dist. Approval/No.04/2018-19 | 132/33 kV SS at Pitlam in Nizamabad District (13, dt.20.1.18 | System Improvement | 31.10.2018 | 31.03.2023 (Expected) | 29.5454 | 0.2846 | 3.24 | 1.7077 | 1.0198 | 35.7975 |  |  | 31.8 |  |  |  | REC | -0.05 | 5 |  |  |  |  | 0.11 |  |  |  | 0.06
57 | TOO (CE-construction) MS.NO.177 dt:30-11-2017 | S-17-20 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 132 KV DC/SC line from 220KVSS Chegur (Kothur) to existing 132KVSS Kothur | System Improvement | 01.04.2019 | 24.07.2020 | 5.2691 | 0.0423 | 0.5678 | 0.2169 | 0.1516 | 6.2477 |  |  | 5.11 |  |  |  | REC | 0.11 | 4 |  |  |  |  | 5.63 |  |  |  | 5.74
58 | TOO (CE-construction) MS.NO.14 dt:20-01-2018 | S-17-21 | CRN No. TST/TS/Erection of 132/33 KV SS at Pammy in Khammam Dist. Approval/No.03/2018-19 | 132/33kV SS at Pammy in Khammam District (14, dt.20.1.18) | System Improvement | 01.04.2020 | 31.03.2024 (Expected) | 18.4685 | 0.3015 | 1.73 | 1.8088 | 1.0804 | 23.3892 |  |  | 20.64 |  |  |  | REC | 3.31 | -- |  |  |  |  | 1.72 |  |  |  | 5.03
59 | T.O.O (CE-Construction-I)MS.No. 186 Dated: 11.09.2013 2) T.O.O (CE-Construction) Ms. No. 103 Dated:11.07.2017 | S-17-23 | CRN TST/TS/220/ Switching Station/Mahaboobnagar/132 KV Features /Invest,Approval No.14/17-2017-18 | erection of 132 kV features at 220 kV Thimmajipet Switching Station in Mahaboobnagar District and extending connectivity to 132 kV Jadcherla Sub-Station from Thimmajipet | System Improvement | 01.04.2019 | 22.07.2022 and the line work is under progress (132 kV DC line on Galvanised Towers with Panther ACSR from the existing proposed 220/132 kV Thimmajipet Sub-Station, to the existing 132/33 kV Jadcherla Sub-Station.) | 24.43 | 0.733 | 2.443 | 1.4858 | 2.6262 | 31.718 |  |  | 26.39 |  |  |  | REC | 3.07 | 5 |  |  |  |  | 15.54 |  |  |  | 18.61
60 | TOO (CE-construction) MS.NO.43 dt:06-03-2018 | S-18-01 | CRN No.TST/TS/Erection of 132/33 KV Substation at Peechara in Wranagal District. Approval No. 05/2018-19 | 132/33 kV SS at Peechara in Warangal Dist. | System Improvement | 01.04.2020 | 31.03.2024 (Expected) | 36.3068 | 0.3432 | 4.42 | 2.0594 | 1.2299 | 44.3593 |  |  | 39.1 |  |  |  | REC | 8.54 | 10 |  |  |  |  | 0.12 |  |  |  | 8.66
61 | T.O.O (CE-Construction) MS.No .294 Dated:29.01.2019 | S-18-02 | CRN No: TST/TS/Erecion of 220/132 kV Substation at Ammavaripet, Kazipet(M) in Warangal Urban District.F. Approval/ No.13/18/2018-19 | erection of 220/132 kV Sub-Station at Ammavaripet in Warangal-Urban District | System Improvement | 31.10.2018 | 31.03.2024 (Expected) | 84.9 | 2.547 | 15.02 | 15.282 | 9.1268 | 126.8757 |  |  | 87.24 |  |  |  | PFC | 16.01 | 20 |  |  |  |  | 74.4 |  |  |  | 90.41
62 | T.O.O (CE-Construction) Ms. No.254, Dt:26.11.18 | S-18-03 | Proceedings No: 28/APERC/Secy/Dir(Engg)/E-725/2013, dated.06.05.2013 | 132/33kV SS at Padmanagar in Karimnagar District | System Improvement | 01.04.2019 | 31.03.2023 (Expected) Work under progress | 16.075 | 0.48225 | 1.929 | 1.0047 | 1.7281 | 21.219 |  |  | 16.33 |  |  |  | PFC | 7.4 | 10 |  |  |  |  | 12.2 |  |  |  | 19.6
63 | TOO (CE Construction) MS NO.193, Dt:30.08.2018 | S-18-04 | CRN No. TST/TS/Erection of 132/33 SS at Nagaram in Suryapet Dist. Approval/No.14/18/2018-19 | 132/33 KV SS Nagaram,Nalgonda District | System Improvement | 01.04.2019 | 27.03.2022 | 26.2586 | 0.2904 | 4.64 | 1.7427 | 1.0407 | 33.9724 |  |  | 26.15 |  |  |  | PFC | 0.92 | 2 |  |  |  |  | 11.15 |  |  |  | 12.07
64 | TOO (CE_Construction-1)Ms.No.217 Dt:25.09.2018 | S-18-06 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 33 KV features at 132 KV Railway Traction Switching Station, Kothagudem, Kothagudem Bhadradri District | System Improvement | 01.04.2019 | 31.03.2024 (expected) | 6.9998 | 0.1909 | 0.9 | 1.1453 | 0.684 | 9.92 |  |  | 7.64 |  |  |  | PFC | 0.01 | -- |  |  |  |  | 0.04 |  |  |  | 0.05
65 | TOO (CE-construction) MS.NO.375 dt:03-06-2019 | S-19-03 | CRN/TST/TS/Erection of 132/33 KV SS at Patancheru in Sangareddy District. Approval /NO 05/2019-20 dt:22.11.2019- | 132 KV SS Patancheru in Medak District | System Improvement | 01.04.2020 | 30.11.2022 | 18.3178 | 0.54953 | 1.6486 | 1.1449 | 1.9692 | 23.63 |  |  | 20.85 |  |  |  | REC | 3.37 | 4 |  |  |  |  | 11.33 |  |  |  | 14.7
66 | T.O.O (CE-Construction) MS.No .341 Dated:02.04.2019 | S-19-04 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 33 kV Features at upcoming 220/132 KV Sub-Station, Ammavaripet in Kazipet (M), Warangal Urban (District)- | System Improvement | 01.04.2019 | 30.12.2022 | 6.2791 | 0.18837 | 0.56512 | 0.39244 | 0.675 | 8.1 |  |  | -- |  |  |  | TSTransco funds | 0.13 | 0 |  |  |  |  | 1.72 |  |  |  | 1.85
67 | T.O.O (CE-Construction) MS. No. 402 Dated: 08.07.2019 | S-19-05 | CRN/TST/TS/Erection of 132 KV SS at Manikonda in Rangareddy District.Approval NO 08/2019-20 dt:27.12.2019 | 132/33 kV Gas Insulated Sub-Station (GIS) at Manikonda in Ranga Reddy District along with connected line with 132 KV XLPE UG cable | System Improvement | 31.09.2019 | 15.09.2022 | 83.0853 | 2.4926 | 7.4777 | 5.1928 | 8.9317 | 107.18 |  |  | 96.46 |  |  |  | REC | 18.37 | 20 |  |  |  |  | 67.18 |  |  |  | 85.55
68 | T.O.O (CE-Construction) Ms. No. 965 Dated: 05.02 2021. | S-20-02 | TST/TS/Erection of 132/33 KV SS at Dandumalkapur(V) in Yadadri Bhuvangiri Dist.Approval No.01/2021-22, dt:09.06.2021 | Administrative approval for erection of 132/33 KV Sub-station Dandu Malkapur (V) in Chotuppal (M) of Yadadri Bhuvanagiri District | System Improvement | 05.02.2021 | 31.03.2024(Expected ) | 24.5 | 0.735 | 2.82 | 6.86 | 2.6338 | 37.5487 |  |  | -- |  |  |  | Transco funds | 0.02 | 1 |  |  |  |  | 0.05 |  |  |  | 0.07
69 | T.O.O (CE-Construction) Ms.No.1099 Dated: 30.06.2021. | S-21-01 | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | Erection of 132/33 kV Sub-Station at Pasra (V) of Govindaraopet (M) in Mulugu District. | System Improvement | 30.06.2021 | 31.01.2022 | 7.9 | 0.237 | 0.711 | 2.212 | 0.84925 | 11.9093 |  |  | -- |  |  |  | Transco funds | 1.73 | 2 |  |  |  |  | 6.23 |  |  |  | 7.96
70 | T.O.O (CE-Construction) Ms.No.1208 Dated: 04.10.2021. | S-21-06 | (CRN) TST/TS/Erection of 132KV DC line from 400/220/132 KV SS Narsapur to 132/33 KV SS Yeldurthy in Medak District.Approval NO.04/2021-2022 | 132 kV DC line from 400/220/132 kV SS Narsapur to 132/33 kV SS Yeldurthy in Medak District | System Improvement | 05.11.2022 | 31.03.2024 ( expected) Work in progress | 21.91 | 0.66 | 1.71 | 3.94 | 2.36 | 30.58 |  |  | 30.58 |  |  |  | Transco funds | 6.66 | 8 | [8 empty] | 6.66
72 | T.O.O. (CE-400kV) Ms.No.07 Dated: 09.01.2018 | P-12-02 |  | NIRMAL POWER TRANSMISSION SCHEME | Power Evacuation | 23.06.2018 | 30.11.2024 | [5 empty] | 345.98 | [6 empty] | REC | 6.38 | 3 |  |  |  |  | - |  |  |  | 6.38
73 | T.O.O.(CE-Projects-I) Ms.No.8 Dt:19 .01.2016. | P-15-01 |  | Dindi System Improvement Scheme | System Improvement | 18.09.2017 | 31.03.2024 | [5 empty] | 77.93 | [6 empty] | REC | 0.97 | 0 |  |  |  |  | - |  |  |  | 0.97
74 | T.O.O.(CE-Projects-I)Ms.No.15 Dt:29-04 -2016. | P-15-03 |  | Bhadradri Thermal Power Tranmsission Scheme | System Improvement | 22.03.2018 | 31.07.2024 | [5 empty] | 174.3 | [6 empty] | PFC | 14.75 | 10 |  |  |  |  | - |  |  |  | 14.75
75 | T.O.O. (CE-400kV) Ms.No. 139 Dt: 11.09.2017 | P-15-04 |  | KTPS (Stage VII-1 x 800MW) Scheme | Power Evacuation | 23.04.2018 | 31.08.2024 | [5 empty] | 218.09 | [6 empty] | PFC | 3.97 | 1 |  |  |  |  | - |  |  |  | 3.97
76 | T.O.O.(CE-400kV) Ms.No.104 , Dt:12.07.2017 | P-16-01 |  | Telangana STPP-I (2 X 800MW) Power Evacuation Scheme | Power Evacuation | 29.10.2018 | 31.03.2024 | [5 empty] | 107.3 | [6 empty] | REC | 0 | 0 |  |  |  |  | - |  |  |  | 0
77 | T.O.O (CE-Construction) Ms. No.401 Dated:08.07.2019. | P-19-01 |  | 315MVA ICT at BTPS & DC lne 4m Manuguru | System Improvement | 31.09.2019 | 31.03.2024 | 51.5969 | 1.5479 | 4.6437 | 3.2248 | 5.5467 | 66.56 | [6 empty] | REC | 3.53 | 1 |  |  |  |  | 34.32 |  |  |  | 37.85
78 | T.O.O. (CE-400kV) Ms.No.451 Dated: 10.10.2019 | P-19-02 |  | Yadadri Thermal Power(5X 800MW) Evacuation Scheme | Power Evacuation | 01.02.2021 | 31.01.2025 | [5 empty] | 211.86 | [6 empty] | PFC | 36.37 | 25 |  |  |  |  | - |  |  |  | 36.37
79 | T.O.O.(CE-Projects-I) Ms.No. 11, Date: 15.03.2016 | S-14-02 |  | Suryapet Power Transmission Scheme | System Improvement | 21.11.2016 | 31.03.2024 | [5 empty] | 86.13 | [6 empty] | REC | -0.01 | 0 |  |  |  |  | - |  |  |  | 0
80 | T.O.O.(CE-400kV) Ms.No.297 Dt:09.02.2019 | S-19-01 |  | KTPP System Improvement scheme | System Improvement | 11.06.2020 | 31.03.2025 | [5 empty] | 209.06 | [6 empty] | PFC | 9.14 | 6.5 |  |  |  |  | - |  |  |  | 6.5
81 | - | S-03-01 |  | CONDUCTING RECONNOITERY & DETAILED SURVE | System Improvement |  | 31.03.2024 | [5 empty] | - | [7 empty] | -0.01 | 0 | [8 empty] | -0.01
82 | - | S-08-07 |  | COND. RECONNETIORY AND DETAILED SURVEY F | System Improvement |  | 31.03.2024 |  |  |  | 82.7134 |  | - | [7 empty] | -0.01 | 0 | [8 empty] | -0.01
Total | [7 empty] | 2891.5382 | 58.7195 | 273.8306 | 207.0587 | 207.4801 | 4986.5706 |  |  | 2626.2928 |  |  |  |  | 242.58 |  |  |  |  | 0 | 1121.72 |  |  |  | 1361.67

## Schemes-22-23 - DC work
ANNEXURE- II
1.1(D) ABSTRACT OF ACTUAL INVESTMENT INCURRED DURING FY: 2022-23 OF 220KV & 132KV SCHEMES (DC Works)
|  |  | Financial Year 2022-23 | [24 empty] | (Amount Rs. in Crores)
Sl No. | TOO NO. | Scheme IDs | Project Code (ERC Approval) | Project Title | Project Purpose | Project Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [5 empty] | SOURCE OF FINANCING | [6 empty] | Actual Expenditure from 01.04.2022 to 31.03.2023 | Investments proposed for the year FY 2022-23 |  |  |  | Cumulative expenditure as on 31.03.2022 |  |  |  | Cumulative progress upto 31.03.2023 |  |  |  | Remarks
Internal Accrual Component of capex in year
[8 empty] | Base Cost (in Rs.Crores) | Contigency | IDC | TAXES | Expence Capatalised | Total Cost (in Rs.Crores) |  | Equity Component of capex in year | Loan Amount | Interest Rate | Moratorium period | Repayment period | Loan source |  | Proposed investment in the year(Rs. Crores) | Proposed IDC | Proposed other expense | % Capatalisation | Actual investment in the year | IDC incurred | Other expense incurred | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation
|  |  |  | Brought Forward (BF) | [16 empty] | 242.58
1 |  | D-13-02 |  | 132 KV switching station for evacuation of power from solar power plant at NTPC | DC Works | 13.05.2015 | 05.05.2016 | [5 empty] | 10.17 | [7 empty] | 0.06
2 |  | D-15-08 |  | 220KV YELLURU & GOURIDEVIPALLY SS | DC Works | Y & G- 24.02.2016 | Y-03.11.17 G-08.12.17 | [5 empty] | 79.5 | [7 empty] | -0.02
3 |  | D-16-08 |  | 132 KV DC Mandamarry-Bellampally line from Loc.No.132 to 136 and Loc.No.141 to 145 for a length of 5.938 KM and dismantling of 132 KV Bellampally-SCCL( Mandamarry) line from loc.No.6 to Loc.No.28 and connected bay | DC Works | 28.10.2015 | 26.02.2017 | [5 empty] | 8.51 | [7 empty] | -0.07
4 |  | D-16-14 |  | Providing Open access metering systems Viz., main, check and stand by metering to the existing 132 KV HT consumer | DC Works | 21.06.2018 | 11.08.2020 | [5 empty] | 1.78 | [7 empty] | 0.05
5 |  | D-17-04 |  | 132 KV Radial 2-Phase DC/SC line from existing 132/11 KV Gangadhara LISS to proposed 132/25KV Kothapally Railway Traction Substation | DC Works | 06.04.2018 | 05.10.2018 | [5 empty] | 1291.31 | [7 empty] | -0.01
6 |  | D-17-11 |  | 132 KV lne 4m Miryalaguda to RTSS and Ramannapet to Ramannapet | DC Works | 02.06.2018 | 27.09.2019 | [5 empty] | 8.37 | [7 empty] | 0.15
[5 empty] | DC Works | 02.06.2018 | 06.12.2018 | [5 empty] | 7.04
7 |  | D-18-10 |  | Divrsn of Gajwl-Kndapka etc Komrveli mal | DC Works | 26.09.2018 | 09.12.2020 | [5 empty] | 17.6 | [7 empty] | -0.02
11 |  | D-18-12 |  | Extnsion of power supply to RTSS Manoharabad | DC Works | 15.04.2019 | 25.11.2020 | [5 empty] | 1.05 | [7 empty] | 0.28
12 |  | D-18-13 |  | Pwr sply 2 132KV RTSS Divitipally(RVNL) | DC Works | 21.01.2020 | 22.07.2022 | [5 empty] | 9.76 | [7 empty] | 0.3
13 |  | D-18-15 |  | Extn of 132 KV lne 4 kamrdy 2 Tlamdla Ra | DC Works | 24.03.2021 | 31.03.2023 | [5 empty] | 14.55 | [7 empty] | 3.27
14 |  | D-18-16 |  | Extn of Pwr sply 2 132/25 KV RTS Jankamp | DC Works | 25.11.2020 Mbay- 07.10.2022 | work in progress(Scheduled completion date- 24.08.2021 M-bay 06.07.2023) | [5 empty] | 19.05 | [7 empty] | 3.03
15 |  | D-18-17 |  | Erection of metering bay at 132 KV Parigi SS | DC Works | supervision work | 24.03.2016 | [5 empty] | 0.41 | [7 empty] | 0.05
16 |  | D-18-18 |  | Extn of 132 KV sply 2 RTSS at Wanaparthy | DC Works | 06.01.2022 | 04.08.2023 | [5 empty] | 15.6 | [7 empty] | 8.11
16 |  | D-18-19 |  | Extn of HT sply 2 Thimmapr RTSS 4m Shams | DC Works | 08.11.2018( Line & bay at Shamshabad) 21.01.2019 (Bays at RTSS) | work under progress (Scheduled completion date-07.08.2019 (Line & bay at Shamshabad) & 20.10.2019 (Bays at RTSS)) | [5 empty] | 35.05 | [7 empty] | 7.63
17 |  | D-18-21 |  | 220KV DC line Dindi-Bonguluru loc no 5 | DC Works | 07.05.2019 | 05.02.2020 | [5 empty] | 7.91 | [7 empty] | 0.08
18 |  | D-18-22 |  | Shifting of existing 132 KV Makthal-Krishna RTSS DC line between Loc.No.29A to 29B near Maganooru Village in Mahaboobnagar District | DC Works | 07.03.2019 | 23.12.2019 | [5 empty] | 4.14 | [7 empty] | 0.01
19 |  | D-19-02 |  | Shift Gachibowli-Madapur-I&II DC lines b | DC Works | 29.11.2019 | 28.05.2020 | [5 empty] | 13.02 | [7 empty] | 1.64
20 |  | D-19-03 |  | Sft 220KV Gachibowli-S.nagar-Egadda line | DC Works | 29.11.2019 | 31.08.2021 | [5 empty] | 19.61 | [7 empty] | -1.03
21 |  | D-19-04 |  | Shifting 132kV lines from Road number 45 Durgam Cheruvu | DC Works | 30.01.2019 | 13.06.2020 | [5 empty] | 18.8 | [7 empty] | 0.46
22 |  | D-19-09 |  | 220KV Monopole DC/SC line from 220KV SS Ghanapur to M/s.CPRI | DC Works | 31.05.2023 | work under progress (Scheduled completion date-30.11.2024) | [5 empty] | 55.16 | [7 empty] | 0.38
23 |  | D-20-01 |  | 132/33 KV SS at E-city Fabcity | DC Works | 21.09.2020 (SS & Bays) 22.04.2021 (Line) | 16.09.2023(SS) 31.08.2023 (bays) 31.08.2023 (Line) | [5 empty] | 47.99 | [7 empty] | 3.55
24 |  | D-20-02 |  | Extension of 132KV supply to RTSS Manopa | DC Works | [15 empty] | 0.04
25 |  | D-20-06 |  | 132kV DC/SC line from 132/33kV SS Morthad | DC Works | 15.04.2021 | 29.04.2022 | [5 empty] | 5.81 | [7 empty] | 0.34
26 |  | D-20-07 |  | Modifictn of power lne of Bhadrachalam-S | DC Works | 20.10.2020 | 28.07.2021 | [5 empty] | 61.16 | [7 empty] | -0.92
27 |  | D-20-09 |  | Gajwel-chegunta for manoharabad 2 Kothapally | DC Works | 29.01.2021 | 03.07.2021 | [5 empty] | 2.69 | [7 empty] | 0.11
28 |  | D-21-18 |  | Shifting of 220kV Miryalaguda-KTPS SC Line | DC Works | [15 empty] | 0.35
29 |  | D-21-22 |  | Shifting of 132KV Nandipet-Nizamabad | DC Works | [15 empty] | 0.23
30 |  | D-21-23 |  | 400kV 1000Sqmm XLPE Cable etc. _ Srisailam | DC Works | [15 empty] | 0.08
31 |  | D-21-24 |  | 132kV DC.SC line Ganganpally-RTSS Pandur | DC Works | 11.10.2021 | 10.04.2022 | [5 empty] | 14.55 | [7 empty] | 2.96
32 |  | D-21-27 |  | Data centers at TSIIC- M/s. Amazon | DC Works | [15 empty] | 37.16
|  |  |  | a)220KV MC/DC line from 220/132 KV Fabcity SS to proposed site of M/s.Amazon Data services India Pvt.Ltd at TSIICIndustrial park Fabcity | DC Works | 14.10.2021(bays at Fabcity end) 11.10.2021(line) 14.10.2021(Bays at Amazon end) | 28.06.2023 28.06.2023 13.07.2023 | [5 empty] | 40.49
|  |  |  | b) 2 No.s single circuits with 220KV XLPE 1000 Sq.mm UG cable from 400/220KV Maheshwaram ss to proposed 220KV Amazon (Pharmacity) SS | DC Works | 23.11.2021(bays at maheshwaram end) 06.01.2022 (Line) 14.10.2021(Bays at Amazon end) | 18.08.2023 18.08.2023 16.09.2023 | [5 empty] | 72.76
|  |  |  | c) 2 No.s 220KV bays proposed at 220/132/33 KV SS Chandanvally (TSIIC) and 220KV single moose DC line from proposed 220/132/33 KV Chandanvally (TSIIC) SS to proposed 220KV M/s.Amazon (Chandanvally) SS | DC Works | 01.08.2022 | Work under progress ( Scheduled date-30.04.2023) | [5 empty] | 34.58
33 |  | D-21-30 |  | Industrial Park at Chandanvally(V), Shadnagar | DC Works | SS-14.10.2021 Line-25.10.2021 Bays-23.11.2021 | SS-16.01.2023 Line-13.01.2023 Bays-10.01.2023 | [5 empty] | 108.33 | [7 empty] | 31.12
34 |  | D-21-33 |  | Shifting of 220kV Shapurnagar - Janagaon SC | DC Works | Supervision work | 14.06.2022 | [13 empty] | 1.31
35 |  | D-21-37 |  | Shifting of 1 no.220KV DC line of Regumanugadda-Wanaparthy & Singotam | DC Works | 21.09.2022 | 19.08.2022 & 26.08.2022 | [5 empty] | 9.56 | [7 empty] | 7.35
36 |  | D-21-38 |  | Shifting of existing 132 KV SC line (9KM) with INVAR HTLS Conductor of 132/33 KV Jadcherla SS to 220/132 KV SS Boothpur SC line in Mahabubnagar District | DC Works | 22.12.2021 | 02.07.2023 | [5 empty] | 11.7 | [7 empty] | 7.25
37 |  | D-21-44 |  | M/s.Mahalakshmi Profiles Pvt.Ltd | DC Works | Supervision work | [6 empty] | 1.26 | [7 empty] | 0.28
38 |  | D-21-47 |  | 220/132/33 KV SS including 2 No.s 220KV incoming feeders and 8 No.s 33 KV feeder bays at Kakatiya Mega Textile Park, Shyampet (V), Geesukonda (M). | DC Works | 28.10.2022 | Work under progress(Scheduled completion date- 27.07.2023) | [5 empty] | 189.2 | [7 empty] | 19.92
39 |  | D-21-48 |  | 132 KV DC line from existing 132/33 KV SS Geesugonda to M/s,Kitex Garments Limited proposed to be established at M/s.Kakatiya Mega Textile park , Shayampet (V), Geesugonda(M), Warangal District | DC Works | 17.11.2022 | Work under progress(Scheduled completion date- 16.05.2023) | [5 empty] | 19.99 | [7 empty] | 6.41
40 |  | D-21-50 |  | Diversion of 132 KV Yacharam-Ibrahimpatnam-Bongulur SC line from Loc.No.s 370/1 to 370/3 of Ibrahimpatnam DC line passing through M/s. BEL's land located at Sy.no.s 254 to 256 of Ibrahimpatnam Khalan Village of Ranga Reddy District | DC Works | 25.11.2022 | 11.05.2023 | [5 empty] | 8.88 | [7 empty] | 2.18
41 |  | D-22-01 |  | 132KV DC line from existing 132/33 KV SS Chandrugonda to proposed 132/25KV Chandrugonda Railway Traction Substation | DC Works | 11.01.2023 | Work under progress(Scheduled completion date- 10.10.2023) | [5 empty] | 20.7 | [7 empty] | 1.15
42 |  | D-22-18 |  | 1 No.132 KV bay at 220/132 KV Chandanvally SS (M/s.TSIIC) and 132 KV MC line from proposed 220KV Chandanvally SS (M/s.TSIIC) 132 KVSS Ester Film Tech Limited | DC Works | Supervision work | 18.01.2023 | [5 empty] | 2.49 | [7 empty] | 0.28
43 |  | L-12-02 |  | 2 Nos 132kV Bays at Jaipur for SCCL | DC Works | [15 empty] | 0.08
44 |  | D-20-10 |  | Extn.of cntrl room bal wrks at 220 KV S | DC Works | [15 empty] | 0.53
|  |  |  | Grand Total | [8 empty] | 2290.53 | [7 empty] | 388.69

## Schemes- 22-23-Non Plan
1.1(D) ABSTRACT OF ACTUAL INVESTMENT INCURRED DURING FY: 2022-23 OF 220KV & 132KV SCHEMES.(Non Plan Capital Works)
|  |  | Financial Year 2021-22 | [24 empty] | (Amount Rs. in Crores)
Sl No. | TOO NO. | Scheme IDs | Project Code (ERC Approval) | Project Title | Project Purpose | Project Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [5 empty] | SOURCE OF FINANCING | [6 empty] | Actual Expenditure from 01.04.2021 to 31.03.2022 | Investments proposed for the year FY 2022-23 |  |  |  | Cumulative expenditure as on 31.03.2022 |  |  |  | Cumulative progress upto 31.03.2023 |  |  |  | Remarks
Internal Accrual Component of capex in year
[8 empty] | Base Cost (in Rs.Crores) | Contigency | IDC | TAXES | Expence Capatalised | Total Cost (in Rs.Crores) |  | Equity Component of capex in year | Loan Amount | Interest Rate | Moratorium period | Repayment period | Loan source |  | Proposed investment in the year(Rs. Crores) | Proposed IDC | Proposed other expense | % Capatalisation | Actual investment in the year | IDC incurred | Other expense incurred | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation
|  |  |  | Brought Forward (BF) | [16 empty] | 388.69
1 |  | N-18-01 |  | Other Non Planned Project Str 2018-19 | [16 empty] | 0.53
2 |  | N-19-01 |  | Non Plan Capital works Exe by Const wing | [16 empty] | 0.87
3 |  | N-20-01 |  | Non Plan Capital works Exe by Const wing | [16 empty] | 0
4 |  | N-21-01 |  | Non Plan Capital works Exe by Const wing | [16 empty] | 5.89
5 |  | N-22-01 |  | Non Plan Capital works Exe by Const wing | [16 empty] | 0.03
|  |  |  | Grand Total | [16 empty] | 396.01

## Tra,RMI Aug 22-23
ANNEXURE-II Transmission wing (For FY:2019-2020 to FY:2023-2024 each year)
| Abstractof Actual Expenditure incurred for FY:2022-23 of Augmentation of PTRs, Lines & RMI Schemes | [27 empty] | ANNEXURE- II
Form 1.1d
This form captures investments as planned and actually incurred
| FY: 2022-23 |  |  |  | Please fill in the required details pertaining to each year | [13 empty] | (Figures Rs. in crores)
Sl.No | PROJECT DETAILS | [5 empty] | PLANNED CAPITAL EXPENDITURE | [6 empty] | SOURCE OF FINANCING | [6 empty] | Investments Proposed for the year annual |  |  |  | Investments incurred in the year annual |  |  |  | Cumulativr Progress (Year on Year) |  |  |  | Remarks
| Project Code* | Project Title | Project Purpose** | Expenditure as on 31.03.2022 | Project Star Date (DD-MM-YY) | Project Completion date (DD-MM-YY) | Base Cost | Contigency | IDC | Duties | Taxes | Expense Capitalised | Total Cost in crores | Internal Accrual Component of capex in year | Equity Component of capex in year | Debt Component of Capex in year
[16 empty] | Loan Amount | Interest Rate | Moratorium Period | Prepayment Period | Loan Source | Proposed investment in the year (Rs.Cr) | Proposed IDC | Proposed Other expense | Percentage captalisation | Actual investment in the year (Rs.Cr) | IDC incurred | Other expense Incurred | Percentage captalisation | Actual investment in the year | IDC incurred | Other expense Incurred | Percentage captalisation
1 | A-15-06 | Augmentation of PTR capacities at variou | To meet the growing loads | 8.211 | 01.05.2015 | 31.03.2023 | 233.75 | Incl |  | Incl | Incl | Incl | 233.75 | [6 empty] | REC | -0.005 | - | - | -0.002139% | -0.002 | - | - | -0.0008556% | 8.209 | - | - | 3.512%
2 | A-16-06 | Aug with 160 MVA inplace of 100 MVA at 400 KV Gajwel | To meet the Industrial, Agriculture and etc., loads | 4.93 | 01.03.2016 | 31.03.2023 | 8.95 | Incl |  | Incl | Incl | Incl | 8.95 | [6 empty] | REC | 0.01 | - | - | -0.1634% | 0 | - | - | 0% | 4.93 | - | - | 55.08%
3 | A-17-01 | Augmentation of PowerTransformer capacities at various EHT SS in Warangal and Karimnagar Zones | To meet the Industrial, Agriculture and etc., loads | 36.25 | 2017-05-20 | 31.03.2023 | 59.91 | 2.2 | 0 | 0 | 2.23 | 7.89 | 72.23 |  |  | 63.13 |  |  |  | PFC:37203017 | 0.995 | - | - | 99.84% | 0.01 | - | - | 0.01384% | 36.26 | - | - | 50.2%
4 | A-17-02 | Augmentation of Transformer capacities at various EHT SS for extending 24 Hrs. Agl. supply in Metro and Rural Zones | To meet the Industrial, Agriculture and etc., loads | 44.722 | 2017-06-02 | 31.03.2023 | 42.15 | 1.67 | 0 | 0 | 1.5 | 5.97 | 51.29 |  |  | 41.32 |  |  |  | PFC:37203017 | 1.995 | - | - | 199.8% | 0 | - | - | 0% | 44.722 | - | - | 87.19%
5 | A-18-02 | Aug of PTR cap.at YWGI | To meet the Industrial, Agriculture and etc., loads | 2.944 | 18.07.2018 | 31.03.2023 | 6.68 | Incl |  | Incl | Incl | Incl | 6.68 | [6 empty] | REC | 0.044 | - | - | 0.6587% | 0.04 | - | - | 0.5988% | 2.984 | - | - | 44.67%
6 | A-19-04 | Augmentation of PTRs at 220 KV Hayathnag | To meet the growing loads | 11.044 | 18.03.2020 | 31.03.2023 | 14.4 | Incl |  | Incl | Incl | Incl | 14.4 | [6 empty] | TSTRANSCO Funds | 9.833 | - | - | 68.28% | 0 | - | - | 0% | 11.044 | - | - | 76.69%
7 | A-20-01 | Augmentation at 220KV Manthani SS & 132K | To meet the growing loads | 0.323 | 10.06.2020 | 31.03.2023 | 8.97 | Incl |  | Incl | Incl | Incl | 8.97 | [6 empty] | TSTRANSCO Funds | 1.0855 | - | - | 34.3% | 1.086 | - | - | 12.11% | 1.409 | - | - | 15.71%
8 | A-20-02 | Aug of 3rd 220/132KV PTR at 400KV Narsap | To meet the growing loads | 1.467 | 26.06.2020 | 31.03.2023 | 3.63 | Incl |  | Incl | Incl | Incl | 3.63 | [6 empty] | TSTRANSCO Funds | 1.245 | - | - | 34.3% | 0.349 | - | - | 9.614% | 1.816 | - | - | 50.03%
9 | A-20-03 | Aug of PTR at Warangal & Karimnagar Circ | To meet the growing loads | 2.418 | 03.01.2020 | 31.03.2023 | 8.26 | Incl |  | Incl | Incl | Incl | 8.26 | [6 empty] | TSTRANSCO Funds | 0.212 | - | - | 2.567% | 0.39 | - | - | 4.722% | 2.808 | - | - | 34%
10 | A-20-06 | Aug of 3rd PTR at 132KV MDPally SS | To meet the growing loads | 3.181 | 05.02.2021 | 31.03.2023 | 3.92 | Incl |  | Incl | Incl | Incl | 3.92 | [6 empty] | TSTRANSCO Funds | 3.088 | - | - | 78.78% | 0.74 | - | - | 18.88% | 3.921 | - | - | 100%
11 | A-20-07 | Aug of 4rd PTR at 132KV Pashmailaram SS | To meet the growing loads | 0.547 | 30.03.2021 | 31.03.2023 | 1.56 | Incl |  | Incl | Incl | Incl | 1.56 | [6 empty] | TSTRANSCO Funds | 0.543 | - | - | 34.81% | 0.07 | - | - | 4.487% | 0.617 | - | - | 39.55%
12 | A-21-01 | Aug of 160 MVA PTR at 400KV Suryapet SS | To meet the growing loads | 1.295 | 12.04.2021 | 31.03.2023 | 8.35 | Incl |  | Incl | Incl | Incl | 8.35 | [6 empty] | TSTRANSCO Funds | 1.295 | - | - | 15.51% | 1.86 | - | - | 22.28% | 3.155 | - | - | 37.78%
13 | A-21-02 | Aug of 132/33 KV PTRs at Mamidipally & 4 | To meet the growing loads | 0.227 | 07.05.2021 | 31.03.2023 | 11.47 | Incl |  | Incl | Incl | Incl | 11.47 | [6 empty] | TSTRANSCO Funds | 0.227 | - | - | 1.979% | 0.04 | - | - | 0.3487% | 0.267 | - | - | 2.328%
14 | A-21-04 | Aug. of PTR capacity at 220KV Huzurabad | To meet the growing loads | 1.097 | 18.08.2021 | 31.03.2023 | 6.03 | Incl |  | Incl | Incl | Incl | 6.03 | [6 empty] | TSTRANSCO Funds | 1.097 | - | - | 18.19% | 0 | - | - | 0% | 1.097 | - | - | 18.19%
15 | A-21-05 | Augmentations of 220KV PTRs at 5Nos Subs | To meet the growing loads | 1.097 | 18.08.2021 | 31.03.2023 | 6.03 | Incl |  | Incl | Incl | Incl | 6.03 | [6 empty] | TSTRANSCO Funds | 1.097 | - | - | 18.19% | 3.27 | - | - | 54.23% | 4.367 | - | - | 72.42%
16 | A-21-06 | Augmentations of 132KV PTRs at 24Nos Sub | To meet the growing loads | 2.862 | 07.10.2021 | 31.03.2023 | 48.75 | Incl |  | Incl | Incl | Incl | 48.75 | [6 empty] | TSTRANSCO Funds | 2.862 | - | - | 5.871% | 6.71 | - | - | 13.76% | 9.572 | - | - | 19.63%
17 | A-22-01 | Augmentation of PTR at 132 KV Medchal SS | To meet the growing loads | 0 | 06.06.2022 | 31.03.2023 | 0.25 | Incl |  | Incl | Incl | Incl | 0.25 | [6 empty] | TSTRANSCO Funds | 0.25 | - | - | 5.871% | 0.197 | - | - | 78.8% | 0.197 | - | - | 78.8%
18 | A-22-02 | Augmentation of PTR at 132KV Balanagar S | To meet the growing loads | 0 | 11.10.2022 | 31.03.2023 | 6.27 | Incl |  | Incl | Incl | Incl | 6.27 | [6 empty] | TSTRANSCO Funds | 3.135 | - | - | 5.871% | 0.094 | - | - | 1.499% | 0.094 | - | - | 1.499%
19 | A-22-03 | Aug. of PTR at Kaithalapur & Bhongir | To meet the growing loads | 0 | 21.12.2022 | 31.03.2023 | 0.49 | Incl |  | Incl | Incl | Incl | 0.49 | [6 empty] | TSTRANSCO Funds | 0.245 | - | - | 5.871% | 0.096 | - | - | 19.59% | 0.096 | - | - | 19.59%
20 | D-16-06 | Erection 33KV Bays TSNPDCL | DC Works | 12.981 | 31.03.3016 | 31.03.2023 | 19.31 | Incl |  | Incl | Incl | Incl | 19.31 | [6 empty] | Customer Contribution | 0.242 | - | - | 1.253% | 0 | - | - | 0% | 12.981 | - | - | 67.22%
21 | D-18-03 | Implementation of DAS for RTSS | DC Works | 2.592 | 11.01.2018 | 31.03.2023 | 3.8 | Incl |  | Incl | Incl | Incl | 3.8 | [6 empty] | Customer Contribution | 0.143 | - | - | 3.763% | 0.002 | - | - | 0.05263% | 2.594 | - | - | 68.26%
22 | D-18-20 | Providing of ABT meters at Railway Traction SS | DC Works | 3.636 | 1/4/2020 | 31.03.2023 | 9.64 | Incl |  | Incl | Incl | Incl | 9.64 | [6 empty] | Customer Contribution | 0.832 | - | - | 8.631% | 0.25 | - | - | 2.593% | 3.886 | - | - | 40.31%
23 | D-19-06 | 132KV Durshed-Karimnagar SC-DC line | DC Works | 0 | 01.04.2023 | 31.03.2023 | 2.98 | Incl |  | Incl | Incl | Incl | 2.98 | [6 empty] | Customer Contribution | 0.003 | - | - | - | 0.003 | - | - | 0% | 0 | - | - | 0%
24 | D-19-07 | ABT Metering at 132 KV Manuguru & Kothag | DC Works | -0.334 | 2020-01-04 | 31.03.2023 | 1.352 | Incl |  | Incl | Incl | Incl | 1.352 | [6 empty] | Customer Contribution | - | - | - | - | 0.15 | - | - | 11.09% | -0.184 | - | - | 13.61%
25 | D-19-08 | Providing of ABT meters at OCM & Mandamarry SS of M/s.SCCL. | DC Works | 6.957 | 1/4/2020 | 31.03.2023 | 14.1 | Incl |  | Incl | Incl | Incl | 14.1 | [6 empty] | Customer Contribution | 1.667 | - | - | 11.82% | -0.23 | - | - | -1.631% | 6.727 | - | - | 47.71%
26 | D-19-14 | 33KV Bay Extension at 220KV manuguru | DC Works | 0 | 1/4/2020 | 31.03.2023 | 0.18 | Incl |  | Incl | Incl | Incl | 0.18 | [6 empty] | Customer Contribution | 0.17 |  |  | 96% | 0.17 | - | - | 93% | 0.17 |  |  | 93%
27 | D-20-16 | Erection of 4Nos 33KV Bays for M/s Amazo | DC Works | 0.727 | 01.04.2020 | 31.03.2023 | 2.6604 | Incl |  | Incl | Incl | Incl | 2.6604 | [6 empty] | Customer Contribution | 0.122 | - | - | 4.586% | 0.03 | - | - | 1.128% | 0.757 | - | - | 28.45%
28 | D-20-21 | 33KV bays for SCCL Bittupally at 132KV Manthani | DC Works | 0 | 01.04.2020 | 31.03.2023 | 0.4 | Incl |  | Incl | Incl | Incl | 0.4 | [6 empty] | Customer Contribution | 0.122 | - | - | 4.586% | 0.03 | - | - | 7.5% | 0.03 | - | - | 7.5%
29 | D-20-22 | CT Replacement for Kesoram at Malyalaplly | DC Works | 0 | 01.04.2020 | 31.03.2023 | 0.1 | Incl |  | Incl | Incl | Incl | 0.1 | [6 empty] | Customer Contribution | 0.1 | - | - | 4.586% | 0.04 | - | - | 40% | 0.04 | - | - | 40%
30 | D-20-36 | 220KV Shivarampally SS 4Nos. Bays | DC Works | 0 | 01.04.2020 | 31.03.2023 | 1.2 | Incl |  | Incl | Incl | Incl | 1.2 | [6 empty] | Customer Contribution | 0.122 | - | - | 4.586% | 0 | - | - | 0% | 0 | - | - | 0%
31 | D-20-43 | 33KV Bays for NPDCL Dasnagar | DC Works | 0 | 01.04.2020 | 31.03.2023 | 0.25 | Incl |  | Incl | Incl | Incl | 0.25 | [6 empty] | Customer Contribution | 0.122 | - | - | 4.586% | 0.22 | - | - | 88% | 0.22 | - | - | 88%
32 | D-21-16 | 4Nos 33KV Bays in substation in OMC Wara | DC Works | 0.26896 | 25.02.2022 | 31.03.2023 | 0.84 | Incl |  | Incl | Incl | Incl | 0.84 | [6 empty] | Customer Contribution | 0.26896 | - | - | 32.02% | 0.15 | - | - | 17.86% | 0.15 | - | - | 17.86%
33 | D-21-20 | 33KV Bay for Raghuram at 132KV Suglampal | DC Works | 0.058 | 03.01.2021 | 31.03.2023 | 0.23 | Incl |  | Incl | Incl | Incl | 0.23 | [6 empty] | Customer Contribution | 0.058 | - | - | 25.22% | 0.115 | - | - | 50% | 0.173 | - | - | 75.22%
34 | D-21-22 | Shiefting of 132KV Nandipet- Nizamabad S | DC Works | 0 | 23.07.2021 | 12.01.2022 | 2.93 | Incl |  | Incl | Incl | Incl | 2.93 | [6 empty] | Customer Contribution | 0.058 | - | - | 25.22% | 0.23 | - | - | 7.85% | 0.23 | - | - | 7.85%
35 | D-21-26 | 33KV Bay for singareni at 132KV Penuball | DC Works | 0.083 | 07.09.2020 | 31.03.2023 | 0.17 | Incl |  | Incl | Incl | Incl | 0.17 | [6 empty] | Customer Contribution | 0.083 | - | - | 48.82% | 0.003 | - | - | 1.765% | 0.086 | - | - | 50.59%
36 | D-21-46 | 33KV Bay at 132KV B Gangaram | DC Works | 0 | 01.04.2021 | 31.03.2023 | 0.18 | Incl |  | Incl | Incl | Incl | 0.18 | [6 empty] | Customer Contribution | 0.083 | - | - | 48.82% | 0.11 | - | - | 61.11% | 0.11 | - | - | 61.11%
37 | D-21-49 | Construction of wall and other for NHAI at Asifabad | DC Works | 0 | 01.04.2021 | 31.03.2023 | 0.3 | Incl |  | Incl | Incl | Incl | 0.3 | [6 empty] | Customer Contribution | 0.083 | - | - | 48.82% | 0.17 | - | - | 56.67% | 0.17 | - | - | 56.67%
38 | D-22-03 | Replacement of 132KV metring CTs PTs | DC Works | 0 | 01.04.2022 | 31.03.2023 | 0.25 | Incl |  | Incl | Incl | Incl | 0.25 | [6 empty] | Customer Contribution | 0.083 | - | - | 48.82% | 0.03 | - | - | 12% | 0.03 | - | - | 12%
39 | N-16-OMCP-OPEN | Migarte to OMC Open Capital inventory | NON PLAN | 0 | 01.04.2022 | 31.03.2023 | 0.08 | Incl |  | Incl | Incl | Incl | 0.08 | [6 empty] | TSTRANSCO Funds | 0.346 | - | - | 9.83% | 0.08 | - | - | 100% | 0.08 | - | - | 100%
40 | N-18-OMCP | FY 2018-19 capital material drawn in O&M | NON PLAN | 0 | 01.04.2019 | 31.03.2023 | 0 | Incl |  | Incl | Incl | Incl | 0 | [6 empty] | TSTRANSCO Funds | 0 | - | - | 9.83% | 0 | - | - | 0% | 0 | - | - | 0%
41 | N-19-OMCP | FY 2019-20 capital material drawn in O&M | NON PLAN | 0 | 01.04.2019 | 31.03.2023 | 0 | Incl |  | Incl | Incl | Incl | 0 | [6 empty] | TSTRANSCO Funds | 0.346 | - | - | 9.83% | -0.01 | - | - | 0% | -0.01 | - | - | 0%
42 | N-19-02 | Non Planned Capital works (O&M) 2019-20 | NON PLAN | 1.379 | 01.04.2019 | 31.03.2023 | 3.52 | Incl |  | Incl | Incl | Incl | 3.52 | [6 empty] | TSTRANSCO Funds | 0.346 | - | - | 9.83% | 0.05 | - | - | 1.42% | 1.429 | - | - | 40.6%
43 | N-20-02 | Non Planned Capital works (O&M) 2020-21 | NON PLAN | 1.293 | 01.04.2020 | 31.03.2023 | 6.3 | Incl |  | Incl | Incl | Incl | 6.3 | [6 empty] | TSTRANSCO Funds | 0.145 | - | - | 2.302% | 0.93 | - | - | 14.76% | 2.223 | - | - | 35.29%
44 | N-21-02 | Non Planned Capital works (O&M) 2021-22 | NON PLAN | 2.713 | 01.04.2021 | 31.03.2023 | 10.8 | Incl |  | Incl | Incl | Incl | 10.8 | [6 empty] | TSTRANSCO Funds | 2.713 | - | - | 25.12% | 5.18 | - | - | 47.96% | 7.893 | - | - | 73.08%
45 | N-22-02 | Non Planned Capital works (O&M) 2022-23 | NON PLAN | 0 | 01.04.2022 | 31.03.2023 | 25.01 | Incl |  | Incl | Incl | Incl | 25.01 | [6 empty] | TSTRANSCO Funds | 12.505 | - | - | 5.871% | 6.21 | - | - | 24.83% | 6.21 | - | - | 24.83%
46 | O-16-01 | Rolling Stock | Procurement of Major SS Equipment | 0.323 | 1/4/2022 | 31/03/2023 | 39.53 | - | - | Inclusive | Inclusive |  | 39.53 | - | - | 35.57 | - | - | - | REC |  |  |  |  | 0.323 | - | - | 0.8171 | 0.323 | - | - | 0.8171% | -
47 | R-15-01 | RMI | Replacement of old and obsolute equipment of substations and lines of TSTRANSCO | 0.137 | 1/4/2022 | 31/03/2023 | 53.08 |  |  | inclusive | inclusive |  | 53.08 |  |  | 47.72 |  |  |  | PFC |  |  |  |  | 0.137 |  |  | 0.2581 | 0.137 |  |  | 31.8%
48 | R-16-02 | PSDF |  | 42.8 | 07.09.2020 | 31/03/2022 | 59.97 | Incl |  | Incl | Incl | Incl | 59.97 | [6 empty] | Grant | 0.083 | - | - | 48.82% | 0.15 | - | - | 0.2501% | 42.95 | - | - | 71.62%
49 | R-17-02 | 132KV Bellampally-Sirpurkagaznagar tower |  | 0 | 07.09.2020 | 31/03/2022 | 4.9 | Incl |  | Incl | Incl | Incl | 4.9 | [6 empty] | Customer Contribution | 0.083 | - | - | 48.82% | 0.67 | - | - | 13.67% | 0.67 | - | - | 13.67%
50 | R-17-01 | RMI |  | 4.799 | 1/4/2022 | 31/03/2023 | 100.22 |  |  | inclusive | inclusive |  | 100.22 |  |  | 90.22 |  |  |  | REC |  |  |  |  | 4.799 |  |  | 4.7885 | 4.799 |  |  | 4.788%
51 | R-20-01 | RMI |  | 12.783 | 1/4/2022 | 31/03/2023 | 75.65 |  |  | inclusive | inclusive |  | 75.65 |  |  | 68.04 |  |  |  | REC |  |  |  |  | 12.783 |  |  | 16.8976 | 12.783 |  |  | 16.9%
52 | R-21-01 | RMI |  | 2.137 | 1/4/2022 | 31/03/2023 | 59.7 |  |  | inclusive | inclusive |  | 59.7 | [6 empty] | Transco Internal funds |  |  |  |  | 2.137 |  |  | 3.5796 | 2.137 |  |  | 3.58%
53 | S-22-01 | Const. of 33KV bays at 132/33KV Substati | System Improvement | 0 | 1/4/2022 | 31/03/2023 | 1.2 | Incl |  | Incl | Incl | Incl | 1.2 | [6 empty] | Transco Internal funds | 0.083 | - | - | 48.82% | 0.9 | - | - | 75% | 0.9 | - | - | 75%
54 | Z-21-01 | Rolling Stock | Procurement of Major SS Equipment | 12.892 | 1/4/2022 | 31/03/2023 |  | - | - |  |  |  | - | - | - |  | - | - | - | [5 empty] | 12.892 | - | - |  | 12.892 | - | - | - | -
55 | Z-99-01 | Rolling Stock | Procurement of Major SS Equipment | 2.749 | 1/4/2022 | 31/03/2023 |  | - | - |  |  |  | - | - | - |  | - | - | - | [5 empty] | 2.749 | - | - |  | 2.749 | - | - | 0% | -
56 | T-18-01 | PSDF IMP OPGW |  | 0 | 07.09.2020 | 31/03/2022 | 19.52 | Incl |  | Incl | Incl | Incl | 19.52 | [6 empty] | Grant | 0.083 | - | - | 48.82% | 15.91 | - | - | 81.51% | 15.91 | - | - | 81.51%
| Total | [5 empty] | 1000.1724 | 3.87 | 0 | 0 | 3.73 | 13.86 | 1021.6324 | [11 empty] | 82.313 |  |  |  | 279.81
Chief Engineer/ Transmission
Abstract
| Sl.No | Description | Capital Expenditure
| 1 | RMI | 11.29
| 2 | Schemes & Non plan and other capital works | 46.81
58.1
4 | A-15-22 | STRENGTHENING OF 10 NOS. OVERLOAD LINES | [19 empty] | - | - |  |  | - | - |  |  | - | -
7 | A-19-05 | Augmentation of PTRs at gesukonda & Tiru | To meet the growing loads | 0.845 | 18.03.2020 | 31.03.2023 | 1.47 | Incl |  | Incl | Incl | Incl | 1.47 | [6 empty] | TSTRANSCO Funds | 0.385 | - | - | 26.19% | 0 | - | - | 0% | 0.845 | - | - | 57.48%
1 | A-15-05 | AUGof PTR@EHT SS for extending 9Hrs | To meet the growing loads | 25.869 | 01.05.2015 | 31.03.2023 | 283.03 | Incl |  | Incl | Incl | Incl | 283.03 | [6 empty] | REC | 0.083 | - | - | 0.02933% | 0 | - | - | 0% | 25.869 | - | - | 9.14%
3 | A-15-07 | Augmentation of PTR capacities at 220kV | To meet the growing loads | 3.453 | 02.07.2015 | 31.03.2023 | 11.35 | Incl |  | Incl | Incl | Incl | 11.35 | [6 empty] | REC | 0 | - | - | 0% | 0 | - | - | 0% | 3.453 | - | - | 30.42%
4 | A-15-25 | Aug. at 220KV SS Gachibowli ADDL. 50MVA. | To meet the growing loads | 3.915 | 23.06.2015 | 31.03.2023 | 6.2 | Incl |  | Incl | Incl | Incl | 6.2 | [6 empty] | REC | 0 | - | - | 0% | 0 | - | - | 0% | 3.915 | - | - | 63.15%
5 | A-16-01 | 3rd 31.5MVA PTR at Adilabad SS | To meet the Industrial, Agriculture and etc., loads | 0.884 | 01.03.2016 | 31.03.2023 | 3.06 | Incl |  | Incl | Incl | Incl | 3.06 | [6 empty] | REC | -0.005 | - | - | -0.1634% | 0 | - | - | 0% | 0.884 | - | - | 28.89%
12 | A-19-03 | Augmentation of 80 MVA at 132 KV IDPL SS | To meet the growing loads | 0.319 | 07.03.2020 | 31.03.2023 | 0.72 | Incl |  | Incl | Incl | Incl | 0.72 | [6 empty] | TSTRANSCO Funds | 0 | - | - | 0% | 0.112 | - | - | 15.56% | 0.431 | - | - | 59.86%
6 | A-18-05 | PSDF STRENGTHENING-7NO'S 220KV EHT LINES |  | 90.727 | 18.09.2018 | 31.03.2023 | 100.5 | Incl |  | Incl | Incl | Incl | 100.5 | [6 empty] | PSDF Grant | 0.147 | - | - | 0% | 0.147 | - | - | 0.1463% | 90.874 | - | - | 90.42%
7 | A-19-01 | Aug of 4th 160 MVA at 220KV Gachibowli | To meet the growing loads | 3.964 | 03.07.2019 | 31.03.2023 | 6.2 | Incl |  | Incl | Incl | Incl | 6.2 | [6 empty] | TSTRANSCO Funds | 0 | - | - | 0% | 0.092 | - | - | 1.484% | 4.056 | - | - | 65.42%
10 | A-20-04 | Augmentation of PTR at 132KV Donthanpall | To meet the growing loads | 2.708 | 03.11.2020 | 31.03.2023 | 3.3 | Incl |  | Incl | Incl | Incl | 3.3 | [6 empty] | TSTRANSCO Funds | 2.708 | - | - | 82.06% | 0 | - | - | 0% | 2.708 | - | - | 82.06%
11 | A-20-05 | Augmentation of PTR at 132KV Khaithalapu | To meet the growing loads | 2.37 | 18.11.2020 | 31.03.2023 | 32.64 | Incl |  | Incl | Incl | Incl | 32.64 | [6 empty] | TSTRANSCO Funds | 0.326 | - | - | 59.27% | 3.274 | - | - | 10.03% | 5.644 | - | - | 17.29%
38 | R-16-02 | PSDF | To improve system protection | 42.803 | 08.02.2016 | 31.03.2023 | 59.97 | Incl |  | Incl | Incl | Incl | 59.97 | [6 empty] | PSDF Grant | 0.033 | - | - | 0.05503% | 0.152 | - | - | 0.2535% | 42.955 | - | - | 71.63%
39 | R-15-01 | RMI | Replacement of old and obsolute equipment of substations and lines of TSTRANSCO | 15.559 | 1/4/2021 | 31.03.2023 | 53.08 |  |  | inclusive | inclusive |  | 53.08 |  |  | 47.72 |  |  |  | PFC | 0.173 | - | - | 0.3259% | 0.173 | - | - | 0.3259% | 15.732 | - | - | 29.64%
40 | R-17-01 | RMI |  | 21.14 | 1/4/2021 | 31.03.2023 | 80.22 |  |  | inclusive | inclusive |  | 80.22 |  |  | 72.176 |  |  |  | REC | 5.025 | - | - | 6.264% | 5.025 | - | - | 6.264% | 26.165 | - | - | 32.62%
41 | R-17-02 | 132 KV BEL'PALLY - S' KHAGAZ NAGAR TOWER |  | 0.53 | 23/04/2018 | 31.03.2023 | 4.9 |  |  | inclusive | inclusive |  | 4.9 | [6 empty] | TSTRANSCO Funds | 0.53 |  |  | 10.82% | 0.53 | - | - | 10.82% | 0.53 | - | - | 10.82%
42 | R-20-01 | RMI |  | 17.05 | 1/4/2021 | 31.03.2023 | 75.65 |  |  | inclusive | inclusive |  | 75.65 |  |  | 68.04 |  |  |  | REC | 7.88 | - | - | 10.42% | 7.88 | - | - | 10.42% | 24.93 | - | - | 32.95%
43 | O-16-01 | Rolling Stock | Procurement of Major SS Equipment | 15.51 | 1/4/2021 | 31.03.2023 | 39.53 | - | - | Inclusive | Inclusive |  | 39.53 | - | - | 35.57 | - | - | - | REC | 0.324 | - | - | 0.8196% | 0.324 | - | - | 0.8196% | 15.834 | - | - | 40.06% | -
44 | O-18-01 | Rolling Stock | Procurement of Major SS Equipment | 0.951 | 1/4/2021 | 31.03.2023 | 26.43 | - | - | Inclusive | Inclusive |  | 26.43 | - | - | 23.787 | - | - | - | REC | 0 | - | - | 0% | 0 | - | - | 0% | 0.951 | - | - | 3.598% | -
45 | Z-21-01 | Rolling Stock | Procurement of Major SS Equipment | 11.32 | 1/4/2021 | 31.03.2023 | 53 | - | - |  |  |  | 53 | - | - |  | - | - | - | TSTRANSCO Funds | 14.576 | - | - | 27.5% | 14.576 | - | - | 27.5% | 25.896 | - | - | 48.86% | -

## CE-LIS-22-23
Annexure -I : ABSTRACT OF ACTUAL EXPENDITURE INCURRED FOR FY 2022-23 : LIFT IRRIGATION SCHEMES
| Form 1.1d - INVESTMENT PLAN |  |  | This form captures investments as planned and actually incurred | [26 empty] | ANNEXURE- II
| FY: 2022-23 | [31 empty] | Rs. In Crores
Sl. No. | Project Code | Project Title | SAP Scheme ID's | Project Purpose | Opening CWIP as at 31.03.2023 | Project Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [6 empty] | SOURCE OF FINANCING | [6 empty] | Investments proposed for the year |  |  |  | Investments incurred in the year FY 2022-23 |  |  |  | CUMULATIVE EXPENDITURE |  |  |  | Remarks
[8 empty] | Base Cost (in Rs.Crores) | Contigency | IDC | Duties | TAXES | Expence Capatalised | Total Cost | Internal Accrual Component of capex in year | Equity Component of capex in year | Debt Component of capex in year |  |  |  |  | Annual |  |  |  | Annual |  |  |  | Cumulative progress (Year on year)
[17 empty] | Loan Amount | Interest Rate | Moratorium period | Repayment period | Loan source | Proposed investment in the year(Rs. Crores) | Proposed IDC | Proposed other expense | % Capatalisation | Actual investment in the year | IDC incurred | Other expense incurred | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation
1 | Bulk Load/ | Godavari LIS | L-05-02 | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  | Apr-17 | 2019-10-19 | 97 | [5 empty] | 97 |  |  | 97 |  |  |  | Govt. of TS Grants I&CAD | 0 |  |  |  | 0.0826 |  |  |  | 15.1002
| DC Works | (a) (132/11kV Gandiramaram, 132/11kV Bommakuru, 132/11kV Rangaraopalli)
|  | (b) 132/11 kV Rajavaram SS | l-19-02 |  |  | 2021-03-21 | Mar-22 | 22.43 | [5 empty] | 22.43 |  |  | 22.43 |  |  |  | Govt. of TS Grants I&CAD | 0 |  |  |  | 0.7839 |  |  |  | 17.0956
2 | Bulk Load/ | Kaleshwaram Lift Irrigation Project | D-15-03 L-15-02 L-15-03 L-15-04 L-16-02 L-16-03 L-16-05 | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  | 2016-08-01 | 2020-06-20 | 3086.44 | [5 empty] | 3086.44 | 3086.44 | 3086.44 | 3086.44 |  |  |  | Govt. of TS Grants I&CAD | 0 |  |  |  | 33.48 |  |  |  | 1298.6758
| DC Works | (400kV Medaram,400kV Ramadugu,400kV Sundilla,220kV Medigadda, 220kV Annaram, 400kV Tippapur, 400kV Chandlapur,400kV Tukkapur, 132kV Malakpet)
3 | Bulk Load/ | Chanaka Korata LIS | L-17-01 | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  | Apr-17 | 2019-05-19 | 41.15 | [5 empty] | 41.15 |  |  | 41.15 |  |  |  | Govt. of TS Grants I&CAD | 0 |  |  |  | 0.0864 |  |  |  | 4.0056
| DC Works | 132/11kV Hatighat
4 | Bulk Load/ | Thotapally Reservoir to Gouravelly Reservoir LIS (220/132kV Huzurabad SS and CL) | D-11-05 L-11-01 | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  | Feb-15 | Mar-22 | 69.7031 | [5 empty] | 69.7031 |  |  | 69.7031 |  |  |  | Govt. of TS Grants I&CAD | 0 |  |  |  | 0.1215 |  |  |  | 38.373
DC Works
5 | Bulk Load/ | Lift Irrigation Scheme along Flood Flow Cancal | L-17-03 | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  | Feb-18 | 2020-05-20 | 186.9 | 189.3608 |  |  |  |  | 186.9 | 186.9 | 186.9 | 186.9 |  |  |  | Govt. of TS Grants I&CAD | 0 |  |  |  | 0.2924 |  |  |  | 86.5544
| DC Works | 220/11 kV Rampur SS, 220/11kV Rajeswerraopeta SS, 220/11kV Mupkal SS
6 | Bulk Load/ | Kaleshwaram PKGS-20,21&22 | L-14-02 | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  | 2019-04-01 | Sep-23 | 264.82 | [5 empty] | 264.82 | 264.82 | 264.82 | 264.82 |  |  |  | Govt. of TS Grants I&CAD | 0 |  |  |  | 12.92 |  |  |  | 173.6844
| DC Works | 220/11kV Sarangapur, 220/11kV Manichippa, 220/11kV Yacharamthanda
7 | Bulk Load/ | JCR Phase-III Supplemental &Augmentation works at Bheemghanpur | L-18-02 | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  | 2018-05-13 | 2019-08-13 | 23.99 | [5 empty] | 23.99 |  |  | 23.99 |  |  |  | Govt. of TS Grants I&CAD | 0 |  |  |  | 0.05 |  |  |  | 11.6982
| DC Works | 220/11kV Bheemghapur
8 | Bulk Load/ | Kaleshwaram Lift Irrigation Schemes | L-19-01 | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  | 2020-05-20 | Sep-23 | 67.77 | [5 empty] | 67.77 |  |  | 67.77 |  |  |  | Govt. of TS Grants I&CAD | 0 |  |  |  | 3.14 |  |  |  | 20.8614
| DC Works | 220/11 kV New Manchippa SS and 220/11 kV New Mentrajpally SS
9 | Bulk Load/ | JCR Phase-III 220/11kV Devvanapeta SS | L-18-01 | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  | Dec-19 | Mar-23 | 138.66 | [5 empty] | 138.66 | 138.66 | 138.66 | 138.66 |  |  |  | Govt. of TS Grants I&CAD | 0 |  |  |  | 22.9 |  |  |  | 112.939
| DC Works | 220/11kV Devvanapeta SS
10 | Bulk Load/ | Kaleshwaram Lift Irrigation Scheme | L-20-01 D-20-08 | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  | April-20 | Mar-23 | 2946.539 | [5 empty] | 2946.539 | 2946.539 | 2946.539 | 2946.539 |  |  |  | Govt. of TS Grants I&CAD | 0 |  |  |  | 467.09 |  |  |  | 496.04
| DC Works | Additional Loads under KLIS Link -I and IV
11 | Bulk Load/ | Dr. BRAPCSS LIS (Kanakapur) | l-16-04 | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  | 2016-12-01 | 2018-11-11 | 31.35 |  |  |  | 31 |  | 31.35 | 31 |  | 31.35 |  | Govt. of TS Grants | 10 | Govt. of TS Grants I&CAD | 0 |  | 10 |  | 0.0109 |  |  |  | 1.9909
DC/Woks
12 | Bulk Load/ | Lift Irrigation Scheme at Jogapur | L-14-01 | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  | 2016-12-16 | 2018-05-17 | 45.12 |  |  |  | 45.12 |  | 45.12 | 45.12 |  | 45.12 |  | Govt. of TS Grants | 38.63 | Govt. of TS Grants I&CAD | 0 |  | 38.63 |  | 0.0269 |  |  |  | 0.1572
DC Works
13 | Bulk Load/ | Kaleshwaram Lift Irrigation Scheme OLD | L-13-02 | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  | 2016-12-01 | Jun-20 | 31.39 | [5 empty] | 31.39 |  |  | 31.39 |  |  |  | Govt. of TS Grants I&CAD |  |  |  |  | 0.51 |  |  |  | 15.5794
| DC Works | 132/11kV Beersagar(Kannepalli) LIS | [19 empty] | 0
14 | Bulk Load/ | AMRP LLC Lift Irrigation Project at Puliathanda |  | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  | 2016-01-16 | 2018-01-16 | 3.37 |  |  |  | 3.9108 |  | 3.37 | 3.37 | 3.37 | 3.37 |  | Govt. of TS Grants | 3.9108 | Govt. of TS Grants I&CAD | 0 |  | 3.9108 |  | -0.03 |  |  |  | 0.256
| DC Works |  | L-15-01
16 | Bulk Load/ | Kaleshwaram Lift Irrigation Scheme- Package -14 | L-17-04 | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  | 2018-04-01 | Apr-20 | 197.66 | [5 empty] | 197.66 |  |  | 197.66 |  |  |  | Govt. of TS Grants I&CAD | 0 |  |  |  | 1.01 |  |  |  | 107.6045
| DC Works | (Akkaram & Markook)
18 | Bulk Load/ | Thumilla Lift Irrigation ( RDS ) | L-18-03 | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  | Aug-18 | 2018-11-18 | 34.3 | [5 empty] | 34.3 | 34.3 | 34.3 | 34.3 |  |  |  | Govt. of TS Grants I&CAD | 0 |  |  |  | -0.19 |  |  |  | 4.868
| DC Works | 132/11kVThumilla
19 | Bulk Load/ | PRLIS Diversion of 3Nos. 220kV lines due to submerging in the proposed Anjanagiri Project | L-17-05 | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  | 2018-05-01 | 2020-12-01 | 18.23 | [5 empty] | 18.23 |  |  | 18.23 |  |  |  | Govt. of TS Grants I&CAD | 0 |  |  |  | -0.713 |  |  |  | 7.1272
DC Works
20 | Bulk Load/ | CMD OF 220 MVA@ IND SAGAR RUDRA LIS | L-13-01 | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | [16 empty] | Govt. of TS Grants I&CAD | 0 |  |  |  | 0.0048 |  |  |  | 0.0048
DC Works
|  |  | Total in Rs. |  |  |  |  | 7306.8221 | 189.3608 |  |  | 80.0308 |  | 7306.8221 | 6737.149 | 6661.029 | 7306.8221 |  |  | 52.5408 |  |  |  | 52.5408 |  | 541.5764 |  |  |  | 2412.6156

## CE-400LIS
Abstract of Actual Expenditure incurred for FY:2022-23 of 400kV Schemes-LIS | [27 empty] | ANNEXURE- II
Format 1.1(d)
FY: 2022-23 | [26 empty] | (Amount Rs. in Crs)
S.No. | Project Code | Project Title | Project Purpose | Projrct Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [5 empty] | SOURCE OF FINANCING | [6 empty] | Investments proposed for the year |  |  |  | Investments incurred in the year |  |  |  | Cumulative progress (year on year) |  |  |  | Remarks
[6 empty] | Base Cost (in Rs.Crs) | Contigency | IDC | TAXES | Expence Capatalised | Total Cost | Internal Accrual Component of capex in year | Equity Component of capex in year | Loan Amount | Interest Rate | Moratorium period | Repayment period | Loan source | Proposed investment in the year(Rs. Crs.) | Proposed IDC | Proposed other expence | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation | Actual investment in the year(Rs.in Crs) | IDC incurred | Other expence incurred | % Capatalisation
1 | Bulk Load/DC works | Indira Sagar Rudrammakota LIS (L-13-01) | Providing Supply to LI pumps | Mar'2014 | Aug'2017 | 290.14 | -- | -- | -- | -- | 290.14 | [6 empty] | Govt TS Grants | - |  |  |  | 0.004 |  |  |  | 0.004 |  |  | 100
2 | Bulk Load/DC works | Sita Rama Lift Irrigation scheme (L-18-04) | Providing Supply to LI pumps | Sep'2018 | May'2023 | 418.45 | -- | -- | -- | -- | 418.45 | [6 empty] | Govt TS Grants | - |  |  |  | 4.454 |  |  |  | 4.454 |  |  | 100
| Total | [9 empty] | 708.59 | [7 empty] | - |  |  |  | 4.458 |  |  |  | 4.458
C:\Users\aderac.TSVSHYD.052\Desktop\[ApR 22-23 1.1d-400kV_LIS - 22.12.2023.xls]2021-22

## CE-PRLIS
ANNEXURE- II
Format 1.1(d) Abstract of Actual Expenditure incurred for FY:2022-23 of PRLIS Scheme)
(Amount Rs. in Crs)
Base Year 2022-23
S.No. | Project Code | Project Title | CWIP as on 31.03.2022 | Project Purpose | Projrct Start Date DD-MM-YY | Project Completion Date DD-MM-YY | PLANNED CAPITAL EXPENDITURE | [5 empty] | SOURCE OF FINANCING | [6 empty] | Investments proposed for the year |  |  |  | Investments incurred in the year |  |  |  | Cumulative progress (year on year) |  |  |  | Remarks
[7 empty] | Base Cost (in Rs.Crs) | Contigency | IDC | TAXES | Expence Capatalised | Total Cost | Internal Accrual Component of capex in year | Equity Component of capex in year | Loan Amount | Interest Rate | Moratorium period | Repayment period | Loan source | Proposed investment in the year(Rs. Crs.) | Proposed IDC | Proposed other expence | % Capatalisation | Actual investment in the year | IDC incurred | Other expence incurred | % Capatalisation | Actual investment in the year(Rs.in Crs) | IDC incurred | Other expence incurred | % Capatalisation
1 | Bulk Load/ DC works | Palamuru Ranga Reddy Lift Irrigation Scheme (L-17-02) | 744.89 | Lift Irrigation works (DCW) | Mar'2018 | May'2024 | 2155.04 | -- |  |  |  | 2155.04 | [6 empty] | Grants | 300 |  |  |  | 403.14 |  |  |  | 1148.03
| Total |  | 744.89 | [8 empty] | 2155.04 | [7 empty] | 300 |  |  |  | 403.14 |  |  |  | 1148.03