## Proj CapEx 26-27
TRANSMISSION CORPORATION OF TELANGANA LIMIED
Annual Tariff Petition for 2026-27 for SLDC Activity filed with TGERC
Work wise details of Capital Expenditure proposed for Financial Year 2026-27
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme maybe given) | Justification | Project Purpose (SI/SE/SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total TGERC approved Cost (in Cr) | Source of funds |  |  |  | Proposed Project Start Date DD-MM-YY | Proposed Project Completion Date DD-MM-YY | CWIP O.B. | FY:2025-26 |  |  | Projected expenditure for 2026-27 (in Cr) | Spill over Yearly Capital Expenditure projected for works taken up in or before 2025-26 (in Cr) |  | Projected Capitalizaion in 2026-27 | Total Cumulative Expenditure (in Cr) | Present Status of work | Whether approved in Resource Plan
[10 empty] | SLDC funds (in Cr) | Loan source (in Cr) | Loan Amount (in Cr) | Grants, if any |  |  |  | 1st Half (Apr-Sept) (Actuals) (in Cr) | 2nd Half (Oct-Mar) (Projected) (in Cr) | Total 25-26 (Projected) (in Cr) |  | 2027-28 | 2028-29
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 23 | 24 |  | 25 | 26 | 27
SLDC
I. Ongoing Schemes as on 01.04.2026 (Investment approval accorded by Hon'ble TGERC)
1 | - | Upgradation of existing SCADA system at Main SLDC, Hyderabad & Establishment of SCADA/EMS system as Backup SLDC at Warangal | Upgradation of existing SCADA system at Main SLDC, Hyderabad & Establishment of SCADA/EMS system as Backup SLDC at Warangal |  | SI & SE | Ms No 1644 Dt 02.5.2023 | NA | 02/2023-24 | 62.16 | 6.216 | HUDCO | 55.944 | NA | 6.1.25 | 5.9.26 | 0 | 0 | 31.08 | 31.08 | 31.08 | 0 | 0 | 62.16 | 62.16 | NOA issued to M/s L & T on 6.1.2025 and subsequently contract was entered. As on date approvals of Functional Design Specification are being provided to M/s L & T for initiating procurement . | No
|  | Sub-Total-I (SLDC) | [7 empty] | 6.22 | [7 empty] | 31.08 | 31.08 | 31.08 | 0 | 0 | 62.16 | 62.16
II. New works to be taken up during 2026-27
1 |  | Renovation of existing SLDC control room and server room, UPS room, SLDC video conference room and Telecom room |  |  | SI | Will be obtained | NA | NA | Will be obtained | 1.89 | NA | NA | NA | 01.04.26 | 31.03.27 | 0 | 0 | 0 | 0 | 1.89 | 0 | 0 | 1.89 | 1.89 |  | No
2 | SS-22-07 | Implementation of SAMAST in Telangana |  |  | SE | Ms No 1406, Dt. 30.05.2022 | NA | NA | NA | 5.17 | NA | 12.48 | NA | 01.04.26 | 31.03.27 | 0 | 0 | 0 | 0 | 5.17 | 0 | 0 | 5.17 | 5.17 | Out of total project cost of 21.95 Cr, Grant is 12.48 Cr & Entity portion is 9.47 Cr of which SLDC portion is 5.17 Cr & balance 4.3 cr is to be borne by TGTRANSCO. Rs. 1.495 Cr grant was utilized by TGTRANSCO | No
3 | - | Replacement of old equipment and upgradation of equipment at main & Backup control centers for transmission of Voice & Data to SLDC. New OLTES are required to install for transmission of data to proposed backup control center at warangal & upgradation of NMS |  |  | SI | Will be obtained | NA | NA | Will be obtained | 1 | NA | NA | NA | 01.04.26 | 31.03.27 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 |  | No
4 | - | Personal Computers |  |  | SR | Will be obtained | NA | NA | NA | 0.074 | NA | NA | NA | 01.04.26 | 31.03.27 | 0 | 0 | 0 | 0 | 0.074 | 0 | 0 | 0.074 | 0.074 |  | No
5 | - | Furniture for Main SLDC (Computer Tables, Chairs, etc) |  |  | SI | Will be obtained | NA | NA | NA | 0.05 | NA | NA | NA | 01.04.26 | 31.03.27 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.05 | 0.05 |  | No
6 | - | Cyber Security |  |  | SR | Will be obtained | NA | NA | NA | 0.1815 | NA | NA | NA | 01.04.26 | 31.03.27 | 0 | 0 | 0 | 0 | 0.1815 | 0 | 0 | 0.1815 | 0.1815 |  | No
7 | - | Miscellaneous / Unforeseen Expenses (Other than SCADA) (Software) |  |  | SI | Will be obtained | NA | NA | NA | 0.025 | NA | NA | NA | 01.04.26 | 31.03.27 | 0 | 0 | 0 | 0 | 0.025 | 0 | 0 | 0.025 | 0.025 |  | No
8 | - | Miscellaneous / Unforeseen Expenses (Other than SCADA) (Hardware) |  |  | SI | Will be obtained | NA | NA | NA | 0.025 | NA | NA | NA | 01.04.26 | 31.03.27 | 0 | 0 | 0 | 0 | 0.025 | 0 | 0 | 0.025 | 0.025 |  | No
9 | - | Unforseen expenses for EMS/ SCADA (Not Covered under AMC) (Software) |  |  | SI | Will be obtained | NA | NA | NA | 0.05 | NA | NA | NA | 01.04.26 | 31.03.27 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.05 | 0.05 |  | No
10 | - | Unforseen expenses for EMS/ SCADA (Not Covered under AMC) (Hardware) |  |  | SI | Will be obtained | NA | NA | NA | 0.05 | NA | NA | NA | 01.04.26 | 31.03.27 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.05 | 0.05 |  | No
Sub=Total-II (SLDC) | [9 empty] | 8.5155 | [5 empty] | 0 | 0 | 0 | 0 | 8.5155 | 0 | 0 | 8.5155 | 8.5155
CIVIL
1 | …... | …... | Supply, Transport and Installation of 1 No. 2.0 TR 5 Star Split Air Conditioner, Inverter Model, Make: O general for the use at UPS and Battery Room SLDC 5th floor, A-Block, and 1 No. 4 Tonne Tower Air Conditioner for the use at Telecom Exchange Room No:118, A-Block, Vidyut Soudha, Hyderabad | …... | …... | L.P.O.No.03 /25-26 /CE/Civil | …... | …... | …... | Yes | …... | …... | …... | …... | …... | …... | 0 | 0.02 | 0.02 | 0.05 | …... | …... | 0.05 | 0.07 | Completed | * 0.02 Cr expenditure incurred in 2025-26 was capitalized in the same year
|  | Sub-Total-III (Civil) | [14 empty] | 0 | 0.02 | 0.02 | 0.05 | 0 | 0 | 0.05 | 0.07
|  | Grand total | [7 empty] | 14.7355 | [6 empty] | 0 | 31.1 | 31.1 | 39.6455 | 0 | 0 | 70.7255 | 70.7455
[22 empty] | add Interest During Construction | 5.59
[22 empty] | Total with IDC | 76.32

## CapEx 25-26
TRANSMISSION CORPORATION OF TELANGANA LIMIED
Annual Tariff Petition for 2026-27 for SLDC Activity filed with TGERC
Work wise details of Capital Expenditure incurred during the Financial Year 2025-26
Sl.No | Project Code/ Scheme ID ( SAP Code) | Project Title | Scope of Work | Project Purpose (SI/SE/SR/GE | Administrative approval | SRPC Approval | TGERC approval | Total Cost (Cr) | Source of Funds |  |  |  | Project Start Date | Project Completion | DOC | Opening CWIP as on 31.3.25 | Actual Expenditure from 1.4.25 to 31.3.26 (Cr) | Cumulative Expenditure upto 31.3.26 (Cr) | Projected Capitalization in 2025-26 (Cr) | % Capitalization | Remarks/Balance works if any
[9 empty] | SLDC (Cr) | Loan Source | Loan Amount | Grants
SLDC
1 | N-24-01HQ-190099080601 | Construction of building & Providing infrastructure at Backup SLDC |  | SE | NA | NA | Work initated in 4th Control Period | 9.3124 | Yes | NA | NA | NA | 15.11.23 | 31.3.26 | 31.3.26 | 1.723 | 7.587 | 9.3124 | 9.3124 | 100 | Nil
2 | NA | Upgradation of existing SCADA system at Main SLDC, Hyderabad & Establishment of SCADA/EMS system as Backup SLDC at Warangal |  | SI & SE | Ms No 1644 Dt 02.5.2023 | NA | 02/2023-24 | 62.16 | 6.216 | HUDCO | 55.944 | NA | 6.1.25 | 5.9.26 | 5.9.26 | 0 | 31.08 | 31.08 | 0 | 0 | Nil
3 | NA | Establishment of New Server room, New UPS room and Temporary Control room |  | SI | Under Process | NA | Will be obtained | 2.3 | Yes | NA | NA | NA | 1.12.25 | 31.03.26 | 31.03.26 | 0 | 2.3 | 2.3 | 2.3 | 100 | Nil
4 | NA | Backup SLDC infrastructure |  | SE | Under Process | NA | Will be obtained | 8.01 | Yes | NA | NA | NA | 1.12.25 | 31.03.26 | 31.03.26 | 0 | 8.01 | 8.01 | 8.01 | 100 | Nil
5 | NA | Procurement of Personal Computers |  | SR | Will be obtained | NA | NA | 0.43648 | Yes | NA | NA | NA | 1.12.25 | 31.03.26 | 31.03.26 | 0 | 0.43648 | 0.43648 | 0.43648 | 100 | Nil
6 | NA | Procurement of Laptops |  | SI | Under Process | NA | NA | 0.145 | Yes | NA | NA | NA | 01.12.25 | 31.03.26 | 31.03.26 | 0 | 0.145 | 0.145 | 0.145 | 100 | Nil
7 | NA | Furniture for Main SLDC (Computer Tables, Chairs, etc) |  | SI | Will be obtained | NA | NA | 0.05 | Yes | NA | NA | NA | 1.12.25 | 31.03.26 | 31.03.26 | 0 | 0.05 | 0.05 | 0.05 | 100 | Nil
8 | NA | Cyber Security |  | SR | Will be obtained | NA | NA | 0.165 | Yes | NA | NA | NA | 1.12.25 | 31.03.26 | 31.03.26 | 0 | 0.165 | 0.165 | 0.165 | 100 | Nil
9 | NA | Miscellaneous / Unforeseen Expenses (Other than SCADA) (Software) |  | SI | Will be obtained | NA | NA | 0.025 | Yes | NA | NA | NA | 1.12.25 | 31.03.26 | 31.03.26 | 0 | 0.025 | 0.025 | 0.025 | 100 | Nil
10 | NA | Miscellaneous / Unforeseen Expenses (Other than SCADA) (Hardware) |  | SI | Will be obtained | NA | NA | 0.025 | Yes | NA | NA | NA | 1.12.25 | 31.03.26 | 31.03.26 | 0 | 0.025 | 0.025 | 0.025 | 100 | Nil
11 | NA | Unforseen expenses for EMS/ SCADA (Not Covered under AMC) (Software) |  | SI | Will be obtained | NA | NA | 0.05 | Yes | NA | NA | NA | 1.12.25 | 31.03.26 | 31.03.26 | 0 | 0.05 | 0.05 | 0.05 | 100 | Nil
12 | NA | Unforseen expenses for EMS/ SCADA (Not Covered under AMC) (Hardware) |  | SI | Will be obtained | NA | NA | 0.05 | Yes | NA | NA | NA | 1.12.25 | 31.03.26 | 31.03.26 | 0 | 0.05 | 0.05 | 0.05 | 100 | Nil
13 | NA | Replacement of old equipment and upgradation of equipment at main & Backup control centers for transmission of Voice & Data to SLDC. New OLTES are required to install for transmission of data to proposed backup control cnter at warangal & upgradation of NMS |  | SI | Will be obtained | NA | NA | 3.6 | Yes | NA | NA | NA | 1.12.25 | 31.03.26 | 31.03.26 | 0 | 2.6 | 2.6 | 2.6 | 100 | Nil
14 |  | Supply, Transport and Installation of 1 No. 2.0 TR 5 Star Split Air Conditioner, Inverter Model, Make: O general for the use at UPS and Battery Room SLDC 5th floor, A-Block, and 1 No. 4 Tonne Tower Air Conditioner for the use at Telecom Exchange Room No:118, A-Block, Vidyut Soudha, Hyderabad |  |  | L.P.O.No.03 /25-26 /CE/Civil |  |  |  | Yes | [7 empty] | 0.02 |  | 0.02 | 100
Sub-Total-I (SLDC) | [15 empty] | 1.723 | 52.5435 | 54.2489 | 23.1889
Power Systems
15 | NA | Procurement of 3 Nos. new PSS®E software licenses | - | SI | will be obtained | NA | NA | 0.83 | Yes | NA | NA | NA | 01.12.25 | 31.03.26 | 31.03.26 | 0 | 0.83 | 0.83 | 0.83 | 100 | Nil
Sub-Total-II (Power Systems) | [15 empty] | 0 | 0.83 | 0.83 | 0.83
Grand Total | [15 empty] | 1.723 | 53.3735 | 55.0789 | 24.0189

## Actual Expr 2024-25
TRANSMISSION CORPORATION OF TELANGANA LIMIED
Annual Tariff Petition for 2026-27 for SLDC Activity filed with TGERC
Work wise details of Capital Expenditure (Actuals) incurred during the Financial Year 2024-25
SI.No. | Project Code /Scheme ID (SAP Code) | Project Title | Scope of work | Justification | Project Purpose (SI/SE/SR/GE) | Administrative approval | SRPC Approval | TGERC Approval | Total Cost (Cr) | Source of Funds |  |  |  | Project Start Date | Project Completion | DOC | Opening CWIP as on 31.03.2024 | Actual Expenditure from 01.04.2024 to 31.03.2025 | Cumulative Expenditure upto 31.03.2025 | % Capitalization | Remarks/ Balance works if any
[10 empty] | TGTRANSCO | Loan Source | Loan Amount | Grants
1 | N-24-01HQ-190099080101 | Procurement & Installation of 2 Nos Tower Air Conditioners | Procurement & Installation of 2 Nos Tower Air Conditioners | Old Tower Air Conditioners have served useful life and frequent performance issues were observed. Hence, old Tower Air Conditioners were replaced with New Air Conditioners | SR | 439/24-25 | NA | NA | 0.0334 | Yes | NA | NA | NA | 12.06.2024 | 12.06.2024 | 12.06.2024 | 0 | 0.0334 | 0.0334 | 100
2 | N-24-01HQ-190099080601 | Construction of Backup SLDC in the premises of 220 kV SS Warangal | Construction of Backup SLDC in the premises of 220 kV SS Warangal | For Establishing Backup SLDC | SE | Note Approval 2081 Dt 22.11.22 | NA | Work initiated in the 4th control period | 9.312 | Yes | NA | NA | NA | 21.06.2023 | CWIP | CWIP | 0 | 1.723 | 1.723 | 0
3 | N-24-01HQ-190099080201 | Procurement of 2 Nos HP make printers for use in the O/o CE/Telecom/VS | Procurement of 2 Nos HP make printers for use in the O/o CE/Telecom/VS | Replacement of old printers which are beyond repair | SR | Note Approval Dt 06.08.24 | NA | NA | 0.00338 | Yes | NA | NA | NA | 04.12.2024 | 04.12.2024 | 04.12.2024 | 0 | 0.0034 | 0.0034 | 100
4 | N-20-01HQ-190099080901 | Establishment REMC at Telangana SLDC | Establishment REMC at Telangana SLDC | For Establishing REMC | SE | Note Approval Dt 30.11.2019 | NA | NA | 8.35 | NA | NA | NA | Yes | 31.03.2021 | 30.09.2024 | 30.09.2024 | 0 | 0.1727 | 8.35 | 100
| Total | [7 empty] | 17.6988 | [8 empty] | 1.9325 | 10.1098

## Actual capitalization 24-25
Transmission Corporation of Telangana Limited
Annual Tariff Petition for 2026-27 for SLDC Activity filed with TGERC
Work-wise details of Actual Capitalization in FY: 2024-25
Work Period
SI. No. | Voltage | Project Code/ Scheme ID (SAP Code) | Project Title | Scope of work | Justification | Project Purpose (SI/SE/ SR/GE) | Administrative approval | SRPC Approval | TGERC approval | Start Date |  | Completion Date |  | Capitalization date | Approved cost as per investment approval | Source of Funds |  |  |  | Capitalization upto previous year (n-1) (as per audited financial statements) (in Cr) | Capital Expenditure in (2024-25)(in Cr) | Capitalization claimed in (2024-25) | Whether part capitalization or full capitalization | Addition to the networks |  |  |  | PCC | FCC | Remarks/ Reasons for cost & Time overruns if any
[10 empty] | Sch | Act | Sch | Act |  |  | TGTRANSCO | Loan Source | Loan Amount | Grants |  |  |  |  | SS | Lines | PTR | Bays
1 | NA | N-24-01HQ-190099080101 | Procurement & Installation of 2 Nos Tower Air Conditioners | Procurement & Installation of 2 Nos Tower Air Conditioners | Old Tower Air Conditioners have served useful life and frequent performance issues were observed. Hence, old Tower Air Conditioners were replaced with New Air Conditioners | SR | 439/24-25 | NA | NA | 07.06.2024 | 07.06.2024 | 12.06.2024 | 12.06.2024 | 12.06.2024 | NA | Yes | NA | NA | NA | 0 | 0.0334 | 0.0334 | Full | NA |  |  |  | 2025000231 | 2025000714 | NA
2 | NA | N-24-01HQ-190099080201 | Procurement of 2 Nos HP make printers for use in the O/o CE/Telecom/VS | Procurement of 2 Nos HP make printers for use in the O/o CE/Telecom/VS | Replacement of old printers which are beyond repair | SR | Note Approval Dt 06.08.24 | NA | NA | 04.12.2024 | 04.12.2024 | 04.12.2024 | 04.12.2024 | 04.12.2024 | NA | Yes | NA | NA | NA | 0 | 0.00338 | 0.00338 | Full | NA |  |  |  | 2025000250 | 2025000715 | NA
3 | NA | N-20-01HQ-190099080901 | Establishment REMC at Telangana SLDC | Establishment REMC at Telangana SLDC | For Establishing REMC | SE | Note Approval Dt 30.11.2019 | NA | NA | 31.03.2021 | 31.03.2021 | 30.09.2024 | 30.09.2024 | 30.09.2024 | NA | NA | NA | NA | Yes | 8.18 | 0.17 | 0.17 | Full | NA |  |  |  | 2023001574 | 2024000034 | NA
|  | Total | [18 empty] | 0.20678 | 0.20678