## 400kV Fy26-27-R1
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2026-27 for Transmission Business filed with TGERC
Scheme wise details of Capital Expenditure proposed for Financial Year 2026-27
400kV Transmission Schemes :
Sl No. | Project Code/ Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme maybe given) | Justification | Project Purpose (SI/SE/ SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total TGERC approved Cost (in Cr) | Source of funds |  |  |  | Proposed Project Start Date DD-MM-YY | Proposed Project Completion Date DD-MM-YY | CWIP O.B. | FY:2025-26 |  |  | Projected expenditure for 2026-27 | Spill over Yearly Capital Expenditure projected for works taken up in or before 2026-27 (in Cr) |  |  | Total Cumulative Expenditure (in Cr) | Present Status of work
[10 empty] | TGTransco funds | Loan source | Loan Amount | Grants, if any |  |  |  | 1st Half (Apr-Sept) (Actuals) | 2nd Half (Oct-Mar) (Projected) | Total (Projected) |  | 2027-28 | 2028-29 | 2029-30
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27)
I. Ongoing Schemes as on 01.04.2026 (Investment approval accorded by Hon'ble TGERC)
1 | S-14-02 | Suryapet Power Transmission Scheme | 1) 400/220/132 kV Suryapet Substation 2) LILO of 400kV VTS – Malkaram DC Line to Suryapet 400kV SS 3) 400kV Kamavarapukota - Suryapet QMDC Line 4) 400kV Suryapet - Shankarapally QMDC Line | Transmission System improvement in Nalgonda District and surrounding area | S I | 01/ 17.01.2014 49/ 04.12.2014 11/ 15.03.2016 | 36th & 39th SCPSPSR Meetings dtd. 04.09.2013 & 29.12.2015 respectively | APT/TS/ 400kV Suryapet/ F-INVST-28/2014 dt.21.01.2015 | 1738.03 | 420.76 | REC | 1317.27 | - | Sept., 2013 | Apr.' 2018 | 0.007 | -0.003 | 0 | -0.003 | 0 | 0 | 0 | 0 | 650.118 | All works completed
2 | P-16-01 | Telangana STPP-I Power (2x800MW) Evacuation Scheme | 1) 400/220kV Ramadugu Substation; 2) 400kV TSTPP - Ramadugu QMDC Line; 3) 400kV TSTPP - Narsapur QMDC Line | Power evacuation from Telangana STPP-I (2x800MW) | G E | 34/ 25.11.2016 104/ 12.07.2017 | 40th & 41st Meetings of SCPSPSR dtd. 19.11.2016 & 22.09.2017 respectively | 10/2017, dt.23.08.2017 | 1151.6 | 20.43 | REC | 1131.17 | - | Oct' 2017 | Aug.' 2021 | 0.502 | -0.005 | 0 | -0.005 | 0 | 0 | 0 | 0 | 861.196 | All works completed
3 | S-17-08 | Rayadurg System Improvement Scheme | 1) 400/220/132KV GIS at Rayadurg; 2) 400KV Kethireddypally - Rayadurg DC Line; 3) LILO of 220kV Gachibowli – Shivarampally Line to Rayadurg GIS; 4) LILO of 220kV Gachibowli – Shapurnagar Line to Rayadurg GIS; 5) LILO of 220kV Gachibowli – Miyapur Line to Rayadurg GIS; 6) LILO of 220kV Gachibowli – Erragadda Line to Rayadurg GIS; 7) 132kV Rayadurg - Madhapur DC Line; 8) 132kV Rayadurg - Jubileehills DC Line; 9) LILO of 132kV Jubilee Hills – Shivarampally SC Line to Rayadurg | Transmission System Improvement | S I | 44/ 22.03.2017 79/ 13.04.2018 | 41st Meeting of SCPSPSR dated 22.09.2017 | 02/2018-19, Dt. 24.05.2018 | 1786.4 | 8.14 | PFC | 1778.26 | - | Sep' 2018 | Apr' 2022 | 10.447 | -0.296 | 0 | -0.296 | 0 | 0 | 0 | 0 | 1745.611 | All works completed
4 | A-21-07 | Augmentation Scheme-IV | Erection of 315/500 MVA ICT’s at 400kV Suryapet, Asupaka, Veltoor, Dichpally & Gajwel Sub-stations | Transmission System Improvement | S I | 1311/ 14.02.2022; 1530/ 03.12.2022 | 41st Meeting of SCPSPSR dated 22.09.2017 CEA Lr. Dt. 10.12.2021 | 01 / 2022-23 Dt.05.05.2022; 01 / 2024-25 Dt.17.05.2024 | 187.48 | 19.18 | HUDCO | 168.3 | - | Dec.' 2020 | Sept., 2023 | 1.273 | 1.273 | 0 | 1.273 | 0 | 0 | 0 | 0 | 128.4 | All works completed
5 | S-21-05 | HVWS for 500MVA ICTs at 400kV Substations | HVWS for 500MVA ICTs at 400kV Substations | System improvement by protecting existing ICTs | S I | - | - | - | - | - | - | - | - | Dec' 2021 | May' 2022 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.894 | All works completed
6 | S-19-02 | Reactor Scheme-III | Installation of 125MVAR Bus Reactors at Suryapet, Rayadurg, Kethireddypalli, Narsapur, Maheshwaram, Janagaon and Dindi 400kV Substations and Installation of 80MVAR Bus Reactor & 63MVAR Switchable Line Reactors at Asupaka 400kV SS | System improvementby limiting over Voltages in the Grid | S I | 304/ 23.02.2019 | 41st Meeting of SCPSPSR dated 22.09.2017 & 1st Meeting of SRSCT dated 07.09.2018 | 04 / 2019-20; Dt. 09.12.2019 | 249.79 | 249.79 | PSDF | 0 | 158.72 | Jan' 2020 | Dec., 2025 | 93.48 | 0.915 | 1 | 1.915 | 0 | 0 | 0 | 0 | 152.223 | All works completed
7 | S-19-01 | KTPP System Improvement Scheme | 400/220/132kV Substation at KTPP Switchyard, Bhupalapally | To meet the load of existing 220kV & 132kV Substations and to reduce transmission losses in Bhupalapally District | S I | 297/ 09.02.2019 | 1st Meeting of SRSCT dated 07.09.2018 | 03 / 2019-20 Dt. 22.11.2019 | 454.23 | 49.23 | PFC | 405 | - | Jan' 2020 | March, 2026 | 170.826 | 3.627 | 2 | 5.627 | 10 | 6 | 0 | 0 | 226.848 | Substation commissioned on 19.02.2025 and balance works in progress
8 | P-19-02 | Yadadri Thermal Power Evacuation Scheme | 1) 400/220kV Dameracherla SS; 2) 400/220/132kV Choutuppal SS; 3) 400kV YTPPS - Damaracherla QMDC Line; 4) LILO of 400kV Mamidipally-Khammam TMDC Line to Choutuppal SS; 5) 400kV YTPP Switchyard - Dindi QMDC Line; 6) 400kV YTPP Switchyard - Choutuppal QMDC Line; 7) 400kV YTPP Switchyard - Jangoan QMDC Line: | Transmission Scheme for evacuation of 4000MW (5x800MW) Power from Yadadri Thermal Power Project at Damaracherla | G E | 451/ 10.10.2019 | 39th meeting of SCPSPSR dated 28-29.12.2015 & 1st meeting of SRPCTP dt.16.12.19 | 09 / 2019-20, Dt. 27.01.2020 | 2354.35 | 141.44 | PFC & REC | 1102.26 & 1110.65 | - | Jan' 2020 | Dec., 2026 | 991.677 | 45.863 | 30 | 75.863 | 125 | 25 | 0 | 0 | 1795.19 | All works completed except YTPP-Jangaon 400kV Line
[15 empty] | Oct., 2025 |  | YTPP-Choutuppal 400kV QMDC Line is commissioned on 30.10.2025 and PCC No.2025000527 is issued on 13.11.2025. Expenditure incurred so far for this Line is Rs.375.18 Crore as on 31.10.2025 (as per SAP-ERP).
Sub-total-I | [15 empty] | 1268.222 | 51.374 | 33 | 84.374 | 135 | 31 | 0 | 0 | 5560.48
II. New schemes to be taken up during 2026-27 :
1 | - | ICT Augmentation at 400kV Raidurg GIS Substation | Augmentation of 3rd 500MVA, 400/220kV ICT at 400/220/ 132/33kV Raidurg GIS Substation (including future ICT-4 Bay) | To provide load relief on existing 2x500 MVA ICTs in 400/220/132/ 33kV Raidurg GIS Substation and to meet future load growth in the area. | S I | 2448/ 24.07.2025 | CEA Lr.dt. 07.10.2024 | Proposal submitted to Hon'ble TGERC vide letter dated 22.08.2025 | - | 9.908 | To be tied-up | 89.174 | - | April, 2026 | March, 2028 | 0 | 0 | 0 | 0 | 79.26 | 19.822 | 0 | 0 | 99.082 | Works will be initiated after Investment approval
2 | - | 400kV Augmentation Scheme-V | Erection of 500/ 315 MVA, 400/220kV ICTs at 400kV Maheswharam, Shankarapally, Dindi & Kethireddipally Sub-stations | To provide load relief on existing ICTs and to meet future load growth in the area. | S I | 2440/ 18.07.2025 | CEA Lrs.dt. 07.10.2022, 07.03.2025 | Proposal submitted to Hon'ble TGERC vide letter dated 23.09.2025 | - | 16.357 | To be tied-up | 147.213 | - | April, 2026 | March, 2029 | 0 | 0 | 0 | 0 | 16.36 | 130.85 | 16.36 | 0 | 163.57 | Works will be initiated after Investment approval
3 | - | 400kV Bus Split Arrangement | 400kV Bus Split Arrangement in Maheswaram 400kV SS | For controlling High Short-Circuit current level in Maheswaram 400kV Substation | S I | 2539/ 13.10.2025 | CEA Lrs.dt. 07.10.2022, 07.03.2025 09.10.2025 | - | - | 1.912 | To be tied-up | 17.208 | - | April, 2026 | March, 2028 | 0 | 0 | 0 | 0 | 15 | 4.12 | 0 | 0 | 19.12 | -
4 | - | 400/220kV Chandavelly GIS SS & connected Lines | 1) 400/220kV GIS at Chandanvelly, 2) LILO of one circuit of 400kV Suryapet - Kehireddipally QMDC Line; 3) 400 kV QMDC Line to upcoming 400kV CTRLS Switching Station; 4) 220kV DC Line to existing Chandanvelly Substation; 5) Diversion of 220kV KRPally - CVally TMDC Line; | To meet exponential industrial load growth in and around Chandanvelly I.P. Area | S I | To be issued | CEA Lr.dt. 21.07.2025 (MOM dated 07.07.2025) | To be submitted after Administrative approval | - | - | - | - | - | April, 2026 | March, 2029 | 0 | 0 | 0 | 0 | 240.52 | 481.02 | 80.17 | 0 | 801.71 | Administrative approval in process
5 | - | 400kV Shadnagar GIS SS & connected Network | 1) 400/220kV Shadnagar GIS 2) LILO of one circuit of 400kV Suryapet - Kethireddipally QMDC Line to 400kV Shadnagar GIS SS | Transmission Ssytem for integration of Kurnool-IV (3GW Phase-II) Scheme of CTUIL | S I | To be issued | CEA Lr.dt. 21.07.2025 (MOM dated 07.07.2025) | To be submitted after Administrative approval | - | - | - | - | - | April, 2026 | March, 2029 | 0 | 0 | 0 | 0 | 200 | 300 | 68.45 | 0 | 568.45 | Administrative approval in process
6 | - | 400/220kV Parigi SS & connected Lines | 1) 400/220kV Parigi SS 2) LILO of one circuit of 400kV Shankarpally-Kethireddypally QMDC Line to Parigi (400kV) 3) 220kV Parigi (400kV) -Parigi (existing 220kV) SMDC Line 4) 220kV Parigi (400kV) -Tandur (existing 220kV) SMDC Line 5) 220kV Parigi (400kV) - KP Laxmidevipalli TMDC Line | To provide alternate connectivity (intra-state) to 220/132 kV Tandur SS, to reduce loading on ICTs at 400/220kV Shankarpally SS by providing connectivity to 220kV Parigi & 220kV Tandur SS and to reduce loading on ICTs at 400/220kV Kethireddypally SS by providing connectivity to 220/11kV KP Laxmidevipally LI SS | S I | To be issued | CEA Lr.dt. 03.10.2025 (MOM dated 01.09.2025) | - | - | - | - | - | - | April, 2026 | March, 2029 | 0 | 0 | 0 | 0 | 100 | 215.5 | 215.5 | 0 | 531 | Estimation in process
7 | - | 400kV Augmentation Scheme-VI | Erection of 500/315 MVA, 400/220kV ICTs at 400kV Gajwel, Mamidipally, Veltoor & Nirmal Sub-stations | To provide load relief on existing ICTs and to meet future load growth in the area. | S I | To be issued | CEA Lr.dt. 09.10.2025 (MOM dated 01.09.2025) |  | - |  |  |  | - | April, 2026 | March, 2029 | 0 | 0 | 0 | 0 | 70 | 150 | 15.6 | 0 | 235.6 | Estimation in process
8 | - | 220kV features at Tukkapur 400/11kV LI Substation | Providing 2x500MVA, 400/220kV ICTs in the exsting 400/11kV Tukkapur LI Substation | to improve the voltage profile in the area, reduce transmission losses, alleviate loading on ICTs | S I | To be issued | CEA Lr.dt. 21.07.2025 (MOM dated 07.07.2025) |  | - |  |  |  | - | April, 2026 | March, 2029 | 0 | 0 | 0 | 0 | 79.5 | 159 | 26.5 | 0 | 265 | Estimation in process
Sub-Total-II : | [15 empty] | 0 | 0 | 0 | 0 | 800.64 | 1460.312 | 422.58 | 0 | 2683.532
III. Non-plan schemes proposed to be taken up during 2026-27
1 | DC Work | Integrated Steel Plant Transmission Scheme* | 1) 400/220kV Integrated Steel Plant SS in Khammam Dist. 2) 400kV Julurupadu - Integrated Steel Plant QMDC Line, and associated 400kV Bays | - | S E | - | - | - | - | Depository Contribution Work (Consumer Contribution) |  |  |  | Oct., 2026 | March, 2029 | 0 | 0 | 0 | 0 | 10 | 218.005 | 208.005 | 0 | 436.01 | State Govt. approval for Integrated Steel Plant is yet to be received *.
Sub-total-III | [15 empty] | 0 | 0 | 0 | 0 | 10 | 218.005 | 208.005 | 0 | 436.01
Grans Total I + II + III | [15 empty] | 1268.222 | 51.374 | 33 | 84.374 | 945.64 | 1709.317 | 630.585 | 0 | 8680.022
Note :* As per AP Re-Organization Act 2014, Telangana State was assured for establishment of Integrated Steel Plant. In this connection, Mines Department, Telangana requested to furnish the feasibility report for construction of SS& lines for the three sites proposed by M/s. MECON Limited, (Engineering and Consultancy Services). Accordingly TSTRANSCO has submitted detailed report for providing power supply to proposed Integrated Steel Plant vide Letter dated 27.06.2018. No further correspondence received from Govt. of Telangana regarding extension of power supply to proposed steel plant. This Integrated Steel Plant Transmission Scheme will be taken up only after finalization of steel plant site and also based on the System Studies Report, to extend the power supply to proposed steel plant.
Chief Engineer/ 400kV
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please
3 | Z-99-01 | Rolling Stocks Procurement N Consumption | Rolling Stocks Procurement N Consumption | - | - | - | - | - | - | - |  |  |  | - |  | 0.018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | DC Work | 400kV GIS at CTRLS Data Cetnre and connected Line | 1) 400kV GIS Switching-station at CTRLS; 2) LILO of one Ckt. of 400kV Maheswaram - Shankarapally TMDC Line | - | S E | To be issued | - | - | - | Depository Contribution Work (Consumer Contribution) |  |  |  | June, 2026 | May, 2028 | 0 | 0 | 0 | 0 | 50 | 100 | 66.2565 | 0 | 216.2565