## CapEx-24-25
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Tariff Petition for 2026-27 for Transmission Business filed with TGERC
Scheme-wise details of Capital Expenditure incurred in FY: 2024-25 of 5th control period
400kV Transmission Schemes : | [18 empty] | (Figures in Crores)
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme) | Justification | Project Purpose (SI/SE/ SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total approved Cost | Source of funds |  |  |  | Project Start Date | Project Completion Date | DOC | Opening CWIP | Actual Expenditure from 01.04.2024 to 31.03.2025 | Cumulative expenditure upto 31.03.2025 | % Capata-lisation | Remarks/ Balance works, if any.
[10 empty] | TGTransco Funds | Loan source | Loan Amount | Grants, if any |  |  | (DD-MM-YY) | as on 31.03.2024
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22)
I. Ongoing Schemes as on 01.04.2024
1 | S-14-02 | Suryapet Power Transmission Scheme | 1) 400/220/132 kV Suryapet Substation 2) LILO of 400kV VTS – Malkaram DC Line to Suryapet 400kV SS 3) 400kV Kamavarapukota - Suryapet QMDC Line 4) 400kV Suryapet - Shankarapally QMDC Line | Transmission System improvement in Nalgonda District and surrounding area | S I | 01/ 17.01.2014 49/ 04.12.2014 11/ 15.03.2016 | 36th & 39th SCPSPSR Meetings dtd. 04.09.2013 & 29.12.2015 respectively | APT/TS/ 400kV Suryapet/ F-INVST-28/2014 dt. 21.01.2015 | 1738.03 | 420.76 | REC | 1317.27 | - | Sept., 2013 | Apr.' 2018 | - | 0.007 | -1.511 | 650.121 | 100%
2 | A-15-10, A-15-11 | 400kV Augmentation Scheme | Augmentation of 315 MVA PTRs at Dichpally & Mahaboobnagar and 500MVA ICT at Gajwel 400kV SS | To provide load relief on existing ICTs and to meet future load growth in the area. | S I | 20/ 29.08.2015 04/ 11.01.2017 49/ 28.03.2017 | 39th & 40th meetings of SCPSPSR dated 28-29.12.2015 & 19.11.2016 respectively | 03/17, 2017-18 dt.04.05.2017 | 95.59 | 15.75 | PFC | 79.84 | - | Feb' 2016 | Mar' 2020 | - | -0.003 | 0 | 45.288 | 100%
3 | S-15-13 | 765kV Wardha– Hyderabad Link Transmission Scheme | 1) 400/220kV Maheshwaram; 2) 400kV QMDC Line from Maheshwaram 765/400kV (PGCIL) SS; 3) 400kV Maheswaram - Shankarapally TMDC Line; 4) 400/220/132kV Kethireddypalli SS; 5) LILO of 400kV Shankarpally-Suryapeta QMDC Line to 400kV Kethireddypalli SS; 6) 400kV QMDC line from 400kV Dichpally SS to 400kV Nirmal SS; 7) LILO of 400kV Dindi-Mamidipally TMDC Line to 400kV Maheshwaram SS | Transmission System Improvement | S I | 146/ 05.08.2015 30/ 04.10.2016 105/ 15.07.2017 | 36th & 37th SCPSPSR Meetings dtd. 04.09.2013 & 31.07.2014 respectively | 16/17-2017-18, Dt.19.12.2017 | 1178.97 | 177.32 | PFC | 1001.65 | - | Nov' 2015 | Mar' 2022 | - | 0.051 | -1.921 | 936.824 | 100%
4 | P-16-01 | Telangana STPP-I Power Evacuation Scheme | 1) 400/220kV Ramadugu Substation; 2) 400kV TSTPP - Ramadugu QMDC Line; 3) 400kV TSTPP - Narsapur QMDC Line | Power evacuation from Telangana STPP (2x800 MW) | G E | 34/ 25.11.2016 104/ 12.07.2017 | 40th & 41st Meetings of SCPSPSR dtd. 19.11.2016 & 22.09.2017 respectively | 10/2017, dt.23.08.2017 | 1151.6 | 20.43 | REC | 1131.17 |  | Oct' 2017 | Mar' 2022 | - | 0.502 | -0.479 | 861.201 | 100%
5 | S-17-08 | Rayadurg System Improvement Scheme | 1) 400/220/132KV GIS at Rayadurg 2) 400KV Kethireddypally - Rayadurg DC Line 3) LILO of 220kV Gachibowli – Shivarampally Line to Rayadurg GIS; 4) LILO of 220kV Gachibowli – Shapurnagar Line to Rayadurg GIS; 5) LILO of 220kV Gachibowli – Miyapur Line to Rayadurg GIS; 6) LILO of 220kV Gachibowli – Erragadda Line to Rayadurg GIS; 7) 132kV Rayadurg - Madhapur DC Line; 8) 132kV Rayadurg - Jubileehills DC Line; 9) LILO of 132kV Jubilee Hills – Shivarampally SC Line to Rayadurg | Transmission System Improvement | S I | 44/ 22.03.2017 79/ 13.04.2018 | 41st Meeting of SCPSPSR dated 22.09.2017 | 02 / 2018-19, Dt. 24.05.2018 | 1786.4 | 8.14 | PFC | 1778.26 | - | Sep' 2018 | Apr' 2022 | - | 10.447 | 4.392 | 1745.907 | 99.79%
6 | S-19-01 | KTPP System Improvement Scheme | 400/220/132kV Substation at KTPP Switchyard, Bhupalapally | Transmission System Improvement | S I | 297/ 09.02.2019 | 1st Meeting of SRSCT dated 07.09.2018 | 03 / 2019-20 Dt. 22.11.2019 | 454.23 | 49.23 | PFC | 405 | - | Jan' 2020 | Mar' 2024 | - | 170.826 | 34.395 | 205.221 | 99.65%
7 | S-19-02 | Reactor Scheme-III | Installation of 125MVAR Bus Reactors at Suryapet, Rayadurg, Kethireddypalli, Narsapur, Maheshwaram, Janagaon and Dindi 400kV Substations and Installation of 80MVAR Bus Reactor & 63MVAR Switchable Line Reactors at Asupaka 400kV SS | System improvementby limiting over Voltages in the Grid | S I | 304/ 23.02.2019 | 1st Meeting of SRSCT dated 07.09.2018 | 04 / 2019-20 Dt. 09.12.2019 | 249.79 | 91.07 | PSDF | 0 | 158.72 | Jan' 2020 | Mar' 2023 | - | 93.48 | 16.989 | 150.308 | 100%
8 | P-19-02 | Yadadri Thermal Power Evacuation Scheme | 1) 400/220kV Dameracherla SS; 2) 400kV YTPP Switchyard - Damaracherla QMDC Line; 3) 400kV YTPP Switchyard - Jangoan QMDC Line: and 4) 400/220/132kV Choutuppal SS; 5) LILO of 400kV Mamidipally-Khammam TMDC Line to Choutuppal SS; 6) 400kV YTPP Switchyard - Choutuppal QMDC Line; 7) 400kV YTPP Switchyard - Dindi QMDC Line | Transmission Scheme for evacuation of 4000MW (5x800MW) Power from Yadadri Thermal Power Project at Damaracherla | G E | 451/ 10.10.2019 | 39th meeting of SCPSPSR dated 28-29.12.2015 & 1st meeting of SRPCTP dt.16.12.19 | 09 / 2019-20, Dt. 27.01.2020 | 2354.35 | 141.44 | PFC & REC | 1102.26 & 1110.65 | - | Jan' 2020 | Mar' 2024 | - | 991.677 | 134.138 | 1569.327 | 53.69%
9 | S-21-05 | HVWS for 500MVA ICTs at 400kV Substations | HVWS for 500MVA ICTs at 400kV Substations | System improvement by protecting existing ICTs | S I | - | - | - | - | - | - | - | - | Dec' 2021 | May' 2022 | - | 0.01 | 0.041 | 0.894 | 100%
10 | A-21-07 | Augmentation Scheme-IV | Erection of 315/500 MVA ICT’s at 400kV Suryapet, Asupaka, Veltoor, Dichpally & Gajwel Sub-stations | To provide load relief on existing ICTs and to meet future load growth in the area. | S I | 1311/ 14.02.2022 | CEA Lr. Dated 10.12.2021 | 01 / 2022-23 Dt.05.05.2022 01 / 2024-25 Dt.17.05.2024 | 187.48 | 19.18 | HUDCO | 168.3 | - | Dec.' 2020 | Sept., 2023 | - | 1.273 | 0.412 | 127.127 | 100%
Sub-total-I | [16 empty] | 1268.27 | 186.456 | 6292.218
II. New Schemes taken up during 2024-25 : - NIL -
Sub-total-II | [16 empty] | 0 | 0 | 0
III. Non-Planned Schemes :
1 | N-22-01 | Non Planned Capital works | Survey for Towers Shifting of BTPS to JLPD 400kV Line | - |  | - | - | - | - | - |  |  | - |  |  | - | 0.041 | 0 | 0.041 | - | -
2 | N-23-01 | Non Planned Capital works | Laying CC Road NH 365B to 400Jangaon SS | - |  | - | - | - | - | - |  |  | - |  |  | - | 0 | 0.286 | 0.286 | 100% | -
Sub-Total-III | [16 empty] | 0.041 | 0.286 | 0.327
Grans Total I + II + III | [16 empty] | 1268.311 | 186.742 | 6292.545
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
Chief Engineer/ 400kV
The statement to be printed on A3 size sheets please
1 | L-18-04 | Sita Rama Lift Irrigation Scheme | 1) 400/220/11kV Kamalapuram LI SS, 2) 220/11kV B.G.Kothur LI SS, 3) 220/11kV V.K.Ramavaram LI SS, 4) 400kV Julurupadu - Kamalapuram TMDC Line, 5) LILO of one circuit of 220kV KTPS-Manuguru Line to B.G.Kothur, 6) LILO of one circuit of 220kV KTPS V-Lower Sileru -II Line to B.G.Kothur, 7) LILO of 220kV KTS – Lower Sileru-I Line at 400/220 kV Asupaka SS, 8) LILO of 220kV KTS - Asupaka Line to V.K.Ramavaram 220kV LI SS, 9) 220kV TMDC Line from 400/220/11kV Kamalapuram SS to 220/11 kV V.K.Ramavaram | For extension of Power supply to Lift Irrigaiton Pumping Stations | Bulk Load & DC Works | - | 41st Meeting of SCPSPSR dated 22.09.2017 | - | - | I&CAD, Govt.of TG Funds |  |  |  | Sep' 2018 | May, 2023 | 28.04.23 | 12.819 | 7.379 | 342.338 | 96.15%
Grans Total I + II + III | [16 empty] | 1281.13 | 194.121 | 6634.883
[17 empty] | 1281.13 | 194.121 | 650.414

## CapEx-24-25Lis
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Tariff Petition for 2026-27 for Transmission Business filed with TGERC
Scheme-wise details of Capital Expenditure incurred in FY: 2024-25 of 5th control period
400kV Lift Irrigaiton Transmission Schemes : | [18 empty] | (Figures in Crores)
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme) | Justification | Project Purpose (SI/SE/ SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total approved Cost | Source of funds |  |  |  | Project Start Date | Project Completion Date | DOC | Opening CWIP | Actual Expenditure from 01.04.2024 to 31.03.2025 | Cumulative expenditure upto 31.03.2025 | % Capata-lisation | Remarks/ Balance works, if any.
[10 empty] | TGTransco Funds | Loan source | Loan Amount | Grants, if any |  |  | (DD-MM-YY) | as on 31.03.2024
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22)
I. Ongoing Schemes as on 01.04.2024
1 | L-18-04 | Sita Rama Lift Irrigation Scheme | 1) 400/220/11kV Kamalapuram LI SS, 2) 220/11kV B.G.Kothur LI SS, 3) 220/11kV V.K.Ramavaram LI SS, 4) 400kV Julurupadu - Kamalapuram TMDC Line, 5) LILO of one circuit of 220kV KTPS-Manuguru Line to B.G.Kothur, 6) LILO of one circuit of 220kV KTPS V-Lower Sileru -II Line to B.G.Kothur, 7) LILO of 220kV KTS – Lower Sileru-I Line at 400/220 kV Asupaka SS, 8) LILO of 220kV KTS - Asupaka Line to V.K.Ramavaram 220kV LI SS, 9) 220kV TMDC Line from 400/220/11kV Kamalapuram SS to 220/11 kV V.K.Ramavaram | For extension of Power supply to Lift Irrigaiton Pumping Stations | Bulk Load & DC Works | - | 41st Meeting of SCPSPSR dated 22.09.2017 | - | - | I&CAD, Govt.of TG Funds |  |  |  | Sep' 2018 | May, 2023 | 28.04.23 | 12.819 | 7.379 | 329.519 | 100%
Sub-total-I | [16 empty] | 12.819 | 7.379 | 329.519
Chief Engineer/ 400kV
The statement to be printed on A3 size sheets please

## CapN24-25
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Tariff Petition for 2026-27 for Transmission Business filed with TGERC
[6 empty] | Scheme wise details of Actual Capitalisation for FY 2024-25 | [20 empty] | (Figures in Crore Rs)
400kV Transmission Schemes : | [8 empty] | Work Period | [5 empty] | Source of Funds | [7 empty] | Additions to Network
Sl No. | Voltage Level | Project Code (SAP Code) / Scheme IDs | Project Title (SAP Project title) | Scope of work (Names of all the Substations and Lines included in the Scheme) | Project Purpose (SI/SE/SR/GE) | Administrative approval No. with date | SRPC approval No. with Date (if any) | Investment Approval No. with Date | Start Date |  | Completion Date (Charging date) |  | Date of Capitalization | Approved Cost as per Investment Approval | Transco Funds | Loan Source | Loan Amount | Grants, if any | Capitalisation Upto Previous Year (n-1) (as per Audited Financial Statements) | Capital Expenditure during the current year (2024-25) | Capital-isation claimed for the Current year (2024-25) | Whether Part Capitalization or Full Capitalisation | Sub-stations (Nos) | Lines (ckm) | PTR (MVA) | Bays (Nos) | Physical Completion Certificate Nos. | Financial Completion Certificate Nos. | Remarks / Reasons for Cost & Time overruns (if any)
[9 empty] | Schedule | Actual | Schedule | Actual
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30)
I. Ongoing Schemes as on 01.04.2024
1 | 400kV | S-14-02 | Suryapet Power Transmission Scheme | 1) 400/220/132 kV Suryapet Substation 2) LILO of 400kV VTS – Malkaram DC Line to Suryapet 400kV SS 3) 400kV Kamavarapukota - Suryapet QMDC Line 4) 400kV Suryapet - Shankarapally QMDC Line | S I | 01 / 17.01.2014 49/ 04.12.2014 11/ 15.03.2016 | 36th & 39th SCPSPSR Meetings dtd. 04.09.2013 & 29.12.2015 respectively | APT/TS/ 400kV Suryapet/ F-INVST-28/2014 dt.21.01.2015 | July 2013 | Sept' 2013 | Mar' 2017 | Apr. 2018 |  | 1738.03 | 420.76 | REC | 1317.27 |  | 651.625 | -1.511 | -1.503 | Part | - | - | - | - | 2019000039 | 0202000198
2 | 400kV | S-15-13 | 765kV Wardha– Hyderabad Link Transmission Scheme | 1) 400/220kV Maheshwaram; 2) 400kV QMDC Line from Maheshwaram 765/400kV (PGCIL) SS; 3) 400kV Maheswaram - Shankarapally TMDC Line; 4) 400/220/132kV Kethireddypalli SS; 5) LILO of 400kV Shankarpally-Suryapeta QMDC Line to 400kV Kethireddypalli SS; 6) 400kV QMDC line from 400kV Dichpally SS to 400kV Nirmal SS; 7) LILO of 400kV Dindi-Mamidipally TMDC Line to 400kV Maheshwaram SS | S I | 146/ 05.08.2015 30/ 04.10.2016 105/ 15.07.2015 | 36th & 37th SCPSPSR Meetings dtd. 04.09.2013 & 31.07.2014 respectively | 10/15, Dt.11.11.2015 & 16/17-2017-18, Dt.19.12.2017 | Jan. 2016 | Feb. 2016 | Mar' 2019 | Feb' 2021 |  | 1178.97 | 177.32 | PFC | 1001.65 |  | 938.745 | -1.921 | -1.87 | Part | - | - | - | - | 2019000040 2019000043 | 0202001469 0202000157
3 | 400kV | S-17-08 | Rayadurg System Improvement Scheme | 1) 400/220/132KV GIS at Rayadurg 2) 400KV Kethireddypally - Rayadurg DC Line 3) LILO of 220kV Gachibowli – Shivarampally Line to Rayadurg GIS; 4) LILO of 220kV Gachibowli – Shapurnagar Line to Rayadurg GIS; 5) LILO of 220kV Gachibowli – Miyapur Line to Rayadurg GIS; 6) LILO of 220kV Gachibowli – Erragadda Line to Rayadurg GIS; 7) 132kV Rayadurg - Madhapur DC Line; 8) 132kV Rayadurg - Jubileehills DC Line; 9) LILO of 132kV Jubilee Hills – Shivarampally SC Line to Rayadurg | S I | 44/ 22.03.2017; 79/ 13.04.2018 | 41st Meeting of SCPSPSR dated 22.09.2017 | 02 / 2018-19, Dt. 24.05.2018 | May 2018 | Sep' 2018 | May 2020 | Apr' 2022 |  | 1786.4 | 8.14 | PFC | 1778.26 |  | 1731.728 | 4.392 | 10.44 | Part | - | - | - | - | 2022000085 2022000120 2022000129 2022000141 2022000151 2022000181 2022000223 2022000224 2022000225 | 2023000609 0202200172 0202200170 0202200167 0202200165 0202200168 0202200160 0202200159 0202200158
4 | 400kV | S-19-01 | KTPP System Improvement Scheme | 400/220/132kV Substation at KTPP Switchyard | S I | 297/ 09.02.2019 | 1st Meeting of SRSCT dated 07.09.2018 | 03 / 2019-20 Dt. 22.11.2019 | Jan' 2020 |  | Mar' 2024 | U/C |  | 454.23 | 49.23 | PFC | 405 |  | 0 | 34.395 | 204.507 | Part | 1 | - | 1000 | 12 | 2025000282 | 2025000713
5 | 400kV | S-19-02 | Reactor Scheme-III | Installation of 125MVAR Bus Reactors at Suryapet, Rayadurg, Kethireddypalli, Narsapur, Maheshwaram, Janagaon and Dindi 400kV Substations and Installation of 80MVAR Bus Reactor & 63MVAR Switchable Line Reactors at Asupaka 400kV SS | S I | 304/ 23.02.2019 |  | 04 / 2019-20 Dt. 09.12.2019 | Jan' 2020 | Jan' 2020 | Mar' 2023 | Oct. 2024 |  | 249.79 | 249.79 | PSDF | 0 | 158.72 | 48.489 | 16.989 | 110.469 | Part | - | - | - | 4 | 2023001149 2023001150 2023001176 2024000447 2024000878 2024000919 2024000940 | 2024000694 2023000712 2024000514 2025000711 2025000576 2025000592 2025000281
6 | 400kV | P-19-02 | Yadradri Thermal Power Evacuation Scheme | 1) 400/220kV Dameracherla SS; 2) 400kV YTPP Switchyard - Damaracherla QMDC Line; 3) 400kV YTPP Switchyard - Jangoan QMDC Line: 1) 400/220/132kV Choutuppal SS; 2) LILO of 400kV Mamidipally-Khammam TMDC Line to Choutuppal SS; 3) 400kV YTPP Switchyard - Choutuppal QMDC Line; 4) 400kV YTPP Switchyard - Dindi QMDC Line | G E | 451/ 10.10.2019 | 39th meeting of SCPSPSR dated 28-29.12.2015 & 1st meeting of SRPCTP dt.16.12.19 | 09 / 2019-20, Dt. 27.01.2020 | Jan' 2020 | Dec' 2021 | May 2022 | U/C |  | 2354.35 | 141.44 | PFC & REC | 1102.26 1110.65 |  | 443.227 | 134.138 | 399.002 | Part | - | 207.566 | - | 1 | 2023000422 2023000444 2023000445 2023001134 2023001136 2023001148 2023001151 2023001261 2024000448 | 2023000674 2023000697 2023000618 2023000710 2023000711 2023000663 2023000671 2024000749 2025000280
7 | 400kV | S-21-05 | HVWS at 500MVA ICTs | HVWS at 500MVA ICTs System Impvmt Scheme | S I | - | - | - |  | Dec., 2021 |  | May, 2022 | [6 empty] | 0.853 | 0.041 | 0.051 | Part | - | - | - | - | 2023000448 | 2023000713
8 | 400kV | A-21-07 | Augmentation Scheme-IV | Erection of 315/500 MVA ICT’s at 400kV Suryapet, Asupaka, Veltoor, Dichpally & Gajwel Sub-stations | S I | 1311/ 14.02.2022 |  | 01 / 2022-23 Dt.05.05.2022 01 / 2024-25 Dt.17.05.2024 | Dec.' 2020 |  | Sept., 2023 | U/C |  | 187.48 | 19.18 | HUDCO | 168.3 |  | 125.441 | 0.412 | 1.685 | Part | - | - | 630 | - | 2023001175 2023001263 2023001274 2024000129 2024000449 2024000871 | 2024000693 2024000748 2024000515 2024000692 2025000574 2025000278
|  |  |  | Total : | [16 empty] | 722.781 |  | 1 | 207.566 | 1630 | 17
II. Non-planned Schemes :
1 | 400kV | N-23-01 | Non Planned Capital works | Laying CC Road NH 365B to 400Jangaon SS | [15 empty] | 0.286 | 0.286 | Full | 0 | 0 | 0 | 0 | 2024000899 | 2025000712
|  |  |  | Total (I) & (II) : | [16 empty] | 723.067 |  | 1 | 207.566 | 1630 | 17
Chief Engineer/ 400kV
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please
Note on O11: Excluding IDC of Rs.100.08 Crore Total incl. IDC Rs.1279.05

## CapN24-25Lis
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Tariff Petition for 2026-27 for Transmission Business filed with TGERC
[6 empty] | Scheme wise details of Actual Capitalisation for FY 2024-25 | [20 empty] | (Figures in Crore Rs)
400kV Lift Irrigation Transmission Schemes : | [8 empty] | Work Period | [5 empty] | Source of Funds | [7 empty] | Additions to Network
Sl No. | Voltage Level | Project Code (SAP Code) / Scheme IDs | Project Title (SAP Project title) | Scope of work (Names of all the Substations and Lines included in the Scheme) | Project Purpose (SI/SE/SR/GE) | Administrative approval No. with date | SRPC approval No. with Date (if any) | Investment Approval No. with Date | Start Date |  | Completion Date (Charging date) |  | Date of Capitalization | Approved Cost as per Investment Approval | Transco Funds | Loan Source | Loan Amount | Grants, if any | Capitalisation Upto Previous Year (n-1) (as per Audited Financial Statements) | Capital Expenditure during the current year (2024-25) | Capital-isation claimed for the Current year (2024-25) | Whether Part Capitalization or Full Capitalisation | Sub-stations (Nos) | Lines (ckm) | PTR (MVA) | Bays (Nos) | Physical Completion Certificate Nos. | Financial Completion Certificate Nos. | Remarks / Reasons for Cost & Time overruns (if any)
[9 empty] | Schedule | Actual | Schedule | Actual
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14) | (15) | (16) | (17) | (18) | (19) | (20) | (21) | (22) | (23) | (24) | (25) | (26) | (27) | (28) | (29) | (30)
I. Ongoing Schemes as on 01.04.2024
1 | 400kV | L-18-04 | Sita Rama LI Scheme | 1) 400/220/11kV Kamalapuram LI SS, 2) 220/11kV B.G.Kothur LI SS, 3) 220/11kV V.K.Ramavaram LI SS, 4) 400kV Julurupadu - Kamalapuram TMDC Line, 5) LILO of one circuit of 220kV KTPS-Manuguru Line to B.G.Kothur, 6) LILO of one circuit of 220kV KTPS V-Lower Sileru -II Line to B.G.Kothur, 7) LILO of 220kV KTS – Lower Sileru-I Line at 400/220 kV Asupaka SS, 8) LILO of 220kV KTS - Asupaka Line to V.K.Ramavaram 220kV LI SS, 9) 220kV TMDC Line from 400/220/11kV Kamalapuram SS to 220/11 kV V.K.Ramavaram | Bulk & DC Works | 449 & 450 Dated 10.10.2019 | 41st Meeting of SCPSPSR dated 22.09.2017 | N/A | Sept. 2018 |  | May, 2023 | April 2024 |  |  | I&CAD, Govt. of Telangana Funds |  |  |  | 308.974 | 7.38 | 20.198 | Part | - | - | - | - | 2020000587 2021000024 2021000025 2023000327 2023000329 2023000328 2023000353 2023000354 2024000445 2024000446 | 0202000375 0202100164 0202100163 2023000423 2023000422 2023000421 2024000320 2023000420 2025000653 2025000654
CHIEF ENGINEER/ 400kV
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please
9 | 400kV | P-07-01 | Erec Bay Exte @ Malkaram 400kV SS | ERE BAY EXTE@ MALKARAM 400 KV SS | S I | - | - | - |  | - | - | [9 empty] | 0.061
10 | 400kV | D-15-09 | 2Nos 400kV BE - 400kV Dichpally SS | 2Nos 400kV BE - 400kV Dichpally SS | S I | - | - | - |  | Feb., 2016 | Feb., 2017 | [9 empty] | -0.002
11 | 400kV | D-20-03 | Diversion of 400kV Julurupadu-KTPS & KTPS-PGCIL Line) | Diversion of 400kV Julurupadu-KTPS & KTPS-PGCIL Line) (D-20-03) | DC Works | - | - | - |  | Aug., 2020 | Aug., 2021 | [9 empty] | 0.434