## SI works
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2026-27 for Transmission Business filed with TGERC
Scheme wise details of Actual Capitalisation for FY 2024-25
(Figures in Rs Crore)
[8 empty] | Work Period | [5 empty] | Source of Funds | [7 empty] | Addition to Network
Sl No. | Project Code (SAP Code) / Scheme IDs | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the Scheme) | Project Purpose (SI/SE/SR/GE) | Administrative approval no. with date | SRPC approval no with date (if any) | Investment Approval No. with Date | Start Date |  | Completion Date (Charging date) |  | Date of Capitalization | Approved Cost as per Investment Approval | TGransco Funds | Loan Source | Loan Amount | Grants, if any | Capitalisation Upto Previous Year (n-1) (as per Audited Financial Statements) | Capital Expenditure during the current year (2024-25) | Capitalisation claimed for the Current year (2024-25) | Whether Part Capitalization or Full Capitalisation | Lines (CKM) | PTR (MVA) | Bays (Nos) | Physical Completion Certificate Nos. | Financial Completion Certificate Nos. | Remarks / Reasons for Cost & Time overruns (if any)
[8 empty] | Schedule | Actual | Schedule | Actual
1 | S-03-03 | ERECTION OF 220 KV SS & LINES UNDER PFC | a) 220KV SS Jurala b) 220KV DC line from Veltoor to Wanaparthy | SI | T.O.O (CE-Transmission) Ms.No.313, Dated:10.03.2003 | - | - | 31.03.2008 | 15.09.2009 | 31.03.2011 | a)30.01.2012 b)08.09.2010 | - | 228.81 | - | PFC | 210 | - | - | 0 | 0 | Full | - | - | - | 2024000275 2019000896 | 2024000676 202000765 | -
2 | S-07-02 | Erection of 132 KV LILO to Jurala from e | a) 220/132 KV SS (2x100MVA) adjacent to Priyadarshini Jurala Hydroelectric Project Switchyard b)220KV DC line from 400KV SS Veltoor to 220KV SS Jurala c) 132 KV LILO line to 220/132 KV SS Jurala from Gadwal-Makthal 132 KV line including 1km of river crossing with JC towers | SI | T.O.O (CE-Transmission) Ms.No.105,Dt:22.08.2007 | - | - | 31.04.2009 | 12.06.2009 | 11.03.2010 | 25.05.2010 | - | - | - | Bank of Baroda | 42 | - | - | 0.03 | 0.03 | Full | - | - | - | 2019000884 2022000428 | 202000770 202200358 | -
3 | S-07-03 | Erragadda and O.U GIS &Cables scheme | a) 220/132 kV Substation at Erragadda with 3 X 160 MVA power Transformer capacity b)220 kV LILO UG XPLE cable to the proposed Erragadda substation from Gachibowli – Shapurnagar line(8kM) c)220/132/33 kV Substation at Osmania University with 2 X 160 + 2 x80 MVA power Transformer capacity (Radial) d)220 kV DC UG XPLE cable to the proposed Osmania University substation from 220kV Moulali SS(14.40KM) e)220 kV Bay extensions at Moulali (2Nos.) | SI | T.O.O (CE-Construction-I) Ms.No.245,Dt:29.09.2011 | - | - | 29-09-2011 | 27.12.2011 | 31.03.2014 | E-27.05.2015 OU-14.10.2015 | - | 525.25 | - | PFC | 415 | - | - | -0.26 | -0.26 | Full | 44.8 | 960 | 6 | 2019000183 2019000186 2019000196 2019000554 2020000328 | 202001409 202000318 202001636 202001435 202000378 | -
4 | S-07-04 | TWIN CITIES TRANSMISSION SYSTEM | The details are enclosed in the annexure-I | SI | TOO (CE-Construction) MS NO.379, Dt:17.01.2012 | - | - | 01.08.2014 | 10.09.2015 | 17.10.2017 | The charging details are enclosed in Annexure-I | - | 1410 | - | JICA | 1200 | - | - | 0.52 | 2.1 | Full | - | - | - | 2020000298 2019000506 2019000189 2020000299 2019000199 | 202000046 202000615 202001455 202001466 202001503 | -
5 | S-08-08 | 132 /33 KV GIS Narayanaguda Scheme | a) 132/33 kV GIS Sub-Station at Narayanguda (Shanthi Theatre) with 2 x 50MVA B) 132 kV Line with XLPE UG Cable from 132/33 kV Sub-Station, Fever Hospital to the proposed 132/33 kV Sub-Station, Narayanguda (Shanthi Theatre). (3KM) | SI | TOO (CE-Transmission) MS No.140, Dt:13.10.2016 (Revised) | - | CRN.No./TST/TS/220-132 KV GIS-Hyd/F.Invst./99/2019, Dt:20.02.2009 | 13.10.2016 | 31.05.2013 | 31.03.2016 | 08.12.2017 | - | 156.23 | - | PFC | 150 | - | - | 0 | 0 | Full | 3 | 47.5 | 2 | 2019000195 | 202001682 | -
6 | S-08-11 | 132KV Mamidipally SS with connected line | a)132/33 kV Substation at Mamidipally with 1x31.5 + 1x50 MVA PTR Capacity (Radial) b))220 kV DC line from proposed 132/33 kV Mamidipally substation up to Loc.No.12 of 220 kV line to the proposed 220/132 kV Fab city from 400/220 kV Mamidipally substation with narrow based towers.(6KM) c)220 kV 2 circuits(3rd & 4th circuit) stringing from Loc. No. 12 on the existing narrow based M/C towers up to 220/132 kV Fab city on the 220 kV DC line from 400/220 kV Mamidipally substation to 220/132 kV Fab city( circuit 1 & 2 are already covered under Fab city line)(4KM) d)132 kV Bay extension-1 No. | SI | T.O.O (CE-Transmission) Ms. No. 59 Dated:19.04.2016 | - | APT/TS/132 kV SS-Mamidipalli/ F-INVST - 12/2013 | 31.10.2008 | 31.12.2008 | 31.03.2015 | 31.03.2016 20.08.2016 | - | 21.92 | - | PFC | 19.72 | - | - | -0.1 | -0.1 |  | 20 | 81.5 | 4 | 2019000522 2019000523 | 202000278 202000277 | -
7 | S-10-14 | ERECTION220/132 KV SUBSTATION MANTHANi | 1)220/132kV Substation at Manthani with 2*100 MVA PTR Capacity 2)220kV LILO to proposed 220kV SS, Manthani from 220kV RSS-Warangal DC line (25KM) 3a)Stringing of two circuits on the already proposed multi-circuit towers from the proposed 220 kV SS, Manthani to Location No. AP 10 of 132kV Line from proposed 220kV SS, Manthani to the proposed 132kV SS, Kamanpur(9.5Km) b)Erection of 132 kV DC Line from Location No. AP – 10 of 132 kV Kamanpur Line to the Tap point of 132 kV RSS – Kamalapur DC Line(0.5KM) 4)132kV LILO to132kV Chelpur SS from 132 kV RSS - OCM feeder DC line(3KM) 5)Erection of 132 kV DC Line on Multi - Circuit Towers for LILO of Manthani - Kataram Line to 220 kV Sub-Station, Manthani(5Km) 6)132kV Bay extensions at 132kV Chelpur SS & 2 Nos at 220kV SS, Manthani | SI | T.O.O (CE-Construction-I) Ms. No. 18 , Dated: 15.04.2014 (Revised) | - | APT/TS/220/132KV/33KV -Manthani/F.-Invest.-01/2010,08.10.2014 | 2013-12-01 | 19.10.2013 | 2015-03-01 | 06.01.2016 | - | 55.21 | - | UCO bank | 49.66 | - | - | 0.07 | 0.07 | Full | 86 | 200 | 4 | 2021000368 2025000289 2025000290 | 2025000098 202001310 202100249 202100076 202001314 202001317 | -
8 | S-10-17 | 132 /33KV SUBSTATION AT N.V.PURAM | a)132/33 kV Substation at N.V.Puram with 2 x 16 MVA (Released) PTR Capacity (Radial) b)132kV DC/SC line from Kamalapuram 132/33 kV SS in Warangal district to the proposed 132/33 kV N.V.Puram Substation(5.5KM) c) 220 kV DC/SC line on Galvanized JC Towers with Moose conductor in Godavari river crossing area (4.5KM) d)132 kV Bay extension at Kamalapuram in Warangal district (1 No.) | SI | T.O.O (CE-Construction-I) Ms. No. 11 , Dated: 07.03.2014 (Revised) | - | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 07.03.2014 | 17.08.2016 | 31.03.2019 | 24.06.2019 | - | 18.01 | - | REC | 10.55 | - | - | -0.07 | -0.07 | Full | 10 | 32 | 2 | 2020000530 2020000532, 2020000310, 2020000313 2020000310 | 202000034 0202000036 0202000037 | RC pile foundations casted in Godavari river.
9 | S-10-21 | 132 KV SS AT TOOPRANPET | 132/33 KV Sub-station at Dandu Malkapur (V) in Chotuppal (M) of Yadadri Bhuvanagiri District is issued instead of Toopranpet | [14 empty] | - | - | 0.01 | Full | - | - | - | - | - | -
10 | S-11-06 | 2ND CIRCUIT FROM 132KV SHALIGOURARAM SS | a)Erection of 2nd circuit stringing from 132 kV Shaligouraram SS to new Aitipamula 132 kV SS. | SI | T.O.O (CE-Construction-I) MS. No. 447 Dated: 21.01.2011 | - | Not Necessary | 21.01.2011 | 26.02.2012 | 29.03.2012 | 27.02.2013 | - | 3.66 | - | UCO Bank | 2.34 | - | - | 0 | 0 | Full | 28.5 | - | 2 | 2019000852 2019000851 2019000850 | 202001421 202001426 202001427 | -
11 | S-11-09 | erection of 132/33 KV Chippalpalli ss | a)132/33 kV Substation at Chippapalli with 3 x 10/16 MVA (released) MVA PTR Capacity (Radial) b)132kV DC/SC line from Kamareddy 220/132 kV Substation to the proposed 132/33 kV Chippapalli Substation c)132 kV Bay extension at Kamareddy 220/132 kV Substation | SI | T.O.O (CE-Transmission) Ms. No. 201 Dated: 30.10.2015 | - | APT / TS / 132 KVSS-Chippapally / F-INVST/31/2013. | 29.07.2013 | 29.7.2013 | 7.01.2014 | 21.12.2015 | - | 32.96 | - | NABARD | 28.07 | - | - | 0.18 | 0.18 | Full | 61 | 47.5 | 2 | 2024000369 2023000747 | 0202001265 0202001267 0202001712 | -
12 | S-11-19 | ERECTION 132/33 KV KATHLAPUR SS | a)132/33 kV Substation at Kathlapur with 2 x 16 MVA (Released) PTR Capacity (Radial)) b)132kV DC/SC line from Korutla 132 kV Substation to the proposed 132/33 kV Kathlapur Substation(15KM) c)132 kV Bay extension at Korutla132 kV Substation (1 No.) | SI | T.O.O (CE-Construction-I) Ms. No. 297 ,Dated: 21.11.2011 | - | CRN;APT/TS/ 132 kV SS Kathlapur / F.INVST - 09/2014. | 21.11.2011 | 10.12.2015 | 31.03.2017 | 11.01.2018 | - | 14.15 | - | TMB | 12 | - | - | 0.16 | 0.16 | Full | 15 | 32 | 2 | 2024000597 2024000595 | 202001263 202001266 202001268 202001270 | -
13 | S-11-26 | ERECTION OF 132/33 KV SUBSTATION AT MUN | a)132/33 kV Substation at Munugodu with 1 x31.5 + 1 x 16 MVA (Released) PTR Capacity (Radial) b)132kV DC/SC line from 132/33 kV Nalgonda Substation to the proposed 132/33 kV Munugodu Substation(25KM) c)132 kV Bay extension at 132/33 kV Nalgonda Substation | SI | T.O.O (CE-Construction-I) Ms. No.5 ,Dated: 06.04.2011 | - | APT/TS/132kV SS-Munugodu/F-INVST-08/2014 | 11.08.2011 | 13.06.2016 | 31.03.2017 | 05.10.2017 | - | 19.34 | - | REC | 16.14 | - | - | 0 | 0 | Full | 25 | 47.5 | 2 | 2020000566 | 202001045 | -
14 | S-11-28 | 132/33 KV SS At NIMMAPALLI | a)132/33 kV Sub-Station at Nimmapally with 2X10/16 MVA (Released) PTRs b)132 kV DC / SC line with Panther ACSR Conductor on Galvanised Towers from the proposed 220/132 kV SS, Sircilla to proposed 132/33 kV Sub-station at Nimmapally(21KM) | SI | TOO (CE-Transmission) MS.NO.161 dt:26-08-2015 | - | Not Necessary | 04.01.2015 | 23.3.2018 | 04.01.2016 | 29.04.2021 | - | 19.7 | - | REC | 17.73 | - | - | 0 | 0.02 | Full | 21 | 32 | 2 | 2021000275 2023000534 2023000535 | 202200384 202100077 202001277 | -
15 | S-11-38 | 132/33 KV YELDURTHY SS & LINE | 1)132/33 kV Substation at Yeldurthy with 2 x 31.5 MVA PTR Capacity (Radial) 2a)132kV XLPE Cable from Chegunta 132 kV Substation to AP.No. 1 (0.7KM) b)132kV DC/SC line from Chegunta 132 kV Substation to the proposed 132/33 kV Yeldurthy Substation(17.3KM) 3)132 kV Bay extension at Chegunta 132 kV Substation(1KM) | SI | T.O.O (CE-Construction-I) MS. No. 173 Dated: 03.09.2012 | - | APT/TS/132 kV SS -Yeldurthy/F-INVST - 7/2013 | 03.09.2012 | 29.12.2016 | 31.03.2018 | 02.08.2018 | - | 23.07 | - | NABARD | 17.27 | - | - | 0 | 0 | Full | 18 | 63 | 2 | 2019000211 2019000170 2019000171 | 202001228 202000633 202000635 | -
16 | S-12-02 | 132/33 kV SS at Arempula along with 132K | a)Erection of 132/33kV Substation at Arempula with released 3X10/16 MVA PTRs. B) Erection of 132kV DC line to proposed Arempula 132/33kV SS by making LILO of second circuit of existing 132kV DC line from 220/132kV Budidampadu SS to 132kV Khammam Substation (15KM) | SI | T.O.O (CE-Construction) Ms.No. 16 Dated: 22 .06.2015 | - | TST/TS/132/33kV SS Arempula / F-INVST- 12/2015 | 01.04.2016 | 06.06.2016 | 31.03.2017 | 10.08.2017 | - | 21.53 | - | Tamilnadu Mercantile Bank | 19.37 | - | - | -0.13 | -0.13 | Full | 30 | 48 | 2 | 2019000386 2019000387 | 202000389 202000388 | -
17 | S-12-09 | 132KV DC/SC LINE YDMLRM-PMAILARAM | a) 132 kV DC/SC line with narrow based towers from 220 kV Yeddumailaram SS to 132 kV Pashamailaram SS b)132 kV Bay extension at 220 kV Yeddumailaram SS and 132 kV Pashamailaram SS | SI | T.O.O (CE-Construction-I) MS. No. 61 Dated: 25.05.2012 | - | APT/TS/132/Yeddumailram/F-INVST-27/2013 | 01.12.2018 | 09.05.2019 | 26.04.2021 | 27.09.2022 | - | 9.31 | - | NABARD | 9.22 | - | - | 0.13 | 0.11 | Full | 34 | - | 2 | 2023001117 2023001118 2023001114 | 2023000470 2023000471 2023000472 | -
18 | S-12-15 | 132/33 KV SS SALKUNOOR & LINE | a)132/33 kV Substation at Salkunoor with 2 x 16 MVA Capacity (Released) PTRs b)132kV DC line for making one circuit LILO of 132 kV DC line from 220/132 kV substation Miryalaguda to 132/33 kV substation Suryapet line at the proposed 132 kV Sub-Station, Salkanoor(3KM) | SI | T.O.O (CE-Transmission) Ms. No. 30 ,Dated: 18.02.2016 | - | Not Necessary | 01.04.2026 | - | - | - | - | 12.38 | - | REC | 10.38 | - | - | - | 0.04 | Full | 6 | 32 | - | - | - | Work is yet to be started.
19 | S-12-29 | Up gradation of 132 KV SS Renjal to 220 | Covered in downstream work of 400KV Nirmal power Transmisison scheme | [15 empty] | - | 0 | - | - | - | - | - | - | -
20 | S-13-03 | 220/132/33KV Bonguloor SS in RR District | a)Erection 220/132 /33kV SS at Bonguloor with 2X100 MVA + 2X50 MVA PTR Capacity b)Erection of 220 KV line on Narrow Based Multi Circuit Towers with 4 Circuits for LILO of both Circuits of Dindi - Chandrayangutta 220 KV DC Line to the proposed 220 kV SS, Bonguloor.(1KM) c)Erection of 132 kV DC Line on Narrow Based Towers for LILO of 132 kV Ibrahimpatnam - Turkayamzal SC Line to the proposed 220 kV SS, Bonguloor (5KM) d)Supply, Erection, Laying, Testing, Commissioning including the cost of accessories of 132 kV 630 sq.mm XLPE UG DC cable for LILO of 132 kV Ibrahimpatnam - Turkayamzal SC Line to the proposed 220 kV SS, Bonguloor(3KM) | SI | T.O.O (CE-Construction-I) MS.No. 117 ,Dated: 30.05.2014 | - | CRN.No. APT/TS/220 KVSS -Bonguluru/F.Invest-27/2014 | 30.05.2013 | 30.05.2014 | 31.03.2015 | 31.10.2015 | - | 63.4 | - | NABARD | 60 | - | - | -0.1 | -0.1 | Full | 20 | 300 | 6 | 2019000540 2019000541 2020000357 2021000144 2022000053 | 202000284 202200054 202100152 202000619 202000622 | -
21 | S-13-10 | ERECTION OF 132/33KV SS AT KACHAPUR | a)132/33 kV Substation at Kachapur with 3 x 10/16 MVA (Released) PTR Capacity (Radial)) b)132 kV DC/SC line from proposed 220/132 kV Huzurabad LIS substation to the proposed 132/33 kV Kachapur substation c)132 kV Bay extension at proposed 220/132 kV Huzurabad | SI | T.O.O (CE-Transmission) Ms.No.193 Dated:07.10.2015 | - | TST/TS/132kV / Kachapur SS/F-INVST- 17/2016 | 07.10.2015 | 22.09.2015 | 08.11.2016 | 04.05.2018 | - | 21.53 | - | REC | 20.28 |  | - | -0.04 | -0.04 | Full | 37.5 | 48 | 2 | 2023000749 2023000750 2023000751 | 202001280 202001281 202001283 202001286 202001289 202001288 | -
22 | S-13-14 | Revisedadministrative 220kVSSSircilla. | a)220/132 Sub-Station at Sircilla in Karimnagar District with 3 X 100 MVA PTR Capacity, Double Bus Arrangement, 2 Nos 220 kV Feeder Bays, 4 Nos. 132 kV Feeder Bays and Sub-Station Automation System b)220kV DC line With Moose ACSR on Galvanised Towers from 220 kV SS, Durshed to the proposed 220 kV SS, Sircilla. c)220 kV Bay extension at Durshed | SI | T.O.O (CE-Construction) MS.No. 144 Dated:03.08.2015 | - | CRN.No./TST/TS/220/132KV Substation /Sircilla /F.Invst./ App./08/2015 | 03.08.2015 | 22.12.2015 | 23.12.2016 | 15.12.2016 | - | 87.3 | - | REC | 59.9992 |  | - | 0.34 | 0.34 | Full | 134 | 300 | 8 | 2023001099 2023001100 | 202001293 202001298 202001300 202001301 202001304 | -
23 | S-14-03 | 132/33kV SS at Duddeda | a)Erection of 132/33 kV Sub-Station with 2 X 31.5 MVA PTRs, 2 Nos. 132 kV Bays With 4NOs. 33KV O/G Feeders b)Erection of 132 kV DC line with Panther Conductor on Galvanized Towers for LILO of one circuit of 132 kV Siddipet - Gajwel line to the proposed Duddeda 132/33 kV SS (15KM) | SI | T.O.O (CE-Construction) Ms. No. 52 Dated: 15.12.2014 | - | TST/TS/132 kV SS- 220 kV Toopran, 132 kV Ganeshpally & 132 kV Duddeda SS / F-INVST-07/2015 | 10.05.2015 | 31.07.2015 | 31.03.2016 | 02.09.2016 | - | 24.6 | - | REC | 19.06 | - | - | 0 | 0 | Full | 30 | 63 | 2 | 2020000503 2021000323 | 202001233 | -
24 | S-14-05 | 2nd ckt lineDurshed SS toWater Works SS | a)Erection of 132 kV 2nd circuit line on under construction 132 kV DC/SC line from 22kV Durshed SS to 132kV Water Works Karimnagar Town SS (7.5KM) b)132 kV Bay extension at 220 kV Durshed substation. C)132 kV Bay extension at 132 kV Water Work substation Karimnagar Town. | SI | T.O.O (CE-Construction-I) MS.No.08, Dated: 26.02.2014 | - | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 26.02.2014 | 26.03.2016 | 31.03.2020 | 27.02.2021 | - | 2.43 | - | REC | 2.18 | - | - | 0.1 | 0.1 | Full | 7.5 | -- | 2 | 2024000678 2024000593 2024000592 | 202001306 202001308 202001309 | -
25 | S-15-02 | Up-gradation132/33kVA'pet to 220kV SS | a)220 kV features at existing 132/33 kV Aswaraopet Sub-Station with 2 X 100 MVA (Released) PTR Capacity. b)220 kV DC line from proposed 400 kV Asupaka SS to the proposed 220 kV Aswaraopet SS (20KM) c)220 kV DC line for making LILO of KTPS - Lower Sileru-I to the proposed 400 kV Asupaka SS (15KM) d)Stringing of 132 kV 2nd circuit on the existing 132 kV DC/SC line from 132/33 kV Awaraopet to 132 kV B.Gangaram (30KM) e)132 kV Bay Extension at B.Gangaram. | SI | T.O.O (CE-Transmisssion) MS.No. 159 , Dated: 24.08.2015 | - | CRN.No. TST/TS//132/33 KVSS Aswaraopet SS up-gradation to 220/132 KV Invest. App/07/15, Dt.05.10.2015 | 24.08.2015 | 18.01.2017 | 31.03.2020 | 28.04.2018 | - | 52.82 | - | PFC | 42.55 | - | - | -0.11 | -0.11 | Full | 100 | 200 | 8 | 2020000136, 2019000093 2019000613 2020000522 | 202000027 202000035 202001650 202000023 | -
26 | S-15-04 | 132/33 kV Sub-Station at Jangapally | a)132/33 kV Sub-Station at Jangapally with 3 X 10/16 MVA PTRs (Released) b)132 kV DC line on Galvanised Towers with Panther ACSR for making LILO of 132 kV Durshed to Shanigaram line to the proposed 132/33 kV Sub-Station, Jangapally (14KM) | SI | T.O.O (CE-Construction) Ms. No. 140 ,Dated: 30.07.2015 | - | Not Necessary | 30.07.2015 | 03.03.2018 | 31.12.2019 | 02.06.2019 | - | 19.79 | - | PFC | 16.68 | - | - | 0.32 | 0.32 | Full | 28 | 48 | 2 | 2024000589 2024000586 | 202001316 202001319 | -
27 | S-15-06 | alternate Chennur & KataramfromManthani | a) Stringing of two circuits on already approved (under construction) 132 KV Multi circuit towers from 220/132 KV SS Manthani upto Loc. No. 19 of existing 132Kv Manthani – Kataram line, (5KM) b)132 kV DC line ( 5.00 KM) from existing Loc. No. 19 upto Loc.No. 34A, of 132 kV Manthani – Kataram line,(5KM) c)Stringing of 2nd circuit from newly proposed DC line (from Loc No. 34A of 132 kV Manthani – Kataram) to 132/33 kV Chennur SS on the existing DC/SC line,(19KM) d)Stringing of 2nd circuit from Loc. No. 34A of existing 132 kV Manthani – Kataram line to 132/33 kV SS Kataram,(26KM) e)32 KV bay (at 220/132 KVSS Manthan - 2 Nos., at 132 kV SS kataram - 1No.at 132 kV SS Chennur - 1 No.) TOTAL-4Nos. | SI | T.O.O (CE-Transmission) MS.No.210 Dated:06.11.2015 | - | Not Necessary | 07.02.2018 | 09.05.2020 | 22.07.2022 | 26.07.2024(Between Chennur & Kataram)- Work in Progress between Manthani & Kataram | - | 12.13 | - | REC | 10.917 | - | - | 0.25 | 0.71 | Full | 60 | - | 4 | 2024000717 2024000715 | 2025000094 2025000673 | ROW issues
28 | S-15-07 | 2ndckt 220/132KVKamareddy SS- Domakonda | a)Stringing of 132 kV 2nd Circuit from 220/132 kV SS Kamareddy to Loc No 33-34 of existing new 132 kV DC/SC line of 132 kV SS Chippapally ( 5 KM) B)Erection of 132 kV DC/SC line from loc 33-34 of existing new 132 kV DC/SC line of 132 kV SS Chippapally to 132/33 kV SS Domakonda (5.5KM) c)Stringing of 132 kV 2nd Circuit from 132/33 kV SS Domakonda to 132/33 kV SS Biknur (9KM) d)Erection of 132 kV Bays (Domakonda - 2 Nos, Kamareddy - 1No and Biknoor - 1 No) | SI | T.O.O (CE-Transmission) MS.No.162 Dated:26.08.2015 | - | Not Necessary | 15.03.2024 | 25.03.2024 | 14.04.2025 | a) 21.05.2025 b)Work cancelled c)26.09.2025 | - | 8.55 | - | PFC | 7.21 | - | - | 4.8 | 2.27 | Full | 24.5 | - | 4 | 2025000180 2025000177 | 2025000454 2025000456 | -
29 | S-15-10 | 132KV Narayanpet SS | a)132/33kV Substation with 2X31.5 MVA PTRS at Narayanpet in Mahaboobnagar District. B)132kV DC/SC line from 132/33kV Marikal Substation to proposed 132/33kV Narayanpet Substation.(15KM) c)132kV Bay Extension at 132/33kV Marikal Substation. | SI | T.O.O (CE-Construction) Ms. No. 128 ,Dated: 17.07 2015 | - | CRN.No.TST/TS/132/33 KVSS/Narayanpet, Mahabubnagar/Invest.Apprl.No.5/16,2016-17 | 17.07 2015. | 21.09.2016 | 31.03.2017 | 28.12.2017 | - | 21.23 | - | REC | 19.65 | - | - | 0.16 | 0.16 | Full | 15 | 63 | 2 | 2019000383 2019000384 2019000380 | 202100295 202000925 202000926 | -
30 | S-15-13 | 765kVWardha-HYD Link transmision Scheme | The details are enclosed in the annexure | SI | T.O.O (CE-400KV) MS.No.105 Dated: 15.07.2017 | - | Covered in 400KV | 25.01.2018 | 25.01.2018 | 31.03.2025 | The charging details are enclosed in Annexure | - | Covered in 400KV | - | PFC | 937.63 +139.49 | - | - | 0.28 | 0.29 | Full | 258 | 1040 | 8 | 2019000002 2019000003 2019000004 2019000256 | 2019000003 2020000523 2019000004 2019000002 | -
31 | S-15-29 | 132KV DC line from 220KV HSBD. LISS, BAY | a)1 No. 100 MVA additional PTR at 220/132 kV LI SS, Huzurabad with equipment totalling to 2 X 100 MVA (Released PTR) b)132 kV line with four circuits on Galvanised Multi-Circuit towers with Panther ACSR for making LILO of both 132kV Husnabad – Huzurabad & 132kV Mulkanoor – Huzurabad circuits at 220/132kV new Huzurabad LISS c)Stringing of 132 kV second circuit between 220/132 kV Durshed SS and 132/33 kV Manakonduru SS. d)132 kV Bays (Huzurabad - 4Nos, Manakondur - 2Nos, ) | SI | T.O.O (CE-Construction) MS. No. 136 Dated: 27.07.2015 | - | Not Necessary | 27.07.2015 | 11.11.2016 | 31.03.2018 | 29.12.2017 | - | 18 | - | REC | 16.5 | - | - | -0.01 | -0.01 | -0.01 | 17 | 100 | 6 | 2023000538 2023000539 | 202001357 202001353 202001356 202001359 202001361 | -
32 | S-15-31 | 2nd Ckt 220KV SRMP to 132kv ASFNGR & Con | a)2nd circuit from 220kV SS Shivarampally to 132kV SS Asifnagar by laying 220kV XLPE UG Cable b)132 kV Bay extension at 220 kV Shivarampally substation. c)132 kV Bay extension at 132 kV Asifnagar substation. | SI | T.O.O (CE-Construction-I) MS. No. 55 Dated: 25 .03 .2015 | - | CRN.No.TST/TS Asifnagar SS alternatesource of supply/Invest.App.06/2015, dt.05.10.2015 | 05.10.2015 | 21.01.2016 | 31.03.2018 | 31.05.2019 | - | 45.97 | - | REC | 41.36 | - | - | -0.07 | 0 | Full | 4 | - | 2 | 2020000356 2019000006 2019000005 2020000354 | 202000287 202000290 202000291 202000292 | -
33 | S-15-32 | Erec of 220KVSS at Pedagopati & line KMM | a)220/132/33 kV Sub-Station at Pedagopati with 2 X 100 + 2 X 31.5 MVA PTR Capacity b)220 kV DC line from proposed 400 kV Julurupadu (Bommanapalli) SS to the proposed 220 kV Pedagopati SS | SI | T.O.O (CE-Transmisssion) MS.No. 211 , Dated: 07.11.2015 | - | TST/TS/ 220 kV Pedagopati SS / Investment approval No. 19/16-2016 | 07.11.2015 | 27.02.2017 | 31.03.2020 | 01.12.2018 | - | 124.44 | - | REC | 121.24 | - | - | -0.05 | -0.05 | Full | 220 | 263 | 4 | 2019000088 2019000103 | 202000025 202000029 | -
34 | S-15-33 | Erection of 132/33KV SS at Sarangapur & | a)132/33 kV Sub-Station at Sarangapur in Adilabad District with 3 X 10/16 MVA PTRs (Released) b) | SI | T.O.O (CE-Transmisssion) MS.No. 231 Dated: 21.12.2015 | - | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 21-12-2015 | 04.04.2018 | 31.01.2020 | 11.12.2019 | - | 19.93 | - | REC | 14.72 | - | - | 0.35 | 0.35 | Full | 28 | 48 | 2 | 2020000621 2020000620 | 202001545 202001544 | -
35 | S-15-34 | 220 KV D/C LN from 400KV GAJWEL-SIDDIPET | a)220 kV DC line on Galvanised Towers with Moose ACSR from 400/220/132 kV SS Gajwel to 220/132 kv SS Siddipet b) 220 KV Bays (Gajwel-2, Siddipet-2) | SI | T.O.O (CE-Transmission) MS.No. 225 Dated: 10.12.2015 | - | CRN.No.TST/TS/Erection of 220 KV DC line Gajwel/Siddipet/Invest.App. 4/17-2017-18 dt:02.07.2017 | 4.12.2017 | 4.12.2017 | 3.12.2018 | 19.11.2022 | - | 38.12 | - | REC | 35 | - | - | 1.09 | 1.09 | Full | 80 | __ | 4 | 2023001110 2023001111 2023001112 | 2023000465 2023000467 2023000468 | -
36 | S-15-38 | 2nd ckt 132KV Wgl-S.Nagr @ Jngan&kolnpk | Erection of 132 kV lines for making LILO of (i) 2nd Circuit of 132kV Warangal – Shapurnagar DC line at 132kV SS Jangaon (1KM) (ii) 2nd Circuit of 132kV Warangal – Shapurnagar DC line at 132kV SS Kolanpak (5KM) | SI | TOO / CE/Trans/ MS No. 158 Dated 22.08.2015 | - | Not Necessary | 22.08.2015 | 07.02.2018 | 31.03.2019 | J-28.12.2019 K-16.11.2019 | - | 8.38 | - | PFC | 7.02 | - | - | -0.01 | 0.12 | Full | 12 | -- | 4 | 2020000510 2020000508 2020000509 | 202000335 202000337 202000339 | -
37 | S-16-12 | Erection of 132/33 kV SS at Kotagiri | a)132/33 kV Sub-Station at Kotagiri in Nizamabad District with 3 X 10/16 MVA PTRs (Released) b)132 kV DC/SC line on Galvanised Towers with Panther ACSRfrom 132/33 kV Sub-Station, Jakora to the proposed 132kV Sub-Station at Kotagiri in Nizamabad District . c)132 kV Bay extensions at 132/33 kV Sub-Station, Jakora | SI | T.O.O (CE-Transmission) Ms. No. 88 Dated: 30.06.2016. | - | Not necessary | 28.06.2019 | 28.06.2019 | 31.03.2020 | 11.05.2022 | - | 15.05 | - | PFC | 12.98 | - | - | 0.32 | 0.35 | Full | 12 | 48 | 1 | 2023000284 2023000283 2023000282 | 2023000156 2023000157 2023000158 | -
38 | S-16-14 | 220/132/33 kV SS Borampet & Line | a) 220/132/33 kV Sub-Station at Borampet with 2 X 160 MVA + 2 X 80 MVA PTR Capacities b)220 kV Multi Circuit OH line on MC Towers with Moose ACSR from 400 kV Narsapur SS to proposed 220 kV Borampet SS-38 KM c)220 kV DC line with UG Cable from 400 kV Narsapur SS to proposed 220 kV Borampet SS – 5 KM. d)220 kV Bays at 400 kV Narsapur(2 No.s) | SI | T.O.O (CE-Transmission) Ms. No. 72 Dated: 13.05.2016 | - | CRN.No.TST/TS/220/132/33 KVSS Borampet, R.R.Dist. /Invest. Apprl/No.7/16-2016-17, dt.19.10.2016 | 28.11.2016 | 19.05.2019 | 31.03.2022 | SS-04.03.2025, 2nd PTR-20.03.2025 line-27.02.2025 | - | 212.2 | - | PFC | 182.98 | - | - | 13.14 | 221.9 | Full | 48 | 480 | 2 | 2024000982 2024000983 2024000981 2024000869 | 2025000245 2024000246 2024000244 2024000580 | ROW issues and statutory permissions from various authorities
39 | S-16-16 | Erec of 220/33 Kv SS at Domalapenta in N | a) 220/33 kV Sub-Station with 2 Nos., 220/33 kV 31.5 MVA, PTRs at Domalapenta Village of Nagarkurnool District. b)220 kV DC line on Galvanised Towers with Moose ACSR for LILO of one circuit of the existing 220 kV Srisailam – Dindi DC Line to the proposed 220 kV Sub-Station, Domalapenta. | SI | T.O.O (CE-Transmission) Ms. No. 173 Dated: 15.12.2016. | - | Not necessary | 15.12.2016 | 05.03.2018 | 30.11.2019 | 26.07.2019 | - | 14.2 | - | PFC | 12.41 | - | - | 0.03 | 0.03 | Full | 2 | 63 | 2 | 2020000642 2020000643 | 202000930 202000930 | -
40 | S-17-01 | erection of 220/33 kV GIS at Chanchalgud | a)220/33 kV GIS substation at Chanchalguda with 3 X 50 MVA PTR b)220 kV DC line with 1000 Sqmm 220 kV UG cable for LILO of Chandrayangutta - Imlibun line (UG Cable) to the proposed 220/33 kV GIS substation, Chanchalguda | SI | T.O.O (CE-Transmission) Ms. No. 26, Dated: 27.02.2017. | - | CRN TS/TST/220/33 KV, GIS, Chanchaguda/Invest.Approval No.7/17-2017-18 | 27.02.2017 | 28.02.2018 | 31.03.2021 | 20.03.2021 | - | 89.12 | - | REC | 80.208 | - | - | -3.26 | 1.37 | Full | 2 | 150 | -- | 2021000035 | 202100160 | -
41 | S-17-03 | 132/33 kV Sub-Station at Moulali ZTS | a)132/33 kV Moulali ZTS SS with 2X50 MVA PTR b)132 kV DC line with 630 Sqmm 132 kV UG cable from 220 kV Moulali Sub-Station to the proposed Moulali ZTS SS c)132 kV Bay extensions at220 kV Moulali substation | SI | T.O.O (CE-Transmission) Ms. No. 31, Dated: 27.02.2017. | - | CRN TS/TST/132/33 KV, Moulali-ZTS SS, Investment Approval No.17/17, 2017-18 | 04.05.2019 | 04.05.2019 | 03.02.2020 | 30.07.2021 | - | 49.78 | - | REC | 44.47 | - | - | 1.73 | 1.93 | Full | 7 | 100 | 2 | 2022000496 2022000497 2022000498 | 2023000065 2023000066 2023000067 | -
42 | S-17-04 | erection of 132/33 KVSS Gachibowli | a)132/33 kV Sub-Station at Gachibowli with 2X80 MVA PTR b) 132 kV DC OH line on galvanised towers with Panther ACSR from 220/132/33 kV Gachibowli SS to the proposed 132/33 kV Gachibowli SS | SI | T.O.O (CE-Transmission) Ms. No.27, Dated: 27.02.2017. | - | Not necessary | 27.02.2017 | 11.06.2019 | 10.12.2020 | 22.09.2021 | - | 18.73 | - | REC | 16.52 | - | - | -0.03 | 0.01 | Full | 2 | 160 | -- | 2022000374 2022000375 2022000376 | 202200406 202200407 202200408 | -
43 | S-17-09 | 220/132/33 kV SS Meenajipet & lines | a) 220/132/33 kV Sub-Station at Meenajipet, with 2 X 100 MVA + 2 X 31.5 MVA PTRs With 2Nos., 220kV Incoming Feeder Bays, 4 Nos. 132 kV Feeder Bays and 4 No.33KV Feeder Bays b) 220 kV DC line with Moose ACSR Conductor on Galvanised Towers from proposed Narsapur 400/220/132 kV SS to the now proposed Meenajipet 220/132/33 kV SS c)132 kV DC/SC Line with Panther ACSR Conductor on Galvanized Towers from the proposed 220/132/33 kVMeenajipet SS to 132/33 kV Doulathabad SS d)132 kV DC Line with Panther ACSR Conductor on Galvanized Towers from the proposed 220/132/33 kV Meenajipet SS to 132/33 kV Thunki Bollarum SS e)Stringing of second circuit from 132/33 kV Thunki Bollarum to 132/33 kV Ganeshpally SS f) 220 kV Bays at 400/220/132 kV SS Narsapur for connectivity from 400/220/132 kV Narsapur SS to the 220/132/33 kV Meenajipet SS g)132 kV Bays at Doulathabad 132 kV SS.(1),132kV Thunki Bollarum SS (3) and 132kV Ganeshpally SS (1) | SI | T.O.O (CE-Transmission) Ms. No. 28, Dated: 27.02.2017. | - | CRN/TS/TST/220/132/33kV SS/Meenajipet instead of Toopran/Invst.Appl.No.15/17-2017-18, Dt.Dec.2017. | 27.05.2017 | 23.12.2016 | 31.03.2021 | 06.02.2020 | - | 76.78 | - | REC | 68.43 | - | - | 0.19 | 0.2 | Full | 110 | 263 | 12 | 2020000000 2020000001 | 202000576 202000577 | -
44 | S-17-13 | Erec of 132 KVSS at Yadgirigutta temple | a)132/33 kV Sub-Station at Yadagirigutta Temple Town with 2 X 31.5 MVA PTRs b)132 kV DC line with Panther ACSR Conductor on Galvanised Towers for LILO of LILO of 132 kV Bhongiri - Raghunathapally (Bhongir-Shapurnagar-Kolanpak) line to the proposed 132 kV Yadagirigutta SS.(2KM) | SI | TOO (CE_Transmission)Ms.No.69 Dt:09.05.2017 | - | Not Necessary | 09.05.2017 | 16.07.2018 | 31.03.2019 | 11.12.2019 | - | 15.06 | - | PFC | 13.16 | - | - | -0.05 | 0.05 | Full | 4 | 63 | 2 | 2019000921 2019000922 | 202000883 202000886 | -
45 | S-17-15 | Erec of 132/33 KV SS at Chinna Shankaram | a)132/33 kV Sub-Station at Chinna Shankarampet in Medak District with 2 X 10/16 MVA PTRs(Released) b)132 kV DC line for LILO of 132 kV Chegunta- Yeldurthy DC/SC line at the proposed 132/33 kV Chinna Shankarampet Sub- Station | SI | T.O.O (CE-Construction) Ms. No. 124, Dated: 19.08.2017 | - | Not necessary | 19.08.2017 | 01.04.2018 | 31.03.2021 | 23.01.2021 | - | 16 | - | REC | 13.96 | - | - | -0.07 | 0.02 | Full | 12 | 32 | -- | 2021000138 2021000140 | 202100228 202100229 | -
46 | S-17-16 | 132kV 2nd ckt Str on W.pally - Peddanaga | a)Stringing of 2nd circuit on 132KV DC/SC line from existing 220/132KV SS Waddekothapally to existing 132/33KV SS Peddanagaram with Panther ACSR Conductor.(30KM) b)132 KV feeder bays (at 220/132 KVSS Waddekothapally - 1 Nos. and at 132 kV SS PeddaNagaram 1 No.) TOTAL-2Nos. | SI | T.O.O (CE-Construction) MS.No..149 Dated:09.10.2017 | - | Not necessary | 09.10.2017 | 22.02.2020 | 21.08.2021 | 06.11.2021 | - | 7.02 | - | REC | 6.32 | - | - | 0.02 | 0.01 | Full | 30 | -- | 2 | 2022000382 2022000383 2022000384 | 202200374 202200376 202200375 | -
47 | S-17-21 | erec 132/33 kV SS Pammy n Khammam dist | a) 132/33 kV Sub-Station at Pammy in Khammam District with 2 X 31.5 MVA PTRs b)132 kV DC line for LILO of 132 kV Kusumanchi-Chilakallu line at the proposed 132/33 kV Pammy Sub- Station | SI | T.O.O (CE-Construction) Ms. No.14 Dated:20.01.2018. | - | TST/TS/Erection of 132/33 KV SS at Pammy in Khammam District/Approval No.03/2018-19, 01.06.2018 | 20.01.2018 | 13.01.2022 | 31.03.2024 | 20.02.2024 | - | 23.39 | - | REC | 20.64 | - | - | 1.29 | 2.38 | Full | 16 | 63 | - | 2024000001 2024000000 | 2024000064 2024000066 | -
48 | S-18-02 | 220/132 kV SS at Ammavaripet in Warangal | a)220/132 kV Sub-Station at Ammavaripet with 2X100 MVA PTR Capacity in Warangal Dist b) 220 kV DC Line on Galvanized Towers with Moose ACSR Conductor for LILO of one circuit of 220 kV Mahabubabad - Warangal line to proposed 220 kV Ammavaripet SS c)132 kV DC Line on Galvanized Towers with Panther ACSR Conductor from the proposed 220/132 kV Sub-station Ammavaripet to the existing 132/33 kV Sub-Station, Geesukonda. d)132 kV Line on Multi-circuit Towers with Panther ACSR Conductor for accomdation of 132 KV Line to 132KV SS Inavole and 132KV Line to 132KV SS Wardhannapet from the proposed 220/132 kV Sub-station Ammavaripet to AP 8. e)132 kV DC/SC Line on Galvanized Towers with Panther ACSR Conductor from the AP.8 to the 132/33 kV SS Inavole f)32 kV DC/SC Line on Galvanized Towers with Panther ACSR Conductor from the AP.8 to the 132/33 kV SS Wardhannapet g)132 kV Bays (2 Nos at 132 kV Geesukonda, 1 No at 132 KV Wardannapet & 1No at 132 kV Inavole) | SI | T.O.O (CE-Construction) MS.No .294 Dated:29.01.2019 | - | CRN No.TST/TS/ Erection of 220/132 KV SS at Ammavaripet, Kazipet(M) in Warangal Urban District. Approval / NO 02/2019-20 dt:10.08.2018 | 06.07.2020 | 06.07.2020 | 5.11.2021 | 30.11.2022 | - | 111.84 | - | PFC | 87.24 |  | - | 0.53 | 0.87 | Full | 133.55 | -- | 4 | 2023000369 2023000306 2023000368 2023000303 | 2023000320 2023000321 2023000322 2023000323 | -
49 | S-18-03 | Erect 132kV SS Padmanagar | a)132/33 kV Sub-Station Padmanagar (V) in Karimnagar District with 2X31.5 MVA PTR capacity b)LILO of132 KV Line (one circuit) from 220/132 KV SS Durshad to the 132/33 KV SS Siricilla to proposed 132/33 KV SS Padmanagar c)132 kV DC line erection on 400 kV DD Type Towers. | SI | T.O.O (CE-Construction) Ms. No.254 Dated: 26.11 2018. | - | Not necessary | 26.11.2018 | 31.10.2020 | 31.03.2023 | 15.05.2023 | - | 19.29 | - | PFC | 16.33 |  | - | 0.22 | 0.22 | Full | 14 | 63 | - | 2023001228 2023001229 | 2024000265 2024000267 | -
50 | S-18-04 | erc of 132KV SS Nagaram in Suryapet Dist | a)132/33 kV Sub-Station at Nagaram , Suryapet Dist with 1 X 31.5 + 1x10/16 MVA PTRs b)132 kV line with ACSR Panther Conductor on Galvanised Towers by making making LILO of 132 kV DC/SC line from 400/220/132 kV Suryapet SS to 132/33 KV Thungathurthy SS at newly proposed 132/33 KV Nagaram SS | SI | T.O.O (CE-Construction) Ms. No. 193, Dated: 30.08 2018. | - | TST/TS/Erection of 132/33 KV SS at Nagaram in Suryapet District. Approval No.14/18/2018-19 dt:12.12.2018 | 30.08.2018 | 27.10.2020 | 26.04.2022 | 27.03.2022 | - | 33.97 | - | PFC | 26.15 |  | - | 0.17 | 0.17 | Full | 32 | 47.5 | -- | 2022000074 2022000076 | 202200171 202200173 | -
51 | S-18-06 | 33kV features at RTSS Kothagudem in bhad | 33 KV features at 132 KV Railway Traction Switching Station, Kothagudem, Kothagudem Bhadradri District with 2 X 10/16 MVA PTRs | SI | T.O.O (CE-Construction) MS.No . 217 Dated: 25.09.2018 | - | Not necessary | 25.09.2019 | 25.09.2020 | 31.10.2023 | 21.11.2023 | - | 9.92 | - | PFC | 7.64 | - | - | 0.71 | 5.28 | Full | - | 32 | - | 2023001195 | 2024000084 | -
52 | S-18-07 | LILO Maddur-Makthal to 132/33 KV SS Nara | a)LILO of existing 132 kV Maddur – Makthal DC/SC line to existing newly charged 132/33 kV Narayanpet SS with Panther ACSR Conductor.(1KM) B)Erection of 132 KV feeder bays at 132/33 KV SS Narayanpet - 2Nos. | SI | T.O.O (CE-Construction) MS.No .12 Dated:20.04.2018 | - | Not necessary | 19.12.2024 | 19.12.2024 | 18.01.2025 | 22.02.2025 | - | 5.67 | - | REC | 5.11 | - | - | 1.66 | 1.66 | Full | 2 | - | 2 | 2025000051 2025000050 | 2025000418 2025000417 | -
53 | S-19-01 | KTPP system Improvement Scheme | a) LILO of existing 220kV Pulukurthy-Bhimghanapur SC line to proposed 400/220/132kV KTPP SS at Ramappa point with Twin Moose DC Line b)LILO of existing 220kV Salivagu-Bhimghanapur SC line to proposed 400/220/132kV KTPP SS at Ramappa point with Twin Moose DC Line c)220KV Single Moose DC Line from proposed 400/220/132kV KTPP SS to 220/132kV Manthani SS and bay extensions at Manthani SS d)Upgradation of existing 220kV Nagaram-Warangal DC Line with HTLS Conductor e)32KV Single Moose DC Line from proposed 400/220/132kV KTPP SS to 132/33KV Chelpur SS on 220kV Multi Circuit Towers and bay extensions at Chelpur | SI | T.O.O (CE-400KV) MS.No . 297 Dated: 09.02.2019 | - | Covered in 400KV | 05.05.2020 | 05.05.2020 | 31.3.2025 | a) 22.06.2023 b)6.09.2023 e)24.09.2022 | - | Covered in 400KV | - | PFC | 405 | - | - | -2.85 | -1.74 | Full | - | - | - | 2022000388 2023000242 2023001362 | 2023000196 2024000093 2024000096 | -
54 | S-19-03 | 132/33 KV Sub-Station at Patancheru in S | a)132/33 kV Sub-Station at Patancheru, Sangareddy Dist with 2 X 31.5 MVA PTRs b)132 KV DC/SC line with ACSR Panther conductor from Loc.no.16 (of existing 132 KV line from RC Puram to M/s MHPL) to proposed 132/33 KV Patancheru substation on Narrow Base Towers. | SI | T.O.O (CE-Construction) Ms.No.375 Dated: 03.06.2019 | - | CRN/TST/TS/Erection of 132/33 KV SS at Patancheru in Sangareddy District. Approval /NO 05/2019-20 dt:22.11.2019 | 06.07.2020 | 06.07.2020 | 5.11.2021 | 30.11.2022 | - | 23.64 | - | REC | 20.85 | - | - | 0 | 0.04 | Full | 4.7 | 63 | -- | 2022000074 2022000076 | 202200171 202200173 | -
55 | S-19-04 | 33 kV Featu at 220/132 KV SS Ammavaripet | Providing of 33 kV Features at upcoming 220/132 KV Sub-Station, Ammavaripet in Kazipet (M), Warangal Urban (District) with 1X50 MVA (new) and 1X50 MVA (released) PTRs | SI | T.O.O. (CE-Construction) Ms. No. 1724 Dated: 15.07.2023 | - | Not necessary | 18.09.2020 | 11.12.2020 | 17.09.2021 | 30.12.2022 | - | 13.65 | TGTransco funds | - | 13.65 | - | - | 0.21 | 0.21 | Full | - | 100 | - | 2023001330 2023001313 | 2024000090 2024000117 | -
56 | S-19-05 | 132 KV GIS Manikonda -RR Dist | a)132/33 kV GIS Sub-Station at Manikonda with 2 X 80 MVA PTRs b)LILO of existing 132 kV Shivarampally-Erragadda SC OH feeder between Loc No.80 and Loc No.81 with laying of 132 KV XLPE UG cable of 1200 Sq mm for cable length of 2.5 Km. | SI | T.O.O (CE-Construction) MS.No .402 Dated: 08.07.2019. | - | CRN/TST/TS/Erection of 132 KV SS at Manikonda in Rangareddy District.Approval NO 08/2019-20 dt:27.12.2019 | 18.03.2021 | 18.03.2021 | 17.03.2022 | 15.09.2022 | - | 107.18 | - | REC | 96.46 | - | - | 1.91 | 2.08 | Full | __ | 160 | -- | 202300002 202300003 202300004 | 2023000277 2023000278 2023000279 | -
57 | S-20-01 | 132/33 KV SS at Koutala (V)- Komaram Bhe | a)132/33 kV Sub-Station at Koutala in Komaram Bheem Asifabad Dist with 2 X 10/16 MVA PTRs (Released) b)132 KV DC/SC line from existing 132 KV Sirpur Kagaznagar SS to proposed 132 KV SS Koutala(43.53KM) c)132 KV feeder bay at existing 132 KV SS Sirpur Kagaznagar (1No.) | SI | T.O.O (CE-Construction) Ms.No. 981 Dated: 22.02.2021. | - | TST/TS/Erection of 132/33 KV SS at Koutala(V), Koutala (M) of Komaram Bheem Asifabad District.Approval No.02/2021-22, dt:10.06.2021 | 18.05.2023 | 25.10.2023 | 17.05.2024 | 25.04.2025 | - | 66.56 | - | REC | 96.46 | - | - | 18.14 | 0.18 | Full | 43.52 | 32 | 1 | 205000166 | 2025000637 | -
58 | S-21-01 | 132/33 Kv SS at Pasra -Mulugu Dist. | a)132/33 kV Sub-Station Pasra (V) in Mulugu District with 2X10/16 MVA PTR capacity (Released) b)LILO of existing 132 kV Kamalapur - Chelpur to proposed 132/33 KV SS Pasra | SI | T.O.O (CE-Construction) Ms.No.1099 Dated: 30.06.2021. | - | Not necessary | 30.06.2021 | 25.10.2021 | 31.12.2022 | 31.01.2022 | - | 12.8 | TGTransco funds | - | 12.8 | - | - | 0.18 | 0.18 | Full | 3.8 | 32 | -- | 2022000264 2022000381 | 202200373 202200274 | -
59 | S-21-02 | 2nd CKT stringing from 220KV CHGR to KTR | a)2nd circuit Stringing on existing 132 kV DC/SC line from 220/132/33 kV Chegur SS to 132/33 kV SS Kothur. b)132 kV Bay Extensions (1 No at 220kV SS Chegur, 1 No at 132 kV SS Kothur) | SI | T.O.O (CE-Construction) Ms.No.1165 Dated:17.08.2021 | - | Not necessary | 17.08.2021 | 31.12.2022 | 31.12.2025 | - | - | 3.39 | TGTransco funds | - | 3.39 | - | - | -0.1 | -0.07 | Full | 7 | - | 2 | - | - | -
60 | S-21-06 | line 4m 400KV Narsapur 2 132 KV Yeldurth | a)132kV DC line on Galvanized Towers with Panther ACSR conductor from 400/220/132 kV SS Narsapur to 132/33 kV SS Yeldurthy (23KM) b)132 kV feeder bays ( 2 Nos at Narsapur & 2 Nos at Yeldurthy) (4No.s) | SI | T.O.O (CE-Construction) Ms.No.1208 Dated: 04.10.2021 | - | (CRN) TST/TS/Erection of 132KV DC line from 400/220/132 KV SS Narsapur to 132/33 KV SS Yeldurthy in Medak District.Approval NO.04/2021-2022 | 05.11.2022 | 07.11.2023 | 06.11.2024 | 06.01.2025 | - | 30.58 | HUDCO | - | 27.45 | - | - | 5.93 | 23.98 | Full | 46 | - | 4 | 2025000158 2025000155 2025000154 | 2025000106 2025000108 2025000107 | -
61 | S-21-08 | 2nd ckt 4m Shaligowraram-Mothkur | a)2nd circuit stringing on existing 132 kV DC/SC line from 132/33 kV Shaligowraram SS to 132/33 kV SS Mothkur with Panther ACSR conductor (22KM) b)132kV Bay Extensions (1 No at 132kV SS Shaligowraram, 1 No at 132/33 kV SS Motkur) | SI | T.O.O (CE-Construction) Ms.No.1271 Dated: 20.12.2021 | - | Not Necessary | 15.10.2022 | 25.04.2024 | 19.11.2023 | 06.01.2025 | - | 6.53 | TGTransco funds | - | 6.53 | - | - | 4.04 | 4.16 | Full | 22 | - | 2 | 2024000962 2024000961 2024000960 | 2025000452 2025000450 2025000449 | -
62 | S-21-12 | 132/33 kV SS Nuthankal | a)132/33kV Sub-station at Nuthankal in Suryapet District with PTRs capacity of (2x50 MVA) + (1x10/16 MVA Released.) b)Stringing of 2nd circuit from Loc.No.16 to Loc.No.75 (Tapping Tower) on existing 132kV DC/SC line from 400/220/132 kV SS Suryapet to 132/33kV SS Thungathurthy towers with Panther ACSR conductor(16.5KM) c)132kV DC/SC line from Loc.No.75 (Tapping tower) to proposed to 132/33kV SS Nuthankal on Galvanised towers with Panther ACSR conductor(9.5KM) d)132 kV Bay extension at 400/220/132kV SS Suryapet(1 No.) | SI | T.O.O (CE-Construction) Ms.No.1330 Dated:10.03.2022. | - | (CRN) TST/TS/Erection of 132/33 KV Sub Station at Nuthankal(V&M) in Suryapet District instead of 1323/33 KV Aipoor SS in Suryapet District.Approval NO.02/2022-2023 | 22.02.2023 | 25.08.2023 | 21.02.2024 | 30.12.2024 | - | 30.55 | - | REC | 18.91 | - | - | 9.76 | 21.02 | Full | 26 | 116 | 1 | 2024000956 2024000957 2024000958 2024000959 | 2025000443 2025000445 2025000447 2025000448 | -
63 | S-22-05 | LILO of 132 KV Dharmaram-Godur to 220/1 | a)LILO of 132kV Darmaram-Godur line to 220/132 KV SS Jagityal in Jagityal District on multi circuit tower with panther ACSR conductor(1KM) b)132kV Bay Extensions (2 No's at 220/132 kV SS Jagityal.)( 2No.s) c)Dismantling of TNS,TND,BOOM & Re-stringing of 132KV Jagityal-Gangadara, Jagityal-Pudur, Jagityal-Jagityal, Jagityal-Korutla line near TT Tower at 220 kV SS Jagityal. | SI | T.O.O (CE-Construction) Ms.No.1590 Dated:14.03.2023. | - | Not necessary | 15.08.2023 | 10.12.2023 | 14.08.2024 | 21.01.2025 | - | 5.12 | TGTransco funds | - | 5.12 | - | - | 2.97 | 2.98 | Full | 2 | - | 2 | 2025000217 2025000218 | 2025000095 2025000096 | -
64 | P-10-01 | Jaipur Power Trn scheme | a)132 kV DC Line from proposed 400/220/132kV Narsapur SS to existing 132 kV Gummadidala SSand bay extensions at Gummadidala SS b) LILO of 132kV Narsapur –Koudipalli SC Line to proposed 400/220/132kV Narsapur SS. | SI | Ref:TO.O.(CE-Construction/400kV) Ms.No.19, Date: 02-05-2014. | - | Covered in 400KV | 01.01.2016 | 01.01.2016 | a) 10.01.2017 b)05.01.2017 | a) 15.07.2017 b)11.07.2017 | - | Covered in 400KV | - | REC | 898.49 |  | - | 0 | 0 |  |  |  |  | 2019000246 2019000589 | 202000126 202000203 202000265 202000312 | -
65 | P-12-02 | NIRMAL POWER TRANSMISSION SCHEME | a)Up gradation of 132/33 kV Renzal SS to 220/132 kV Renzal Sub Station and 220kV DC Line from proposed 400/220kV Nirmal SS to the proposed up graded 220/132 kV Renzal SS b)220/132 KV SS at Indravelly in Utnoor District c)220kV DC Line from proposed 400/220kV Nirmal SS to the proposed 220/132 kV Indravelly SS d)132kV DC Line from proposed 220/132 kV Indravelly SS to 132/33 kV Utnoor S Sand 132 KV Bay extension at Utnoor-2, e)220kV Multicircuit line for making LILO of existing 220kV RSS(Malyalpalli) –Nirmal and RSS-Vemnur-Nirmal DC line to existing 220/132kV Jagityal Substation and 220kV Bay Extensions at 220kV Jagityal SS f)220kV DC Line from proposed 400/220kV Nirmal SS to the existing 220kV Nirmal SS on Multi circuit towers g)132 KV DC line with Single moose from proposed 220/132 kV Indravelly SS to 132/33 kV Asifabad SS on 220kV Galvanized DC towers & 132 KV bay extension at Asifabad -2. h)132kV DC line from Proposed 220/132 kV Indravelly SS to the existing 132kV Adilabad SS & 132 KV bay extension at Adilabad -2. | SI | T.O.O. (CE-400kV) Ms.No.07 Dated: 09.01.2018 | - | covered in 400KV | 10.03.2019 | 10.03.2019 | 31.03.2024 | a) 15.02.2020 b)27.08.2021 c)18.08.2021 e)20.11.2019 f)29.12.2017 g)work in progress h)31.03.2022 | - | Covered in 400KV | - | REC | 843.16+166.30 |  | - | 7.84 | 1.48 | Full |  |  |  | 2019000034 2019000035 2023000532 2019000735 2019000736 2019000736 2020000529 2019000283 2019000281 | 202000085 202000088 202001169 202001172 202001478 202001482 202001726 202001901 202001903 | -
-
-
66 | P-15-01 | DINDI SYSTEM IMPROVEMENT SCHEME | a)220 kV features at 132/33 KV Substation at Nagarkurnool b)220KV DC Line from proposed 400KVSS Dindi to proposed 220 kV Nagarkurnool SubStation. C)220KV DC Line from proposed 400KVSS Dindi to existing 220 kV Kondamallepally SubStation. | SI | T.O.O.(CE-Projects-I) Ms.No.8 Dt:19 .01.2016. |  | Covered in 400KV | 25.07.2017 | 25.07.2017 | 31.03.2022 | a) 03.04.2019 b)03.04.2019 c)31.03.2022 | - | Covered in 400KV | - | REC | 273.55 |  | - | 0.03 | 0.03 | Full |  |  |  | 2019000534 2022000008 2019000253 2019000259 2019000250 | 202100287 202200175 202001143 202001369 202001373 | -
67 | P-15-03 | Bhadradri Thermal Power Transmisn Scheme | a)220/132/33 kV Kallur Sub Station b)132kV Chandragonda Sub Station c)220kV DC line from proposed 400/220kV Bommanapalli to the proposed 220/132 kV Kallur SS (Single Moose) d)132kV DC line from proposed 220/132kV SS Peddagopati to 132/33kV SS Madhira and bay extensions at Madira e)132kVDC Line with Multi-Circuit towers for making LILO of existing132kV Budidampadu - Penubali & 132 kV Thallada- Penuballi f)132kV DC line from proposed 220/132kV SS Peddagopati to 132/33kV SS Thallada and bay extensions at Thallada g)132kV line with Multi-Circuit towers for making LILO of existing132kV Khammam - Chilakallu DC line to proposed 220/132 kV Peddagopati h)132 KV DC/SC line from proposed 220/132 KV SS Kalluru to 132/33 KV SS Chandrugonda | SI | T.O.O.(CE-Projects-I)Ms.No.15 Dt:29-04 -2016. | - | Covered in 400KV | 30.05.2017 | 30.05.2017 | 31.03.2023 | a) 3.08.2018 b)2.11.2019 c)3.08.2018 d)26.05.2023 e)09.08.2018 f)28.12.2019 g)23.12.2022 h)02.11.2019 | - | Covered in 400KV | - | PFC | 1150.16 |  | - | 4.4 | 4.41 | Full |  |  |  | 2019000428 2021000326 2023001015 2023001202 2023001201 2019000743 2019000100 2020000128 2020000144 2020000102 2019000101 2019000064 2019000125 2019000128 2020000145 2019000398 | 202001899 202200201 2023001090 2024000072 2024000073 202000026 202000028 202000030 202000031 202000032 202000062 202000092 202000548 202000956 202001644 202001838 | -
[6 empty] | - | [11 empty] | -
68 | P-19-01 | 315MVA ICT at BTPS & DC lne 4m Manuguru | a)Supply,Erection, Testing & Commissioning of 400/220 kV, 1X315 MVA Auto Transformer along with PTR Bays and Bus coupler including civil works at BTPS. b)220 KV DC line from 220/132/33 KV Manuguru SS to 400 KV Bhadradri Thermal Power Station switch yard c)220 kV Bays (2 Nos at 220 kV Manuguru, 2 Nos at BTPS) | GE | T.O.O (CE-Construction) MS. No. 401 Dated: 08.07.2019 | - | CRN No. TST/TS Erection of 400/220 KV 1x315 MVA ICT at BTPS switch yard Manuguru & Erection of 220 KV DC line from 220/132/33 KV Manuguru SS to 400 KV BTPS switch yard Approval/No.06/2019-20 dt:22.11.2019 | 31.09.2019 | 31.09.2019 | 31.03.2021 | 12.03.2021 | - | 66.56 | - | REC | 59.91 |  | - | -0.67 | -0.67 | Full |  |  |  | 2021000007 2021000006 | 202100047 202100080 | -
69 | P-19-02 | Yadadri Thermal Power (5x800MW) Evacuati | a)220KV TMDC line from proposed 400/220KV Damarcherla SS to 220KV Miryalaguda SS and bay extensions at Miryalaguda b)220KV SMDC line from proposed 400/220KV Damarcherla SS to 220KV Huzurnagar SS and bay extensions at Huzurnagar c)LILO of both circuits of 220KV Malkaram-Narketpally DC line to proposed 400/220/132 KV Choutuppal SS on MC towers d)132 KV DC line from proposed 400KV SS Choutuppal to 132 KV SS Choutuppal and 2 No.s 132 KV bays at 132/33 KV SS Choutuppal e)32kV DC line from proposed 400/220/132 KV Choutuppal SS to proposed 132 KV Dandumalkapur SS and 132 KV bay extension at 132 KV SS Dandumalkapur | GE | T.O.O.(CE-400kV) Ms.No.51 , Dt:10.10.2019 | - | Covered in 400KV | 15.11.2020 | 15.11.2020 | 31.03.2025 | a)Ckt-I charged on 29.08.2022 and Ckt-II charged on 29.12.2022 b)work in progress c)LILO of Ckt-I charged on 23.03.2023 and LILO of Ckt-II charged on 20.03.2023 d)work in progress | - | Covered in 400KV | - | PFC | 1102.26 |  | - | 4.64 | 51.25 | Full |  |  |  | 2023000000 2023000001 | 2023000963 2023000001 | -
Total | [17 empty] | 0 | 81.09 | 353.57
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please
1 | S-02-03 | EREC 132KV BAY AT NIRMAL-KHANPUR FEEDER | 132/33 kV substation at Khanapur along with connected line from Akkapur to proposed 132/33 kV Khanapur substation in Adilabad district | SI | T.O.O (CE-Construction) Ms. No. 277 Dated: 26.02.2009 |  | CRN:APT/TS/ 132/33kV SS / F.INVST - 37/2003 | 26.02.2009 | 15.05.2011 | 31.03.2013 | 09.09.2013 | - | 17.62 | TGTransco funds |  | 17.62 |  | - | 0.21 | 0.21 | Full | 32.5 | 16 | 1 | 2023001169 2024000384 2023001168 | 202001483 202001487 202001488
5 | S-10-02 | ERECTION OF 132/33 KV SS AT ASIFABAD IN | a)132/33 kV Substation at Asifabad with 2 x 16 MVA (Released) PTR Capacity (Radial) b)132kV DC/SC line from Sirpurkagaznagar 132/33 kV SS to the proposed 132/33 kV Asifabad Substation c)132 kV Bay extension at Sirpurkagaznagar 132 kV substation. | SI | T.O.O (CE-Construction) Ms. No. 267 Dated: 6.10.2010 |  | CRN.No.APT/TS/132 KVSS/ Asifabad/Invest.24/12 | 29.11.2012 | 01.01.2014 | 23.01.2016 | 25.11.2015 | - |  |  | REC | 18 |  | - | -0.06 | -0.06 | Full | 35 | 32 | 1 | yes | 202001547 202001550 202001552
6 | S-10-13 | Erection of 132/33KV LGMPET SS | a)132/33 kV Substation at LGM Pet with 1 x 31.5 + 1 x 16 MVA (Released) PTR Capacity Radial b)132kV DC/SC line from 220/132 kV Malkaram to the proposed 132/33 kV LGM Pet Substation c)132 kV Bay extension at 220/132 kV Malkaram substation. | SI | T.O.O (CE-Trans) Ms. No. 27 Dated: 17.02.2016 |  | APT/TS/132kv SS- LGM Peta/F-INVST-17/2012 | 31.06.2011 | 16.09.2011 | 31.03.2020 | 18.08.2016 | - | 31.9 |  | UCO Bank | 14.79 |  | 0.76 | 0.05 | 0.05 | Full | 19.581 | 47.5 | 2 | 2019000346 2019000397 2023000971 | 202000488 202000492 202000489
7 | S-10-18 | ERECTION OF 132/33 KV SUBSTATION AT RAI | a) 132/33 kV Substation at Raikal with 1 x 31.5 + 1 x 16 MVA (Released) PTR Capacity (Radial) b) 132kV DC/SC line from Jagityal 220/ 132 kV SS to the proposed 132/33 kV Raikal Substation c)32 kV Bay extension at Jagityal 220/ 132 kV SS No. | SI | T.O.O (CE-Construction-I) Ms. No. 394 Dated: 15.12.2010 |  | APT/TS/132 kV SS -Raikal/ F-INVST -20/2013 | 16.01.2012 | 17.10.2015 | 31.03.2017 | 07.09.2016 | - | 14.12 |  |  |  |  | - |  | -0.03 | Full | 14 | 47.5 | 1 | - | 202001249 202001252 202001254 202001257
8 | S-10-20 | 220KV SWG SS AT THIMJIPET & LINES | a)220 switching station at Thimmajipet. b)220 kV DC line from 400 kV Veltoor Sub-Station to the proposed 220 switching station at Thimmajipet. c)220 kV DC line from 400 kV Veltoor Sub-Station to the proposed 220 switching station at Thimmajipet. d)220 kV LILO line from 220 kV Bhoothpur-Kalwakurthy circuit –II to the proposed 220 switching station at Thimmajipet. | SI | T.O.O (CE-Construction) MS. No.319 Dated: 06.11.2010 |  | APT/TS/220 kV - SW.Stn / F-INVST - 2/2013 | 05.07.2013 | 30.09.2013 | 31.03.2020 | 07.06.2017 | - | 29.32 |  | PFC | 67.46 |  | - |  | 1.33 | Full | 94 | 0 | 8 | 2019000486 2019000487 2019000492 20190000488 2021000184 | 202100291 202000833 202100290 202000232 202100380
9 | S-10-23 | 132/33 KV SUBSTATION AT WATER WORKS | a)132/33 kV Substation at Water works in Karimnagar Town with 1 x 31.5 + 1 x 16 MVA (Released) PTR Capacity (Radial) b)132kV DC/SC line from Durshed 220/132 /33 kV SS to the proposed 132/33 kV Water works in Karimnagar Town Substation c)132 kV SC UG Cable to the proposed 132/33 kV Water works in Karimnagar Town Substation d)132 kV Bay extension at Durshed 220/132 /33 kV SS | SI | T.O.O (CE-Construction-I) Ms. No.185 Dated: 11.08.2011 |  |  | 10.05.2013 | 12.07.2013 | 11.04.2014 | 06.09.2014 | - | 47.5 |  | Oriental Bank of Commerce | 42.5 |  | 0.04 | 0 | 0 | Full | 7.5 | 47.5 | 1 | - | 202001260 202001262
10 | S-10-28 | 220KVsingle moose DC line from 400KV |  | SI | - |  | - | - | - | - | - | - | - | - | - | - | - | - | 0 | 0.01 | Full
11 | S-11-03 | 2ND CKT FROM BHEEMGAL SS TOSIRIKONDA SS | a)132 kV 2nd circuit stringing on existing 132 kV DC/SC line from 220 kV Bheemgal to 132 kV Sirikonda b)132 kV Bay extension at 132/33 kV Sirikonda substation. C)132 kV Bay extension at 220/132 kV Bheemgal substation. | SI | T.O.O (CE-Construction-I) MS. No. 357 Dated: 31.12.2011- |  |  | 31.12.2011 | 15.10.2012 | 31.05.2014 | 29.10.2014 | - | 2.9 | TGTransco funds |  | 2.9 |  | 0 | 0 | 0 | Full | 16.1 | - | 2 |  | 202000626 202000627
14 | S-11-21 | 132KV line Dharmapuri- Luxxettipet | a)132 kV DC/SC line from 132/33 kV Dharmapuri SS to 132/33 kV Luxxettipet SS b)132 kV bays at 132 /33 kV SS Dharmapuri and 132/33 kV SS Luxxettipet SS | SI | T.O.O (CE-Construction-I) MS. No. 251 Dated: 10.10.2011 |  | APT/TS/132 kV -DC/SC Line- Luxettipet-Dharmapuri/ F-INVST -13/2013 | 12.12.2014 | 12.12.2014 | 01.01.2016 | 12.12.2017 | - | 10.91 |  | PFC | 10.91 |  | - | 0.01 | 0.01 | Full | 25 | - | 1 | Yes | 202001271 202001273 202001274
15 | S-11-29 | 132/33 KV SUBSTATION AT PADMAJIWADi | a)132/33 kV Substation at Padmajiwadi with 1 x 31.5 + 1 x16 MVA PTR Capacity (LILO) b)132kV LILO line from 132 kV Dichpalli - Kamareddy to the proposed 132/33 kV Padmajiwadi Substation | SI | T.O.O (CE-Construction-I) Ms. No. 2 Dated: 6.04.2011 |  | - | 07.01.2013 | 29.02.2014 | 31.03.2014 | 29.03.2014 | - | 10.39 |  | REC | 7.79 |  | #REF! | -0.02 | -0.02 | Full | 2 | 47.5 | - |  | 202001002 202001004
16 | S-11-30 | 220KV SS at Parigi in RR District | a)220/132 kV Substation at Parigi with 2*100 MVA PTR’s Capacity with 4 Nos 132 KV out going feeder bays. B)220 kV DC line with single Moose conductor from 400/220 kV Yeddumailram Sub-Station to the proposed 220/132 KV Pargi SS. C)220KV Bay extensions at 400/220 kV Yeddumailram SS |  | T.O.O (CE-Construction–I) MS. No.180 Dated: 09.08.2011 |  | CRN:APT/TS/220/132kV Parigi/ F.INVST-1/2013 Dt:11.05.2012 | 09.08.2011 | 19.10.2013 | 31.03.2020 | 04.03.2016 | - | 60.35 |  | REC | 54.27 |  | 1.28 | 0.01 | 0.01 | Full | 110 | 200 | 2 | 2019000418 2019000420 2019000412 2019000419 | 202000500 202000501 202000502 202000503
17 | S-11-35 | Shifting of 132kV SS at Wadapally | a)132/33 kV SS Wadapally (NEW) and 132 kV LILO arrangements to 132/33 kV SS Wadapally (NEW) along with PLCC equipment b)132/33 kV Sub-Station at Wadapally with 1 X 31.5 +1 X 16 MVA PTRs With 7 Nos., 132 kV Incoming Feeder Bays, 4 Nos. 33 kV Feeders | SI | T.O.O (CE-Construction) Ms.No. 106 Dated:17 .06.2015 |  | Not Necessary | 22.04.2013 | 22.4.2013 | 2014-01-01 | 26.11.2016 | - | 4.99 |  | PFC | 4.4 |  | 0.87 | 0.07 | 0.07 | Full | - | 47.5 | - | 2021000070 2021000071 | 202001056 202001057
18 | S-12-05 | ERECTION OF 33KV FEATURES AT JANKAMPET | Providing 33 kV features at 132/11 kV Lift Irrigation substation at Jankampet in Nizamabad district with 2*16 MVA PTR Capacity | SI | T.O.O (CE-Construction-I) Ms. No. 283 Dated: 20.12.2012 |  | Not Necessary | 20.09.2016 | 01.11.2016 | 31.03.2020 | 16.02.2018 | - | 4.18 |  | REC | 3.5 |  | 0.46 | 0.04 | 0.04 | Full | 0 | 32 | 0 | 2019000254 2019000255 2019000140 2019000141 | 202000041 202000355 202001053 202001139
19 | S-12-06 | 2NDCkt 220KV LINE 220KV RSS -MANDAMARRI | a)2nd circuit stringing on existing 220 kV DC/SC line from 220 kV Ramagundam SS to 220 kV Mandamarri (Bellampally) SS b)220kV Bay Extensions at 220 kV Ramagundam & Mandamarri Sub-Stations. | SI | T.O.O (CE-Construction-I) MS. No. 261 Dated: 28.11.2012 |  | Not Necessary | 28.11.2012 | 06.10.2012 | 31.03.2020 | 20.10.2015 | - | 10.67 |  | REC | 9.6 |  | 0.21 | -0.01 | -0.01 | Full | 34 | -- | 2 |  | 202001290 202001292 202001722
21 | S-12-10 | MD Pally SS& LINE scheme | a)132/33 kV Sub-Station at Mylardevpally (Kattedan) with 2 X 50 MVA Power Transformer Capacity - Radial b)132 kV DC line with 630 Sq. MM XLPE UG Cable from 220/132/33 kV Sub-Station, Shivarampally to the proposed 132/33 kV Sub-Station Mylardevpally (Kattedan). c)132 kV Bay Extensions at 220 kV Sub-Station, Shivarampally.(2 No.s) | SI | T.O.O (CE-Construction) Ms.No.27 Dated: 12 .02.2015 |  | TST/TS/132kV / MD Pally, Kattedan /F-INVST- 03/2016 | 12.02.2015 | 05.08.2015 | 06.08.2016 | 25.09.2017 | - | 54.71 |  | PFC | 33.864 |  | 7.11 | 0.02 | 0.02 | Full | 7 | 100 | 4 | 2019000538 2019000539 | 202000282
22 | S-12-11 | 132/33 KV SUBSTATION AT MUNAGALA | a)132/33 kV Sub-Station at Munagala with 3 X 10/16 (Released) MVA PTRs b) 132 kV DC line (37 KM) from 400 kV Suryapet to existing 132 kV Kodada with 1 circuit LILO (6 KM) to the upcoming 132 kV Munagala SS. TOTAL 37 + 6 = 43 KM | SI | T.O.O (CE-Construction) Ms. No.127 Dated: 17.07.2015 |  | TST/TS/132/33kV SS Munagala / F-INVST- 13/2015 | 17.07.2015 | 20.06.2016 | 21.07.2016 | 22.12.2017 | - | 35.53 |  | REC | 30.95 |  | 28.83 | -0.01 | -0.01 | Full | 86 | 48 | 4 | 2020000551 2019000676 | 202001103
23 | S-13-02 | ERECTION 220/132KV SS AT AYYAGARIPALLY | a)220/132 Sub-Station at Ayyagaripally (Mahabubabad) in Warangal District with 2 X 100 MVA PTR Capacity, Double Bus, Arrangement, 5 Nos 220 kV Feeder Bays, 4 Nos. 132 kV Feeder Bays and Sub-Station Automation System b)220kV Line with Four (4) Circuits on Multi - Circuit Towers for LILO of both the Circuits of 220 kV Warangal - Boodidampadu DC Line at proposed 220 kV SS, Ayyagaripally (Mahabubabad) c)132kV DC/SC line from the proposed 220/132 kV SS,Ayyagaripally (Mahabubabad) to 132 kV SS, Nekkonda d)132 kV Bay extension at Nekkonda | SI | T.O.O (CE-Transmission)MS.No. 5 Dated:11.01.2016 |  | TST/TS / 220/132 kV SS Ayyagaripally, Mahabubabad /F-INVST- 03/16 - 2016-17 | 05.01.2016 | 02.03.2016 | 06.02.2017 | 29.01.2018 | - | 78.33 |  | REC | 68.9 |  | -0.03 | 1.91 | 1.91 | Full | 94 | 200 | 9 | 2019000282 2019000305 2019000306 2019000308 2019000519 2019000737 2020000597 2019000739 | 202001637 202000310 202001635 202000320 202000317 202000316 202000319 202000315
27 | S-14-02 | SURYAPET POWER TRANSMISSION SCHEME | a)LILO of one Circuit of Chillakallu – Narkatpally DC line to the proposed 400/220/132kV Suryapet Substation b)220kV DC Moose line to make LILO of (ckt-I&II) of 220kV Miryalaguda – Khammam at the proposed 400/220/132kV Suryapet SS c)132 KV DC line from 400/220/132kV Suryapet Substation to 132kV existing Suryapet Substation d)132 kV DC/SC line from 400/220/132kV Suryapet Substation to 132kV existing Shaligowraram Substation e)132 kV DC/SC line from 400/220/132kV Suryapet Substation to 132kV existing Thungathurthy SS | SI | T.O.O.(CE-Projects-I) Ms.No. 11, Date: 15.03.2016. |  | Covered in 400KV | 15.03.2016 | 15.03.2016 | 05.10.2018 | a) 21.12.2016 b)07.10.2016 c)06.12.2019 d)14.082017 e)06.08.2017 | - | Covered in 400KV |  | REC | 131.72 |  | -0.01 | 0.06 | 0.06 | Full | 181 | - | 4 | 2019000641 2019000640 2019000063 2019000062 2019000639 2019000638 | 202000634 202000636 202000641 202000661 202000663 202000842
29 | S-15-01 | Second source to 132KV SS LGMPET | a) 132 kV DC line on Galvanised Towers with Panther ACSR for making LILO of 132 kV Line from 220 kV Sub-Station, Medchal to 132 kV Sub-Station,Gajwel to 132/33 kV Sub-Station, Lalgadi Malakpet. b)132 kV Bays at 132/33 kV Sub-Station, Lalgadi Malakpet Villasge(2 No.s) | SI | T.O.O (CE-Construction) Ms. No. 54 Dated: 25.03.2015. |  | Not necessary | 19.08.2015 | 20.10.2015 | 31.10.2017 | 18.10.2019 | - | 7.31 |  | PFC | 6.2 |  | 10.17 | -0.03 | -0.03 | Full | 16 | - | 2 | 2020000010 2020000009 | 202001129 202001134 | Severe ROW issues. Some of the locations got completed with police protection.Additional towers erected due to ROW.
28 | S-14-12 | erec of132/33kV khaitlapur | a)132/33 kV Substation at Khaitalapur with 2 x 31.5 MVA PTR Capacity b)132kV DC XLPE (UG Cable) from 220/132kV Miyapur SS to the proposed 132/33kV Khaitalapur SS c)132 kV Bay extension at proposed 220/132 kV Miyapur SS(2 No.s) | SI | T.O.O (CE-Construction) Ms. No. 22 Dated: 10.09.2014 |  | CRN.No.TST/TS/132 KVSS -Khitlapur/R.R.Dist./Invest.App./04/2015 dt.09.2015 | 10.09.2014 | 04.07.2016 | 31.08.2020 | 27.08.2019 | - | 66.04 |  | REC | 59.09 |  | 55.56 | 5.9 | 5.9 | Full | 15 | 63 | 4 | 2020000006, 2020000007 2020000008 2021000240 2021000242 | 202000507 202000508 202000509 202100302 202100303
30 | S-15-09 | 132kV line G'pur- Imbn line to Nagole | 132 kV LILO line of 132KV Ghanapur - Imlibun DC line to the proposed 220/132/33 kV SS Nagole (Uppal) (0.2 KM OH + 1.6 KM UG cable ) | SI | T.O.O (CE-Construction) Ms. No 26 Dated: 12.02.2015 |  | Not necessary | 12.02.2015 | 16.03.2016 | 17.04.2017 | 21.09.2017 | - | 11.98 |  | REC | 10.77 |  |  | 0 | 0 | Full | 0.2 KM (OH) 1.6KM (UG cable) | - | - | 2019000514 | 202000624
31 | S-15-11 | 2nd220 KV RSS-NirmalDC/SCline&RSStoJGl | a)Stringing of 220 kV 2nd Circuit on existing 220 kV DC/SC line from 220 kV RSS to 220 kV Nirmal SS b)Stringing of 220 kV 2nd Circuiton existing 220kV DC/SC line from 220 kV RSS to 220 kV Jagityal SS c)220 kV Bays (RSS-2Nos, Nirmal-1 No, Jagityal-1 No.) | SI | T.O.O (CE-Construction) Ms. No.164 Dated: 06.11.2017 |  | CRN/TS/TST/220 KV2nd Ckt/RSS to Nirmal SS and RSS to Jagityal SS/Invst. App/No.15/2015,dt.17.12.15 | 06.11.2017 | 19.11.2016 | 31.03.2020 | N-30.12.2016 J-02.11.2016 | - | 46.4 |  | PFC | 38.06 |  | 18.87 | 0.48 | 0.48 | Full | 208 | __ | 4 | 2023001162 2023000538 | 202001323 202001326 202001334 202001338 202001345
32 | S-15-12 | 132/33 kV Sub-Station at Gandimasanipet | a)132/33 kV Sub-Station at Gandimasanipet of Yellareddy Constituency with 3 X 10/16 MVA PTRs (Released) b)132 kV DC line on Galvanised Towers with Panther ACSR for making LILO of 3rd circuit of 132 kV Minpur – Nizamsagar feeder at the proposed 132kV Sub-Station at Gandimasanipet of Yellareddy Constituency. | SI | T.O.O (CE-Transmission) MS.No. 179 Dated: 07.09.2015 |  | Not Necessary | 07.09.2015 | 11.11.2016 | 31.03.2018 | 29.12.2017 | - | 18 |  | PFC | 13.4 |  | 1.6 | 0 | 0 | Full | 12 | 48 | 2 | 2019000018 2019000019 | 202000638 202000639
39 | S-16-07 | 33KV Features at Exg 132KVSS KDNDPR NLG | 33 kV features at existing 132 kV Switching Station at Kodandapur with 2 X 31.5 MVA PTRS | SI | T.O.O (CE-Transmission) Ms. No.31, Dated: 18.02.2016 |  | Not necessary | 18.02.2016 | 20.08.2018 | 31.03.2020 | 25.03.2019 | - | 8.91 |  | REC | 8.01 |  | 0.54 | 0.01 | 0.01 | Full | -- | 63 | -- | 2019000336 | 202000879
46 | S-17-14 | 33 KV features at 220 KV SS Mahabubabad | Providing of 33 kV Features at upcoming 220/132KV Substation Mahabubabad, in Mahabubabad District with Released 2X10/16 MVA PTRs | SI | T.O.O (CE-Construction) Ms. No.170, Dated: 16.11.2017 |  | Not necessary | 16.11.2017 | 20.02.2020 | 19.08.2021 | 26.05.2021 | - | 8.54 |  | REC | 7.44 |  | 2.87 | 0.05 | 0.05 | Full | -- | 32 | -- | 2021000061 | 202200369
49 | S-17-23 | 132 KV feat at 220 KV Thimmajipet SS in | a)132 KV features at 220 kV Thimmajipet Switching Station with 2 X 100 MVA PTR Capacity. B)132 kV DC line on Galvanised Towers with Panther ACSR from the existing proposed 220/132 kV Thimmajipet Sub-Station, to the existing 132/33 kV Jadcherla Sub-Station. c)132 kV Bay extensions at 132/33 kV Sub-Station, Jadcherla( 2 No.s) | SI | T.O.O (CE-Construction) Ms. No. 103 Dated:11.07.2017 |  | CRN/TS/TST/220kV Switching Station/Mahaboobnagar/132kV features/Invest.Appl.No.14/17, 2017-18, Dt.Dec.2017. | 07.03.2020 | 07.03.2020 | 06.12.2020 | 22.07.2022 | - | 29.32 |  | REC | 26.39 |  | 7.34 | 1.28 | 0 | Full | 36 | -- | 2 | 2023001163 | 2023000825
61 | P-11-01 | PULICHINTALA HYDRO ELECTRIC PROJECT(4X30 | a) 220 kV DC Line from Pulichintala HES to the proposed 220 kV Sub-Station, Huzurnagar b)220 kV Bays at 220/132 kV Sub-Station, Huzurnagar | GE | T.O.O (CE-Construction-I) MS. No. 339 Dated:08.02.2013 |  | APT/TS/Pulichintala-Evac/F-INVST-02/2014 | 09.02.2014 | 09.02.2014 | 31.10.2015 | 31.03.2016 | - | [7 empty] | 0 | Full
66 | P-16-01 | Telangana STPP-I (2X800MW) Power Evacuat | a)LILO of both circuits of 220kV Durshed - Sircilla line to 400kV Ramadugu SS on Multi circuit towers b)LILO of 220kV Malyalpalli-Bheemgal at 400/220kV Ramadugu Sub-Station | GE | T.O.O.(CE-400kV) Ms.No.104 , Dt:12.07.2017 |  | Covered in 400KV | 13.08.2018 | 13.08.2018 | 31.03.2020 | a)03.03.2020 b)19.02.2021 | - | Covered in 400KV |  | REC | 1131.17 |  |  | 0.03 | 0.03 | Full |  |  |  | 2021000350 | 202001180 202001182

## DC works
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2026-27 for Transmission Business filed with TGERC
Scheme wise details of Actual Capitalisation for FY 2024-25
(Figures in Rs Crore)
[8 empty] | Work Period | [5 empty] | Source of Funds
Sl No. | Project Code (SAP Code) / Scheme IDs | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the Scheme) | Project Purpose (SI/SE/SR/GE) | Administrative approval no. with date | SRPC approval no with date (if any) | Investment Approval No. with Date | Start Date |  | Completion Date (Charging date) |  | Date of Capitalization | Approved Cost as per Investment Approval/Scheme cost | Transco Funds | Loan Source | Loan Amount | Grants, if any | Capitalisation Upto Previous Year (n-1) (as per Audited Financial Statements) | Capital Expenditure during the current year (2024-25) | Capitalisation claimed for the Current year (2024-25) | Whether Part Capitalization or Full Capitalisation | Lines (CKM) | PTR (MVA) | Bays (Nos) | Physical Completion Certificate Nos. | Financial Completion Certificate Nos. | Remarks / Reasons for Cost & Time overruns (if any)
[8 empty] | Schedule | Actual | Schedule | Actual
Brought Forward | [17 empty] | 0 | 81.09 | 353.57
1 | D-18-05 | shftng of lns B/w manoharbd-Kothapalli n | Shifting/Modification of 132 KV & 220KV lines between Manoharabad and Kothapalli Railway line in Siddipet District | DCW | - | - | - | 31.03.2018 | 01.05.2018 | 01.04.2019 | 02.07.2019 | - | 21.39 | - | Consumer contribution | - | - | - | 0 | 0 | Full | - | - | - |  |  | -
2 | D-18-10 | Divrsn of Gajwl-Kndapka etc Komrveli mal | i) Diversion of 220 KV Gajwel-Kondapaka and 220 KV Kamareddy-Kondapaka lines (b/w Loc.No.25/1 to Loc. No.25/15) and 132 KV Doulthabad –Gajwel DC/SC line(b/w Loc.No.62 to Loc.No.69) (7 KM including 1.5 KM Multi circuit towers)1.5 KM Multi circuit towers) (ii) Diversion of old 132 KV Siddipet –Gajwel DC line (13KM) in b/w Loc. No.203 & 227 which are falling under submeregence area of proposed Sri Komaravelli Mallanasagar Reservoir under DC works & (iii) Diversion of 132 KV line (3.5KM) from location no.11 to 25 of 400 KV SS Gajwel to 132 KV SS Thunikibollaram for Pranahita-Chevella Package -14 Kaleswaram LIS in Siddipet District. | DCW | - | - | - | 26.09.2018 | 26.09.2018 | 25.03.2019 | 09.12.2020 | - | 17.599 | - | Consumer contribution | - | - | - | 0.43 | 0.48 | Full | - | - | - | - | - | -
3 | D-18-12 | Extn of pwr sply 2 RTSS Manoharabad 4m N | Extension of 132 KV Power supply for a CMD of 10MVA to the proposed Railway Traction SS at Manoharabad (V), Toopran(M), Siddipet Circle in Medak District | DCW | - | - | - | 15.04.2019 | 15.04.2019 | 14.10.2019 | 25.11.2020 | - | 1.05 | - | Consumer contribution | - | - | - | 0 | 0 | Full | - | - | - | - | - | -
4 | D-18-13 | Pwr sply 2 132KV RTSS Divitipally(RVNL) | Pwr sply 2 132KV RTSS Divitipally(RVNL) | DCW | - | - | - | PO.Issued Dt:10.01.2019 DoH Bay-21.01.2020 Line- 29.04.2019 Metering Bay 28.09.2021 | - | Bay-20.10.2020 Line-28.01.2020 Metering Bay- 27.06.2022 | 22.07.2022 | - | 9.76 | - | Consumer contribution | - | - | - | 0.25 | 0.24 | Full | - | - | - | - | - | -
5 | D-18-15 | Extn of 132 KV lne 4 kamrdy 2 Tlamdla Ra | Extension of 132 KV Radial 2 –phase DC/SC line (8KM) from existing 220/132 KV SS Kamareddy to proposed 132/25 KV Talamadla Railway Traction Substation. | DCW | - | - | - | 24.03.2021 | 24.03.2021 | 23.12.2021 | 31.03.2023 | - | 14.55 | - | Consumer contribution | - | - | - | 1.13 | 1.15 | Full | - | - | - | - | - | -
6 | D-18-16 | Ere of Pwr sply 2 132/25 KV RTS Jankamp | Extension of power supply to proposed 132/25 KV Railway Traction Substation Jankampet by erection of 132 KV radial 2-phase DC/SC line (12KM from proposed 220/132 KV SS Renjal | DCW | - | - | - | 25.11.2020 Mbay- 07.10.2022 | 11.10.2022 | 21.11.2023 | 04.11.2024 | - | 19.05 | - | Consumer contribution | - | - | - | 2.86 | 14.04 | Full | - | - | - | - | - | -
7 | D-18-18 | Extn of 132 KV sply 2 RTSS at Wnaprthy 4 | Extension of 132 KV supply to railway traction SS at Wanaparthy from existing 132/11 KV Kothakota LIS in Mahaboobnagar District. | DCW | - | - | - | 06.01.2022 | 06.01.2022 | 05.01.2022 | 04.08.2023 | - | 15.6 | - | Consumer contribution | - | - | - | 0 | 0.04 | Full | - | - | - | - | - | -
8 | D-19-01 | Shftng of 132KV Erragadda-Shivarampally | Shifting of existing 132KV Erragadda – Shivarampally SC Feeder between Loc.No. 85 & 86 for GHMC under strategic road development programme Phase-III near Malkaram cheruvu | DCW | - | - | - | 07.03.2019 | 07.03.2019 | 06.09.2019 | 11.03.2020 | - | 0.94 | - | Consumer contribution | - | - | - | 0.08 | 0.08 | Full | - | - | - | - | - | -
9 | D-19-02 | Shift Gachibowli-Madapur-I&II DC lines b | Shifting of Gachibowli – madhapur – I & II DC lines crossing at Botonical Garden Junction Hyderabad | DCW | - | - | - | 29.11.2019 | 29.11.2019 | 28.05.2020 | 28.06.2022 | - | 13.02 | - | Consumer contribution | - | - | - | 0.79 | 0.96 | Full | - | - | - | - | - | -
10 | D-19-03 | Sft 220KV Gachibowli-S.nagar-Egadda line | Shifting of 220KV Gachibowli – Shapurnagar – Erragadda – DC line at Kothaguda Junction, Hyderabad under DC Works | DCW | - | - | - | 29.11.2019 | 29.11.2019 | 28.05.2020 | 31.08.2021 | - | 19.61 | - | Consumer contribution | - | - | - | 0.13 | 0.29 | Full | - | - | - | - | - | -
11 | D-19-04 | Sft 132KV lines 4m Roadno.45-Durgam Cher | Shifting of 132KV Jubilee Hills – Chandrayanagutta DC feeder and 132 KV Erragadda – Shivarampally SC feeder at 132KV SS Jubilee Hills for GHMC for construction of elevation corridor from road no.45 to Durgam Cheruvu under DC Work | DCW | - | - | - | 30.01.2019 | 22.03.2019 | 21.09.2019 | 13.06.2020 | - | 18.8 | - | Consumer contribution | - | - | - | 0.03 | 0.04 | Full | - | - | - | - | - | -
12 | D-20-01 | 132/33 KV SS at E-city Fabcity | 132/33KV Sub-station at Electronic Manufacturing Cluster at E-City Fabcity, (ii) 132 KV line from existing 220/132 KV Fabcity SS to proposed 132/33 KV E-City Fabcity SS for proposed 132/33 KV E-city Fabcity SS in Raviryal Village, Maheshwaram Mandal, Ranga Reddy District | DCW | - | - | - | 21.09.2020(SS & bays) | 21.09.2020(SS & bays) | 22.06.2021(SS & bays) | 16.09.2023 (SS) 31.08.2023(Bays) | - | 47.99 | - | Consumer contribution | - | - | - | 0.75 | 0.84 | Full | - | - | - | - | - | -
[5 empty] | - | - | - | 22.04.2021(Line) | 22.04.2021(Line) | 21.01.2022(Line) | 31.08.2023(Line) | - |  | - | Consumer contribution | - | - | - |  |  | Full | - | - | - | - | - | -
13 | D-20-02 | Extension of 132KV supply to RTSS Manopa | i) 1 No.132 KV bay at existing 132/33 KV Alampur SS for 132 KV RTSS Manopad, (ii) 132 KV DC/SC line from existing 132/33 KV Alampur SS to proposed RTSS Manopad for a length of about 12 KM in Jogulamba District (iii) 1 No.132 KV metering bay at proposed 132 KV RTSS Manopad in Jogulamba District | DCW | - | - | - | 25.01.2023 | 12.02.2023 | 24.02.2024 | 19.06.2024 | - | 8.85 | - | Consumer contribution | - | - | - | 2.38 | 11.13 | Full | - | - | - | - | - | -
13 | D-20-06 | 132 KV DC/SC lne 4m 132/33 KV SS Morthad | (i) Extension of 132 KV radial 2-phase DC/SC line (0.5 KM) from existing 132/33 KV SS Morthad to proposed 132/25 KV Morthad Railway traction substation (CMD of 10 MVA) (ii) 1 No.132 KV Bay extension at 132/33 KV SS Morthad and (iii)1 No.132 KV bay along with metering bay at proposed 132/25KV Morthad Railway Traction Substation in Nizamabad Dsitrict | DCW | - | - | - | 15.04.2021 | 15.04.2021 | 14.01.2021 | 29.04.2022 | - | 5.81 | - | Consumer contribution | - | - | - | -0.01 | 0 | Full | - | - | - | - | - | -
14 | D-21-24 | 132kV DC.SC line Ganganpally-RTSS Pandur | (i) Erection of 2Nos 132kV bays at 132/33kV Ganganpally SS (a) for 132kV Pandurangaswamy road RTSS and (b) for 2nd circuit stringinging from 220kV Jurala SS in 132/33kV Ganganpally SS in Jogulamba Dist.Gadwal(Jogulamba) District. (ii) Erection of 132kV DC/SC line to existing 132/33kV Ganganpally SS to proposed RTSS Pandurangaswamy road in Gadwal(Jogulamba) Dist. (iii) Erection of 1No. 132kV Bay at 220/132kV Jurala SS for 132kV Ganganpally SS. (iv) stringing of 2nd circuit from 220/132kV Jurala SS to | DCW | - | - | - | P.O.:11.10.2021 DOH: Bays and 132KV Line 29.09.2021. 2nd Ckt: profile:11.10.2021 | __ | 10.04.2022 | 132kV Line: 28.10.2022 2nd Ckt 10.04.2023 | - | 14.55 | - | Consumer contribution | - | - | - | 0.67 | 1.08 | Full | - | - | - | - | - | -
15 | D-21-27 | Data centres at TSIIC -M/s.Amazon | a) 220KV MC/DC line from 220/132 KV Fabcity SS to the proposed site of M/s.Amazon Data Services India Pvt Ltd.at TSIIC industrial park Fabcity(2.5Kms) b) 2 no.s 220KV feeder bays at 220/132KV Fabcity SS c) 2 No.s 220KV bays at Amazon SS | DCW | - | - | - | 14.10.2021(bays at Fabcity end) 11.10.2021(line) 14.10.2021(Bays at Amazon end) | 14.10.2021(bays at Fabcity end) 11.10.2021(line) 14.10.2021(Bays at Amazon end) | 13.07.2022 10.07.2022 13.07.2022 | 28.06.2023 28.06.2023 13.07.2023 | - |  | - | Consumer contribution | - | - | - | 6.8 | 3.67 | Full | - | - | - | - | - | -
|  |  | (a) 2 No.s single circuits with 220KV XLPE UG cable 1000 Sq.mm from 400/220 KV Maheshwaram SS to 220KV Amazon SS (b) 2 No.s 220KV bays at 400/220KV SS Maheshwaram (c) 2 No.s 220KV Bays at Amazon | DCW | - | - | - | 23.11.2021(bays at maheshwaram end) 06.01.2022 (Line) 14.10.2021(Bays at Amazon end) | 23.11.2021(bays at maheshwaram end) 06.01.2022 (Line) 14.10.2021(Bays at Amazon end) | 22.08.2022 05.10.2022 13.07.2023 | 18.08.2023 18.08.2023 16.09.2023 | - | 40.49 | - | Consumer contribution | - | - | - |  |  | Full | - | - | - | - | - | -
17 | D-21-30 | Industrial park at Chandanavally(V), Sha | (i) 220/132/33 KV at Chandanavally (ii) 220Kv TMDC line from 400/220KV Kethireddypally SS to proposed 220KV Chandanavally (TSIIC) for a length of 12.663 KM (4.663 KM) on 400KV Quad moose MC towers + 8.0 KM on 220KV TMDC towers instead of 220KV SMDC line on normal 220KV DC towers (iii) 2 no.s 220KV feeder bays at 400/220KV Kethireddypally SS for proposed 220KV Chandanavally SS, Shabad Mandal in Ranga Reddy District. | DCW | - | - | - | SS-14.10.2021 Line-25.10.2021 Bays-23.11.2021 | SS-12.12.2021 Line-14.12.2021 Bays-10.01.2022 | SS-12.10.2022 Line-22.10.2022 Bays-01.01.023 | SS-16.01.2023 Line-13.01.2023 Bays-10.01.2023 | - | - | - | Consumer contribution | - | - | - | 4.41 | 6.5 | Full | - | - | - |  |  | -
18 | D-21-38 | Jadcherla 2 boothpur SC line in Mbnr Dis | Shifting of existing 132 KV SC line (9KM) with INVAR HTLS conductor between loc.no.494 and loc.no.521 of 132/33 KV Jadcherla SS to 220/132 KV Boothpur SC line in Mahabubnagar Dist. | DCW | - | - | - | 22.12.2021 | 22.12.2021 | 21.09.2022 | 02.07.2023 | - | 11.7 | - | Consumer contribution | - | - | - | -0.58 | 0.15 | Full | - | - | - | - | - | -
19 | D-21-48 | M/s.Kitex Garments Limited | Extension of power supply to M/s. Kitex Garments Limited- Erection of (i) 132 KV DC line (3.2 KM) from proposed 220/132/33 KV SS at Kakatiya Mega Textile Park(KMTP) to M/s.Kitex Garments Limited proposed to establish at KMTP(ii) 2 No.s 132 KV bays at proposed 220/132/33 KV KMTP (iii) 2 No.s 132 KV metering bay extensions at M/s.Kitex Garments Limited in Warangal District. | DCW | - | - | - | 17.11.2022 | 17.11.2022 | 16.05.2023 | Work in progress | - | 19.99 | - | Consumer contribution | - | - | - | 3.9 | 3.51 | Full | - | - | - | - | - | -
20 | D-21-50 | M/s.BEL- 132 KV Yacharam- Ibrahimpatnam- | Diversion of 132 KV Yacharam-Ibrahimpatnam-Bongulur SC line from Loc.No.367 to 372 and LILO Loc No.s 370/1 to 370/3 of Ibrahimpatnam DC line passing through M/s.BEL’s land located at Sy.No.s 254 to 256 of Ibrahimpatnam Khalan Village, Ibrahimpatnam Mandal, Ranga Reddy District | DCW | - | - | - | 25.11.2022 | 25.11.2022 | 10.04.2023 | 11.05.2023 | - | 8.88 | - | Consumer contribution | - | - | - | 0.04 | 0.03 | Full | - | - | - | - | - | -
21 | D-22-01 | 132/33 KV SS Chandrugonda-Railway Tracti | Extending power supply at 132KV level to the proposed 132/25KV Railway Traction Sub-station at 132/33 KV SS Chandrugonda in Khammam District. | DCW | - | - | - | 11.01.2023 | 11.01.2023 | 10.10.2023 | work in progress | - | 20.7 | - | Consumer contribution | - | - | - | 1.63 | 6.74 | Full | - | - | - | - | - | -
22 | D-22-06 | Shiftng of Shivarampally-Gachibowli -Gir | Shifting of existing 220KV Shivarampally-Gachibowli DC line between Loc.No.66 to Loc.No.68 & 132 KV Chandrayanagutta-Jubilee Hills DC line bbetween Loc.No.86 to Loc.No.89 for M/s.Giridhari | DCW | - | - | - | Supervision work |  |  | 31.12.2022 | - | 1.22 | - | Consumer contribution | - | - | - | - | 0.01 |  | - | - | - | - | - | -
23 | D-22-14 | 132 KV DC lne 4m 132/33 KV Makthal SS 2 | (i) 132 KV DC line (10.00 KM) from existing 132/33 KV Makthal SS to proposed 132/25KV Makthal Railway Traction substation (CMD of 10MVA) ii) 2 No.s 132 KV bays extension at 132/33 KV SS Makthal and (iii) 2 No.s 132 KV bays along with Metering arrangement at proposed 132/25KV Makthal Railway Traction Substation in Mahabubnagar District | DCW | - | - | - | 07.08.2023 | 10.01.2024 | 15.08.2024 | 04.02.2025 | - | 66.14 | - | Consumer contribution | - | - | - | 5.84 | 18.79 | Full | - | - | - | - | - | -
24 | D-22-18 | 132kV SS Ester Film Tech Ltd-220/132 KV | Extension of 132 KV supply for a CMD of 22.5MVA in a phased manner to M/s.Ester Film Tech Limited, Chandanvally, Shabad,Mandal, Rangareddy District | DCW | - | - | - | Supervision work |  |  | 18.01.2023 | - | 2.49 | - | Consumer contribution | - | - | - | 0.21 | 0.21 | Full | - | - | - | - | - | -
25 | D-23-08 | M/s.Microsoft Corporation (India)-Chanda | Extension of HT supply for a CMD of 163MVA in phased manner with an initial load of 17MVA to M/s. Microsoft corporation (india) Pvt Ltd, Plot.No.10, Nagarguda, Shamshabad Road, Hayathabad, Chandanvally(V), Shabad (M), R.R Dist., | DCW | - | - | - | Supervision work |  |  | 26.09.2024 | - | 10.9 | - | Consumer contribution | - | - | - | -0.25 | 0.17 | Full | - | - | - | - | - | -
26 | D-23-19 | Shifting of 132/33 KV Kodad SS for road | Shifting of existing 132/33KV Kodad Substation for road widening of Kodad-Khammam section of NH-365 in Suryapet District Kodada | DCW | - | - | - | Supervision work |  |  | 28.03.2024 | - | 0.62 |  | Consumer contribution |  |  | - | 0.17 | 0.17 | [6 empty] | -
27 | D-23-98 | Shifting of EHT lines under DC works-220 | Shifting of EHT lines under DC works-220 | DCW | - | - | - | Supervision work |  |  | - | - | - |  | Consumer contribution |  |  | - | 0.01 | 0.01 | [6 empty] | -
28 | D-24-03 | Extn.of HT sply -load 80MW to M/s.VITP | Extension of HT supply for a load of 80 MW at 220KV Voltage level to M/s.VITP Pvt. Ltd. at Plot No.17, Survey No. 64/2, Software Units Layout, Madhapur | DCW | - | - | - | Supervision work |  |  | 31.12.2025 | - | 1.99 |  | Consumer contribution |  |  | - | 1.99 | 0.99 | [6 empty] | -
29 | L-12-02 | 2Nos 132kV Bays at Jaipur for SCCL | i) 220 KV LILO (10.80 KM) line from existing 2nd circuit of 220KV RSS-Nagaram DC line to M/s Ramgundam Fertilizers & Chemicals Ltd. (RFCL), Ramgundam ii) 2 Nos. 220 KV Bays along with Metering Arrangements at RFCL, Ramgundam on Turnkey Basis in Peddapally District | DCW | - | - | - | 10.01.2024 | 10.01.2024 | 09.10.2024 | 09.04.2015 | - | 17.34 | - | Consumer contribution | - | - | - | 0.67 | 0.72 | Full | - | - | - | - | - | -
[18 empty] | 0 | 115.42 | 425.61
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please
1 | D-13-02 | SWICHYARDSTATION NTPC SOLAR EVACUATION | i) 132 KV switching station for evacuation of power from Solar Power plant at NTPC Ramagundam (ii) 132 KV LILO line from 132 KV RTS-B-Kalwasrirampur line (0.7KM) to proposed 132 KV switching station at NTPC | DCW | - | - | - | 01.09.2012 | 07.08.2014 | 13.05.2015 | 05.05.2016 | - | 10.17 | - | Consumer contribution | - | - | 0.2 | 0 | 0 | Full | - | - | - | - | - | -
2 | D-16-09 | DCW-132KV DC LINE 132KV MATTAMPALLI TO R | 132 KV DC line from Mattampally to RTSS and 2 no.s 132 KV bay extensions at Mattampally | DCW | - | - | - | 18.11.2016 | 15.12.2016 | 14.05.2017 | 22.09.2017 | - | 6.79 | - | Consumer contribution | - | - | 0.35 | 0 | 0 | Full | - | - | - | - | - | -
3 | D-17-06 | 220 KV LILO 4m RSS-Nagaram DC lne 2 M/s | 220 KV LILO (10.80 KM) line from existing 2nd circuit of 220KV RSS-Nagaram DC line to M/s Ramgundam Fertilizers & Chemicals Ltd. (RFCL), Ramgundam ii) 2 Nos. 220 KV Bays along with Metering Arrangements at RFCL, Ramgundam on Turnkey Basis in Peddapally District | DCW | - | - | - | 06.12.2017 | 06.12.2017 | 05.06.2018 | 10.04.2019 | - |  | - | Consumer contribution | - | - | 1.25 | 0.02 | 0.02 | Full | - | - | - | - | - | -
4 | D-17-11 | 132 KV lne 4m Miryalaguda to RTSS and cn | i) 132 KV DC/SC line from 220/132/33 KV Miryalaguda SS to 132/33 KV RTSS Miryalaguda and connected bays in Nalgonda District & for supply, erection, testing & commissioning of 132KV DC/SC line from 132/33 KV Ramannapet SS to Ramannapet RTSS (2.2 KM) and connected bays in Yadadri-Bhongiri District. | DCW | - | - | - | 02.06.2018 (Miryalaguda line) | 02.06.2018 (Miryalaguda line) | 01.12.2018 (Miryalaguda line) | 27.09.2019 | - | 8.374 | - | Consumer contribution | - | - | 5.11 | 0 | 0 | Full | - | - | - | - | - | -
5 | D-18-05
6 | D-20-10 | Extn.of cntrl room bal wrks at 220 KV S | 50MW Solar Power Projects of M/s. Suraj Kiran Renewable Resources Pvt Ltd (SPV of M/s. Sky Power Southeast Asia III Investments Limited) near Mansing Tanda with interconnecting substation at 220/132 KV SS KM Pally in Nalgonda District- Extension of control room and other balance works at 220/132 KV SS KM Pally in Nalgonda District. | DCW | - | - | - | Pertains to CE/Civil wing |  |  |  | - |  | - | Consumer contribution | - | - |  | 0.14 | 0.14 | Full | - | - | - | - | - | -
7 | D-21-18 | Shiftng 220KV Miryalaguda-KTPS SC lne at | Shifting of 220KV Miryalaguda-KTPS SC line at Loc.No.537-538 at Railway Track crossing at Kukkadam Village under DC works on turnkey basis in Nalgonda District | DCW | - | - | - | Payment not yet received |  |  |  | - | 1.61 | - | Consumer contribution | - | - | 0.81 | 0.02 | 0.02 | Full | - | - | - | - | - | -
8 | D-21-37 | shiftng lne of Regumanugadda-Wanapthy(An | Shifting of 1 No.220KV DC line of Regumanugadda-Wanaparthy & Singotam of length 2KM with ACSR Moose conductor in Kollapur Mandal (Total Length : 5km) due to submerging in Anjangiri proposed package -3 canal in Nagarkurnool District. | DCW | - | - | - | 22.12.2021 | 22.12.2021 | 21.09.2022 | 19.08.2022 & 26.08.2022 | - | 9.56 | - | Consumer contribution | - | - | 7.35 | 0.31 | 0.31 | Full | - | - | - | - | - | -

## Non-Plan works
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2024-25 for Transmission Business filed with TGERC
Scheme wise details of Actual Capitalisation for FY 2023-24
(Figures in Rs Crore)
[8 empty] | Work Period | [5 empty] | Source of Funds | [7 empty] | Additions to Network
Sl No. | Project Code (SAP Code) / Scheme IDs | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the Scheme) | Project Purpose (SI/SE/SR/GE) | Administrative approval no. with date | SRPC approval no with date (if any) | Investment Approval No. with Date | Start Date |  | Completion Date (Charging date) |  | Date of Capitalization | Approved Cost as per Investment Approval/Scheme cost | Transco Funds | Loan Source | Loan Amount | Grants, if any | Capitalisation Upto Previous Year (n-1) (as per Audited Financial Statements) | Capital Expenditure during the current year (2024-25) | Capitalisation claimed for the Current year (2024-25) | Whether Part Capitalization or Full Capitalisation | Sub-stations (Nos) | Lines (CKM) | PTR (MVA) | Bays (Nos) | Physical Completion Certificate Nos. | Financial Completion Certificate Nos. | Remarks / Reasons for Cost & Time overruns (if any)
[8 empty] | Schedule | Actual | Schedule | Actual
|  | Brought Forward | [16 empty] | 115.42 | 425.61
1 | N-18-01 | Other Non Planned Project Str 2018-19 | [15 empty] | - | -0.02 | 0 | Full
3 | N-20-01 | Non Planned Capital works for FY 2020-21 | [15 empty] | - | 0.17 | 0 | Full
4 | N-21-01 | Non Planned Capital works for FY 2021-22 | [15 empty] | - | 0.01 | 0.47 | Full
5 | N-22-01 | Non Planned Capital works for FY 2022-23 | [15 empty] | - | 4.3 | 2.91 | Full
6 | N-23-01 | Non Planned Capital works for FY 2023-24 | [15 empty] | - | 2.33 | 2.03 | Full
7 | N-24-01 | Non Planned Capital works for FY 2024-25 | [15 empty] | - | 1.92 | 0.47 | Full
Total | [18 empty] | 124.13 | 431.49
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please