## Capex 25-26
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2026-27 for Transmission Business filed with TGERC
Scheme wise details of Capital Expenditure proposed for Financial Year 2025-26
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme maybe given) | Justification | Project Purpose (SI/SE/SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total TGERC approved Cost (in Cr)/Scheme Cost | Source of funds |  |  |  | Proposed Project Start Date DD-MM-YY | Proposed Project Completion Date DD-MM-YY | DOC | Estimated Yearly Capital Expenditure proposed (in Cr) | [7 empty] | Present Status of work | Whether included in resource plan or not
[10 empty] | TGTransco funds | Loan source | Loan Amount | Grants, if any |  |  |  | CWIP O.B. | Expenditure incurred from 01.04.25 to 30.09.25 | Expenditure Projected from 01.10.2025 to 31.03.2026 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | Totals
On going works
1 | S-07-04 | TWIN CITIES TRANSMISSION SYSTEM | The details are enclosed in the annexure | In order to cope up with the load growth in the twin cities and to provide quality power supply | SI | TOO (CE-Construction) MS NO.379, Dt:17.01.2012 | - | - | 1410 | - | JICA | 1200 | - | 01.08.2014 | 31.03.2026 | The charging details are enclosed in Annexure-I | 0.01 | 1.2 | 0.15 | 1.36
2 | S-08-11 | 132 KV Mamidipally SS with connected line | a)132/33 kV Substation at Mamidipally with 1x31.5 + 1x50 MVA PTR Capacity (Radial) b))220 kV DC line from proposed 132/33 kV Mamidipally substation up to Loc.No.12 of 220 kV line to the proposed 220/132 kV Fab city from 400/220 kV Mamidipally substation with narrow based towers. c)220 kV 2 circuits(3rd & 4th circuit) stringing from Loc. No. 12 on the existing narrow based M/C towers up to 220/132 kV Fab city on the 220 kV DC line from 400/220 kV Mamidipally substation to 220/132 kV Fab city( circuit 1 & 2 are already covered under Fab city line) d)132 kV Bay extension | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Transmission) Ms. No. 59 Dated:19.04.2016 | - | APT/TS/132 kV SS-Mamidipalli/ F-INVST - 12/2013 | 21.92 | - | PFC | 19.72 | - | 26.06.2009 | 31.03.2026 | 31.03.2016 | 0 | 0.04 | 0.01 | 0.05
3 | S-10-20 | 220KV SWG SS AT THIMJIPET & LINES | a)220 switching station at Thimmajipet. b)220 kV DC line from 400 kV Veltoor Sub-Station to the proposed 220 switching station at Thimmajipet. c)220 kV DC line from 400 kV Veltoor Sub-Station to the proposed 220 switching station at Thimmajipet. d)220 kV LILO line from 220 kV Bhoothpur-Kalwakurthy circuit –II to the proposed 220 switching station at Thimmajipet. | For system strengthening in addition to the already approved System Improvement / Evacuation schemes under Comprehensive Transmission Requirement Scheme for the Years 2012 – 2017 | SI | T.O.O (CE-Construction) MS. No.319 Dated: 06.11.2010 | - | APT/TS/220 kV - SW.Stn / F-INVST - 2/2013 | 74.76 | - | PFC | 67.46 | - | 30.09.2013 | 31.03.2026 | 01.03.2016 | 0.17 | -0.03 | -0.01 | 0.13
4 | S-11-06 | 2ND CIRCUIT FROM 132KV SHALIGOURARAM SS | a)Erection of 2nd circuit stringing from 132 kV Shaligouraram SS to new Aitipamula 132 kV SS. B)132 kV Bay extensions at 132 kV Shaligowraram SS and new Atipamula 132 kV SS (2 no.s) | To meet (n-1) contingency | SI | T.O.O (CE-Construction-I) MS. No. 447 Dated: 21.01.2011 | - | Not Necessary | 3.66 | - | UCO Bank | 2.34 | - | 22.02.2012 | 31.03.2026 | 27.02.2013 | 0 | 0.07 | 0.05 | 0.12
5 | S-11-11 | 132KV parigi dmsagar line | a)132 kV DC line from the proposed 220/132/33 kV SS Parigi to 132/33 kV SS Dharmasagar b)132 kV Bay extension 2 Nos. at 220/132/33 kV SS Parigi and 2 Nos. at 132/33 kV SS Dharmasagar | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Construction) MS.No .82 Dated:18.04.2018 | - | CRN.No.TST/TS132 kV SSt Donthanpalli/F-INVST-06/2013/Dt:08.10.2014 | 32.15 | - | REC | 19.26 | - | 13.12.2016 | 31.03.2026 | Work in Progress | 21.36 | 0.41 | 0.05 | 21.82
6 | S-11-18 | 132/33 KV SS Kamanpur | a)132/33 kV Substation at Kamanpur with 2 x 16 MVA (Released) PTR Capacity (Radial)) b)Erection of 132kV DC/SC line with multi circuit towers from Manthani 220 kV SS upto 9.5KM (AP 31) to accommodate both 132kV DC/SC line to Kamanpur SS & 132 kV LILO line from 132kV RSS - Kamalapur line(Stringing one circuit )(9.5KM) c)Erection of 132 kV DC/SC line (normal towers) from Loc. No. 31(end of multi circuit towers) to proposed 132 kV Kamanpur SS (13.9KM) d)132 kV Bay extension at Manthani 220/132 kV Substation (1No.) | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Construction) Ms. No.3 ,Dated: 27.06.2014 | - | APT/TS/132 kV SS -Kamanpur/ F-INVST -19/2013 | 22.32 | - | PFC | 15.53 | - | 16.07.2014 | 31.03.2026 | 05.10.2016 | - | 0.58 | 0.27 | 0.85
7 | S-11-28 | 132/33 KV SS At NIMMAPALLI | a)132/33 kV Sub-Station at Nimmapally with 2X10/16 MVA (Released) PTRs b) 132 kV DC / SC line with Panther ACSR Conductor on Galvanised Towers from the proposed 220/132 kV SS, Sircilla to proposed 132/33 kV Sub-station at Nimmapally. | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | TOO (CE-Transmission) MS.NO.161 dt:26-08-2015 | - | Not necessary | 19.7 | - | REC | 17.73 | - | 23.03.2018 | 31.03.2026 | 29.04.2021 | 0.05 | -0.0066585 | 0.02 | 0.063341
8 | S-11-30 | 220KV SS AT PARIGI IN RR DISTRICT | a)220/132 kV Substation at Parigi with 2*100 MVA PTR’s Capacity with 4 Nos 132 KV out going feeder bays. B)220 kV DC line with single Moose conductor from 400/220 kV Yeddumailram Sub-Station to the proposed 220/132 KV Pargi SS. C)220KV Bay extensions at 400/220 kV Yeddumailram SS | To meet the industrial load growth and reliable power supply for proposed industries | SI | T.O.O (CE-Construction–I) MS. No.180 Dated: 09.08.2011 | - | CRN:APT/TS/220/132kV Parigi/ F.INVST-1/2013 Dt:11.05.2012 | 60.35 | - | REC | 54.27 | - | 09.08.2011 | 31.03.2026 | 04.03.2016 | - | 0.1 | 0.02 | 0.12
9 | S-12-09 | 132KV DC/SC LINE YDMLRM-PMAILARAM | a) 132 kV DC/SC line with narrow based towers from 220 kV Yeddumailaram SS to 132 kV Pashamailaram SS b)132 kV Bay extension at 220 kV Yeddumailaram SS and 132 kV Pashamailaram SS | For strengthening of 132 kV system | SI | T.O.O (CE-Construction-I) MS. No. 61 Dated: 25.05.2012 | - | APT/TS/132/Yeddumailram/F-INVST-27/2013 | 9.31 | - | NABARD | 9.22 | - | 09.05.2019 | 31.03.2026 | 27.09.2022 | 0.02 | -0.01 | 0.01 | 0.02
10 | S-13-10 | ERECTION OF 132/33KV SS AT KACHAPUR | a)132/33 kV Substation at Kachapur with 3 x 10/16 MVA (Released) PTR Capacity (Radial)) b)132 kV DC/SC line from proposed 220/132 kV Huzurabad LIS substation to the proposed 132/33 kV Kachapur substation c)132 kV Bay extension at proposed 220/132 kV Huzurabad | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Transmission) Ms.No.193 Dated:07.10.2015 | - | TST/TS/132kV / Kachapur SS/F-INVST- 17/2016 | 21.53 | - | REC | 20.28 | - | 22.09.2015 | 31.03.2026 | 04.05.2018 | 0 | 0 | 0 | 0
11 | S-13-11 | 132 KV KANDUKURU SS & LINE FROM FABCITY | a)132/33 kV Substation at Kandukuru with 1x31.5 + 1 x 16 MVA(Released) PTR Capacity (Radial)) b)132 kV DC/SC line from proposed 220/132 kV Fab city substation to the proposed 132/33 kV Kandukuru substation on narrow based towers c)132 kV DC/SC line from proposed 220/132 kV Fab city substation to the proposed 132/33 kV Kandukuru substation on normal towers d)132 kV Bay extension at proposed 220/132 kV Fabcity substation | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Construction-I) Ms.No. 347 Dated: 13.02.2013 | - | TST/TS/132 kV SS-Kandukuru/ F-INVST-05/2015 | 22.75 | - | REC | 20.0578 | - | 09.09.2016 | 31.03.2026 | Ckt-II charged on 14.08.2025 & SS Work in Progress | 27.75 | 1.09 | 2.5 | 31.34
12 | S-14-02 | SURYAPET POWER TRANSMISSION SCHEME | a)LILO of one Circuit of Chillakallu – Narkatpally DC line to the proposed 400/220/132kV Suryapet Substation b)220kV DC Moose line to make LILO of (ckt-I&II) of 220kV Miryalaguda – Khammam at the proposed 400/220/132kV Suryapet SS c)132 KV DC line from 400/220/132kV Suryapet Substation to 132kV existing Suryapet Substation d)132 kV DC/SC line from 400/220/132kV Suryapet Substation to 132kV existing Shaligowraram Substation e)132 kV DC/SC line from 400/220/132kV Suryapet Substation to 132kV existing Thungathurthy SS | Covered in 400KV scheme | SI | T.O.O.(CE-Projects-I) Ms.No. 11, Date: 15.03.2016. | - | Covered in 400KV |  | - | REC | 131.72 | - | 15.03.2016 | 31.03.2026 | a) 21.12.2016 b)07.10.2016 c)06.12.2019 d)14.082017 e)06.08.2017 | 0 | 0.05 | 0.01 | 0.06
13 | S-14-12 | 132/33kV Khaitlapur | a)132/33 kV Substation at Khaitalapur with 2 x 31.5 MVA PTR Capacity b)132kV DC XLPE (UG Cable) from 220/132kV Miyapur SS to the proposed 132/33kV Khaitalapur SS c)132 kV Bay extension at proposed 220/132 kV Miyapur SS(2 No.s) | To meet the load demands of Kukatpally , Miyapur & industrial areas and also in view of multiple load growth with Commercial complexes coming up in the area | SI | T.O.O (CE-Construction) Ms. No. 22 Dated: 10.09.2014 | - | CRN.No.TST/TS/132 KVSS -Khitlapur/R.R.Dist./Invest.App./04/2015 dt.09.2015 | 66.04 | - | REC | 59.09 | - | 05.07.2016 | 31.03.2026 | 27.08.2019 | -0.05 | 0.06 | 0.01 | 0.02
14 | S-15-07 | 2NDCKT 220/132KVKAMAREDDY SS- DOMAKONDA | stringing of 2nd circuit from 220/132 KV Kamareddy SS to 132 KVSS Domakonda and from 132 KVSS Domakonda to 132 KVSS Biknur under the program for providing 9.00 Hrs Day Time Supply for Agriculture | To overcome the over loading on existing 220/132 kVSS Kamareddy-132/33 kVSS Domakonda line and 132 kV Domakonda - Yellareddypet, it is proposed to provide alternate source of supply to 132 kV SS Domakonda under the program of providing 9 Hrs supply during day time for Agriculture | SI | T.O.O (CE-Transmission) MS.No.162 Dated:26.08.2015 | - | Not necessary | 8.55 | - | PFC | 7.21 | - | 15.10.2024 | 31.03.2026 | a) 21.05.2025 b)Work cancelled c)26.09.2025 | 2.53 | 0.29 | 0.55 | 3.37
15 | S-15-13 | 765kVWardha-HYD Link transmision Scheme | The details are enclosed in the Annexure | Covered in 400KV scheme | SI | T.O.O.(CE-400kV) Ms.No.105 Dt:15.07.2017 | - | Covered in 400KV |  | - | PFC | 937.63 +139.49 | - | 25.01.2018 | 31.03.2026 | The charging details are enclosed in Annexure | 0.19 | 0 | 0.053289 | 0.24329
16 | S-15-31 | 2nd Ckt 220KV SRMP to 132kv ASFNGR & Con | a)2nd circuit from 220kV SS Shivarampally to 132kV SS Asifnagar by laying 220kV XLPE UG Cable b)132 kV Bay extension at 220 kV Shivarampally substation. c)132 kV Bay extension at 132 kV Asifnagar substation. | The 132kV Asifnagar substation is an important substation located in the middle of the city feeding the VIP areas and Old city. As there is no alternative source, it is becoming very difficult to maintain normalcy during incoming supply outages and also to carryout general maintenance works of the feeder at both ends. To have reliable power supply to this substation another source is necessary | SI | T.O.O (CE-Construction-I) MS. No. 55 , Dated: 25 .03 .2015 | - | CRN.No.TST/TS Asifnagar SS alternatesource of supply/Invest.App.06/2015, dt.05.10.2015 | 45.97 | - | REC | 41.36 | - | 16.02.2018 | 31.03.2026 | 31.05.2019 | 0.01 | 0 | 0 | 0.01
17 | S-16-12 | Erection of 132/33 kV SS at Kotagiri | a)132/33 kV Sub-Station at Kotagiri in Nizamabad District with 3 X 10/16 MVA PTRs (Released) b)132 kV DC/SC line on Galvanised Towers with Panther ACSRfrom 132/33 kV Sub-Station, Jakora to the proposed 132kV Sub-Station at Kotagiri in Nizamabad District . c)132 kV Bay extensions at 132/33 kV Sub-Station, Jakora | To meet the load growth and to improve the voltage regulation in the surrounding (Kotagiri, Bhiknoor, Madnoor, Varni & Bodhan Mandals) under System Improvement | SI | T.O.O (CE-Transmission) Ms. No. 88 Dated: 30.06.2016. | - | Not necessary | 15.05 | - | PFC | 12.98 | - | 06.06.2018 | 31.03.2026 | 12.05.2022 | 0.01 | 0.06 | 0 | 0.07
18 | S-16-14 | 220/132/33 kV SS Borampet & Line | a) 220/132/33 kV Sub-Station at Borampet with 2 X 160 MVA + 2 X 80 MVA PTR Capacities b)220 kV Multi Circuit OH line on MC Towers with Moose ACSR from 400 kV Narsapur SS to proposed 220 kV Borampet SS-38 KM c)220 kV DC line with UG Cable from 400 kV Narsapur SS to proposed 220 kV Borampet SS – 5 KM. d)220 kV Bays at 400 kV Narsapur(2 No.s) | It is associated with evacuation of power from 2 X 800 MW Telangana STPP to be established by NTPC at Ramagundam | SI | T.O.O (CE-Transmission) Ms. No. 72 Dated: 13.05.2016 | - | CRN.No.TST/TS/220/132/33 KVSS Borampet, R.R.Dist. /Invest. Apprl/No.7/16-2016-17, dt.19.10.2016 | 212.2 | - | PFC | 182.98 | - | 28.11.2016 | 31.03.2026 | SS-04.03.2025, 2nd PTR-20.03.2025 line-27.02.2025 | 2.9 | 1.11 | 4.5 | 8.51
19 | S-17-01 | erection of 220/33 kV GIS at Chanchalgud | a)220/33 kV GIS substation at Chanchalguda with 3 X 50 MVA PTR b)220 kV DC line with 1000 Sqmm 220 kV UG cable for LILO of Chandrayangutta - Imlibun line (UG Cable) to the proposed 220/33 kV GIS substation, Chanchalguda | To i) reduce overloading of PTRs at 220/132/33 kV Sub-Station, Chandrayangutta and 132/33 kV Sub-Station, Imlibun, (ii) to provide alternate source of supply to the 33/11 kV Sub-Stations (iii) to avoid load shedding and (iv) also to cater to the upcoming loads | SI | T.O.O (CE-Transmission) Ms. No. 26, Dated: 27.02.2017. | - | CRN TS/TST/220/33 KV, GIS, Chanchaguda/Invest.Approval No.7/17-2017-18 | 89.12 | - | REC | 80.208 | - | 28.02.2018 | 31.03.2026 | 220KV GIS bay & bus charged with connected LILO cable on 26.02.2020. PTRs-I, II & III were charged on 20.03.2021, 26.03.2021 and 31.03.2021 respectively. | 0.58 | -0.02 | 0.45 | 1.01
20 | S-17-03 | 132/33 kV Sub-Station at Moulali ZTS | a)132/33 kV Moulali ZTS SS with 2X50 MVA PTR b)132 kV DC line with 630 Sqmm 132 kV UG cable from 220 kV Moulali Sub-Station to the proposed Moulali ZTS SS c)132 kV Bay extensions at220 kV Moulali substation | To (i) reduce overloading at 400/220/132/33 kV Sub-Station, Malkaram & 220/132 33 kV Sub-Station, Moulali, (ii) reduce the length of lines feeding the scheme area, (iii) to provide reliable & uninterrupted power supply, (iv) reduce the overall energy losses in the system and (iv) to cater to the upcoming loads which are increasing multi-fold due to the vertical growth of the city and increase in commercial establishments | SI | T.O.O (CE-Transmission) Ms. No. 31, Dated: 27.02.2017. | - | CRN TS/TST/132/33 KV, Moulali-ZTS SS, Investment Approval No.17/17, 2017-18 | 49.78 | - | REC | 44.47 | - | 01.04.2019 | 31.03.2026 | PTR-2 @ 07.07.2021 PTR-1 @ 30.07.2021 | -0.01 | 0.01 | 0.25 | 0.25
21 | S-17-05 | erection of 132/33 kV GIS at SEETARAMBAG | a)132/33 kV GIS substation at Seetharambagh with 2X80 MVA PTR b)132 kV DC line with 630 Sqmm 132 kV UG cable from Asifnagar Sub-Station to the proposed 132/33 kV GIS substation at Seetharambagh c)132 kV Bay extensions at Asifnagar substation(2 No.s) | To (i) reduce overloading of PTRs at 220/132/33 kV Shivarampally Sub-Station & 132/33 kV Imlibun Sub-Station, (ii) reduce the length of 33 kV lines feeding the scheme area, thereby reducing the time taken in locating faults, attending breakdowns & restoration of supply (iii) to provide reliable & uninterrupted power supply, (iv) reduce the overall energy losses in the system and (iv) to cater to the upcoming loads which are increasing multi-fold due to the vertical growth of the city and increase in commercial establishments | SI | T.O.O (CE-Transmission) Ms. No. 28, Dated: 27.02.2017. | - | CRN TS/TST/132/33 KV, GIS, Seetharambagh/Invest.Approval No.6/17-2017-18 | 63.63 | - | REC | 57.27 | - | 01.04.2019 | 31.03.2026 | SS- Charged on 13.06.2025 & line Ckt-I Charegd on 12.06.2025 | 71.54 | 1.25 | 4.6 | 77.39
22 | S-17-09 | 220/132/33 kV SS Meenajipet & lines | a) 220/132/33 kV Sub-Station at Meenajipet, with 2 X 100 MVA + 2 X 31.5 MVA PTRs With 2Nos., 220kV Incoming Feeder Bays, 4 Nos. 132 kV Feeder Bays and 4 No.33KV Feeder Bays b) 220 kV DC line with Moose ACSR Conductor on Galvanised Towers from proposed Narsapur 400/220/132 kV SS to the now proposed Meenajipet 220/132/33 kV SS c)132 kV DC/SC Line with Panther ACSR Conductor on Galvanized Towers from the proposed 220/132/33 kVMeenajipet SS to 132/33 kV Doulathabad SS d)132 kV DC Line with Panther ACSR Conductor on Galvanized Towers from the proposed 220/132/33 kV Meenajipet SS to 132/33 kV Thunki Bollarum SS e)Stringing of second circuit from 132/33 kV Thunki Bollarum to 132/33 kV Ganeshpally SS f) 220 kV Bays at 400/220/132 kV SS Narsapur for connectivity from 400/220/132 kV Narsapur SS to the 220/132/33 kV Meenajipet SS g)132 kV Bays at Doulathabad 132 kV SS.(1),132kV Thunki Bollarum SS (3) and 132kV Ganeshpally SS (1) | To cater to the upcoming loads in view of the development of Temple Town at Yadagirigutta and its surrounding areas and to provide quality power supply | SI | T.O.O (CE-Transmission) Ms. No. 28, Dated: 27.02.2017. | - | CRN/TS/TST/220/132/33kV SS/Meenajipet instead of Toopran/Invst.Appl.No.15/17-2017-18, Dt.Dec.2017. | 79.04 | - | REC | 68.43 | - | 27.01.2016 | 31.12.2026 | Meenajipet SS and connecetd line is charged on 06.02.2020.The downstream 132 KV line works yet to be started | 0.02 | 0.01 | 0.25 | 0.28
23 | S-17-13 | Erec of 132 KVSS at Yadgirigutta temple | a)132/33 kV Sub-Station at Yadagirigutta Temple Town with 2 X 31.5 MVA PTRs b)132 kV DC line with Panther ACSR Conductor on Galvanised Towers for LILO of LILO of 132 kV Bhongiri - Raghunathapally (Bhongir-Shapurnagar-Kolanpak) line to the proposed 132 kV Yadagirigutta SS. | To cater to the upcoming loads in view of the development of Temple Town at Yadagirigutta and its surrounding areas and to provide quality power supply | SI | TOO (CE_Transmission)Ms.No.69 Dt:09.05.2017 | - | Not Necessary | 15.06 | - | PFC | 13.16 | - | 01.10.2018 | 31.03.2026 | 11.12.2019 | 0.05 | -0.04 | 0 | 0.01
24 | S-17-16 | 132kV 2nd ckt Str on W.pally - Peddanaga | a)Stringing of 2nd circuit on 132KV DC/SC line from existing 220/132KV SS Waddekothapally to existing 132/33KV SS Peddanagaram with Panther ACSR Conductor. b)132 KV feeder bays (at 220/132 KVSS Waddekothapally - 1 Nos. and at 132 kV SS PeddaNagaram 1 No.) TOTAL-2Nos. | To meet (N-1) Contingency in the Network for ensuring satisfactory Power Supply | SI | T.O.O (CE-Construction) MS.No..149 Dated:09.10.2017 | - | Not necessary | 7.02 | - | REC | 6.32 | - | 01.04.2019 | 31.03.2026 | 06.11.2021 | 0.01 | 0 | 0 | 0.01
25 | S-17-21 | erec 132/33 kV SS Pammy n Khammam dist | a) 132/33 kV Sub-Station at Pammy in Khammam District with 2 X 31.5 MVA PTRs b)132 kV DC line for LILO of 132 kV Kusumanchi-Chilakallu line at the proposed 132/33 kV Pammy Sub- Station | To reduce the losses and to meet the load demand | SI | T.O.O (CE-Construction) Ms. No.14 Dated:20.01.2018. | - | TST/TS/Erection of 132/33 KV SS at Pammy in Khammam District/Approval No.03/2018-19, 01.06.2018 | 23.39 | - | REC | 20.64 | - | 13.01.2022 | 31.03.2026 | 20.02.2024 | 0.03 | 0.09 | 0.1 | 0.22
26 | S-17-23 | 132 KV feat at 220 KV Thimmajipet SS in | a)132 KV features at 220 kV Thimmajipet Switching Station with 2 X 100 MVA PTR Capacity. B)132 kV DC line on Galvanised Towers with Panther ACSR from the existing proposed 220/132 kV Thimmajipet Sub-Station, to the existing 132/33 kV Jadcherla Sub-Station. c)132 kV Bay extensions at 132/33 kV Sub-Station, Jadcherla( 2 No.s) | Comprehensive Transmission Requirement Scheme for the years 2012-2017. | SI | T.O.O (CE-Construction) Ms. No. 103 Dated:11.07.2017 | - | CRN/TS/TST/220kV Switching Station/Mahaboobnagar/132kV features/Invest.Appl.No.14/17, 2017-18, Dt.Dec.2017. | 29.32 | - | REC | 26.39 | - | 05.02.2020 | 31.03.2026 | line work is under progress | 14.54 | 1.59 | 0.15 | 16.28
27 | S-18-01 | Eection of 132/33 kV SS at Peechara in W | a)132/33 kV Sub-Station at Peechara, Warangal Dist with 2 X 31.5 MVA PTRs b)132 kV DC line with HTLS Conductor on Galvanised Towers by making LILO of existing 132 kV line from 220/132/33KV Waranagal SS to 132/33KV Jangaon SS at proposed 132/33KV Peechara SS. | To meet the load demand and to improve the Voltage profile | SI | T.O.O (CE-Construction) Ms. No. 43 Dated: 06.03.2018. | - | TST/TS/Erection of 132 /33 SS at Peechara in Warangal District. Approval No.05/2018-19, dt:19.07.2018 | 43.92 | - | REC | 39.1 | - | 02.02.2022 | 31.03.2026 | 20.09.2025 | 14.85 | 13.5 | 0.05 | 28.4
28 | S-18-02 | 220/132 kV SS at Ammavaripet in Warangal | a)220/132 kV Sub-Station at Ammavaripet with 2X100 MVA PTR Capacity in Warangal Dist b) 220 kV DC Line on Galvanized Towers with Moose ACSR Conductor for LILO of one circuit of 220 kV Mahabubabad - Warangal line to proposed 220 kV Ammavaripet SS c)132 kV DC Line on Galvanized Towers with Panther ACSR Conductor from the proposed 220/132 kV Sub-station Ammavaripet to the existing 132/33 kV Sub-Station, Geesukonda. d)132 kV Line on Multi-circuit Towers with Panther ACSR Conductor for accomdation of 132 KV Line to 132KV SS Inavole and 132KV Line to 132KV SS Wardhannapet from the proposed 220/132 kV Sub-station Ammavaripet to AP 8. e)132 kV DC/SC Line on Galvanized Towers with Panther ACSR Conductor from the AP.8 to the 132/33 kV SS Inavole f)32 kV DC/SC Line on Galvanized Towers with Panther ACSR Conductor from the AP.8 to the 132/33 kV SS Wardhannapet g)132 kV Bays (2 Nos at 132 kV Geesukonda, 1 No at 132 KV Wardannapet & 1No at 132 kV Inavole) | The proposal was made to avoid interruptions to the Tri-City caused frequently due failures in power cables at railway crossing as the whole city is fed through 220/132 Sub-Station located on the northern side of Kazipet - Warangal Railway Track and also to feed the upcoming industrial corridor at Madikonda and a Textile Park at Geesugonda | SI | T.O.O (CE-Construction) MS.No .294 Dated:29.01.2019 | - | CRN No.TST/TS/ Erection of 220/132 KV SS at Ammavaripet, Kazipet(M) in Warangal Urban District. Approval / NO 02/2019-20 dt:10.08.2018 | 126.86 | - | PFC | 87.24 | - | a) 20.02.2020 b)20.02.2020 c)18.09.2020 d,e, f & g) 26.02.2021 | 31.03.2026 | a) 31.03.2024 b)31.03.2024 c) 30.12.2023 d,e,f & g) 29.12.2022 | 0.05 | 0.47 | 0.5 | 1.02
29 | S-18-03 | Erect 132kV SS Padmanagar | a)132/33 kV Sub-Station Padmanagar (V) in Karimnagar District with 2X31.5 MVA PTR capacity b)LILO of132 KV Line (one circuit) from 220/132 KV SS Durshad to the 132/33 KV SS Siricilla to proposed 132/33 KV SS Padmanagar c)132 kV DC line erection on 400 kV DD Type Towers. | The scheme was proposed as the existing 132/33 KV SS Vaavilalapally in Karimnagar feeds most of the loads of Karimnagar town. This 132/33 KV Sub-Station has single 132 KV incoming feeder. Further stated that, IT hub is going to be established in the town. The city is recognized for tourism development with manair riverfront as center of attraction. Loads are also expected with increased activities in the town. With the present 132/33 KV SS maintenance of uninterruptable reliable supply to the city in near future will be complex | SI | T.O.O (CE-Construction) Ms. No.254 Dated: 26.11 2018. | - | Not necessary | 19.29 | - | PFC | 16.33 | - | 31.10.2020 | 31.03.2026 | 15.05.2023 | 0.08 | 0.69 | 0.12 | 0.89
30 | S-18-06 | 33kV features at RTSS Kothagudem in bhad | 33 KV features at 132 KV Railway Traction Switching Station, Kothagudem, Kothagudem Bhadradri District with 2 X 10/16 MVA PTRs | To provide uninterrupted power supply to the consumers with better voltage profile. | SI | T.O.O (CE-Construction) MS.No . 217 ,Dated: 25.09.2018 | - | Not necessary | 9.92 | - | PFC | 7.64 | - | 11.01.2023 | 31.03.2026 | 21.11.2023 | 0.12 | 0.09 | 0.1 | 0.31
31 | S-18-07 | 132 KV LILO of existing 132 KV Maddur-Ma | a)LILO of existing 132 kV Maddur – Makthal DC/SC line to existing newly charged 132/33 kV Narayanpet SS with Panther ACSR Conductor.(1KM) B)Erection of 132 KV feeder bays at 132/33 KV SS Narayanpet - 2Nos. | To meet (N-1) Contingency in the Network for ensuring satisfactory Power Supply and provide an alternate source to 132 KV SS Narayanpet | SI | T.O.O (CE-Construction) MS.No .12 Dated:20.04.2018 | - | Not necessary | 5.67 | - | REC | 5.11 | - |  | 31.03.2026 | 22.02.2025 | 0 | 0.07 | 2.3 | 2.37
32 | S-19-01 | KTPP system Improvement Scheme | a) LILO of existing 220kV Pulukurthy-Bhimghanapur SC line to proposed 400/220/132kV KTPP SS at Ramappa point with Twin Moose DC Line b)LILO of existing 220kV Salivagu-Bhimghanapur SC line to proposed 400/220/132kV KTPP SS at Ramappa point with Twin Moose DC Line c)220KV Single Moose DC Line from proposed 400/220/132kV KTPP SS to 220/132kV Manthani SS and bay extensions at Manthani SS d)Upgradation of existing 220kV Nagaram-Warangal DC Line with HTLS Conductor e)32KV Single Moose DC Line from proposed 400/220/132kV KTPP SS to 132/33KV Chelpur SS on 220kV Multi Circuit Towers and bay extensions at Chelpur | covered in 400KV Scheme | SI | T.O.O.(CE-400kV) Ms.No.297 Dt:09.02.2019 | - | Covered in 400KV |  | - | PFC | 405 | - | 05.05.2020 | 31.03.2026 | a)22.06.2023 b)16.09.2023 e) 24.09.2022 | 0.08 | 0.19 | 0.25 | 0.52
33 | S-19-03 | 132/33 KV Sub-Station at Patancheru in S | a)132/33 kV Sub-Station at Patancheru, Sangareddy Dist with 2 X 31.5 MVA PTRs b)132 KV DC/SC line with ACSR Panther conductor from Loc.no.16 (of existing 132 KV line from RC Puram to M/s MHPL) to proposed 132/33 KV Patancheru substation on Narrow Base Towers. | Manjeera water pumping station located at Patancheru which is the main drinking water source to all important commercial and residential zones in cyberabad limits. With the proposed 132 KV Patancheru SS, the Manjeera pumping station will be only 1 KM away and any interruption can be completely eliminated, the length of all 33KV feeders will come down to less than 10KMs and all 33KV feeders can be brought into Ring Main network, thus developing more no of alternate sources to each feeder, thereby improving reliable and quality power supply to major revenue source industrial consumers and to the residential/commercial areas of Patancheru division which are falling within GHMC limits. Also sufficient land is available at the existing 33/11 KV Patancheru Sub-station premises | SI | T.O.O (CE-Construction) Ms.No.375 Dated: 03.06.2019 | - | CRN/TST/TS/Erection of 132/33 KV SS at Patancheru in Sangareddy District. Approval /NO 05/2019-20 dt:22.11.2019 | 23.64 | - | REC | 20.85 | - | 23.06.2020 | 31.03.2026 | 30.11.2022 | 0.01 | -0.01 | 0.02 | 0.02
34 | S-19-05 | 132 KV GIS Manikonda -RR Dist | a)132/33 kV GIS Sub-Station at Manikonda with 2 X 80 MVA PTRs b)LILO of existing 132 kV Shivarampally-Erragadda SC OH feeder between Loc No.80 and Loc No.81 with laying of 132 KV XLPE UG cable of 1200 Sq mm for cable length of 2.5 Km. | To overcome the low voltage problems, to cater to the upcoming loads and also to provide quality power supply to the consumers | SI | T.O.O (CE-Construction) MS.No .402 Dated: 08.07.2019. | - | CRN/TST/TS/Erection of 132 KV SS at Manikonda in Rangareddy District.Approval NO 08/2019-20 dt:27.12.2019 | 107.18 | - | REC | 96.46 | - | 18.03.2021 | 31.03.2026 | 15.09.2022 | 1.2 | 0.52 | 0.01 | 1.73
35 | S-20-01 | 132/33 KV SS at Koutala (V)- Komaram Bhe | a)132/33 kV Sub-Station at Koutala in Komaram Bheem Asifabad Dist with 2 X 10/16 MVA PTRs (Released) b)132 KV DC/SC line from existing 132 KV Sirpur Kagaznagar SS to proposed 132 KV SS Koutala c)132 KV feeder bay at existing 132 KV SS Sirpur Kagaznagar | To provide reliable power supply to consumers and Lift irrigation schemes.To avoid power interruption and to give better supply to the area, it is very much essential to shorten the 33KV lines by erecting new 132/33KV Sub-station at Koutala | SI | T.O.O (CE-Construction) Ms.No. 981 Dated: 22.02.2021. | - | TST/TS/Erection of 132/33 KV SS at Koutala(V), Koutala (M) of Komaram Bheem Asifabad District.Approval No.02/2021-22, dt:10.06.2021 | 56.56 | - | HUDCO | 50.77 | - | 18.05.2023 | 31.03.2026 | - | 28.48 | 1.07 | 0.5 | 30.05
36 | S-21-01 | 132/33 Kv SS at Pasra -Mulugu Dist. | a)132/33 kV Sub-Station Pasra (V) in Mulugu District with 2X10/16 MVA PTR capacity (Released) b)LILO of existing 132 kV Kamalapur - Chelpur to proposed 132/33 KV SS Pasra | The proposal provides uninterrupted and reliable power supply during Asia’s biggest Tribal Bi-annual Sammakka Saaralamma jatara at Medaram village, Tadwai mandal of Mulugu district, where the congregation of more than 1.5 Cr pilgrims participate in the festival will be facilitated for drinking, bathing and lighting during the entire festival days. | SI | T.O.O (CE-Construction) Ms.No.1099 Dated: 30.06.2021. | - | Not necessary | 12.8 | TGTransco funds |  | 12.8 | - | 25.10.2021 | 31.03.2026 | 31.01.2022 | 0 | 0.09 | 0.12 | 0.21
37 | S-21-03 | 2nd CKT strngng from 220KV KWK to ACPT | a)2nd circuit Stringing on existing 132 kV DC/SC line from 220/132/33 kV Kalwakurthy SS to 132/33 kV SS Achampet.(38KM) b)132kV Bay Extensions (1 No at 220kV SS Kalwakurthy, 1 No at 132kV SS Achampet) | To meet N-1 contingency and to reduce overloading on the existing 132 kV Kalwakurthy – Achampet SC line | SI | T.O.O (CE-Construction) Ms.No.1159 Dated: 13.08.2021. | - | Not necessary | 9.68 | TGTransco funds | - | 9.68 | - | 15.06.2022 | 31.03.2026 | 28.08.2025 | 1.1 | 4.56 | 0.5 | 6.16
38 | S-21-06 | line 4m 400KV Narsapur 2 132 KV Yeldurth | a)132kV DC line on Galvanized Towers with Panther ACSR conductor from 400/220/132 kV SS Narsapur to 132/33 kV SS Yeldurthy b)132 kV feeder bays ( 2 Nos at Narsapur & 2 Nos at Yeldurthy) | To mitigate overloading on 132 kV Gajwel – Chegunta DC line | SI | T.O.O (CE-Construction) Ms.No.1208 Dated: 04.10.2021 | - | (CRN) TST/TS/Erection of 132KV DC line from 400/220/132 KV SS Narsapur to 132/33 KV SS Yeldurthy in Medak District.Approval NO.04/2021-2022 | 30.58 | HUDCO |  | 27.45 | - | 05.11.2022 | 31.03.2026 | 06.01.2025 | 0.08 | 0.52 | 0.2 | 0.8
39 | S-21-08 | 2nd ckt 4m Shaligowraram-Mothkur | 2nd circuit stringing on existing 132 kV DC/SC line from 132/33 kV Shaligowraram SS to 132/33 kV SS Mothkur with Panther ACSR conductor 132kV Bay Extensions (1 No at 132kV SS Shaligowraram, 1 No at 132/33 kV SS Motkur) | As the 132/33 KV SS Mothkur is being fed by the 132 KV Mothkur - Shaligowraram DC/SC line which is the only source for the sub-station and to maintain reliable and quality of power supply to the consumers in that area of Nalgonda District | SI | T.O.O (CE-Construction) Ms.No.1271 Dated: 20.12.2021. | - | Not necessary | 6.2 | TGTransco funds |  | 6.2 | - | 25.04.2024 | 31.03.2026 | 06.01.2025 | 0.02 | 0 | 0.2 | 0.22
40 | S-21-12 | 132/33 kV SS Nuthankal | a)132/33kV Sub-station at Nuthankal in Suryapet District with PTRs capacity of (2x50 MVA) + (1x10/16 MVA Released.) b)Stringing of 2nd circuit from Loc.No.16 to Loc.No.75 (Tapping Tower) on existing 132kV DC/SC line from 400/220/132 kV SS Suryapet to 132/33kV SS Thungathurthy towers with Panther ACSR conductor c)132kV DC/SC line from Loc.No.75 (Tapping tower) to proposed to 132/33kV SS Nuthankal on Galvanised towers with Panther ACSR conductor d)132 kV Bay extension at 400/220/132kV SS Suryapet | The Substation is proposed to overcome the low voltage problems, to cater to the upcoming loads and also to provide quality power supply to the consumers. | SI | T.O.O (CE-Construction) Ms.No.1330 Dated:10.03.2022. | - | (CRN) TST/TS/Erection of 132/33 KV Sub Station at Nuthankal(V&M) in Suryapet District instead of 1323/33 KV Aipoor SS in Suryapet District.Approval NO.02/2022-2023 | 30.55 | TGTransco funds | REC | 18.91 | - | 22.02.2023 | 31.03.2026 | 31.03.2026 | 0.14 | -0.03 | 0.12 | 0.23
41 | S-22-02 | 2nd ckt Stringing 4m Shadnagar 2 Srirang | a)2nd circuit stringing on existing 132 kV DC/SC line from 220/132/33 kV Shadnagar SS to 132/33 kV SS Srirangapur with Panther ACSR conductor (including 2 Nos Narrow Base Towers) b)132kV Bay Extensions (1 No at 220/132/33 kV SS Shadnagar & 1 No at 132/33 kV SS Srirangapur) | 2nd nd circuit is propsoed as the 132/33 KV SS Srirangapur being fed by the 132 KV Shadnagar - Srirangapur DC/SC line which is the only source for the sub-station i.e., radial feeder and to maintain reliable and quality power supply to the consumers in that scheme area. | SI | T.O.O (CE-Construction) Ms.No.1461 Dated:19.08.2022 | - | Not necessary | 5.39 | TGTransco funds |  | 5.39 | - | 27.07.2024 | 31.03.2026 | Work in Progress | 2.77 | 0.4 | 0.04 | 3.21
42 | S-22-05 | Making LILO of 132 KV Dharmaram-Godur to 220/1 | a)LILO of 132kV Darmaram-Godur line to 220/132 KV SS Jagityal in Jagityal District on multi circuit tower with panther ACSR conductor b)132kV Bay Extensions (2 No's at 220/132 kV SS Jagityal.) c)Dismantling of TNS,TND,BOOM & Re-stringing of 132KV Jagityal-Gangadara, Jagityal-Pudur, Jagityal-Jagityal, Jagityal-Korutla line near TT Tower at 220 kV SS Jagityal. | The proposal for making LILO of 132KV Dharmaram-Godur line to 220/132KV SS Jagityal in Jagityal District as the construction of 220 KV SS Kathalapur and making LILO of Godur-Dharmaram line to 220KV SS Kathalapur may take some time and augmentation of PTR capacities at 132/33 kV SS Dharmaram and 132/33 kV SS Godur was approved and works at these substations are under taken. This will further increase load on 132KV RSS - Dharmaram line. The load on 132 KV RSS - Dharmaram line can be limited to safe operating limits if loads of Godur SS are fed from 220KVSS Jagityal. Augmentation of PTR capacities from 3x100 MVA to 3x100 MVA+1x160 MVA was approved at 220KVSS Jagityal. Increased PTR capacity at 220KVSS Jagityal will make feeding loads of 132 KVSS Godur is feasible. For this, making LILO of 132 KV Dharmaram-Godur line to 220KVSS Jagityal is required. | SI | T.O.O (CE-Construction) Ms.No.1590 Dated:14.03.2023. | - | Not necessary | 5.12 | TGTransco funds |  | 5.12 | - | 15.08.2023 | 31.03.2026 | 21.01.2025 | -0.01 | -0.02 | 0.5 | 0.47
43 | S-24-08 | Upgradation of existing 132/33 KV SS at Chinna Shankarampet | a)Upgradation of existing 132/33 KV Chinnashankarampet SS to 220/132/33 KV SS with 2x160 MVA PTR capacity in Medak Dist. B)Erection of 220 kV DC line from 400/220/132 kV SS Narsapur to the Upgradation of existing 132/33kV Chinna Shankarampet SS to 220/132/33kV SS on Galvanized Towers with Moose ACSR Conductor (27KM) c)Stringing of 2nd circuit on existing 132kV DC/SC line from 132/33 kV SS Medak to 132/33 kV SS Ramayampet on Galvanized towers with Panther ACSR conductor(19KM) d)Making one circuit LILO of 132 kV Medak – Ramayampet line to the Upgradation of existing 132/33kV Chinna Shankarampet SS to 220/132/33kV SS on Galvanized Towers with Panther ACSR Conductor (14KM) e)220 kV Bay extension at 400/220/132kV SS Narsapur (including Bus extension) f)132 kV Bay extensions (1 No. at 132kV SS Medak & 1 No. at 132 kV SS Ramayampet) | The Northeastern part of the combined Medak District is having Number of 132/33 kV Substations and HT consumers connected from 400/220/132 kV Gajwel, 220/132/33 kV Minpur and 400/220/132 KV Narsapur Substations with 132 kV lengthy lines. The existing 132 KV lines are reaching their maximum capacity. Under these circumstances, it is considered to upgrade any one of the 132 kV SS to 220 KV SS with 220KV source from 400 KV SS the load on the lines reduces, improves the voltage profile of the area and reduces the system losses. | SI | T.O.O. (CE-Construction) Ms.No.2058, Dated: 03.08.2024 | - | (CRN): TGERC/TGTRANSCO/132/33KV-CHINNASHANKARAMPET/IA-6/2024-25 | 118.43 | TGTRANSCO funds | - | - | - | 01.11.2025 | 31.10.2027 | - | - | 0.04 | 5 | 5.04
44 | S-24-10 | 220/132/33KVSS Chinnamadur(Singarajupall | a)Erection of 220/132/33KV SS Chinnamadur(Singarajupally) with 2X160MVA & 2X50MVA PTRs including 220 kV Twin Moose Double Bus system. B)Making LILO of 220KV SC line from 220KV SS Waddekothapally - 400/220 KV SS Jangoan to proposed 220/132/33kV SS Chinnamadur. c)132KV DC/SC line from proposed 220/132/33KV SS Chinnamadur to existing 132/33KV SS Palakurthy. (13KM) d)132KV DC/SC line from proposed 220/132/33KV SS Chinnamadur to existing 132/33KV SS Raghunathpally. (18KM) e)132KV DC/SC line from proposed 220/132/33KV SS Chinnamadur to existing 132/33KV SS Mothkur. (27KM) f)132kV Bays ( 1No.at 132kV SS Mothkur,1No.at 132KV SS Palakurthy & 1No. at 132kV SS Raghunathpally) (3No.s) | The load growth is rapidly increasing year by year due to recent developments in distribution network. Due to increase in agricultural cultivation loads, industrial corridor along Hyderabad-Warangal highway road and increasing the loads in and around Jangaon district. The existing 220 KV SS Waddekothapally, 220 KV SS Jangaon, 132KV SS Raghunathapally, 132KV SS Palakurthy are getting overloaded. In view of increasing agriculture loads, there is high essence of another 220/132/33KV Substation in Jangaon district. This can be achieved with erection of 220/132/33KV Substation at Chinnamadur (Singarajupally) in Jangaon district with an incoming 220 KV DC line and 132 KV downstream connectivity | SI | T.O.O. (CE-Construction) Ms.No.2075, dated:30.08.2024 | - | (CRN):TGERC/TGTRANSCO/220/132/33KV-CHINNAMADUR/IA-1/2025-26 | 130.76 | - | - | - | - | 01.03.2026 | 31.03.2028 | - | - | 0.93 | 0.25 | 1.18
45 | S-24-11 | 33KV features at Kothakota SS | Erection of 33 KV features at existing 132/11 KV LIS Kothakota SS with new 2x50 MVA PTR capacity | To divert the loads of existing over loaded substations i.e. 220/132/33 kV Wanaparthy SS & 132/33 kV Thirumalaipally SS, to meet upcoming loads and to provide reliable power supply to the consumers in Kothakota scheme area | SI | T.O.O (CE-Construction) Ms.No.2178 , Dated:16.01.2025 | - | - | 17.15 | TGTransco funds | - | - | - | 15.10.2025 | 14.09.2026 | - | - | 0 | 0 | 0
46 | S-24-27 | LILO of 132 KV DC lne 4m Chandrayangutta | Making LILO of one circuit of 132 kV DC line from 220 KV Chandrayangutta – 132 kV Jubilee Hills to 132KV Manikonda GIS substation with 1200 Sq mm XLPE UG Cable (1.5 KM) | For providing alternate supply to 132/33 KV GIS Manikonda SS by making LILO of one circuit of 132 KV Chandrayangutta-Jubilee Hills OH line. | SI | T.O.O (CE-Construction) Ms.No.2263, Dated:12.02.2025 | - | Not Necessary | 33.2 | - | - | - | - | 01.04.2026 | 31.03.2027 | - | - | 0.02 | 8 | 8.02
47 | P-12-02 | NIRMAL POWER TRANSMISSION SCHEME | a)Up gradation of 132/33 kV Renzal SS to 220/132 kV Renzal Sub Station and 220kV DC Line from proposed 400/220kV Nirmal SS to the proposed up graded 220/132 kV Renzal SS b)220/132 KV SS at Indravelly in Utnoor District c)220kV DC Line from proposed 400/220kV Nirmal SS to the proposed 220/132 kV Indravelly SS d)132kV DC Line from proposed 220/132 kV Indravelly SS to 132/33 kV Utnoor S Sand 132 KV Bay extension at Utnoor-2, e)220kV Multicircuit line for making LILO of existing 220kV RSS(Malyalpalli) –Nirmal and RSS-Vemnur-Nirmal DC line to existing 220/132kV Jagityal Substation and 220kV Bay Extensions at 220kV Jagityal SS f)220kV DC Line from proposed 400/220kV Nirmal SS to the existing 220kV Nirmal SS on Multi circuit towers g)132 KV DC line with Single moose from proposed 220/132 kV Indravelly SS to 132/33 kV Asifabad SS on 220kV Galvanized DC towers & 132 KV bay extension at Asifabad -2. h)132kV DC line from Proposed 220/132 kV Indravelly SS to the existing 132kV Adilabad SS & 132 KV bay extension at Adilabad -2. | Covered in 400KV scheme | SI | T.O.O. (CE-400kV) Ms.No.07 Dated: 09.01.2018 | - | Covered in 400KV |  | - | REC |  | - | 10.03.2019 | 31.03.2026 | a) 15.02.2020 b)27.08.2021 c)18.08.2021 e)20.11.2019 f)29.12.2017 g)work in progress h)31.03.2022 | 36.19 | 0.44 | 0.06 | 36.69
48 | P-15-03 | Bhadradri Thermal Power Transmisn Scheme | a)Up gradation of 132/33 kVJangaon SS to 220/132/33 kV Jangaon Sub Station. b) 220/132/33 kV Sub Station at Husnabad in Warangal Dist. C)220kV line with Multi circuit towers for making LILO of 220kV Waddekothaplly-Bhongiri DC line(both circuits) to proposed 400kV SS Jangaon with Single moose conductor and 220 KV bay extension at 400kV Jangaon SS for LILO of W.Pally to Bhongir DC line d)220kV DC line for making LILO of 220kV KTPS-Shapurnagar SC line to proposed 400kV SS Jangaon with Single moose conductor and 220 KV bay extension at 400kV Jangoan SS for LILO of KTPS-S.Nagar SC line e)220kV DC line for making LILO of 220kV KTPS-Shapurnagar SC line to 220/132kV SS Waddekothaplly with Single moose conductor and 220 KV bay extension at 220kV W.Pally SS for LILO of KTPS-S.Nagar SC line f)DC line from 400/220kV Jangaon SS to the 220/132/33kV Husnabad SS with Single Moose Conductor g)2nd circuit stringing on existing 132kV DC/SC Husnabad-Palamaukula line h)132kV line with MC towers for making double LILO of 132kV Husnabad-Palamakula DC line to proposed 220/132/33kV Husnabad SS and 132 kV Bay Extensions at Husnabad 132 kV SS and Palamakula 132kV SS | Covered in 400KV scheme | SI | T.O.O. (CE-400kV) Ms.No. 139 Dt: 11.09.2017 | - | Covered in 400KV |  | - | PFC | 937.63 +139.49 | - | 12.10.2018 | 31.03.2026 | a) 20.05.2019 b)Work in progress c)12.06.2019 d)10.08.2019 e)13.08.2019 f)work in progress h)work in progress | 0.01 | 0.46 | 0.72 | 1.19
49 | P-15-04 | KTPS (Stage-VII 1 x 800MW ) Scheme | a)Up gradation of 132/33 kVJangaon SS to 220/132/33 kV Jangaon Sub Station. b) 220/132/33 kV Sub Station at Husnabad in Warangal Dist. C)220kV line with Multi circuit towers for making LILO of 220kV Waddekothaplly-Bhongiri DC line(both circuits) to proposed 400kV SS Jangaon with Single moose conductor and 220 KV bay extension at 400kV Jangaon SS for LILO of W.Pally to Bhongir DC line d)220kV DC line for making LILO of 220kV KTPS-Shapurnagar SC line to proposed 400kV SS Jangaon with Single moose conductor and 220 KV bay extension at 400kV Jangoan SS for LILO of KTPS-S.Nagar SC line e)220kV DC line for making LILO of 220kV KTPS-Shapurnagar SC line to 220/132kV SS Waddekothaplly with Single moose conductor and 220 KV bay extension at 220kV W.Pally SS for LILO of KTPS-S.Nagar SC line f)DC line from 400/220kV Jangaon SS to the 220/132/33kV Husnabad SS with Single Moose Conductor g)2nd circuit stringing on existing 132kV DC/SC Husnabad-Palamaukula line h)132kV line with MC towers for making double LILO of 132kV Husnabad-Palamakula DC line to proposed 220/132/33kV Husnabad SS and 132 kV Bay Extensions at Husnabad 132 kV SS and Palamakula 132kV SS | Covered in 400KV scheme | SI | T.O.O. (CE-400kV) Ms.No. 139 Dt: 11.09.2017 | - | Covered in 400KV |  | - | PFC | 937.63 +139.49 | - | 12.10.2018 | 31.03.2026 | a) 20.05.2019 b)Work in progress c)12.06.2019 d)10.08.2019 e)13.08.2019 f)work in progress h)work in progress | 69.89 | 1.41 | 1.15 | 72.45
50 | P-19-02 | Yadadri Thermal Power (5x800MW) Evacuati | a)220KV TMDC line from proposed 400/220KV Damarcherla SS to 220KV Miryalaguda SS and bay extensions at Miryalaguda b)220KV SMDC line from proposed 400/220KV Damarcherla SS to 220KV Huzurnagar SS and bay extensions at Huzurnagar c)LILO of both circuits of 220KV Malkaram-Narketpally DC line to proposed 400/220/132 KV Choutuppal SS on MC towers d)132 KV DC line from proposed 400KV SS Choutuppal to 132 KV SS Choutuppal and 2 No.s 132 KV bays at 132/33 KV SS Choutuppal e)32kV DC line from proposed 400/220/132 KV Choutuppal SS to proposed 132 KV Dandumalkapur SS and 132 KV bay extension at 132 KV SS Dandumalkapur | Covered in 400KV scheme | GE | T.O.O.(CE-400kV) Ms.No.51 , Dt:10.10.2019 | - | Covered in 400KV |  | - | PFC | 1102.26 | - | 15.11.2020 | 31.03.2026 | a)Ckt-I charged on 29.08.2022 and Ckt-II charged on 29.12.2022 b)work in progress c)LILO of Ckt-I charged on 23.03.2023 and LILO of Ckt-II charged on 20.03.2023 d)work in progress | 0.94 | -0.01 | 1.6 | 2.53
51 | D-17-11 | 132 KV lne 4m Miryalaguda to RTSS and cn | i) 132 KV DC/SC line from 220/132/33 KV Miryalaguda SS to 132/33 KV RTSS Miryalaguda and connected bays in Nalgonda District & for supply, erection, testing & commissioning of 132KV DC/SC line from 132/33 KV Ramannapet SS to Ramannapet RTSS (2.2 KM) and connected bays in Yadadri-Bhongiri District. | - | DCW | - | - | - | 15.41 | - | Consumer contribution | - | - | 02.06.2018 | 31.03.2026 | 27.09.2019 | - | 0.02 | 0 | 0.02
52 | D-18-13 | Pwr sply 2 132KV RTSS Divitipally(RVNL) | Pwr sply 2 132KV RTSS Divitipally(RVNL) | - | DCW | - | - |  | 9.76 | - | Consumer contribution | - | - | 21.01.2020 | 31.03.2026 | 22.07.2022 | 0.07 | 0.18 | 0 | 0.25
53 | D-18-15 | Extn of 132 KV lne 4 kamrdy 2 Tlamdla Ra | Extension of 132 KV Radial 2 –phase DC/SC line (8KM) from existing 220/132 KV SS Kamareddy to proposed 132/25 KV Talamadla Railway Traction Substation. | - | DCW | - | - |  | 14.55 |  | Consumer contribution | - |  | 24.03.2021 | 31.03.2026 | 31.03.2023 | 0.02 | 0 | 0 | 0.02
54 | D-18-16 | Ere of Pwr sply 2 132/25 KV RTS Jankamp | Extension of power supply to proposed 132/25 KV Railway Traction Substation Jankampet by erection of 132 KV radial 2-phase DC/SC line (12KM from proposed 220/132 KV SS Renjal | - | DCW | - | - |  | 19.05 |  | Consumer contribution | - |  | 25.11.2020 Mbay- 07.10.2022 | 31.03.2026 | 04.11.2024 | 0.01 | 0.46 | 0 | 0.47
55 | D-18-18 | Extn of 132 KV sply 2 RTSS at Wnaprthy 4 | Extension of 132 KV supply to railway traction SS at Wanaparthy from existing 132/11 KV Kothakota LIS in Mahaboobnagar District. | - | DCW | - | - |  | 15.6 |  | Consumer contribution | - |  | 06.01.2022 | 31.03.2026 | 04.08.2023 | 0.07 | -0.07 | 0 | 0
56 | D-18-19 | Extn of HT sply 2 Thimmapr RTSS 4m Shams | Extension of HT supply at 132 KV level for a CMD of 10MVA to Thimmapur RTSS from 220/132 KV Shamshabad SS | - | DCW | - | - |  | 34.87 |  | Consumer contribution | - |  | 08.11.2018( Line & bay at Shamshabad) 21.01.2019 (Bays at RTSS) | 31.03.2026 | 24.05.2025 | 31.96 | 0.02 | 0 | 31.98
57 | D-19-02 | Shift Gachibowli-Madapur-I&II DC lines b | Shifting of Gachibowli – madhapur – I & II DC lines crossing at Botonical Garden Junction Hyderabad | - | DCW | - | - |  | 13.02 |  | Consumer contribution | - |  | 29.11.2019 | 31.03.2026 | 28.05.2020 | 0.6 | -0.45 | 0 | 0.15
58 | D-19-03 | Sft 220KV Gachibowli-S.nagar-Egadda line | Shifting of 220KV Gachibowli – Shapurnagar – Erragadda – DC line at Kothaguda Junction, Hyderabad under DC Works | - | DCW | - | - |  | 19.61 |  | Consumer contribution | - |  | 29.11.2019 | 31.03.2026 | 31.08.2021 | 0.95 | 0 | 0 | 0.95
60 | D-19-10 | Diversn of 220KV Gachibwli-Err'da-SH.ngr | Diversion of 220KV Gachibowli-Erragadda-Shapurnagar DC line passing through the premises of M/s.DLF Commercial Developers Limited, IT/ITES IT Park, Gachibowli, Hyderabad | - | DCW | - | - |  | 1.37 |  | Consumer contribution | - |  | 17.09.2019 | 31.03.2026 | 19.10.2020 | 1.53 | -0.01 | 0 | 1.52
61 | D-20-01 | 132/33 KV SS at E-city Fabcity | 132/33KV Sub-station at Electronic Manufacturing Cluster at E-City Fabcity, (ii) 132 KV line from existing 220/132 KV Fabcity SS to proposed 132/33 KV E-City Fabcity SS for proposed 132/33 KV E-city Fabcity SS in Raviryal Village, Maheshwaram Mandal, Ranga Reddy District | - | DCW | - | - | - | 47.99 |  | Consumer contribution | - |  | 21.09.2020 (SS & Bays) 22.04.2021 (Line) | 31.03.2026 | 16.09.2023(SS) 31.08.2023 (bays) 31.08.2023 (Line) | 0.01 | 5.13 | 0 | 5.14
62 | D-20-02 | Extension of 132KV supply to RTSS Manopa | i) 1 No.132 KV bay at existing 132/33 KV Alampur SS for 132 KV RTSS Manopad, (ii) 132 KV DC/SC line from existing 132/33 KV Alampur SS to proposed RTSS Manopad for a length of about 12 KM in Jogulamba District (iii) 1 No.132 KV metering bay at proposed 132 KV RTSS Manopad in Jogulamba District | - | DCW | - | - | - | 20.14 |  | Consumer contribution | - |  | 25.01.2023 | 31.03.2026 | 19.06.2024 | 0.1 | -0.13 | 0 | -0.03
63 | D-21-24 | 132kV DC.SC line Ganganpally-RTSS Pandur | (i) Erection of 2Nos 132kV bays at 132/33kV Ganganpally SS (a) for 132kV Pandurangaswamy road RTSS and (b) for 2nd circuit stringinging from 220kV Jurala SS in 132/33kV Ganganpally SS in Jogulamba Dist.Gadwal(Jogulamba) District. (ii) Erection of 132kV DC/SC line to existing 132/33kV Ganganpally SS to proposed RTSS Pandurangaswamy road in Gadwal(Jogulamba) Dist. (iii) Erection of 1No. 132kV Bay at 220/132kV Jurala SS for 132kV Ganganpally SS. (iv) stringing of 2nd circuit from 220/132kV Jurala SS to | - | DCW | - | - |  | 14.55 |  | Consumer contribution | - |  | 11.10.2021 | 31.03.2026 | 10.04.2022 | 0 | 0.18 | 0 | 0.18
64 | D-21-27 | Data centres at TSIIC-M/s.Amazon | a) 220KV MC/DC line from 220/132 KV Fabcity SS to the proposed site of M/s.Amazon Data Services India Pvt Ltd.at TSIIC industrial park Fabcity(2.5Kms) b) 2 no.s 220KV feeder bays at 220/132KV Fabcity SS c) 2 No.s 220KV bays at Amazon SS | - | DCW | - | - | - | 40.49 | - | Consumer contribution | - |  | 14.10.2021(bays at Fabcity end) 11.10.2021(line) 14.10.2021(Bays at Amazon end) | 31.03.2026 | 28.06.2023 28.06.2023 13.07.2023 | 25.04 | -1.15 | 23.89 | 47.78
|  |  | (a) 2 No.s single circuits with 220KV XLPE UG cable 1000 Sq.mm from 400/220 KV Maheshwaram SS to 220KV Amazon SS (b) 2 No.s 220KV bays at 400/220KV SS Maheshwaram (c) 2 No.s 220KV Bays at Amazon | - |  |  |  |  | 72.76 |  | Consumer contribution | - |  | 23.11.2021(bays at maheshwaram end) 06.01.2022 (Line) 14.10.2021(Bays at Amazon end) |  | 18.08.2023 18.08.2023 16.09.2023
|  |  | a)2 No.s 220KV bays proposed at 220/132/33 KV SS Chandanvally (TSIIC) and (b)220KV single moose DC line from proposed 220/132/33 KV Chandanvally (TSIIC) SS to proposed 220KV M/s.Amazon (Chandanvally) SS on 220KV narrow based towers (c)2 No.s 220KV bays at 220 KV M/s.Amazon(Chandanvally) | - |  |  |  |  | 34.58 |  | Consumer contribution | - |  | 01.08.2022 |  | Work under progress
65 | D-21-30 | Industrial park at Chandanavally(V), Sha | (i) 220/132/33 KV at Chandanavally (ii) 220Kv TMDC line from 400/220KV Kethireddypally SS to proposed 220KV Chandanavally (TSIIC) for a length of 12.663 KM (4.663 KM) on 400KV Quad moose MC towers + 8.0 KM on 220KV TMDC towers instead of 220KV SMDC line on normal 220KV DC towers (iii) 2 no.s 220KV feeder bays at 400/220KV Kethireddypally SS for proposed 220KV Chandanavally SS, Shabad Mandal in Ranga Reddy District. | - | DCW | - | - |  | 108.33 |  | Consumer contribution | - |  | SS-14.10.2021 Line-25.10.2021 Bays-23.11.2021 | 31.03.2026 | SS-16.01.2023 Line-13.01.2023 Bays-10.01.2023 | -0.18 | -0.13 | 0 | -0.31
66 | D-21-47 | 220kv SS at Kakatiya Mega Textile park | Extension of power supply to M/s. Kakatiya Mega Textile Park- Erection of (i) 220/132/33 KV SS (2 X 160+ 2 x 50 MVA) including 2 Nos 220KV incoming feeders and 8 Nos 33KV feeder bays at Kakatiya Mega Textile park, Shyampet(V), Geesukonda (M),(ii) 220KV DC line (29KM) from existing 220KV SS Pulukurthy to proposed 220/132/33 KV SS at Kakatiya Mega Textile Park and (iii) 2 No.s 220KV bay extensions at 220KV SS Pulukurthy in Warangal District. | - | DCW | - | - |  | 189.2 |  | Consumer contribution | - |  | 28.10.2022 | 31.03.2026 | Work under progress | 57.59 | 1.25 | 0 | 58.84
67 | D-21-48 | M/s.Kitex Garments Limited | Extension of power supply to M/s. Kitex Garments Limited- Erection of (i) 132 KV DC line (3.2 KM) from proposed 220/132/33 KV SS at Kakatiya Mega Textile Park(KMTP) to M/s.Kitex Garments Limited proposed to establish at KMTP(ii) 2 No.s 132 KV bays at proposed 220/132/33 KV KMTP (iii) 2 No.s 132 KV metering bay extensions at M/s.Kitex Garments Limited in Warangal District. | - | DCW | - | - |  | 19.99 |  | Consumer contribution | - |  | 17.11.2022 | 31.03.2026 | 09.01.2024 | 8.19 | 0.09 | 0 | 8.28
68 | D-21-50 | M/s. BEL-132 KV Yacharam-Ibrahimpatn | Diversion of 132 KV Yacharam-Ibrahimpatnam-Bongulur SC line from Loc.No.367 to 372 and LILO Loc No.s 370/1 to 370/3 of Ibrahimpatnam DC line passing through M/s.BEL’s land located at Sy.No.s 254 to 256 of Ibrahimpatnam Khalan Village, Ibrahimpatnam Mandal, Ranga Reddy District | - | DCW | - | - | - | 8.88 | - | Consumer contribution | - |  | 25.11.2022 | 31.03.2026 | 11.05.2023 | 0.01 | -0.01 | 0 | 0
69 | D-22-01 | 132/33 KV SS Chandrugonda-Railway Tracti | Extending power supply at 132KV level to the proposed 132/25KV Railway Traction Sub-station at 132/33 KV SS Chandrugonda in Khammam District. | - | DCW | - | - |  | 20.7 |  | Consumer contribution | - |  | 10.10.2023 | 31.03.2026 | 10.06.2024 | 0.07 | -0.01 | 0 | 0.06
70 | D-22-14 | Erection of (i) 132 KV DC line (10.00KM) | (i) 132 KV DC line (10.00 KM) from existing 132/33 KV Makthal SS to proposed 132/25KV Makthal Railway Traction substation (CMD of 10MVA) ii) 2 No.s 132 KV bays extension at 132/33 KV SS Makthal and (iii) 2 No.s 132 KV bays along with Metering arrangement at proposed 132/25KV Makthal Railway Traction Substation in Mahabubnagar District | - | DCW | - | - |  | 66.14 |  | Consumer contribution | - |  | 07.08.2023 | 31.03.2026 | 04.02.2025 | 0 | 0.03 | 0 | 0.03
71 | D-23-08 | M/s.Microsoft Corporation (India)-Chanda | Extension of HT supply for a CMD of 163MVA in phased manner with an initial load of 17MVA to M/s. Microsoft corporation (india) Pvt Ltd, Plot.No.10, Nagarguda, Shamshabad Road, Hayathabad, Chandanvally(V), Shabad (M), R.R Dist., | - | DCW | - | - |  | 10.9 |  | Consumer contribution | - |  | Supervision work | 31.03.2026 | 26.09.2024 | 0.27 | -0.01 | 0 | 0.26
72 | D-23-09 | Extn.of sply 2 M/s.Microsoft, Mekaguda | Extension of HT supply for a CMD of 160MVA in phased manner to M/s. Microsoft Corporation India Limited at Sy No 859,862,880 & 892, Mekaguda Road, Near NATCO Pharma, RangaReddy District under DC works. | - | DCW | - | - |  | 26.85 |  | Consumer contribution | - |  | Supervision work | 31.03.2026 | 16.12.2024 | -3.35 | 0 | 0 | -3.35
73 | D-23-23 | Shifting of 132 KV Shapurnagar-Medchal DC line | Shifting of 132 KV Shapurnagar-Medchal DC line between Loc.Nos.32 to 35 passing through the land of J.Santhi and Chirumamilla Deepthi at sy.Nos.19 & others at Gundla Pochampally Village and Sy.nos.202 & others at Kandlakoya Village, Medchal Mandal in Ranga Reddy District | - | DCW | - | - | - | 2.27 | - | Consumer contribution | - | - | Supervision work |  | 09.07.2025 | 1.69 | -0.05 | 0 | 1.64
74 | D-24-05 | Diversion of existing 220KV Gachibowli-S | Diversion of Existing 220 KV DC Gachibowli - Shankarpally Circuit - I & II HTLS OH line between Location Nos.70 to 72 at M/s. Ventura Estate Developers, Kollur Village, Sanga Reddy District | - | DCW | - | - |  | 0.58 |  | Consumer contribution | - |  | Supervision work |  | 28.08.2024 | 0.02 | -0.02 | 0 | 0
75 | D-24-20 | Shifting of 220KV Shivarampally -Gachibo | (i) 220KV Shivarampally-Gachibowli (Raidurg) DC line with 220KV 1000 Sq.mm XLPE UG cable (650m) & (ii) 132 KV Jubilee Hills-Chandrayangutta DC line with 132 KV 1200 Sq.mm XLPE UG cable (600m) at Puppalaguda, gandipet for M/s. Aparna infrahousing Pvt.Ltd | - | DCW | - | - | - | 4.83 | - | Consumer contribution | - | - | Supervision work |  | 132 Kv & 220KV lines were charged on 08.02.2024 & 18.08.2024 respectively | - | -0.04 | 0 | -0.04
76 | D-24-97 | Shifting of 132KVSolar line for Railways | - | - | DCW | - | - | - |  |  | Consumer contribution | - |  |  |  |  | - | 0.23 | 0 | 0.23
77 | N-19-01 | Non Plan Capital works Exe by Const wing | - | - | - | - | - |  |  |  |  | - |  |  | 31.03.2026 |  | - | 0.01 | 0 | 0.01
78 | N-21-01 | Non Planned Capital works for FY 2021-22 | - | - | - | - | - |  |  |  |  | - |  |  | 31.03.2026 |  | 0.33 | 0 | 0 | 0.33
79 | N-22-01 | Non Planned Capital works for FY 2022-23 | - | - | - | - | - |  |  |  |  | - |  |  | 31.03.2026 |  | 3.82 | 0.74 | 0 | 4.56
80 | N-23-01 | Non Planned Capital works for FY 2023-24 | - | - | - | - | - |  |  |  |  | - |  |  | 31.03.2026 |  | 1.87 | 0.75 | 0 | 2.62
81 | N-24-01 | Non Plan Capital works Exe by Const wing | - | - | - | - | - |  |  |  |  | - |  |  | 31.03.2026 |  | 1.45 | 0.18 | 2.24 | 3.87
82 | N-25-01 | Non Plan Capital works Exe by Const wing | - | - | - | - | - |  |  |  |  | - |  |  | 31.03.2026 |  | 0 | 0.54 | 0.38 | 0.92
|  | Sub Total (On going) | [14 empty] | 429.85 | 41.0333 | 62.8133 | 533.6966 |  | 0 | 0 | 0 | 0
New schemes
1 | S-17-17 | 132/33 KV SS at Kanchanplly (v) of valigonda (M) | 132/33kV SS Kanchanpally(V) of Valigonda(M) | To bifurcate the 33kV loads on 33kV feeders emanating from Ramannapet, Bibinagar and Bhongir 132kV Substations to facilitate 24 hrs agricultural supply and to provide reliable & quality power in the scheme area under System Improvement | SI | T.O.O (CE-Transmission) Ms. No. 76, Dated:19.05.2017 | [6 empty] | - | 01.01.2026 | 31.03.2027 |  |  |  |  | 12.63 | 10.84 |  |  | 23.47 |  | Yes
Erection of 132 kV DC/SC line on Galvanised Towers with Panther ACSR from the existing 132/33 kV Sub-Station, Ramannapet to the proposed 132kV Sub-Station at Kanchanpally
1 No 132kV Bay at 132/33 kV Sub-Station
2 | S-20-02 | 132/33kV SS Dandu Malkapur in Yadadri Bhuvanagiri District | 132/33kV SS Dandu Malkapur in Yadadri Bhuvanagiri District | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses.The Superintending Engineer/OMC/Nalgonda has furnished the feasibility report for shifting of proposed 132/33KV SS Toopranpet to nearby industrial Estate i.e. TSIIC Dandu Malkapur (V), Choutuppal (M) in Yadadri Bhuvanagiri District | SI | T.O.O (CE-Construction) Ms. No. 965,Dated: 05.02 2021. | [6 empty] | - | 01.01.2026 | 31.03.2027 | - |  |  |  | 22.53 | 15.02 |  |  | 37.55 |  | Yes
Erection of 132 KV DC/SC line from 132/33 KV Choutuppal SS to proposed 132/33 KV SS at Dandu Malkapur
1No 132kV Bay at 132/33 KV Choutuppal SS
3 | - | 132/33 KV SS at K.C.Thanda, Maheshwaram | 132/33 kV SS K.C Thanda, Maheswram (M) | To supply quality power to the industries as well as domestic purpose | SI | - | - | [6 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 18.048 | 12.032 |  |  | 30.08 |  | Yes
132 kV LILO of 132kV Shamshabad-132kV SS Kothur to 132 kV K.C.Thanda
4 | - | 132/33 KV SS Boinpally | 132/33kv SS Boinpally | To alleviate low voltage problems in Rajanna Sircilla District | SI | - | - | [6 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 18.648 | 12.432 |  |  | 31.08 |  | Yes
132 kV LILO of 132kV Durshed -Mallaram line to 132/33 kV SS Boinpally
5 | - | 132/33 KV SS at Ankampalem | 132/33kV SS at Ankampalem(V), Dammapet (M) | To meet the demand of power supply as low voltage problems are persisting | SI | - | [7 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 14.328 | 9.552 |  |  | 23.88 |  | Yes
132 kV LILO of 132kV Khammam-132kV SS Peddagopathi to 132 kV Ankampalem
6 | - | 132/33 KV SS at Dilwapur | 132/33kV SS at Dilwapur | To meet the future load demad and to reduce laods on 132/33 KV SS Bibinagar | SI | - | [7 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 20.088 | 13.392 |  |  | 33.48 |  | Yes
132 kV LILO of 132kV Sarangapur-132kV SS Bhainsa to 132 kV Dilwapur
7 | - | 132/33 KV Bommalaramaram SS | 132/33 KV Bommalaramaram SS |  | SI | - | [7 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 25.632 | 17.088 |  |  | 42.72 |  | Yes
132 KV DC line from 220/132/33 KV SS Bhongiri to proposed 132/33 KV SS Bommalaramaram
2 Nos 132kV Bays at 220/132/33 KV SS Bhongiri
8 |  | 132/33 KV SS Aziznagar | 132/33 KV SS Aziznagar. | To meet the load demand of the industries and to avoid low voltage problems in and around Ibrahimpatnam | SI | - | [7 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 18.552 | 12.368 |  |  | 30.92 |  | Yes
132 KV DC line from Kanakamamidi toi proposed 132/33 KV SS Aziznagar
2 Nos 132kV Bays at 132/33kV SSKanakamamidi
9 |  | 132/33 KV SS Abdullapurmet | 132/33 KV SS Abdullapurmet | To meet the future load demand and to improve the voltage profile. | SI | - | [7 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 15.666 | 10.444 |  |  | 26.11 |  | Yes
132 KV LILO of 132 KV Ghanpur-Sangli to proposed 132/33 KV SS Abdullapuemet
132 KV 2nd circuit stringing from 132/33 KV SS Ghanapur to 132/33 KV Abdullapurmet SS
10 | S-22-03 | 132/33kV SS Vemula (V), Addakal (M) | 132/33kV SS Vemula (V), Addakal (M) | To provide quality, reliable & uninterrupted power supply to the consumers and also to meet the future demand and to extend the 9 Hours Power Supply during day time to Agriculture sector | SI | T.O.O (CE-Construction) Ms.No.1491 Dated: 20.10.2022. | [7 empty] | 01.02.2026 | 31.03.2027 |  |  |  |  | 13.17 | 19.75 |  |  | 32.92 |  | Yes
132 kV DC/SC line from 132/33kV SS Khillaghnapur to the proposed 132/33 kV Vemula SS on galvanised towers with panther ACSR Conductor
132kV Bay Extension (1No at 132kV SS Khillaghanapur)
11 | S-22-04 | 132 kV DC/SC line from 220/132 kV SS Madugula to 132kV Switching station Godakondla in Nalgonda Dist | Erection of 132 kV DC/SC line from 220/132 kV SS Madugula to 132kV Switching station Godakondla in Nalgonda Dist. | To facilitate the loads from 220/132/33 KV Madugula and to stream line the loads of 220/132/33 KV SS KMPally, 132 KV Switching station Nasarlapally, 132 KV Switching station Godakondla and 132/33 KV SS Marriguda as the 132 KV feeder from 220 KV SS KMPally to 132KV Switching station Godakondla is over loaded and to maintain reliable and quality power supply to the consumers in that scheme area | SI | T.O.O (CE-Construction) MS.No .1552 Dated:16.01.2023 | [7 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 8.5 | 12.6 |  |  | 21.1 |  | Yes
132kV Bay 1 No at 220 kV SS Madugula and 132kV Bay 1 No at 132 kV SWS Godakondla
12 | S-24-07 | LILO of 132KV Pochampadu - Nirmal line with 2nd circuit stringing on existing DC/SC line from tapping tower location No.28 up to 132/33 KV SS Burugupally by removing solid tapping arrangement | 2nd circuit stringing on existing DC/SC solid tapping line from tapping tower location No. 28 of 132 Kv Pochampad - Nirmal line up to 132/33 KV SS Burgupally. In Adilabad Dist. | Making LILO of 132KV Pochampadu - Nirmal line with 2nd circuit stringing on existing DC/SC line from tapping tower location No.28 up to 132/33 KV SS Burugupally by removing solid tapping arrangement due to operational and maintenance problems | SI | T.O.O (CE-Construction) Ms.No.2046, Dt:25.07.2024 | [7 empty] | 01.01.2026 | 31.03.2027 |  |  |  |  | 4.446 | 3.52 |  |  | 7.966 |  | Yes
132kV Bay at 132/33 KV SS Burugupally
13 | S-25-10 | Proposal for erection of alternate supply from 220/132/33 kV SS Shapurnagar to 132 kV SS Chintal & 220/132/33 kV SS Shapurnagar to 132/33 KV SS IDPL and 132/33 kV SS Chintal to 132/33 kV SS IDPL interlink with UG Cable in Medchal-Malkajgiri district | a)Laying of 132 KV 1200 sqmm. single circuit UG cable from 220KV SS Shapurnagar to 132KV SS Chintal -3.5KM b)Laying of 132 KV 1200 sqmm single circuit UG cable from 220KV SS Shapurnagar to 132KV SS IDPL- 10KM c)Laying of 132 KV 630 sqmm single circuit UG cable from 132 KV SS Chintal to 132 KV SS IDPL - 7.5KM d)132KV feeder Bay at 220 KV SS Shapurnagar (2 No.s) e)132KV feeder Bay at 132 KV SS Chintal(1 No.) f)132KV feeder Bay at 132 KV SS IDPL (2 No.s) | To provide alternate supply to Chintal & IDPL SS | SI | T.O.O (CE-Construction) Ms.No.2507, Dt:03.09.2025 | [7 empty] | 01.01.2026 | 31.03.2027 |  |  |  |  | 92.37 | 100 |  |  | 192.37 |  | Yes
14 |  | 220 KV DC line from 400/220/132 KV Narsapur ss to 220/132/33 KV Minpur SS | 220 KV DC line from 400/220/132 KV Narsapur ss to 220/132/33 KV Minpur SS | To strengthen the network | SI | [8 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 71.592 | 47.728 |  |  | 119.32 |  | Yes
at 400/220/132kV Narsapur SS - 2Nos and at 220/132/33 KV Minpur SS- 2Nos
15 | S-24-21 | Laying of 220KV DC line with 1200Sqmm XLPE UG Cable from 220/132KV GIS SS Osmania University to 220/132KV SS Nagole with connected 220KV Bays | a)Laying of 220KV DC line with 1200Sqmm XLPE UG Cable from 220/132KV GIS SS Osmania University to 220/132KV SS Nagole (7 kM). | To relieve transmission congestion | SI | T.O.O (CE-Construction) Ms.No.2231, Dt:17.02.2025 | [7 empty] | 01.01.2026 | 31.03.2027 |  |  |  |  | 80.352 | 97.15 |  |  | 177.502 |  | Yes
b)Erection of 2No.s 220KV feeder bays at 220/132KV SS Nagole(including SAS system). Erection of 2No.s 220KV GIS feeder bays at c)220/132KV GIS SS Osmania University. (including SAS system).
16 | S-23-03 | 220/33 kV GIS Substation Nemalinagar in Rangareddy Dist | 220/33 kV GIS Substation Nemalinagar in Rangareddy Dist | To meet an expected upcoming load of 140 MVA |  | T.O.O. (CE-Construction) Ms.No.1617 Dated: 12.04.2023. | [7 empty] | 01.03.2024 | 31.03.2027 |  |  |  |  | 113.028 | 75.352 |  |  | 188.38 |  | Yes
Making LILO of 220KV Shivarampally-Gachibowli OH Line to proposed 220/33KV GIS SS Nemalinagar i with 220KV 1200 Sq.mm UG cable.(3km) ii.with OH line on 400 kV Multi circuit Monopole tower with CTT
17 | S-23-02 | erection of 220/33 kV Substation in the premises of Central Power Research Institute (CPRI), Hyderabad | 220/33 kV Substation in the premises of Central Power Research Institute (CPRI) with SAS automation, Hyderabad-2 x 100MVA | 33KV supply can be extended for distribution in the vicinity of CPRI as the load demand is increasing rapidly in the scheme area of CPRI 220/33 kV SS which is at present fed from 220/132/33 kV SS Ghanapur with 33KV lines with a length of about 20 KM |  | T.O.O (CE-Construction) MS.No .1594 Dated:20.03.2023 | [7 empty] | 01.01.2026 | 31.03.2027 |  |  |  |  | 17.478 | 11.652 |  |  | 29.13 |  | Yes
18 | S-24-05 | 33 kV features at existing 220/132 kV SS Thimmajipet in Thimmajipet (M), Nagarkurnool district | 33 kV features at existing 220/132 KV SS Thimmajipet, Marikal (V) in Thimmajipet (M), Nagarkurnool District.2 x 50MVA | To divert increasing loads of 132KV Mahabubnagar - Jadcherla line, 132 KV SS Jadcherla to 220/132 KV SS Thimmajipet, reliable supply to station auxiliaries of 220/132 kV Thimmajipet SS and uninterrupted power supply to the consumers with better voltage profile |  | T.O.O. (CE-Construction) Ms.No.2047 Dated: 25.07.2024. | [7 empty] | 01.12.2025 | 31.03.2026 |  |  |  |  | 4.716 | 3.144 |  |  | 7.86 |  | Yes
19 | S-24-02 | Making LILO of one circuit of existing 220 KV Jagtial – Nirmal DC line to 400 KV SS Nirmal in Nirmal District | Making LILO of one circuit of existing 220 KV Jagitial – Nirmal DC line to 400 KV SS Nirmal in karimnagar Dist. | 400/220kV ICTs at NTPC Ramagundam are getting over loaded due to increase in 220 kV loads fed from 220 kV substation Malyalapally. Presently the 300 MVA load of 220/132kV SS Jagtial is mostly fed from 2 No’s 220 kV Malyalapally feeders. The power from 220 kV SS Nirmal cannot be drawn totally due to overloading of 220 kV feeders from 400 kV Nirmal SS to 220 KV Nirmal SS (only 2 circuits exist). If one circuit of 220kV Jagtial-Nirmal DC line is made LILO to 400 kV Nirmal substation the 220kV Jagtial substation some loads can be met from 400KV Nirmal SS which decreases the drawl from Malyalapally SS which in turn reduces loading of 400/220 kV ICTs at NTPC. Further 220 kV Nirmal SS will have a new 220 kV source line from 400 kV Nirmal SS | SI | T.O.O. (CE-Construction) Ms.No.1999 Dated: 18.06.2024. | [7 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 10.56 | 7.08 |  |  | 17.64 |  | Yes
2 Nos 220kV Bays at 400/220kV Nirmal
20 | S-24-04 | 220/33 kV GIS Substation at Alwal (R.P.Nilayam) in the premises of proposed TIMS (Telangana Institute of Medical Science) super specialty hospital in Medchal-Malkajgiri District instead of 132/33 kV AIS / GIS at R.P.Nilayam in Medchal-Malkajgiri District | 220/33 kV GIS Substation at Alwal (R.P.Nilayam) in the premises of proposed TIMS (Telangana Institute of Medical Science) super specialty hospital in Medchal-Malkajgiri District instead of 132/33 kV AIS / GIS at R.P.Nilayam in Medchal-Malkajgiri District | To (i) reduce overloading at 400/220/132/33 kV Sub-Station, Malkaram, 220/132/33 kV Sub-Station, Moulali and 132/33 kV Gurock (ii) reduce the time for fault location as the existing 33 kV lines which are a composition of Overhead & UG Cable (iii) to avoid the pulling out of PTR from the network, (iv) to provide reliable & uninterrupted power supply and (iv) to cater to the upcoming loads | SI | T.O.O. (CE-Construction) Ms.No.2042 Dated: 24.07.2024. | [7 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 30 | 41.79 |  |  | 71.79 |  | Yes
Making LILO of 220KV Shapurnagar - Moulali over head line (proposed to upgrade from existing 132 kV to 220 kV) with HTLS conductor to proposed 220/33 kV GIS Substation Alwal (R.P. Nilayam)
21 | S-21-07 | Upgradation of existing 132/33 KV SS Kathlapur to 220 kV SS | 1) Upgradation of existing 132/33 KV SS Kathlapur to 220 kV SS 2)Making LILO of 220 kV Medaram – Dichpally line to upgraded 220/132/33 kV Kathalapur SS on Galvanized Towers with Moose ACSR Conductor 3)Making LILO of 132 kV Dharmaram – Godur line to upgraded 220/132/33 kV Kathalapur SS on Galvanized Towers with Panther ACSR Conductor 4)Making LILO of 132 kV Godur – Pochampad line to upgraded 220/132/33 kV Kathalapur SS on Galvanized Towers with Panther ACSR Conductor | To mitigate overloading of both 132 KV RSS-Dharmaram & 132 KV Jagityal-Korutla feeders. | SI | T.O.O. (CE-Construction) Ms.No.1622 Dated: 16.12.2021. | [7 empty] | 01.10.2025 | 31.03.2027 |  |  |  |  | 30 | 43.29 |  |  | 73.29 |  | NO
22 | S-24-03 | 220KV DC line from 220/132KV SS Kamareddy to 220/11KV LISS Yacharam Thanda in Kamareddy District | a)Erection of 220 kV DC line from existing 220/132 kV Kamareddy SS to 220/11 kV LIS SS Yacharam Thanda - (43 kM) b)220 kV Bay at 220/132 kV SS Kamareddy including Bus extension, Bus Bar & Bus Coupler pannels & equipment (1No.) c)2 Nos at 220/11 kV LISS Yacharam Thanda & 1 No. at 220/132 kV SS Kamareddy | At present only one source i.e. 220KV DC line (out of these two 220KV Circuits, one circuit is radial and another circuit is via 220/11KV SS Kondapaka) is available to the existing 220/132KV SS Kamareddy from 400/220/132KV SS Gajwel. And also it is proposed for interlinking the 400/220KV SS Dichpally and 220/132KV SS Kamareddy substations by construction of 220KV DC line from 220/11KV LIS Substation at Yacharam Thanda to 220/132KV SS Kamareddy to provide an alternate source to 220/11 kV LIS substation at Yacharam Thanda from 220/132 kV SS Kamareddy and vice versa and also strengthening of the system can be done and better voltage profile can be maintained | SI | T.O.O. (CE-Construction) Ms.No.2041 Dated: 24.07.2024. | [7 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 50 | 36.14 |  |  | 86.14 |  | NO
23 |  | 220KV DC Line from Annaram SS to 220/132KV SS Manthani in peddapally District | 220KV DC Line from Annaram SS to 220/132KV SS Manthani in peddapally District- (15kM) | To strengthen the network | SI | [8 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 10 | 20 |  |  | 30 |  | NO
24 | S-25-08 | Making LILO of one circuit of Chandrayangutta-Jubilee Hills 132KV DC line to 132KV Mylardevulapally SS | Making LILO of one circuit of Chandrayangutta-Jubilee Hills 132KV DC line to 132KV Mylardevulapally SS with 1200sqmm UG cable (4.5 KM) 132KV feeder Bays at 132KV Mylardevulapally SS with PASS Module( 2 No.s) | Alternate source to 132/33 KV Mylardevulapally SS | SI | T.O.O (CE-Construction) Ms.No.2486, Dt:29.08.2025 | - | [6 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 40 | 65.21 |  |  | 105.21 |  | NO
25 | - | 2nd Circuit from 220KV Huzurabad to 132kV Kachapur SS and LILO the same to 132KVSS Huzurabad SS | 2nd Circuit from 220KV Huzurabad to 132kV Kachapur SS (19kM) and LILO the same to 132KVSS Huzurabad SS -(4kM) | To meet (n-1) contingency | SI | T.O.O (CE-Construction) Ms.No.2225 , Dt:14.02.2025 | [7 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 4 | 6 |  |  | 10 |  | NO
26 | S-25-03 | Stringing of 2nd circuit on 132KV JAKORA –Kotagiri line | Stringing of 2nd circuit on 132KV JAKORA –Kotagiri line -(12kM) | To meet (n-1) contingency | SI | [8 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 2 | 2 |  |  | 4 |  | NO
27 | - | 132kV DC/SC line from 220KV SS Indravelly to 132kV SS utnoo | 132kV DC/SC line from 220KV SS Indravelly to 132kV SS utnoor.-(5 kM) | Covered in 400KV SS Nirmal power Transmisison scheme | SI | T.O.O. (CE-400 kV Ms.No.07 Dated: 09.01.2018 | [7 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 3.5 | 3.5 |  |  | 7 |  | Yes
28 | - | 220/33 KV SS Kollur | a)220/33 KV SS Kollur- 2 x50MVA b) LILO of one circuit of 220KV Shankarpally- Gachibowli DC line for a LILO length of 1.5KM | To meet future load demand | SI | - | [7 empty] | 01.03.2026 | 31.03.2027 |  |  |  |  | 10 | 13.25 |  |  | 23.25 |  | Yes
| Sub Total (New schemes) | [18 empty] | 761.834 | 722.324 | 0 | 0 | 1484.158
| Grand Total | [16 empty] | 41.0333 | 62.8133 | 1295.5306 | 722.324 | 0 | 0 | 1484.158
12.63
22.53
18.048
18.648
14.328
20.088
25.632
18.552
15.666
13.17
8.5
4.446
92.37
71.592
80.352
113.028
17.478
4.716
10.56
30
30
50
10
40
4
2
3.5
10
761.834

## CapEx 26-27
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2026-27 for Transmission Business filed with TGERC
Scheme wise details of Capital Expenditure proposed for Financial Year 2026-27
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme maybe given) | Justification | Project Purpose (SI/SE/SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total TGERC approved Cost (in Cr) | Source of funds |  |  |  | Proposed Project Start Date DD-MM-YY | Proposed Project Completion Date DD-MM-YY | Estimated Yearly Capital Expenditure proposed (in Cr) | [5 empty] | Present Status of work | Whether approved in Resource plan or not
[10 empty] | TGTransco funds | Loan source | Loan Amount | Grants, if any |  |  | CWIP O.B. | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Totals
1 | 2 | 3 | 4 |  | 5 | 6 | - | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 22 | 23
1 | S-17-19 | 132/33 KV SS at Pitlam | 132/33 kV SS at Pitlam | To feed the existing & upcoming loads and to improve the voltage regulation in 33KV feeders. The scheme will also cater the loads of 24 hours Agriculture supply. | SI | T.O.O (CE-Construction) Ms. No.2219, Dated: 12.02.2025 | [7 empty] | 01.04.2026 | 31.03.2028 |  | 21.48 | 17.07 |  |  | 38.55 |  | Yes
132 kV DC/SC line from 220/132/33KV Banswada SS to the proposed 132/33 kV Pitlam SS.
2 | - | 132 kV DC/SC line from existing 132/33KV Zaheerabad Sub-Station to the existing 132/33 kV Narayankhed Sub-Station in Medak District | 132 KV DC/SC line from existing 132/33 KV Zaheerabad SS to existing 132/33 kV SS Narayankhed | To maintain reliable power supply to industries and 24 hrs agriculture supply | SI | T.O.O (CE-Construction) Ms. No. 44 Dated:06.03.2018. | - | [6 empty] | 01.04.2026 | 31.03.2028 |  | 36.21 | 24.14 |  |  | 60.35 |  | Yes
132kV Bay at 132/33 KV Zaheerabad SS - 1No and 132kV Bay at 132/33 kV SS Narayankhed- 1No
3 | - | Connecting the existing 132 kV Shapurnagar – Bhongir – Aleru idle line to 400/220/132 kV Malkaram Sub-Station | connecting the existing 132 kV Shapurnagar – Bhongir – Aleru line to 400/220/132 kV Malkaram SS and 400/220/132 kV Ghanapur SS (UG cable) | For reducing loads on the 220/132 KV Shapurnagar sub-station | SI | T.O.O (CE-Construction) MS.No .11 Dated: 20.04.2018 | - | [6 empty] | 01.04.2026 | 31.03.2028 |  | 11.952 | 7.968 |  |  | 19.92 |  | Yes
Second circuit stringing of existing 132 KV DC/SC line for connecting the existing 132 kV Shapurnagar – Bhongir – Aleru idle line to 400/220/132 kV Malkaram Sub-Station
132kV Bay at 220 KV SS Shapurnagar - 1No 132kV Bay at 400 KV SS Malkaram - 1 No
4 |  | 132kV DC line from 132/33kV SS Munugodu to 400/220/132kV SS choutuppa | 132kV DC line from 132/33kV SS Munugodu to 400/220/132kV SS choutuppal (30KM) | To strengthen the network and to reduce the line loading | SI | - | - | [6 empty] | 01.04.2026 | 31.03.2028 |  | 17.568 | 11.712 |  |  | 29.28 |  | Yes
132kV Bay at 132/33kV SS Munugodu - 2Nos 132kV Bay at 400/220/132kV SS choutuppal - 2Nos
5 |  | 132/33kV SS at Muthireddy gudem | Erection of 132/33kV SS at Muthireddy gudem village of Muthkondur Mandal Yadadri bhongir Dist | To reduce loads on Mothkur & kolanpak SS | SI | - | - | [6 empty] | 01.04.2026 | 31.03.2028 |  | 29.892 | 19.928 |  |  | 49.82 |  | Yes
Erection of 132kV DC/SC line from 132/33kV SS Mothkur to 132/33kV SS Muthireddygudem in Yadadri District.
1 No 132kv bay at 132/33 KV SS Mothkur
6 |  | 132kV DC/SC line from 220/132kV SS Husnabad to 132/33kV SS Mustyal in Jangaon District | Erection of 132kV DC/SC line from 220/132kV SS Husnabad to 132/33kV SS Mustyal in Jangaon District. | To strengthen the network and to reduce the line loading | SI | - | - | [6 empty] | 01.04.2026 | 31.03.2028 |  | 18.75 | 12.5 |  |  | 31.25 |  | Yes
132kV Bay at 220/132/33 KV SS Husbanbad & 132kV Bay at 132/33 kV Mustyal SS
7 |  | 2 nd circuit stringing from 132/33 kV SS NV puram to 132/33 kV SS Kamalapuram in Warangal Dist. S | 2 nd circuit stringing from 132/33 kV SS NV puram to 132/33 kV SS Kamalapuram in Warangal Dist. | To meet n-1 contingency | SI | T.O.O (CE-Construction) Ms.No.2230, Dt:15.02.2025 | - | [6 empty] | 01.04.2026 | 31.03.2028 |  | 2.124 | 1.416 |  |  | 3.54 |  | Yes
132kV Bay at 132/33 KV SS NV Puram & 132kV Bay at Kamalapuram
8 |  | 2nd circuit Stringing from 132/33kV SS Pudur to 132/33/11 kV SS Gangadhara in karimnagar Dist. | 2nd circuit Stringing from 132/33kV SS Pudur to 132/33/11 kV SS Gangadhara in karimnagar Dist. | To meet n-1 contingency | SI | - | - | [6 empty] | 01.04.2026 | 31.03.2028 |  | 2.43 | 1.62 |  |  | 4.05 |  | Yes
132kV Bay at132/33kV SS Pudur & 132kV Bay at 132/33/11 kV SS Gangadhara
9 |  | 220KV Single Moose DC Line from proposed 400/220/132kV KTPP SS to 220/132kV Manthani SS | 220KV Single Moose DC Line from proposed 400/220/132kV KTPP SS to 220/132kV Manthani SS | To meet the load of existing 220kV&132kV Substations and to reduce the transmission losses in Bhupalapally District. The scheme also provides a source to meet the load demand of LI Schemes at Bheemghanpur and Devannapet LI Substations | SI | T.O.O.(CE-400kV) Ms.No.297, Dt:09.02.2019 | - | [6 empty] | 01.04.2026 | 31.03.2028 |  | 42.744 | 28.496 |  |  | 71.24 |  | Yes
220kV Bays at 220kV SS Manthani - 2 Nos
10 |  | 220/132/33KV Medchal (AIS) | 220/132/33KV Medchal (AIS) | To meet the future load demand | SI | - | - | [6 empty] | 01.04.2026 | 31.03.2028 |  | 35 | 35 |  |  | 70 |  | NO
11 | S-25-12 | 220/33 KV HMT Hills (AIS) | a)Erection of 220/33KV HMT Hills GIS Substation with 2X100 MVA PTRs Capacity with SAS automation system b)Making LILO of 220KV Shapurnagar-Gachibowli line to proposed 220/33KV HMT Hills GIS Substation with 2500Sqmm UG cable. (0.2 KM) | To reduce the load on Miyapur, Khaitalapur & Bollaram Substations | SI | T.O.O. (CE-Construction) Ms.No.2512, Dt:09.09.2025 | - | [6 empty] | 01.04.2026 | 31.03.2028 |  | 50 | 49 |  |  | 99 |  | NO
12 | S-24-22 | 220/33KV SS Penpahad | a)Erection of 220/132/33KV SS Penpahad with 2X160MVA (220/132 KV) & 2X50MVA (132/33 kV) PTR Capacity b)Making LILO of 220KV SC line from KTPS - Miryalaguda to proposed 220/132/33kV SS Penpahad.(2KM) c)132KV DC line from proposed 220/132/33KV SS Penpahad to existing 132/33KV SS Munagala. (20KM) d)132kV Bays at 132/33kV SS Munagala (2 No.s) | To provide alternate supply to 132 KV SS Suryapet, 132 KV SS Munagala and to minimize the line losses of KTPS-Miryalaguda 220KV line | SI | T.O.O (CE-Construction) Ms.No.2224, dt:14.02.2025 | - | [6 empty] | 01.04.2026 | 31.03.2028 |  | 25 | 25 |  |  | 50 |  | NO
13 | S-24-20 | 220/132 KV SS Nandipet | a)220/132kV SS Nandipet with 3x160 MVA PTR capacity b)Making double LILO of 220KV Dichpally-Saragapur DC line to proposed 220/132KV SS Nandipet.(16.5KM) c)2nd circuit stringing on existing 132KVNandipet-CH.Kondur DC/SC line.(7.5KM) d)Making LILO of one circuitof 132KV Nandipet-CH.Kondur line to proposed 220/132 KVSS Nandipet.(0.5KM) e)132KV DC line from proposed 220/132KV SS Nandipet to existing 132/33KV SS Bagepally.(2KM) f)132KV DC line from proposed 220/132KV SS Nandipet to existing 132/33KV SS Nandipet.(1.5KM) | To improve the voltage profile, reduction in system losses and to provide alternate source to 132 KV SS Nandipet, 132 KV Ch.Kondur, 132 KV SS Armoor and 132 Kv SS Bagepally | SI | T.O.O (CE-Construction) Ms.No.2234, dt:18.02.2025 | - | [6 empty] | 01.04.2026 | 31.03.2028 |  | 80 | 80 |  |  | 160 |  | NO
14 |  | 132/33 KV SS Epuru | 132/33 KV SS Epuru | To reduce loadings on 132 KV SS Choutuppal, 132 KV SS Ramannapet and 132 KV SS Munugodu | SI | - | [7 empty] | 01.04.2026 | 31.03.2028 |  | 10 | 10 |  |  | 20
15 | S-24-25 | 132/33 KV SS Rasoolpally | a)Erection of 132/33KV SS Rasoolpally with 2X50 MVA PTR Capacity b)Making LILO of both circuits of 132KV Mandamarry - STPP DC line to 132/33 KV proposed Rasoolpally SS on multi circuit towers. | To improve the voltage regulation in the scheme area | SI | T.O.O (CE-Construction) Ms.No.2247, dt:01.03.2025 | - | [6 empty] | 01.04.2026 | 31.03.2028 |  | 15 | 15 |  |  | 30
16 |  | 33KV features at 220KV SS Sadashivpet | 33KV features at 220KV SS Sadashivpet | To meet the increasing load demand and to maintain better voltage profile | SI | - | - | [6 empty] | 01.04.2026 | 31.03.2028 |  | 12 | 8 |  |  | 20
17 |  | LILO of 220 kv line from 400kV Jangaon -Waddekothapally Ckt-I to 220KV SS Jangaon in Janagaon Distric | LILO of 220 kv line from 400kV Jangaon -Waddekothapally Ckt-I to 220KV SS Jangaon in Janagaon District- (3kM) | To meet n-1 contingency | SI | [8 empty] | 01.04.2025 | 01.03.2026 |  | 8 |  |  |  | 8
18 | S-24-23 | 2nd circuit from 132 kV SS RC Puram to 132 kV SS | 2nd circuit from 132 kV SS RC Puram to 132 kV SS Patancheru on existing line -(6 kM) | To meet (n-1) contingency | SI | T.O.O (CE-Construction) Ms.No.2242 , Dated: 25.02.2025 | [7 empty] | 01.04.2025 | 31.03.2026 |  | 5 |  |  |  | 5
19 |  | Alternate supply from 220 kV Siricilla to 132/33kV SS Chippalapally | Alternate supply from 220 kV Siricilla to 132/33kV SS Chippalapally - (32kM) | To strengthen the network and to reduce the line loading | SI | - | - | [6 empty] | 01.04.2025 | 31.03.2026 |  | 7 |  |  |  | 7
[17 empty] | 430.15 | 346.85 | 0 | 0 | 777
1152.474