## 2024-25 SI works
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2026-27 for Transmission Business filed with TGERC
Scheme-wise details of Capital Expenditure incurred in FY: 2024-25 of 4th control period
(figures in Crores)
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme) | Justification | Project Purpose (SI/SE/SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total approved Cost (in Cr) | Source of funds |  |  |  | Project Start Date (DD-MM-YY) | Project Completion Date (DD-MM-YY) | DOC | Opening CWIP as on 31.03.2024 | Actual Expenditure from 01.04.2024 to 31.03.2025 | Cumulative expenditure upto 31.03.2025 | % Capatalisation | Remarks / Balance works , if any.
[10 empty] | TGTransco Funds | Loan source | Loan Amount | Grants, if any
1 | S-03-03 | ERECTION OF 220 KV SS & LINES UNDER PFC | a) 220KV SS Jurala b) 220KV DC line from Veltoor to Wanaparthy | To provide reliable and uninterrupted power supply and to strengthen the network | SI | T.O.O (CE-Transmission) Ms.No.313, Dated:10.03.2003 | - | - | 228.81 | - | PFC | 210 | - | 31.03.2008 | 31.03.2026 | a) 30.01.2012 b)08.09.2010 | - | 0 | 0 | - | -
2 | S-07-02 | ERECTION OF 132 KV LILO TO JURALA FROM E | a) 220/132 KV SS (2x100MVA) adjacent to Priyadarshini Jurala Hydroelectric Project Switchyard b)220KV DC line from 400KV SS Veltoor to 220KV SS Jurala c) 132 KV LILO line to 220/132 KV SS Jurala from Gadwal-Makthal 132 KV line including 1km of river crossing with JC towers | Capacity Addition Programme of 11th five year plan. | SI | T.O.O (CE-Transmission) Ms.No.105,Dt:22.08.2007 | - | - | 45.37 | - | Bank of Baroda | 42 | - | 31.04.2009 | 31.03.2026 | 25.05.2010 | 0 | 0.03 | 0.03 | - | -
3 | S-07-03 | ERRAGADDA AND O.U GIS &CABLES SCHEME | a) 220/132 kV Substation at Erragadda with 3 X 160 MVA power Transformer capacity b)220 kV LILO UG XPLE cable to the proposed Erragadda substation from Gachibowli – Shapurnagar line(8kM) c)220/132/33 kV Substation at Osmania University with 2 X 160 + 2 x80 MVA power Transformer capacity (Radial) d)220 kV DC UG XPLE cable to the proposed Osmania University substation from 220kV Moulali SS(14.40KM) e)220 kV Bay extensions at Moulali (2Nos.) | In order to cope up with the load growth in the twin cities and to provide quality power supply, and to develop the transmission network in the twin cities. | SI | T.O.O (CE-Construction-I) Ms.No.245,Dt:29.09.2011 | - | - | 525.25 | - | PFC | 415 | - | 27.12.2011 | 31.03.2026 | E-27.05.2015 O.U.-14.10.2015 | - | -0.26 | -0.26 | - | -
4 | S-07-04 | TWIN CITIES TRANSMISSION SYSTEM | The details are enclosed in the annexure | In order to cope up with the load growth in the twin cities and to provide quality power supply | SI | TOO (CE-Construction) MS NO.379, Dt:17.01.2012 | - | - | 1410 | - | JICA | 1200 | - | 01.08.2014 | 31.03.2026 | The charging details are enclosed in Annexure-I | 1.59 | 0.52 | 2.11 | - | -
5 | S-08-08 | 132 /33 KV GIS NARAYANAGUDA SCHEME | a) 132/33 kV GIS Sub-Station at Narayanguda (Shanthi Theatre) with 2 x 50MVA B) 132 kV Line with XLPE UG Cable from 132/33 kV Sub-Station, Fever Hospital to the proposed 132/33 kV Sub-Station, Narayanguda (Shanthi Theatre). (3KM) | To provide uninterrupted power supply to twin cities in and around Bachupalli and Narayanguda areas. | SI | TOO (CE-Transmission) MS No.140, Dt:13.10.2016 (Revised) | - | CRN.No./TST/TS/220-132 KV GIS-Hyd/F.Invst./99/2019, Dt:20.02.2009 | 156.23 | - | PFC | 150 | - | 31.05.2013 | 31.03.2026 | 07.12.2017 | - | 0 | 0 | - | -
6 | S-08-11 | 132 KV Mamidipally SS with connected line | a)132/33 kV Substation at Mamidipally with 1x31.5 + 1x50 MVA PTR Capacity (Radial) b))220 kV DC line from proposed 132/33 kV Mamidipally substation up to Loc.No.12 of 220 kV line to the proposed 220/132 kV Fab city from 400/220 kV Mamidipally substation with narrow based towers.(6KM) c)220 kV 2 circuits(3rd & 4th circuit) stringing from Loc. No. 12 on the existing narrow based M/C towers up to 220/132 kV Fab city on the 220 kV DC line from 400/220 kV Mamidipally substation to 220/132 kV Fab city( circuit 1 & 2 are already covered under Fab city line)(4KM) d)132 kV Bay extension-1 No. | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Transmission) Ms. No. 59 Dated:19.04.2016 | - | APT/TS/132 kV SS-Mamidipalli/ F-INVST - 12/2013 | 21.92 | - | PFC | 19.72 | - | 26.06.2009 | 31.03.2026 | 31.03.2016 | 0 | -0.1 | -0.1 | - | -
7 | S-10-14 | ERECTION220/132 KV SUBSTATION MANTHANI | 1)220/132kV Substation at Manthani with 2*100 MVA PTR Capacity 2)220kV LILO to proposed 220kV SS, Manthani from 220kV RSS-Warangal DC line (25KM) 3a)Stringing of two circuits on the already proposed multi-circuit towers from the proposed 220 kV SS, Manthani to Location No. AP 10 of 132kV Line from proposed 220kV SS, Manthani to the proposed 132kV SS, Kamanpur(9.5Km) b)Erection of 132 kV DC Line from Location No. AP – 10 of 132 kV Kamanpur Line to the Tap point of 132 kV RSS – Kamalapur DC Line(0.5KM) 4)132kV LILO to132kV Chelpur SS from 132 kV RSS - OCM feeder DC line(3KM) 5)Erection of 132 kV DC Line on Multi - Circuit Towers for LILO of Manthani - Kataram Line to 220 kV Sub-Station, Manthani(5Km) 6)132kV Bay extensions at 132kV Chelpur SS & 2 Nos at 220kV SS, Manthani | To provide reliable supply to the Domestic, Commercial and Agricultural loads near Manthani, Kataram, Chennur and Chelpur areas | SI | T.O.O (CE-Construction-I) Ms. No. 18 , Dated: 15.04.2014 (Revised) | - | APT/TS/220/132KV/33KV -Manthani/F.-Invest.-01/2010,08.10.2014 | 55.21 | - | UCO bank | 49.66 | - | 09.11.2014 | 31.03.2026 | 06.01.2016 | - | 0.07 | 0.07 | - | -
8 | S-10-17 | 132/33 KV SUBSTATION at N.V.Puram | a)132/33 kV Substation at N.V.Puram with 2 x 16 MVA (Released) PTR Capacity (Radial) b)132kV DC/SC line from Kamalapuram 132/33 kV SS in Warangal district to the proposed 132/33 kV N.V.Puram Substation(5.5KM) c) 220 kV DC/SC line on Galvanized JC Towers with Moose conductor in Godavari river crossing area (4.5KM) d)132 kV Bay extension at Kamalapuram in Warangal district (1 No.) | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Construction-I) Ms. No. 11 , Dated: 07.03.2014 (Revised) | - | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 18.01 | - | REC | 10.55 | - | 07.08.2016 | 31.03.2026 | 24.06.2019 | - | -0.07 | -0.07 | - | -
9 | S-10-20 | 220KV SWG SS AT THIMJIPET & LINES | a)220 switching station at Thimmajipet. b)220 kV DC line from 400 kV Veltoor Sub-Station to the proposed 220 switching station at Thimmajipet.(45KM) c)220 kV DC line from 400 kV Veltoor Sub-Station to the proposed 220 switching station at Thimmajipet.(1KM) d)220 kV LILO line from 220 kV Bhoothpur-Kalwakurthy circuit –II to the proposed 220 switching station at Thimmajipet.(1KM) e)220 KV Bay extension at 400 KV Veltoor SS (2 no.s) | For system strengthening in addition to the already approved System Improvement / Evacuation schemes under Comprehensive Transmission Requirement Scheme for the Years 2012 – 2017 | SI | T.O.O (CE-Construction) MS. No.319 Dated: 06.11.2010 | - | APT/TS/220 kV - SW.Stn / F-INVST - 2/2013 | 74.76 | - | PFC | 67.46 | - | 30.09.2013 | 31.03.2026 | 01.03.2016 | 0.18 | -0.01 | 0.17 | - | -
| S-10-21 | 132 KV SS AT TOOPRANPET | 132/33 KV Sub-station at Dandu Malkapur (V) in Chotuppal (M) of Yadadri Bhuvanagiri District is issued instead of Toopranpet | [13 empty] | 0.01 | - | 0.01 | - | -
10 | S-11-06 | 2ND CIRCUIT FROM 132KV SHALIGOURARAM SS | a)Erection of 2nd circuit stringing from 132 kV Shaligouraram SS to new Aitipamula 132 kV SS(28.5KM) B)132 kV Bay extensions at 132 kV Shaligowraram SS and new Atipamula 132 kV SS (2 no.s) | To meet (n-1) contingency | SI | T.O.O (CE-Construction-I) MS. No. 447 Dated: 21.01.2011 | - | Not Necessary | 3.66 | - | UCO Bank | 2.34 | - | 22.02.2012 | 31.03.2026 | 27.02.2013 | - | 0 | 0 | - | -
11 | S-11-09 | ERECTION OF 132/33 KV CHIPPALPALLI SS | a)132/33 kV Substation at Chippapalli with 3 x 10/16 MVA (released) MVA PTR Capacity (Radial) b)132kV DC/SC line from Kamareddy 220/132 kV Substation to the proposed 132/33 kV Chippapalli Substation(61KM) c)132 kV Bay extension at Kamareddy 220/132 kV Substation(1 No.) | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Transmission) Ms. No. 201 Dated: 30.10.2015 | - | APT / TS / 132 KVSS-Chippapally / F-INVST/31/2013. | 34.08 | - | NABARD | 32 | - | 20.01.2016 | 31.03.2026 | 21.12.2015 | - | 0.18 | 0.18 | - | -
12 | S-11-11 | 132KV parigi dmsagar line | a)132 kV DC line from the proposed 220/132/33 kV SS Parigi to 132/33 kV SS Dharmasagar(35KM) b)132 kV Bay extension 2 Nos. at 220/132/33 kV SS Parigi and 2 Nos. at 132/33 kV SS Dharmasagar (4 no.s) | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Construction) MS.No .82 Dated:18.04.2018 | - | CRN.No.TST/TS132 kV SSt Donthanpalli/F-INVST-06/2013/Dt:08.10.2014 | 32.15 | - | REC | 19.26 | - | 13.12.2016 | 31.12.2026 | Work in Progress | 20.68 | 0.68 | 21.36 | - | -
13 | S-11-16 | 220/132KV SUBSTATION at HUZURNAGAR in | a)220/132/33 kV Substation at Huzurnagar with 2*100 + 2*31.5 MVA PTR Capacity with 4 Nos. 132 kV Bays b)220 kV DC line for LILO of one of the circuits Chilakallu - Narketpally DC Line to the proposed Huzurnagar SS(25KM) c)132 kV DC Line from 132/33 kVMattampally SS to proposed 220 kV Huzurnagar SS(15KM) d)132 kV DC Line from 132/33 kV Vepalasingaram SS to proposed 220 kV Huzurnagar SS(10KM) e)132 kV Bay extensions at 132 kV Mattampally & 132 kV Vepalasingaram SS(4No.s) | To meet the existing and upcoming industrial loads and reliable power supply for industries (Cement Industries and Railway Traction). | SI | T.O.O (CE-Construction-I) MS. No. 83 , Dated: 21.06.2013 | - | CRN.No.APT/TS/220/132 kV SS-Huzurnagar/F-INVST-01/2014/Dt:20.04.2013 | 54.9 | - | PFC | 62.65 | - | 31.10.2013 | 31.03.2026 | 10.12.2018 | 0 | 0 | 0 | - | -
14 | S-11-19 | ERECTION 132/33 KV KATHLAPUR SS | a)132/33 kV Substation at Kathlapur with 2 x 16 MVA (Released) PTR Capacity (Radial)) b)132kV DC/SC line from Korutla 132 kV Substation to the proposed 132/33 kV Kathlapur Substation(15KM) c)132 kV Bay extension at Korutla132 kV Substation (1 No.) | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Construction-I) Ms. No. 297 ,Dated: 21.11.2011 | - | CRN;APT/TS/ 132 kV SS Kathlapur / F.INVST - 09/2014. | 14.15 | - | TMB | 12 | - | 21.11.2011 | 31.03.2026 | 11.01.2018 | 0 | 0.16 | 0.16 | - | -
15 | S-11-26 | ERECTION OF 132/33 KV SUBSTATION AT MUNUGODU | a)132/33 kV Substation at Munugodu with 1 x31.5 + 1 x 16 MVA (Released) PTR Capacity (Radial) b)132kV DC/SC line from 132/33 kV Nalgonda Substation to the proposed 132/33 kV Munugodu Substation(25KM) c)132 kV Bay extension at 132/33 kV Nalgonda Substation | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Construction-I) Ms. No.5 ,Dated: 06.04.2011 | - | APT/TS/132kV SS-Munugodu/F-INVST-08/2014 | 19.34 | - | REC | 16.14 | - | 13.06.2016 | 31.03.2026 | 05.10.2017 | - | 0 | 0 | - | -
16 | S-11-28 | 132/33 KV SS At NIMMAPALLI | a)132/33 kV Sub-Station at Nimmapally with 2X10/16 MVA (Released) PTRs b)132 kV DC / SC line with Panther ACSR Conductor on Galvanised Towers from the proposed 220/132 kV SS, Sircilla to proposed 132/33 kV Sub-station at Nimmapally(21KM) | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | TOO (CE-Transmission) MS.NO.161 dt:26-08-2015 | - | Not Necessary | 19.7 | - | REC | 17.73 | - | 23.03.2018 | 31.03.2026 | 29.04.2021 | 0.07 | 0 | 0.07 | - | -
17 | S-11-35 | SHIFTING OF 132KV SS AT WADAPALLY | a)132/33 kV SS Wadapally (NEW) and 132 kV LILO arrangements to 132/33 kV SS Wadapally (NEW) along with PLCC equipment b)132/33 kV Sub-Station at Wadapally with 1 X 31.5 +1 X 16 MVA PTRs With 7 Nos., 132 kV Incoming Feeder Bays, 4 Nos. 33 kV Feeders | shifting of 132/33 kV Wadapally Sub-Station to outside the premises of M/s India Cements, which was constructed near to the cement plant and commissioned on 19.05.1982, considering the accumulation of dust on the Sub-Station equipment and control room that emanated from the cement plant, thus causing problems that were being encountered in carrying out the day to day operations, regular maintenance, also to avoid failure of equipment and frequent interruptions to the EHT consumers. | SI | T.O.O (CE-Construction) Ms.No. 106 Dated:17 .06.2015 | - | Not Necessary | 11.41 | - | PFC | 4.4 | - | 17.06.2015 | 31.03.2026 | 18.06.2016 | 0 | 0 | 0 | - | -
18 | S-11-38 | 132/33 KV YELDURTHY SS & LINE | 1)132/33 kV Substation at Yeldurthy with 2 x 31.5 MVA PTR Capacity (Radial) 2a)132kV XLPE Cable from Chegunta 132 kV Substation to AP.No. 1 (0.7KM) b)132kV DC/SC line from Chegunta 132 kV Substation to the proposed 132/33 kV Yeldurthy Substation(17.3KM) 3)132 kV Bay extension at Chegunta 132 kV Substation(1KM) | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Construction-I) MS. No. 173 Dated: 03.09.2012 | - | APT/TS/132 kV SS -Yeldurthy/F-INVST - 7/2013 | 23.07 | - | NABARD | 17.27 | - | 12.08.2016 | 31.03.2026 | 02.08.2018 | - | 0 | 0 | - | -
19 | S-12-02 | 132/33 KV SS AT AREMPULA ALONG WITH 132K | a)Erection of 132/33kV Substation at Arempula with released 3X10/16 MVA PTRs. B) Erection of 132kV DC line to proposed Arempula 132/33kV SS by making LILO of second circuit of existing 132kV DC line from 220/132kV Budidampadu SS to 132kV Khammam Substation (15KM) | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Construction) Ms.No. 16 Dated: 22 .06.2015 | - | TST/TS/132/33kV SS Arempula / F-INVST- 12/2015 | 21.53 | - | Tamilnadu Mercantile Bank | 19.37 | - | 06.06.2016 | 31.03.2026 | 10.08.2017 | - | -0.13 | -0.13 | - | -
20 | S-12-09 | 132KV DC/SC LINE YDMLRM-PMAILARAM | a) 132 kV DC/SC line with narrow based towers from 220 kV Yeddumailaram SS to 132 kV Pashamailaram SS(7KM)) b)132 kV Bay extension at 220 kV Yeddumailaram SS and 132 kV Pashamailaram SS | For strengthening of 132 kV system | SI | T.O.O (CE-Construction-I) MS. No. 61 ,Dated: 25.05.2012 | - | APT/TS/132/Yeddumailram/F-INVST-27/2013 |  | - | NABARD | 9.22 | - | 09.05.2019 | 31.03.2026 | 27.09.2022 | 0 | 0.13 | 0.13 | - | -
| S-12-13 | Erection of 132/33 kV SS at Palakurthy | a)132/33 kV Substation at Palakurthy with 2 x 16 MVA (Released) PTR Capacity b)132kV DC/SC line from Waddekothapally 220/132 kV Substation to the proposed 132/33 kV Palakurthy Substation(Radial)(29KM) c)132 kV Bay extension at Waddekothapally 220/132 kV Substation (1No.) | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Construction-I) Ms. No. 399 ,Dated: 21.01.2012 | - | CRN.No. APT/TS/132 KVSS-palakurthy/F.Invest. 16/2013 | 19.63 | - | TMB | 19.11 | - | 12.11.2015 | 31.03.2026 | 29.07.2016 | 0 | - | 0 | - | -
21 | S-12-15 | 132/33 KV SS SALKUNOOR & LINE | a)132/33 kV Substation at Salkunoor with 2 x 16 MVA Capacity (Released) PTRs b)132kV DC line for making one circuit LILO of 132 kV DC line from 220/132 kV substation Miryalaguda to 132/33 kV substation Suryapet line at the proposed 132 kV Sub-Station, Salkanoor(3KM) | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Transmission) Ms. No. 30 ,Dated: 18.02.2016 | - | Not Necessary | 12.38 | - | REC | 10.38 | - | 01.04.2026 | 31.12.2027 | - | 0.04 | - | 0.04 | - | -
| S-12-29 | Up gradation of 132 KV SS Renjal to 220 | Covered in downstream work of 400KV Nirmal power Transmisison scheme | [13 empty] | 0 | - | 0 | - | -
22 | S-13-02 | ERECTION 220/132KV SS AT AYYAGARIPALLY | a)220/132 Sub-Station at Ayyagaripally (Mahabubabad) in Warangal District with 2 X 100 MVA PTR Capacity, Double Bus, Arrangement, 5 Nos 220 kV Feeder Bays, 4 Nos. 132 kV Feeder Bays and Sub-Station Automation System b)220kV Line with Four (4) Circuits on Multi - Circuit Towers for LILO of both the Circuits of 220 kV Warangal - Boodidampadu DC Line at proposed 220 kV SS, Ayyagaripally (Mahabubabad) c)132kV DC/SC line from the proposed 220/132 kV SS,Ayyagaripally (Mahabubabad) to 132 kV SS, Nekkonda d)Erection of 132 kV line with four circuits on Multi Circuit towers forLILO of two circuits of existing 132 kV Ayyagaripally - KTS line to the proposed 220 kV Ayyagaripally (Mahabubabad) SS.(2KM) e)132 kV Bay extension at Nekkonda | The Comprehensive Scheme includes erection of 220/132 kV Sub-Station, Ayyagaripally in Warangal Districtfor system strengthening in addition to the already approved System Improvement / Evacuation schemes | SI | T.O.O (CE-Transmission)MS.No. 5 Dated:11.01.2016 | - | TST/TS / 220/132 kV SS Ayyagaripally, Mahabubabad /F-INVST- 03/16 - 2016-17 | 78.33 | - | REC | 68.9 | - | 02.03.2016 | 31.03.2026 | 29.01.2018 | 0 | 0 | 0 | - | -
23 | S-13-03 | 220/132/33KV BONGULOOR SS IN RR DISTRICT | a)Erection 220/132 /33kV SS at Bonguloor with 2X100 MVA + 2X50 MVA PTR Capacity b)Erection of 220 KV line on Narrow Based Multi Circuit Towers with 4 Circuits for LILO of both Circuits of Dindi - Chandrayangutta 220 KV DC Line to the proposed 220 kV SS, Bonguloor.(1KM) c)Erection of 132 kV DC Line on Narrow Based Towers for LILO of 132 kV Ibrahimpatnam - Turkayamzal SC Line to the proposed 220 kV SS, Bonguloor (5KM) d)Supply, Erection, Laying, Testing, Commissioning including the cost of accessories of 132 kV 630 sq.mm XLPE UG DC cable for LILO of 132 kV Ibrahimpatnam - Turkayamzal SC Line to the proposed 220 kV SS, Bonguloor(3KM) | To meet the industrial load growth and reliable power supply for proposed Industries | SI | T.O.O (CE-Construction-I) MS.No. 117 ,Dated: 30.05.2014 | - | CRN.No. APT/TS/220 KVSS -Bonguluru/F.Invest-27/2014 | 63.4 | - | NABARD | 60 | - | 01.06.2014 | 31.03.2026 | 31.10.2015 | 0 | -0.1 | -0.1 | - | -
24 | S-13-06 | Dp pally & connected cable schemes | a)132/33 kV Substation at Dommarapochampally with 2 x 31.5 MVA PTR Capacity b)132kV LILO of 132 kV LILO line of 132 KV Shapurnagar – Gummadidala feeder between Loc No.310 and Loc No.311 to the proposed 132/33 KV substation at D.P pally (DC UG Cable)(3.6KM) c)Replacement of existing ACSR Wolf conductor with HTLS (High Temparature & Low Sag) conductor from 220 KV Shapurnagar to 132 KV SS Gummadidala.(21KM) | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Construction) MS.No .109 Dated:17.05.2018 (Revised) | - | TST/TS/132kV SS/ Dommarapochampalli /F-INVST- 04/2015 | 40.31 | - | REC | 32.35 | - | 24.12.2016 | 31.03.2026 | 16.07.2018 | 0.01 | - | 0.01 | - | -
25 | S-13-10 | ERECTION OF 132/33KV SS AT KACHAPUR | a)132/33 kV Substation at Kachapur with 3 x 10/16 MVA (Released) PTR Capacity (Radial)) b)132 kV DC/SC line from proposed 220/132 kV Huzurabad LIS substation to the proposed 132/33 kV Kachapur substation(18.75KM) c)132 kV Bay extension at proposed 220/132 kV Huzurabad ( 1 no.) | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Transmission) Ms.No.193 Dated:07.10.2015 | - | TST/TS/132kV / Kachapur SS/F-INVST- 17/2016 | 21.53 | - | REC | 20.28 | - | 22.09.2015 | 31.03.2026 | 04.05.2018 | 0 | -0.04 | -0.04 | - | -
26 | S-13-11 | 132 KV KANDUKURU SS & LINE FROM FABCITY | a)132/33 kV Substation at Kandukuru with 1x31.5 + 1 x 16 MVA(Released) PTR Capacity (Radial)) b)132 kV DC/SC line from proposed 220/132 kV Fab city substation to the proposed 132/33 kV Kandukuru substation on narrow based towers(11KM) c)132 kV DC/SC line from proposed 220/132 kV Fab city substation to the proposed 132/33 kV Kandukuru substation on normal towers (7KM) d)132 kV Bay extension at proposed 220/132 kV Fabcity substation | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | T.O.O (CE-Construction-I) Ms.No. 347 Dated: 13.02.2013 | - | TST/TS/132 kV SS-Kandukuru/ F-INVST-05/2015 | 22.75 | - | REC | 20.0578 | - | 09.09.2016 | 31.03.2027 | Ckt-II charged on 14.08.2025 & SS Work in Progress | 24.89 | 2.86 | 27.75 | - | -
27 | S-13-14 | Revisedadministrative 220kVSSSircilla. | a)220/132 Sub-Station at Sircilla in Karimnagar District with 3 X 100 MVA PTR Capacity, Double Bus Arrangement, 2 Nos 220 kV Feeder Bays, 4 Nos. 132 kV Feeder Bays and Sub-Station Automation System b)220kV DC line With Moose ACSR on Galvanised Towers from 220 kV SS, Durshed to the proposed 220 kV SS, Sircilla.(67KM) c)220 kV Bay extension at Durshed | APTRANSCO made the feasibility studies in respect of the Transmission Requirement for the year 2013-14, under Comprehensive Transmission Requirement Scheme for the Years 2012 – 2017 and proposed certain 400 kV, 220 kV and 132 kV Lines and Sub-Stations for system strengthening in addition to the already approved System Improvement / Evacuation schemes. The Comprehensive Scheme also includes erection of 220/132 kV Sub-Station, Sircilla in Karimnagar District. | SI | T.O.O (CE-Construction) MS.No. 144 Dated:03.08.2015 | - | CRN.No./TST/TS/220/132KV Substation /Sircilla /F.Invst./ App./08/2015 | 87.31 | - | REC | 59.9992 | - | 22.12.2015 | 31.03.2026 | 15.12.2016 | 0.04 | 0.34 | 0.38 | - | -
28 | S-14-02 | SURYAPET POWER TRANSMISSION SCHEME | a)LILO of one Circuit of Chillakallu – Narkatpally DC line to the proposed 400/220/132kV Suryapet Substation b)220kV DC Moose line to make LILO of (ckt-I&II) of 220kV Miryalaguda – Khammam at the proposed 400/220/132kV Suryapet SS c)132 KV DC line from 400/220/132kV Suryapet Substation to 132kV existing Suryapet Substation d)132 kV DC/SC line from 400/220/132kV Suryapet Substation to 132kV existing Shaligowraram Substation e)132 kV DC/SC line from 400/220/132kV Suryapet Substation to 132kV existing Thungathurthy SS f) 132 KV bay extensions at Suryapet SS & Thungathurty SS (2 No.s) | - | SI | T.O.O.(CE-Projects-I) Ms.No. 11, Date: 15.03.2016. | - | Covered in 400KV |  | - | REC | 131.72 | - | 15.03.2016 | 31.03.2026 | a) 21.12.2016 b)07.10.2016 c)06.12.2019 d)14.082017 e)06.08.2017 | 0 | 0 | 0 | - | -
29 | S-14-03 | 132/33kV SS at Duddeda & line | a)Erection of 132/33 kV Sub-Station with 2 X 31.5 MVA PTRs, 2 Nos. 132 kV Bays With 4NOs. 33KV O/G Feeders b)Erection of 132 kV DC line with Panther Conductor on Galvanized Towers for LILO of one circuit of 132 kV Siddipet - Gajwel line to the proposed Duddeda 132/33 kV SS (15KM) | To cater the loads that are to come up in the area in view of the development and also to improve the voltage profile in and around Gajwel. | SI | T.O.O (CE-Construction) Ms. No. 52 Dated: 15.12.2014 | - | TST/TS/132 kV SS- 220 kV Toopran, 132 kV Ganeshpally & 132 kV Duddeda SS / F-INVST-07/2015 | 24.6 | - | REC | 19.06 | - | 31.07.2015 | 31.03.2026 | 02.09.2016 | - | 0 | 0 | - | -
30 | S-14-05 | 2ND CKT LINE DURSHED SS TO WATER WORKS SS | a)Erection of 132 kV 2nd circuit line on under construction 132 kV DC/SC line from 22kV Durshed SS to 132kV Water Works Karimnagar Town SS (7.5KM) b)132 kV Bay extension at 220 kV Durshed substation. C)132 kV Bay extension at 132 kV Water Work substation Karimnagar Town. | Due to rapid growth of the town, the loads are increasing drastically; there is need of having 2nd circuit to feed the increasing loads | SI | T.O.O (CE-Construction-I) MS.No.08, Dated: 26.02.2014 | - | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 2.43 | - | REC | 2.18 | - | 03.03.2018 | 31.03.2026 | 27.02.2021 | 0 | 0.1 | 0.1 | - | -
31 | S-14-12 | 132/33kV Khaitlapur | a)132/33 kV Substation at Khaitalapur with 2 x 31.5 MVA PTR Capacity b)132kV DC XLPE (UG Cable) from 220/132kV Miyapur SS to the proposed 132/33kV Khaitalapur SS(7.5KM) c)132 kV Bay extension at proposed 220/132 kV Miyapur SS(2 No.s) | To meet the load demands of Kukatpally , Miyapur & industrial areas and also in view of multiple load growth with Commercial complexes coming up in the area | SI | T.O.O (CE-Construction) Ms. No. 22 Dated: 10.09.2014 | - | CRN.No.TST/TS/132 KVSS -Khitlapur/R.R.Dist./Invest.App./04/2015 dt.09.2015 | 66.04 | - | REC | 59.09 | - | 05.07.2016 | 31.03.2026 | 27.08.2019 | 0.57 | -0.62 | -0.05 | - | -
32 | S-15-01 | SECOND SOURCE TO 132KV SS LGMPET | a) 132 kV DC line on Galvanised Towers with Panther ACSR for making LILO of 132 kV Line from 220 kV Sub-Station, Medchal to 132 kV Sub-Station,Gajwel to 132/33 kV Sub-Station, Lalgadi Malakpet. (8KM) b)132 kV Bays at 132/33 kV Sub-Station, Lalgadi Malakpet Villasge(2 No.s) | To facilitate the Sub-Station with an alternate source of supply in order to provide reliable power to the surrounding consumers / industrial services of Shameerpet Mandal | SI | T.O.O (CE-Construction) Ms. No. 54 Dated: 25.03.2015. | - | Not necessary | 6.34 | - | PFC | 6.2 | - | 20.10.2015 | 31.03.2026 | 18.10.2019 | 0 | 0 | 0 | - | -
33 | S-15-02 | UP-GRADATION 132/33KVA'PET TO 220KV SS | a)220 kV features at existing 132/33 kV Aswaraopet Sub-Station with 2 X 100 MVA (Released) PTR Capacity. b)220 kV DC line from proposed 400 kV Asupaka SS to the proposed 220 kV Aswaraopet SS (20KM) c)220 kV DC line for making LILO of KTPS - Lower Sileru-I to the proposed 400 kV Asupaka SS (15KM) d)Stringing of 132 kV 2nd circuit on the existing 132 kV DC/SC line from 132/33 kV Awaraopet to 132 kV B.Gangaram (30KM) e)132 kV Bay Extension at B.Gangaram. | In order to have immediate and effective utilization of 400/220KV SS Asupaka, and also to provide 9 Hours Agricultural Supply, it is necessary for up-gradation of existing 132/33 kV Sub-Station at Aswaraopet to 220/132/33 kV Aswaraopet. | SI | T.O.O (CE-Transmisssion) MS.No. 159 , Dated: 24.08.2015 | - | CRN.No. TST/TS//132/33 KVSS Aswaraopet SS up-gradation to 220/132 KV Invest. App/07/15, Dt.05.10.2015 | 52.82 | - | PFC | 42.55 | - | 18.01.2017 | 31.03.2026 | 28.04.2018 | - | -0.11 | -0.11 | - | -
34 | S-15-04 | 132/33 kV Sub-Station at Jangapally | a)132/33 kV Sub-Station at Jangapally with 3 X 10/16 MVA PTRs (Released) b)132 kV DC line on Galvanised Towers with Panther ACSR for making LILO of 132 kV Durshed to Shanigaram line to the proposed 132/33 kV Sub-Station, Jangapally (14KM) | To overcome the low voltage problems, to cater to the upcoming loads and also to provide quality power supply to the consumers | SI | T.O.O (CE-Construction) Ms. No. 140 ,Dated: 30.07.2015 | - | Not Necessary | 19.79 | - | PFC | 16.68 | - | 03.03.2018 | 31.03.2026 | 31.12.2022 | 0 | 0.32 | 0.32 | - | -
35 | S-15-05 | 132 KV Kondapur SS | a)132/33 kV Sub-Station 2 X 31.5 MVA PTRs With 4 NOs. 33KV Feeders b)132 kV DC/SC Line with Zebra Conductor on Galvanized Towers from 132 kV SS, Maddur to the proposed 132/33 kV SS, Kondapur (20KM) c)132 kV Bays at 132 kV SS, Maddur | To improve the voltage regulations and to provide quality power to the consumers in the area. | SI | TOO (CE-Construction) MS NO.2, Dt:03.01.2015 | - | CRN TST/TS/132 KVSS -Kondapur/F.Invst.06/2015 | 24.49 | - | REC | 21.71 | - | 23.03.2017 | 31.03.2027 | - | 0.08 | - | 0.08 | - | -
36 | S-15-06 | alternate Chennur & KataramfromManthani | a) Stringing of two circuits on already approved (under construction) 132 KV Multi circuit towers from 220/132 KV SS Manthani upto Loc. No. 19 of existing 132Kv Manthani – Kataram line, (5KM) b)132 kV DC line ( 5.00 KM) from existing Loc. No. 19 upto Loc.No. 34A, of 132 kV Manthani – Kataram line,(5KM) c)Stringing of 2nd circuit from newly proposed DC line (from Loc No. 34A of 132 kV Manthani – Kataram) to 132/33 kV Chennur SS on the existing DC/SC line,(19KM) d)Stringing of 2nd circuit from Loc. No. 34A of existing 132 kV Manthani – Kataram line to 132/33 kV SS Kataram,(26KM) e)32 KV bay (at 220/132 KVSS Manthan - 2 Nos., at 132 kV SS kataram - 1No.at 132 kV SS Chennur - 1 No.) TOTAL-4Nos. | Alternate supply to 132 /33 kV SS Chennur and 132/33 kV SS Kataram from 220/132 kV SS, Manthani under the program for providing 9.00 Hrs Day Time Supply for Agriculture | SI | T.O.O (CE-Transmission) MS.No.210 Dated:06.11.2015 | - | Not Necessary | 12.13 | - | REC | 10.917 | - | 07.02.2018 | 31.03.2026 | 26.07.2024(Between Chennur & Kataram)- Work in Progress between Manthani & Kataram | 14.08 | 0.25 | 14.33 | - | -
37 | S-15-07 | 2NDCKT 220/132KVKAMAREDDY SS- DOMAKONDA | a)Stringing of 132 kV 2nd Circuit from 220/132 kV SS Kamareddy to Loc No 33-34 of existing new 132 kV DC/SC line of 132 kV SS Chippapally ( 5 KM) B)Erection of 132 kV DC/SC line from loc 33-34 of existing new 132 kV DC/SC line of 132 kV SS Chippapally to 132/33 kV SS Domakonda (5.5KM) c)Stringing of 132 kV 2nd Circuit from 132/33 kV SS Domakonda to 132/33 kV SS Biknur (9KM) d)Erection of 132 kV Bays (Domakonda - 2 Nos, Kamareddy - 1No and Biknoor - 1 No) | To overcome the over loading on existing 220/132 kVSS Kamareddy-132/33 kVSS Domakonda line and 132 kV Domakonda - Yellareddypet, it is proposed to provide alternate source of supply to 132 kV SS Domakonda under the program of providing 9 Hrs supply during day time for Agriculture | SI | T.O.O (CE-Transmission) MS.No.162 Dated:26.08.2015 | - | Not Necessary | 8.55 | - | PFC | 7.21 | - | 15.03.2024 | 31.03.2026 | a) 21.05.2025 b)Work cancelled c)26.09.2025 | - | 4.8 | 4.8 | - | -
38 | S-15-09 | 132 KV line G'pur-Imbn line to Nagole | 132 kV LILO line of 132KV Ghanapur - Imlibun DC line to the proposed 220/132/33 kV SS Nagole (Uppal) (0.2 KM OH + 1.6 KM UG cable ) | For providing alternate source of supply to the 220/132/33 kV Sub-Station, Nagole (HMRL) so as meet the following : I. 220 kV Sub-Stations, Imlibun & Nagole will become a part of the Ring Mains, II. 132 kV Sub-Station, Moosarambagh will have second source of supply, III. 220/132/33 kV Sub-Station, Nagole will have 132 kV source of supply, IV. Metro rail can be provided with an alternate supply to be fed during emergencies. | SI | T.O.O (CE-Construction) Ms. No 26 Dated: 12.02.2015 | - | Not Necessary | 11.98 | - | REC | 10.77 | - | 12.02.2015 | 31.03.2024 | 21.09.2017 | 0.06 | - | 0.06 | - | -
39 | S-15-10 | 132KV NARAYANPET SS | a)132/33kV Substation with 2X31.5 MVA PTRS at Narayanpet in Mahaboobnagar District. B)132kV DC/SC line from 132/33kV Marikal Substation to proposed 132/33kV Narayanpet Substation.(15KM) c)132kV Bay Extension at 132/33kV Marikal Substation. | To overcome the low voltage problems, to cater to the upcoming loads and also to provide quality power supply to the consumers. | SI | T.O.O (CE-Construction) Ms. No. 128 ,Dated: 17.07 2015 | - | CRN.No.TST/TS/132/33 KVSS/Narayanpet, Mahabubnagar/Invest.Apprl.No.5/16,2016-17 | 21.23 | - | REC | 19.65 | - | 21.09.2016 | 31.03.2026 | 28.12.2017 | - | 0.16 | 0.16 | - | -
40 | S-15-13 | 765kVWardha-HYD Link transmision Scheme | The details are enclosed in the Annexure | - | SI | T.O.O.(CE-400kV) Ms.No.105 Dt:15.07.2017 | - | Covered in 400KV |  | - | PFC | 937.63 +139.49 | - | 25.01.2018 | 31.03.2026 | The charging details are enclosed in Annexure | 0.2 | 0.28 | 0.48 | - | -
41 | S-15-29 | 132KV DC line from 220KV HSBD. LISS, BAY | a)Erection of 1 No. 100 MVA additional PTR at 220/132 kV LI SS, Huzurabad with equipment totalling to 2 X 100 MVA (Released PTR) b)Erection of 132 kV line with four circuits on Galvanised Multi-Circuit towers with Panther ACSR for making LILO of both 132kV Husnabad – Huzurabad & 132kV Mulkanoor – Huzurabad circuits at 220/132kV new Huzurabad LISS (7KM) c)Stringing of 132 kV second circuit between 220/132 kV Durshed SS and 132/33 kV Manakonduru SS.(3KM) d)Erection of 132 kV Bays (Huzurabad - 4Nos, Manakondur - 2Nos, ) | For feeding the loads of 132/33kV Huzurabad SS and 132/33kV Mulkanoor SS from 220/132 kV LI Substation Huzurabad to reduce over load on 220/132 KV SS Durshed, to provide reliable power supply to the 132/33 kV Substations at Huzurabad, Mulkanoor, Husnabad & Palamakula, reduce transmission line losses, to maintain good Voltage regulation and to meet the upcoming loads in the area | SI | T.O.O (CE-Construction) MS. No. 136 , Dated: 27.07.2015 | - | - | 18 | - | REC | 16 | - | 09.10.2016 | 31.03.2026 | 29.12.2017 | - | -0.01 | -0.01 | - | -
42 | S-15-31 | 2nd Ckt 220KV SRMP to 132kv ASFNGR & Con | a)2nd circuit from 220kV SS Shivarampally to 132kV SS Asifnagar by laying 220kV XLPE UG Cable (3KM) b)132 kV Bay extension at 220 kV Shivarampally substation. c)132 kV Bay extension at 132 kV Asifnagar substation. | The 132kV Asifnagar substation is an important substation located in the middle of the city feeding the VIP areas and Old city. As there is no alternative source, it is becoming very difficult to maintain normalcy during incoming supply outages and also to carryout general maintenance works of the feeder at both ends. To have reliable power supply to this substation another source is necessary | SI | T.O.O (CE-Construction-I) MS. No. 55 , Dated: 25 .03 .2015 | - | CRN.No.TST/TS Asifnagar SS alternatesource of supply/Invest.App.06/2015, dt.05.10.2015 | 45.97 | - | REC | 41.36 | - | 16.02.2018 | 31.03.2026 | 31.05.2019 | 0.08 | -0.07 | 0.01 | - | -
43 | S-15-32 | Erec of 220KV SS pedagopati & line KMM | a)220/132/33 kV Sub-Station at Pedagopati with 2 X 100 + 2 X 31.5 MVA PTR Capacity b) 220 kV DC line from proposed 400 kV Julurupadu (Bommanapalli) SS to the proposed 220 kV Pedagopatit SS (110KM) | The proposal for erection of 220/132/33 kV Sub-Station at Pedagopati in Khammam District along with connected lines is considered as downstream evacuation Sub-Station for 4 X 270 MW Manuguru Power Station | SI | T.O.O (CE-Transmisssion) MS.No. 211 , Dated: 07.11.2015 | - | TST/TS/ 220 kV Pedagopati SS / Investment approval No. 19/16-2016 | 124.44 | - | REC | 121.24 | - | 27.02.2017 | 31.03.2026 | 01.12.2018 | - | -0.05 | -0.05 | - | -
44 | S-15-33 | Erection of 132/33KV SS at Sarangapur & | a)Erection of 132/33 kV Sub-Station at Sarangapur in Adilabad District with 3 X 10/16 MVA PTRs (Released) b)Erection of 132 kV DC line on Galvanised Towers with Panther ACSR for making LILO of 132 kV Nirmal – Bhainsa line to the proposed 132/33 kV Sub-Station, Sarangapur(14KM) | To have uninterrupted supply, to shorten the length of 33 kV lines and subsequently overcome the low voltage problems, to have better supply conditions, to cater to the projected loads in view of the scheme for providing 9.00 Hours supply during day time for agriculture and the loads of the upcoming water grid project which are expected to be 31100 KVA. | SI | T.O.O (CE-Transmisssion) MS.No. 231 Dated: 21.12.2015 | - | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 19.93 | - | REC | 17.66 | - | 04.04.2018 | 31.03.2026 | 11.12.2019 | - | 0.35 | 0.35 | - | -
45 | S-15-34 | 220 KV D/C LN from 400KV GAJWEL-SIDDIPET | a)220 kV DC line on Galvanised Towers with Moose ACSR from 400/220/132 kV SS Gajwel to 220/132 kv SS Siddipet (40KM) b) 220 KV Bays (Gajwel-2, Siddipet-2) | For meeting the 9.00 Hours day time agricultural supply. | SI | T.O.O (CE-Transmission) MS.No. 225 Dated: 10.12.2015 |  | CRN.No.TST/TS/Erection of 220 KV DC line Gajwel/Siddipet/Invest.App. 4/17-2017-18 dt:02.07.2017 | 38.12 | - | REC | 35 | - | 05.12.2017 | 31.03.2026 | 19.11.2022 | 0.04 | 1.09 | 1.13 | - | -
46 | S-15-36 | erection of 132/33 kV substation at Aipo | Nurthankal T.O.O is issued instead of Aipoor | [13 empty] | 0.15 | - | 0.15 | - | -
47 | S-15-38 | 2nd ckt 132KV Wgl-S.Nagr @ Jngan&kolnpk | Erection of 132 kV lines for making LILO of (i) 2nd Circuit of 132kV Warangal – Shapurnagar DC line at 132kV SS Jangaon (1KM) (ii) 2nd Circuit of 132kV Warangal – Shapurnagar DC line at 132kV SS Kolanpak (5KM) | a)132 kV interlinking lines of (i) Erection of 132 kV DC line for making LILO of second circuit of 132 kV Warangal – Shapurnagar DC Line at 132 kV Jangoan Sub-Station(1KM) and (ii) Erection of 132 kV DC line for making LILO of second circuit of 132 kV Warangal – Shapurnagar DC Line at 132 kV Kolanpaka Sub-Station, as downstream of proposed 220/132 kV SS Jangoan (5KM) b)2 Nos 132kV Bays at 132/33 kV SS kolanpak | SI | TOO / CE/Trans/ MS No. 158 Dated 22.08.2015 | - | Not Necessary | 8.38 | - | PFC | 7.02 | - | 10.03.2017 | 31.03.2023 | (i) 28.12.2019 (ii) 16.11.2019 | 0.12 | -0.01 | 0.11 | - | -
48 | S-15-39 | 132/33 KV SS at Raparthy (V) of Kalher | a)132/33 KV Sub-Station at RAPARTHY with 3X 10/16 (Released) MVA PTRs b)132kv DC/SC line from 132 kvss, Pedda Shankarampet to the proposed 132/33 kvss, Raparthy (16KM) c)132 kV Bay at 132 KVSS, Pedda Shankarampet | To cater the upcoming loads and also to avoid low voltage problem arising in the area | SI | 8.91 | - | - | 21.71 | - | TGTransco funds | 21.71 | - | - | - | - | 0.19 | -0.31 | -0.12 | - | The T.O.O is cancelled
49 | S-16-11 | Erection of 132/33 kV SS at BACHANNAPET | a)132/33 kV Sub-Station at Bachannapet in Warangal District with 3 X 10/16 MVA PTRs (Released) b)132 kV DC/SC line on Galvanised Towers with Panther ACSR from proposed 220/132 kV Sub-Station, Jangoan to the proposed 132kV Sub-Station at Bachannapet.(18KM) C)132kV Bay at 220/132 kV SS, Jangoan(1 No.) | To cater to the loads due to 9.00 Hours supply during day time to Agricultural sector and Water Grid and to improve the voltage profile in the connected area | SI | TOO / CE/Trans/ MS No.76 Dated 25.05.2016 | - | Not Necessary | 19.38 | - | PFC | 16.71 | - | 20.04.2017 | 31.03.2026 | 31.10.2019 | 0.02 | -0.02 | 0 | - | -
50 | S-16-12 | Erection of 132/33 kV SS at Kotagiri | a)132/33 kV Sub-Station at Kotagiri in Nizamabad District with 3 X 10/16 MVA PTRs (Released) b)132 kV DC/SC line on Galvanised Towers with Panther ACSRfrom 132/33 kV Sub-Station, Jakora to the proposed 132kV Sub-Station at Kotagiri in Nizamabad District .(12KM) c)132 kV Bay extensions at 132/33 kV Sub-Station, Jakora(1 No.) | To meet the load growth and to improve the voltage regulation in the surrounding (Kotagiri, Bhiknoor, Madnoor, Varni & Bodhan Mandals) under System Improvement | SI | T.O.O (CE-Transmission) Ms. No. 88 Dated: 30.06.2016. |  | Not necessary | 15.05 |  | PFC | 12.98 |  | 06.06.2018 | 31.03.2026 | 12.05.2022 | 0.04 | 0.32 | 0.36 | - | -
51 | S-16-13 | Erection of 132/33 kV SS at Tallapet | a)Erection of 132/33 kV Sub-Station at Tallapet in Adilabad District with 3 X 10/16 MVA Released PTRs b)Erection of 132 kV DC line for LILO of existing 132 kV Dharmapuri – Luxettipet line at proposed 132/33 kV Tallapet SS.(13KM) | To meet the upcoming loads for providing of 9.00 Hours power supply during day time to agricultural sector and also to ensure quality supply to the consumers in the scheme area | SI | T.O.O. (CE-Construction) Ms. No. 2098 Dated: 14.10.2024. (Revised) | - | Not necessary | 26.27 | - | REC | 14.63 | - | 15.10.2025 | 31.03.2027 | - | 0.61 | -0.3 | 0.31 | - | -
52 | S-16-14 | 220/132/33 kV SS Borampet & Line | a) 220/132/33 kV Sub-Station at Borampet with 2 X 160 MVA + 2 X 80 MVA PTR Capacities b)220 kV Multi Circuit OH line on MC Towers with Moose ACSR from 400 kV Narsapur SS to proposed 220 kV Borampet SS-38 KM c)220 kV DC line with UG Cable from 400 kV Narsapur SS to proposed 220 kV Borampet SS – 5 KM. d)220 kV Bays at 400 kV Narsapur(2 No.s) | It is associated with evacuation of power from 2 X 800 MW Telangana STPP to be established by NTPC at Ramagundam | SI | T.O.O (CE-Transmission) Ms. No. 72 Dated: 13.05.2016 | - | CRN.No.TST/TS/220/132/33 KVSS Borampet, R.R.Dist. /Invest. Apprl/No.7/16-2016-17, dt.19.10.2016 | 212.2 | - | PFC | 182.98 | - | 28.11.2016 | 31.12.2026 | SS-04.03.2025, 2nd PTR-20.03.2025 line-27.02.2025 | 211.66 | 13.14 | 224.8 | - | -
53 | S-16-16 | Erec of 220/33 Kv SS at Domalapenta in N | a) 220/33 kV Sub-Station with 2 Nos., 220/33 kV 31.5 MVA, PTRs at Domalapenta Village of Nagarkurnool District. b)220 kV DC line on Galvanised Towers with Moose ACSR for LILO of one circuit of the existing 220 kV Srisailam – Dindi DC Line to the proposed 220 kV Sub-Station, Domalapenta.(70KM) | For providing power supply to Domalapenta & Eegalapenta Villages, offices & residential quarters of TSGENCO & I&CAD located in the area which are presently being fed from 132/33 kV Sub-Station, Srisailam of APTRANSCO at 33 kV level | SI | T.O.O (CE-Transmission) Ms. No. 173 Dated: 15.12.2016. | - | Not necessary | 14.2 | - | PFC | 12.41 | - | 05.03.2018 | 31.03.2026 | 26.07.2019 | - | 0.03 | 0.03 | - | -
54 | S-17-01 | erection of 220/33 kV GIS at Chanchalgud | a)220/33 kV GIS substation at Chanchalguda with 3 X 50 MVA PTR b)220 kV DC line with 1000 Sqmm 220 kV UG cable for LILO of Chandrayangutta - Imlibun line (UG Cable) to the proposed 220/33 kV GIS substation, Chanchalguda(1KM) | To i) reduce overloading of PTRs at 220/132/33 kV Sub-Station, Chandrayangutta and 132/33 kV Sub-Station, Imlibun, (ii) to provide alternate source of supply to the 33/11 kV Sub-Stations (iii) to avoid load shedding and (iv) also to cater to the upcoming loads | SI | T.O.O (CE-Transmission) Ms. No. 26, Dated: 27.02.2017. | - | CRN TS/TST/220/33 KV, GIS, Chanchaguda/Invest.Approval No.7/17-2017-18 | 89.12 | - | REC | 80.208 | - | 28.02.2018 | 31.03.2026 | 220KV GIS bay & bus charged with connected LILO cable on 26.02.2020. PTRs-I, II & III were charged on 20.03.2021, 26.03.2021 and 31.03.2021 respectively. | 5.21 | -3.26 | 1.95 | - | -
55 | S-17-03 | 132/33 kV Sub-Station at Moulali ZTS | a)132/33 kV Moulali ZTS SS with 2X50 MVA PTR b)132 kV DC line with 630 Sqmm 132 kV UG cable from 220 kV Moulali Sub-Station to the proposed Moulali ZTS SS(3.5KM) c)132 kV Bay extensions at220 kV Moulali substation(2 No.s) | To (i) reduce overloading at 400/220/132/33 kV Sub-Station, Malkaram & 220/132 33 kV Sub-Station, Moulali, (ii) reduce the length of lines feeding the scheme area, (iii) to provide reliable & uninterrupted power supply, (iv) reduce the overall energy losses in the system and (iv) to cater to the upcoming loads which are increasing multi-fold due to the vertical growth of the city and increase in commercial establishments | SI | T.O.O (CE-Transmission) Ms. No. 31, Dated: 27.02.2017. | - | CRN TS/TST/132/33 KV, Moulali-ZTS SS, Investment Approval No.17/17, 2017-18 | 49.78 | - | REC | 44.47 | - | 01.04.2019 | 31.03.2026 | PTR-2 @ 07.07.2021 PTR-1 @ 30.07.2021 | 0.19 | 1.73 | 1.92 | - | -
56 | S-17-04 | erection of 132/33 KVSS Gachibowli | a)132/33 kV Sub-Station at Gachibowli with 2X80 MVA PTR b) 132 kV DC OH line on galvanised towers with Panther ACSR from 220/132/33 kV Gachibowli SS to the proposed 132/33 kV Gachibowli SS(1KM) | To (i) reduce overloading at 220/132/33 KV Substation, Gachibowli (ii) provide alternate source of supply to the 33/11 KV Sub-stations in the scheme area. (iii) Extend supply to 33 kV dedicated feeder applications pending for feasibility from Gachibowli and Madhapur Sub-Stations area for a load of 71.5 MW & the upcoming loads | SI | T.O.O (CE-Transmission) Ms. No.27, Dated: 27.02.2017. | - | Not necessary | 18.73 | - | REC | 16.52 | - | 01.04.2019 | 31.03.2026 | 22.09.2021 | 0.18 | -0.03 | 0.15 | - | -
57 | S-17-05 | erection of 132/33 kV GIS at SEETARAMBAG | a)132/33 kV GIS substation at Seetharambagh with 2X80 MVA PTR b)132 kV DC line with 630 Sqmm 132 kV UG cable from Asifnagar Sub-Station to the proposed 132/33 kV GIS substation at Seetharambagh(4KM) c)132 kV Bay extensions at Asifnagar substation(2 No.s) | To (i) reduce overloading of PTRs at 220/132/33 kV Shivarampally Sub-Station & 132/33 kV Imlibun Sub-Station, (ii) reduce the length of 33 kV lines feeding the scheme area, thereby reducing the time taken in locating faults, attending breakdowns & restoration of supply (iii) to provide reliable & uninterrupted power supply, (iv) reduce the overall energy losses in the system and (iv) to cater to the upcoming loads which are increasing multi-fold due to the vertical growth of the city and increase in commercial establishments | SI | T.O.O (CE-construction-I) Ms.No.2537, Dt:13.10.2025 | - | CRN TS/TST/132/33 KV, GIS, Seetharambagh/Invest.Approval No.6/17-2017-18 | 112.17 | - | REC | 57.27 | - | 01.04.2019 | 31.12.2026 | SS- Charged on 13.06.2025 & line Ckt-I Charegd on 12.06.2025 | 57.54 | 14 | 71.54 | - | -
58 | S-17-06 | erec of 132/33 kV GIS AT PTO Petlaburz | a) 132/33 KV GIS at Police Transport Organisation (PTO), Petlaburz with 2 x80 MVA PTR b)132 KV DC line with 630 Sq.mm 132 KV UG cable from the 220KV GIS substation,Imlibun to the 132/33 KV GIS SS at PTO, Petlaburz(1.5KM) c)Erection of 132 kV DC OH line on galvanised double circuit towers with Panther ACSR(3.5KM) | To (i) reduce overloading of PTRs at 220/132/33 kV Shivarampally Sub-Station & 132/33 kV Imlibun Sub-Station, (ii) reduce the length of 33 kV lines feeding the scheme area, thereby reducing the time taken in locating faults, attending breakdowns, restoration of supply & carrying out the regular maintenance works, (iii) to provide reliable & uninterrupted power supply, (iv) an alternate source of supply in the scheme area and (v) to cater to the upcoming loads | SI | T.O.O (CE-Transmission) Ms. No. 29, Dated: 27.02.2017. | - | CRN TS/TST/132/33 KV, GIS, Petlaburz invest.Approval No.5/17-2017-18 | 39.93 | - | REC | 35.93 | - | 02.03.2018 | 31.03.2027 | - | 23.67 | - | 23.67 | - | -
59 | S-17-09 | 220/132/33 kV SS Meenajipet & lines | a) 220/132/33 kV Sub-Station at Meenajipet, with 2 X 100 MVA + 2 X 31.5 MVA PTRs With 2Nos., 220kV Incoming Feeder Bays, 4 Nos. 132 kV Feeder Bays and 4 No.33KV Feeder Bays b) 220 kV DC line with Moose ACSR Conductor on Galvanised Towers from proposed Narsapur 400/220/132 kV SS to the now proposed Meenajipet 220/132/33 kV SS(25KM) c)Erection of 220 kV Bays at 400/220/132 kV SS Narsapur for connectivity from 400/220/132 kV Narsapur SS to the 220/132/33 kV Meenajipet SS ( 2 No.s) d)132 kV DC/SC Line with Panther ACSR Conductor on Galvanized Towers from the proposed 220/132/33 kVMeenajipet SS to 132/33 kV Doulathabad SS (25KM) e)132 kV DC Line with Panther ACSR Conductor on Galvanized Towers from the proposed 220/132/33 kV Meenajipet SS to 132/33 kV Thunki Bollarum SS(7KM) f)Stringing of second circuit from 132/33 kV Thunki Bollarum to 132/33 kV Ganeshpally SS (21KM) g) 220 kV Bays at 400/220/132 kV SS Narsapur for connectivity from 400/220/132 kV Narsapur SS to the 220/132/33 kV Meenajipet SS h)132 kV Bays at Doulathabad 132 kV SS.(1),132kV Thunki Bollarum SS (3) and 132kV Ganeshpally SS (1)(5No.s) | To cater the loads that are to come up in the area in view of the development and also to improve the voltage profile in and around Gajwel.This Substation is proposed instead of Toopran SS. | SI | T.O.O. (CE-Construction) Ms. No.2140 Dated: 30.11.2024. | - | CRN/TS/TST/220/132/33kV SS/Meenajipet instead of Toopran/Invst.Appl.No.15/17-2017-18, Dt.Dec.2017. | 79.04 | - | REC | 68.43 | - | 27.01.2016 | 31.12.2026 | Meenajipet SS and connecetd line is charged on 06.02.2020.The downstream 132 KV line works yet to be started | 0.03 | 0.19 | 0.22 | - | -
60 | S-17-11 | Erec of 33 KV feat at 132/11 KV CH.Kondu | 33 kV Features at existing 132/11 kV LI Sub-Station, CH. Kondur in Nizamabad District (2x10/16 MVA) | To meet the Agricultural loads under 24.00 Hrs supply and existing and upcoming loads in the scheme area | SI | T.O.O (CE-Transmission) Ms. No. 82 Dated: 23.05.2017 | - | Not necessary | 4.2 | - | PFC | 3.67 | - | 16.04.2018 | 31.03.2026 | 01.10.2018 | 0.05 | -0.04 | 0.01 | - | -
61 | S-17-12 | Erec of 132/33 KV SS at Choppadandi in K | a)132/33 kV Sub-Station at Choppadandi in Karimnagar District with 2 X 31.5 MVA PTRs b)132 kV DC/SC line for LILO of 132 kV line from 220 kV Malyalapally Sub-Station to 220 kV Durshed Sub-Station at the proposed 132/33 kV Choppadandi Sub- Station(13KM) | The existing 33 kV Choppadandi, Dharmaram and Gangadhara Feeders emanating from 132/33 kV Karimnagar Sub-Station, 33 kV Katnapally feeder are overloaded and voltage regulations are beyond permissible limit. It is essential to construct the new 132/33 KV substation to feed the existing and upcoming loads and to extend power supply to Agriculture sector with quality & reliable power | SI | T.O.O (CE-Transmission) Ms. No. 82 Dated: 23.05.2017 | - | CRN TST/TS/132/33KV, Choppadandi, SS /Invest,Approval No.20/18-2017-18 | 22.85 | - | PFC | 19.97 | - | 06.06.2018 | 31.03.2027 | - | 0.04 | - | 0.04 | - | The T.O.O is cancelled vide T.O.O (CE-Construction) Ms.No.2313, Dt:22.04.2025
62 | S-17-13 | Erec of 132 KVSS at Yadgirigutta temple | a)132/33 kV Sub-Station at Yadagirigutta Temple Town with 2 X 31.5 MVA PTRs b)132 kV DC line with Panther ACSR Conductor on Galvanised Towers for LILO of LILO of 132 kV Bhongiri - Raghunathapally (Bhongir-Shapurnagar-Kolanpak) line to the proposed 132 kV Yadagirigutta SS.(2KM) | To cater to the upcoming loads in view of the development of Temple Town at Yadagirigutta and its surrounding areas and to provide quality power supply | SI | TOO (CE_Transmission)Ms.No.69 Dt:09.05.2017 | - | Not Necessary | 15.06 | - | PFC | 13.16 | - | 01.10.2018 | 31.03.2026 | 11.12.2019 | 0.15 | -0.05 | 0.1 | - | -
63 | S-17-15 | Erec of 132/33 KV SS at Chinna Shankaram | a)132/33 kV Sub-Station at Chinna Shankarampet in Medak District with 2 X 10/16 MVA PTRs(Released) b)132 kV DC line for LILO of 132 kV Chegunta- Yeldurthy DC/SC line at the proposed 132/33 kV Chinna Shankarampet Sub- Station(6KM) | Improves the voltage profile of the area and reduces the system losses. | SI | T.O.O (CE-Construction) Ms. No. 124, Dated: 19.08.2017 | - | Not necessary | 16 | - | REC | 13.96 | - | 01.04.2018 | 31.03.2026 | 23.01.2021 | 0.08 | -0.07 | 0.01 | - | -
64 | S-17-16 | 132kV 2nd ckt Str on W.pally - Peddanaga | a)Stringing of 2nd circuit on 132KV DC/SC line from existing 220/132KV SS Waddekothapally to existing 132/33KV SS Peddanagaram with Panther ACSR Conductor.(30KM) b)132 KV feeder bays (at 220/132 KVSS Waddekothapally - 1 Nos. and at 132 kV SS PeddaNagaram 1 No.) TOTAL-2Nos. | To meet (N-1) Contingency in the Network for ensuring satisfactory Power Supply | SI | T.O.O (CE-Construction) MS.No..149 Dated:09.10.2017 | - | Not necessary | 7.02 | - | REC | 6.32 | - | 01.04.2019 | 31.03.2026 | 06.11.2021 | - | 0.02 | 0.02 | - | -
| S-17-18 | Alternate source to 132/33KV Ghanpur SS | a)Stringing of 3rd conductor on the existing 132 kV Raghunathpally – Ghanpur Railway feeder so as to provide alternate supply to the 132 kV SS Ghanpur(16KM) b)Erection of 132 kV Multi-Circuit (Four Circuit) line comprising of two circuits 2 Phase line and two circuits 3 phase line from 132/33 kV SS Ghanpur to Ghanpur Railway Traction Sub-Station duly providing 4 Nos. Multi circuit towers.(1KM) c)2 Nos. 132 kV bay extension at Ghanpur | To provide alternate source of supply to 132/33 kV Ghanpur to meet the industrial loads expected under the upcoming project of Hyderabad - Warangal industrial corridor | SI | T.O.O (CE-Transmission) Ms. No. 70, Dated 09.05.2017 | - | P.No.28/APERC/Secy/Dir(Engg)/E725/2013, Dt:06-05-2013 | 5.8 | - | PFC | 5.,07 |  | 23.10.2018 | 31.03.2026 | 26.06.2019 | 0 | - | 0 | - | -
65 | S-17-19 | erection of 132/33 KV SS Pitlam | a)Erection of 132/33KV SS Pitlam with new 2X50 MVA PTR capacity. b)132 kV DC/SC line from 220/132/33KV Banswada SS to the proposed 132/33 kV Pitlam Sub- Station(26.5KM) c)132KV feeder bay at 220KV SS Banswada (1 No.) | To feed the existing & upcoming loads and to improve the voltage regulation in 33KV feeders. The scheme will also cater the loads of 24 hours Agriculture supply | SI | TOO (CE-construction) MS.No.2219, dt:12.02.2025 | - | CRN No. TST/TS/Erection of 132/33 KV SS at Pitlam in Khammam Dist. Approval/No.04/2018-19 | 32.56 | - | REC | 31.8 | - | 31.10.2018 | 31.03.2027 | - | 0 | - | 0 | - | -
| S-17-20 | 132 KV DC/SC lne from 220 KV Chegur 2 13 | a)132 kV DC/SC line from 220kV Chegur (Kothur) Sub-Station under construction to the existing 132/33 kV Kothur Sub-Station (6KM) b)132kV bay at 132/33kV Kothur SS | To reduce the system losses. | SI | T.O.O (CE-TransmissioT.O.O (CE-Construction) Ms. No.177 Dated: 30.11.2017 | - | Not necessary | 5.58 | - | REC | 5.11 | - | 01.04.2019 | 31.03.2026 | 24.07.2020 | 0.11 | - | 0.11 | - | - | 0.22
66 | S-17-21 | erec 132/33 kV SS Pammy n Khammam dist | a) 132/33 kV Sub-Station at Pammy in Khammam District with 2 X 31.5 MVA PTRs b)132 kV DC line for LILO of 132 kV Kusumanchi-Chilakallu line at the proposed 132/33 kV Pammy Sub- Station(8KM) | To reduce the losses and to meet the load demand | SI | T.O.O (CE-Construction) Ms. No.14 Dated:20.01.2018. | - | TST/TS/Erection of 132/33 KV SS at Pammy in Khammam District/Approval No.03/2018-19, 01.06.2018 | 23.39 | - | REC | 20.64 | - | 13.01.2022 | 31.03.2026 | 20.02.2024 | 1.12 | 1.29 | 2.41 | - | -
67 | S-17-23 | 132 KV feat at 220 KV Thimmajipet SS in | a)132 KV features at 220 kV Thimmajipet Switching Station with 2 X 100 MVA PTR Capacity. B)132 kV DC line on Galvanised Towers with Panther ACSR from the existing proposed 220/132 kV Thimmajipet Sub-Station, to the existing 132/33 kV Jadcherla Sub-Station.(18KM) c)132 kV Bay extensions at 132/33 kV Sub-Station, Jadcherla( 2 No.s) | Comprehensive Transmission Requirement Scheme for the years 2012-2017. | SI | T.O.O (CE-Construction) Ms. No. 103 Dated:11.07.2017 | - | CRN/TS/TST/220kV Switching Station/Mahaboobnagar/132kV features/Invest.Appl.No.14/17, 2017-18, Dt.Dec.2017. | 29.32 | - | REC | 26.39 | - | 05.02.2020 | 31.03.2026 | line work is under progress | 12.16 | 2.38 | 14.54 | - | -
68 | S-18-01 | Eection of 132/33 kV SS at Peechara | a)132/33 kV Sub-Station at Peechara, Warangal Dist with 2 X 31.5 MVA PTRs b)132 kV DC line with HTLS Conductor on Galvanised Towers by making LILO of existing 132 kV line from 220/132/33KV Waranagal SS to 132/33KV Jangaon SS at proposed 132/33KV Peechara SS.(12KM) | To meet the load demand and to improve the Voltage profile | SI | T.O.O (CE-Construction) Ms. No. 43 Dated: 06.03.2018. | - | TST/TS/Erection of 132 /33 SS at Peechara in Warangal District. Approval No.05/2018-19, dt:19.07.2018 | 43.92 | - | REC | 39.1 | - | 02.02.2022 | 31.12.2026 | 20.09.2025 | 13.39 | 1.46 | 14.85 | - | -
69 | S-18-02 | 220/132 kV SS at Ammavaripet in Warangal | a)220/132 kV Sub-Station at Ammavaripet with 2X100 MVA PTR Capacity in Warangal Dist b) 220 kV DC Line on Galvanized Towers with Moose ACSR Conductor for LILO of one circuit of 220 kV Mahabubabad - Warangal line to proposed 220 kV Ammavaripet SS(31KM) c)132 kV DC Line on Galvanized Towers with Panther ACSR Conductor from the proposed 220/132 kV Sub-station Ammavaripet to the existing 132/33 kV Sub-Station, Geesukonda.(23KM) d)132 kV Line on Multi-circuit Towers with Panther ACSR Conductor for accomdation of 132 KV Line to 132KV SS Inavole and 132KV Line to 132KV SS Wardhannapet from the proposed 220/132 kV Sub-station Ammavaripet to AP 8.(6.98KM) e)132 kV DC/SC Line on Galvanized Towers with Panther ACSR Conductor from the AP.8 to the 132/33 kV SS Inavole(2.32KM) f)32 kV DC/SC Line on Galvanized Towers with Panther ACSR Conductor from the AP.8 to the 132/33 kV SS Wardhannapet(16.25KM) g)132 kV Bays (2 Nos at 132 kV Geesukonda, 1 No at 132 KV Wardannapet & 1No at 132 kV Inavole) (4No.s) | The proposal was made to avoid interruptions to the Tri-City caused frequently due failures in power cables at railway crossing as the whole city is fed through 220/132 Sub-Station located on the northern side of Kazipet - Warangal Railway Track and also to feed the upcoming industrial corridor at Madikonda and a Textile Park at Geesugonda | SI | T.O.O (CE-Construction) MS.No .294 Dated:29.01.2019 | - | CRN No.TST/TS/ Erection of 220/132 KV SS at Ammavaripet, Kazipet(M) in Warangal Urban District. Approval / NO 02/2019-20 dt:10.08.2018 | 126.86 | - | PFC | 87.24 | - | a) 20.02.2020 b)20.02.2020 c)18.09.2020 d,e, f & g) 26.02.2021 | 31.03.2026 | a) 31.03.2024 b)31.03.2024 c) 30.12.2023 d,e,f & g) 29.12.2022 | 0.39 | 0.53 | 0.92 | - | -
70 | S-18-03 | Erect 132kV SS Padmanagar | a)132/33 kV Sub-Station Padmanagar (V) in Karimnagar District with 2X31.5 MVA PTR capacity b)LILO of132 KV Line (one circuit) from 220/132 KV SS Durshad to the 132/33 KV SS Siricilla to proposed 132/33 KV SS Padmanagar(6KM) c)132 kV DC line erection on 400 kV DD Type Towers.(1KM) | The scheme was proposed as the existing 132/33 KV SS Vaavilalapally in Karimnagar feeds most of the loads of Karimnagar town. This 132/33 KV Sub-Station has single 132 KV incoming feeder. Further stated that, IT hub is going to be established in the town. The city is recognized for tourism development with manair riverfront as center of attraction. Loads are also expected with increased activities in the town. With the present 132/33 KV SS maintenance of uninterruptable reliable supply to the city in near future will be complex | SI | T.O.O (CE-Construction) Ms. No.1565 , Dated: 04.02 2023. | - | Not necessary | 19.29 | - | PFC | 16.33 | - | 31.10.2020 | 31.03.2026 | 15.05.2023 | 0.08 | 0.22 | 0.3 | - | -
71 | S-18-04 | erc of 132KV SS Nagaram in Suryapet Dist | a)132/33 kV Sub-Station at Nagaram , Suryapet Dist with 1 X 31.5 + 1x10/16 MVA PTRs b)132 kV line with ACSR Panther Conductor on Galvanised Towers by making making LILO of 132 kV DC/SC line from 400/220/132 kV Suryapet SS to 132/33 KV Thungathurthy SS at newly proposed 132/33 KV Nagaram SS (16KM) | To meet the 24 Hrs Agriculture power supply, load demand in the scheme area and to avoid low voltage problems | SI | T.O.O (CE-Construction) Ms. No. 193, Dated: 30.08 2018. | - | TST/TS/Erection of 132/33 KV SS at Nagaram in Suryapet District. Approval No.14/18/2018-19 dt:12.12.2018 | 33.97 | - | PFC | 26.15 | - | 27.10.2020 | 31.03.2026 | 27.03.2022 | - | 0.17 | 0.17 | - | -
72 | S-18-05 | 2ckt 132kV DC/DC line 4m Boothpur to Mar | a)Stringing of 2nd Ckt on existing 132KV DC/SC line from 220/132/33KV Boothpur to 132/33KV SS marikal including bay in Mahaboobnagar District (42KM) b)Erection of 132 KV feeder bays (at 220/132/33 KVSS Boothpur - 1 No. and at 132 kV SS Marikal 1 No.) TOTAL-2Nos. | To meet (N-1) Contingency in the Network for ensuring satisfactory Power Supply | SI | T.O.O (CE-Construction) Ms. No. 193, Dated: 30.08 2018. | - | Not necessary | 11.95 | - | REC | 10.53 | - | 01.11.2025 | 31.12.2026 | - | 0.07 | - | 0.07 | - | -
73 | S-18-06 | 33kV features at RTSS Kothagudem in bhad | 33 KV features at 132 KV Railway Traction Switching Station, Kothagudem, Kothagudem Bhadradri District with 2 X 10/16 MVA PTRs | To provide uninterrupted power supply to the consumers with better voltage profile. | SI | T.O.O (CE-Construction) MS.No . 217 Dated: 25.09.2018 | - | Not necessary | 9.92 | - | PFC | 7.64 | - | 11.01.2023 | 31.03.2026 | 21.11.2023 | 4.69 | 0.71 | 5.4 | - | -
74 | S-18-07 | 132 KV LILO of existing 132 KV Maddur-Ma | a)LILO of existing 132 kV Maddur – Makthal DC/SC line to existing newly charged 132/33 kV Narayanpet SS with Panther ACSR Conductor.(1KM) B)Erection of 132 KV feeder bays at 132/33 KV SS Narayanpet - 2Nos. | To meet (N-1) Contingency in the Network for ensuring satisfactory Power Supply and provide an alternate source to 132 KV SS Narayanpet | SI | T.O.O (CE-Construction) MS.No .12 Dated:20.04.2018 | - | Not necessary | 5.67 | - | REC | 5.11 | - | 19.12.2024 | 31.03.2026 | 22.02.2025 | - | 1.66 | 1.66 | - | -
75 | S-19-01 | KTPP system Improvement Scheme | a) LILO of existing 220kV Pulukurthy-Bhimghanapur SC line to proposed 400/220/132kV KTPP SS at Ramappa point with Twin Moose DC Line (25KM) b)LILO of existing 220kV Salivagu-Bhimghanapur SC line to proposed 400/220/132kV KTPP SS at Ramappa point with Twin Moose DC Line(25KM) c)220KV Single Moose DC Line from proposed 400/220/132kV KTPP SS to 220/132kV Manthani SS(49KM) and bay extensions at Manthani SS(2No.s) d)Upgradation of existing 220kV Nagaram-Warangal DC Line with HTLS Conductor(14KM) e)132KV Single Moose DC Line from proposed 400/220/132kV KTPP SS to 132/33KV Chelpur SS on 220kV Multi Circuit Towers(2KM) and bay extensions at Chelpur(2No.s) | covered in 400KV Scheme | SI | T.O.O.(CE-400kV) Ms.No.297 Dt:09.02.2019 | - | Covered in 400KV |  | - | PFC | 405 | - | 05.05.2020 | 31.03.2026 | a)22.06.2023 b)16.09.2023 e) 24.09.2022 | 1.19 | -2.85 | -1.66 | - | -
76 | S-19-03 | 132/33 KV Sub-Station at Patancheru in S | a)132/33 kV Sub-Station at Patancheru, Sangareddy Dist with 2 X 31.5 MVA PTRs b)132 KV DC/SC line with ACSR Panther conductor from Loc.no.16 (of existing 132 KV line from RC Puram to M/s MHPL) to proposed 132/33 KV Patancheru substation on Narrow Base Towers.(4.7KM) | Manjeera water pumping station located at Patancheru which is the main drinking water source to all important commercial and residential zones in cyberabad limits. With the proposed 132 KV Patancheru SS, the Manjeera pumping station will be only 1 KM away and any interruption can be completely eliminated, the length of all 33KV feeders will come down to less than 10KMs and all 33KV feeders can be brought into Ring Main network, thus developing more no of alternate sources to each feeder, thereby improving reliable and quality power supply to major revenue source industrial consumers and to the residential/commercial areas of Patancheru division which are falling within GHMC limits. Also sufficient land is available at the existing 33/11 KV Patancheru Sub-station premises | SI | T.O.O (CE-Construction) Ms.No.375 Dated: 03.06.2019 | - | CRN/TST/TS/Erection of 132/33 KV SS at Patancheru in Sangareddy District. Approval /NO 05/2019-20 dt:22.11.2019 | 23.64 | - | REC | 20.85 | - | 23.06.2020 | 31.03.2026 | 30.11.2022 | 0.05 | 0 | 0.05 | - | -
77 | S-19-04 | 33 kV Featu at 220/132 KV SS Ammavaripet | Providing of 33 kV Features at upcoming 220/132 KV Sub-Station, Ammavaripet in Kazipet (M), Warangal Urban (District) with 1X50 MVA (new) and 1X50 MVA (released) PTRs | To provide uninterrupted power supply to the consumers with better voltage profile. | SI | T.O.O. (CE-Construction) Ms. No. 1724 Dated: 15.07.2023 | - | Not necessary | 13.65 | TGTransco funds | - | 13.65 | - | 01.04.2019 | 31.03.2026 | 30.12.2022 | 0.12 | 0.21 | 0.33 | - | -
78 | S-19-05 | 132 KV GIS Manikonda -RR Dist | a)132/33 kV GIS Sub-Station at Manikonda with 2 X 80 MVA PTRs b)LILO of existing 132 kV Shivarampally-Erragadda SC OH feeder between Loc No.80 and Loc No.81 with laying of 132 KV XLPE UG cable of 1200 Sq mm for cable length of 2.5 Km. | To overcome the low voltage problems, to cater to the upcoming loads and also to provide quality power supply to the consumers | SI | T.O.O (CE-Construction) MS.No .402 Dated: 08.07.2019. | - | CRN/TST/TS/Erection of 132 KV SS at Manikonda in Rangareddy District.Approval NO 08/2019-20 dt:27.12.2019 | 107.18 | TGTransco funds | REC | 96.46 | - | 18.03.2021 | 31.03.2026 | 15.09.2022 | 1.37 | 1.91 | 3.28 | - | -
79 | S-20-01 | 132/33 KV SS at Koutala (V)- Komaram Bhe | a)132/33 kV Sub-Station at Koutala in Komaram Bheem Asifabad Dist with 2 X 10/16 MVA PTRs (Released) b)132 KV DC/SC line from existing 132 KV Sirpur Kagaznagar SS to proposed 132 KV SS Koutala(43.53KM) c)132 KV feeder bay at existing 132 KV SS Sirpur Kagaznagar (1No.) | To provide reliable power supply to consumers and Lift irrigation schemes.To avoid power interruption and to give better supply to the area, it is very much essential to shorten the 33KV lines by erecting new 132/33KV Sub-station at Koutala | SI | T.O.O (CE-Construction) Ms.No. 981 Dated: 22.02.2021. | - | TST/TS/Erection of 132/33 KV SS at Koutala(V), Koutala (M) of Komaram Bheem Asifabad District.Approval No.02/2021-22, dt:10.06.2021 | 56.56 | - | HUDCO | 50.77 | - | 18.05.2023 | 31.03.2026 | 25.04.2025 | 10.52 | 18.14 | 28.66 | - | -
80 | S-20-02 | 132 KV SS at Dandumalkapur-Yadadri Bhuva | a)132/33 kV Sub-Station at TSIIC Dandu Malkapur , Yadadri Bhuvanagiri Dist with 2 X 50 MVA PTRs capacity b) 132 KV DC/SC line from 132/33 KV Choutuppal SS to proposed 132/33 KV SS at Dandu Malkapur(18KM) c)132 KV feeder bay ( at 132/33 KV SS Choutuppal) | To provide uninterrupted power supply | SI | T.O.O (CE-Construction) Ms. No. 965, Dated: 05.02 2021. |  | TST/TS/Erection of 132/33 KV SS at Dandumalkapur(V) in Yadadri Bhuvangiri Dist.Approval No.01/2021-22, dt:09.06.2021 | 34.73 | TGTransco funds | - | 34.73 | - | 05.02.2021 | 31.03.2027 | - | 0.07 | - | 0.07 | - | -
81 | S-21-01 | 132/33 Kv SS at Pasra -Mulugu Dist. | a)132/33 kV Sub-Station Pasra (V) in Mulugu District with 2X10/16 MVA PTR capacity (Released) b)LILO of existing 132 kV Kamalapur - Chelpur to proposed 132/33 KV SS Pasra(1.9KM) | The proposal provides uninterrupted and reliable power supply during Asia’s biggest Tribal Bi-annual Sammakka Saaralamma jatara at Medaram village, Tadwai mandal of Mulugu district, where the congregation of more than 1.5 Cr pilgrims participate in the festival will be facilitated for drinking, bathing and lighting during the entire festival days. | SI | T.O.O (CE-Construction) Ms.No.1099 Dated: 30.06.2021. | - | Not necessary | 12.8 | TGTransco funds | - | 12.8 | - | 25.10.2021 | 31.03.2026 | 31.01.2022 | 0 | 0.18 | 0.18 | - | -
82 | S-21-02 | 2nd CKT stringing from 220KV CHGR to KTR | a)2nd circuit Stringing on existing 132 kV DC/SC line from 220/132/33 kV Chegur SS to 132/33 kV SS Kothur.(17KM) b)132 kV Bay Extensions (1 No at 220kV SS Chegur, 1 No at 132 kV SS Kothur) | To meet the emergency & N-1 contingency | SI | T.O.O (CE-Construction) Ms.No.1165 Dated:17.08.2021 | - | Not necessary | 3.39 | TGTransco funds | - | 3.39 | - | 21.08.2022 | 31.03.2026 | - | 0.03 | -0.1 | -0.07 | - | -
83 | S-21-03 | 2nd CKT strngng from 220KV KWK to ACPT | a)2nd circuit Stringing on existing 132 kV DC/SC line from 220/132/33 kV Kalwakurthy SS to 132/33 kV SS Achampet.(38KM) b)132kV Bay Extensions (1 No at 220kV SS Kalwakurthy, 1 No at 132kV SS Achampet) | To meet N-1 contingency and to reduce overloading on the existing 132 kV Kalwakurthy – Achampet SC line | SI | T.O.O (CE-Construction) Ms.No.1159 Dated: 13.08.2021. | - | Not necessary | 9.68 | TGTransco funds | - | 9.68 | - | 15.06.2022 | 31.03.2026 | 28.08.2025 | 0.07 | 1.03 | 1.1 | - | -
84 | S-21-06 | line 4m 400KV Narsapur 2 132 KV Yeldurth | a)132kV DC line on Galvanized Towers with Panther ACSR conductor from 400/220/132 kV SS Narsapur to 132/33 kV SS Yeldurthy (23KM) b)132 kV feeder bays ( 2 Nos at Narsapur & 2 Nos at Yeldurthy) (4No.s) | To mitigate overloading on 132 kV Gajwel – Chegunta DC line | SI | T.O.O (CE-Construction) Ms.No.1208 Dated: 04.10.2021 | - | (CRN) TST/TS/Erection of 132KV DC line from 400/220/132 KV SS Narsapur to 132/33 KV SS Yeldurthy in Medak District.Approval NO.04/2021-2022 | 30.58 | HUDCO | - | 27.45 | - | 05.11.2022 | 31.03.2026 | 06.01.2025 | 18.13 | 5.93 | 24.06 | - | -
85 | S-21-08 | 2nd ckt 4m Shaligowraram-Mothkur | a)2nd circuit stringing on existing 132 kV DC/SC line from 132/33 kV Shaligowraram SS to 132/33 kV SS Mothkur with Panther ACSR conductor (22KM) b)132kV Bay Extensions (1 No at 132kV SS Shaligowraram, 1 No at 132/33 kV SS Motkur) | As the 132/33 KV SS Mothkur is being fed by the 132 KV Mothkur - Shaligowraram DC/SC line which is the only source for the sub-station and to maintain reliable and quality of power supply to the consumers in that area of Nalgonda District | SI | T.O.O (CE-Construction) Ms.No.1271 Dated: 20.12.2021 | - | Not Necessary | 6.53 | TGTransco funds | - | 6.53 | - | 25.04.2024 | 31.03.2026 | 06.01.2025 | 0.14 | 4.04 | 4.18 | - | -
86 | S-21-12 | 132/33 kV SS Nuthankal | a)132/33kV Sub-station at Nuthankal in Suryapet District with PTRs capacity of (2x50 MVA) + (1x10/16 MVA Released.) b)Stringing of 2nd circuit from Loc.No.16 to Loc.No.75 (Tapping Tower) on existing 132kV DC/SC line from 400/220/132 kV SS Suryapet to 132/33kV SS Thungathurthy towers with Panther ACSR conductor(16.5KM) c)132kV DC/SC line from Loc.No.75 (Tapping tower) to proposed to 132/33kV SS Nuthankal on Galvanised towers with Panther ACSR conductor(9.5KM) d)132 kV Bay extension at 400/220/132kV SS Suryapet(1 No.) | The Substation is proposed to overcome the low voltage problems, to cater to the upcoming loads and also to provide quality power supply to the consumers. | SI | T.O.O (CE-Construction) Ms.No.1330 Dated:10.03.2022. | - | (CRN) TST/TS/Erection of 132/33 KV Sub Station at Nuthankal(V&M) in Suryapet District instead of 1323/33 KV Aipoor SS in Suryapet District.Approval NO.02/2022-2023 | 30.55 | - | REC | 18.91 | - | 22.02.2023 | 31.03.2026 | 30.12.2024 | 11.4 | 9.76 | 21.16 | - | -
87 | S-22-02 | 2nd Circuit stringing on existing 132KV | a)2nd circuit stringing on existing 132 kV DC/SC line from 220/132/33 kV Shadnagar SS to 132/33 kV SS Srirangapur with Panther ACSR conductor (including 2 Nos Narrow Base Towers) ( 13.4KM) b)132kV Bay Extensions (1 No at 220/132/33 kV SS Shadnagar & 1 No at 132/33 kV SS Srirangapur) (2 No.s) | 2nd nd circuit is propsoed as the 132/33 KV SS Srirangapur being fed by the 132 KV Shadnagar - Srirangapur DC/SC line which is the only source for the sub-station i.e., radial feeder and to maintain reliable and quality power supply to the consumers in that scheme area. | SI | T.O.O (CE-Construction) Ms.No.1461 Dated:19.08.2022 | - | Not Necessary | 5.79 | TGTransco funds | - | 5.79 | - | 12.08.2024 | 31.03.2026 | Work in Progress | 0.14 | 2.63 | 2.77 | - | -
88 | S-22-05 | LILO of 132 KV Dharmaram-Godur to 220/1 | a)LILO of 132kV Darmaram-Godur line to 220/132 KV SS Jagityal in Jagityal District on multi circuit tower with panther ACSR conductor(1KM) b)132kV Bay Extensions (2 No's at 220/132 kV SS Jagityal.)( 2No.s) c)Dismantling of TNS,TND,BOOM & Re-stringing of 132KV Jagityal-Gangadara, Jagityal-Pudur, Jagityal-Jagityal, Jagityal-Korutla line near TT Tower at 220 kV SS Jagityal. | The proposal for making LILO of 132KV Dharmaram-Godur line to 220/132KV SS Jagityal in Jagityal District as the construction of 220 KV SS Kathalapur and making LILO of Godur-Dharmaram line to 220KV SS Kathalapur may take some time and augmentation of PTR capacities at 132/33 kV SS Dharmaram and 132/33 kV SS Godur was approved and works at these substations are under taken. This will further increase load on 132KV RSS - Dharmaram line. The load on 132 KV RSS - Dharmaram line can be limited to safe operating limits if loads of Godur SS are fed from 220KVSS Jagityal. Augmentation of PTR capacities from 3x100 MVA to 3x100 MVA+1x160 MVA was approved at 220KVSS Jagityal. Increased PTR capacity at 220KVSS Jagityal will make feeding loads of 132 KVSS Godur is feasible. For this, making LILO of 132 KV Dharmaram-Godur line to 220KVSS Jagityal is required. | SI | T.O.O (CE-Construction) Ms.No.1590 Dated:14.03.2023. | - | Not necessary | 5.12 | TGTransco funds | - | 5.12 | - | 15.08.2023 | 31.03.2026 | 21.01.2025 | 0 | 2.97 | 2.97 | - | -
89 | P-10-01 | JAIPUR POWER TRN SCHEME | a)132 kV DC Line from proposed 400/220/132kV Narsapur SS to existing 132 kV Gummadidala SS and bay extensions at Gummadidala SS(17.25KM) b) LILO of 132kV Narsapur –Koudipalli SC Line to proposed 400/220/132kV Narsapur SS.(17.25KM) C)132 kV Bay Extensions at Gummadidala 132 kV SS (2No.s) | covered in 400KV Scheme | SI | Ref:TO.O.(CE-Construction/400kV) Ms.No.19, Date: 02-05-2014. | - | Covered in 400KV |  | - | REC | 898.49 | - | 01.01.2016 | 31.03.2026 | a) 15.07.2017 b)11.07.2017 | - | 0 | 0 | - | -
92 | P-12-02 | NIRMAL POWER TRANSMISSION SCHEME | a)Up gradation of 132/33 kV Renzal SS to 220/132 kV Renzal Sub Station and 220kV DC Line from proposed 400/220kV Nirmal SS to the proposed up graded 220/132 kV Renzal SS b)220/132 KV SS at Indravelly in Utnoor District c)220kV DC Line from proposed 400/220kV Nirmal SS to the proposed 220/132 kV Indravelly SS d)132kV DC Line from proposed 220/132 kV Indravelly SS to 132/33 kV Utnoor S Sand 132 KV Bay extension at Utnoor-2, e)220kV Multicircuit line for making LILO of existing 220kV RSS(Malyalpalli) –Nirmal and RSS-Vemnur-Nirmal DC line to existing 220/132kV Jagityal Substation and 220kV Bay Extensions at 220kV Jagityal SS f)220kV DC Line from proposed 400/220kV Nirmal SS to the existing 220kV Nirmal SS on Multi circuit towers g)132 KV DC line with Single moose from proposed 220/132 kV Indravelly SS to 132/33 kV Asifabad SS on 220kV Galvanized DC towers & 132 KV bay extension at Asifabad -2. h)132kV DC line from Proposed 220/132 kV Indravelly SS to the existing 132kV Adilabad SS & 132 KV bay extension at Adilabad -2. | Covered in 400KV scheme | SI | T.O.O. (CE-400kV) Ms.No.07 Dated: 09.01.2018 | - | Covered in 400KV |  | - | REC | - | - | 10.03.2019 | 31.12.2026 | a) 15.02.2020 b)27.08.2021 c)18.08.2021 e)20.11.2019 f)29.12.2017 g)work in progress h)31.03.2022 | 29.83 | 7.84 | 37.67 | - | -
93 | P-15-01 | DINDI SYSTEM IMPROVEMENT SCHEME | a)220 kV features at 132/33 KV Substation at Nagarkurnool b)220KV DC Line from proposed 400KVSS Dindi to proposed 220 kV Nagarkurnool SubStation. C)220KV DC Line from proposed 400KVSS Dindi to existing 220 kV Kondamallepally SubStation. | covered in 400KV Scheme | SI | T.O.O.(CE-Projects-I) Ms.No.8 Dt:19 .01.2016. | - | Covered in 400KV |  | - | REC | 273.55 | - |  | 31.03.2026 | a) 03.04.2019 b)03.04.2019 c)31.03.2022 | - | 0.03 | 0.03 | - | -
94 | P-15-03 | Bhadradri Thermal Power Transmisn Scheme | a)220/132/33 kV Kallur Sub Station b)132kV Chandragonda Sub Station c)220kV DC line from proposed 400/220kV Bommanapalli to the proposed 220/132 kV Kallur SS (Single Moose) d)132kV DC line from proposed 220/132kV SS Peddagopati to 132/33kV SS Madhira and bay extensions at Madira e)132kVDC Line with Multi-Circuit towers for making LILO of existing132kV Budidampadu - Penubali & 132 kV Thallada- Penuballi f)132kV DC line from proposed 220/132kV SS Peddagopati to 132/33kV SS Thallada and bay extensions at Thallada g)132kV line with Multi-Circuit towers for making LILO of existing132kV Khammam - Chilakallu DC line to proposed 220/132 kV Peddagopati h)132 KV DC/SC line from proposed 220/132 KV SS Kalluru to 132/33 KV SS Chandrugonda |  | SI | T.O.O.(CE-Projects-I)Ms.No.15 Dt:29-04 -2016. | - | Covered in 400KV |  | - | PFC | 1150.16 | - | 30.05.2017 | 31.03.2026 | a) 3.08.2018 b)2.11.2019 c)3.08.2018 d)26.05.2023 e)09.08.2018 f)28.12.2019 g)23.12.2022 h)02.11.2019 | 0.02 | 4.4 | 4.42 | - | -
covered in 400KV Scheme
95 | P-15-04 | KTPS ( Stage VII -1X800MW) - scheme | a)Up gradation of 132/33 kVJangaon SS to 220/132/33 kV Jangaon Sub Station. b) 220/132/33 kV Sub Station at Husnabad in Warangal Dist. C)220kV line with Multi circuit towers for making LILO of 220kV Waddekothaplly-Bhongiri DC line(both circuits) to proposed 400kV SS Jangaon with Single moose conductor and 220 KV bay extension at 400kV Jangaon SS for LILO of W.Pally to Bhongir DC line d)220kV DC line for making LILO of 220kV KTPS-Shapurnagar SC line to proposed 400kV SS Jangaon with Single moose conductor and 220 KV bay extension at 400kV Jangoan SS for LILO of KTPS-S.Nagar SC line e)220kV DC line for making LILO of 220kV KTPS-Shapurnagar SC line to 220/132kV SS Waddekothaplly with Single moose conductor and 220 KV bay extension at 220kV W.Pally SS for LILO of KTPS-S.Nagar SC line f)DC line from 400/220kV Jangaon SS to the 220/132/33kV Husnabad SS with Single Moose Conductor g)2nd circuit stringing on existing 132kV DC/SC Husnabad-Palamaukula line h)132kV line with MC towers for making double LILO of 132kV Husnabad-Palamakula DC line to proposed 220/132/33kV Husnabad SS and 132 kV Bay Extensions at Husnabad 132 kV SS and Palamakula 132kV SS | covered in 400KV Scheme | SI | T.O.O. (CE-400kV) Ms.No. 139 Dt: 11.09.2017 | - | Covered in 400KV |  | - | PFC | 937.63 +139.49 | - | 12.10.2018 | 31.03.2026 | a) 20.05.2019 b)17.07.2025 c)12.06.2019 d)10.08.2019 e)13.08.2019 f)17.07.2025 h)work in progress | 60.19 | 9.7 | 69.89 | - | -
96 | P-16-01 | Telangana STPP-I (2X800MW) Power Evacuat | a)LILO of both circuits of 220kV Durshed - Sircilla line to 400kV Ramadugu SS on Multi circuit towers b)LILO of 220kV Malyalpalli-Bheemgal at 400/220kV Ramadugu Sub-Station | Covered in 400Kv scheme | GE | T.O.O.(CE-400kV) Ms.No.104 , Dt:12.07.2017 | - | Covered in 400KV |  | - | REC | 1131.17 | - | 13.08.2018 | 31.03.2026 | a)03.03.2020 b)19.02.2021 | 0.04 | 0 | 0.04 | - | -
97 | P-19-01 | 315MVA ICT at BTPS & DC lne 4m Manuguru | a)Supply,Erection, Testing & Commissioning of 400/220 kV, 1X315 MVA Auto Transformer along with PTR Bays and Bus coupler including civil works at BTPS. b)220 KV DC line from 220/132/33 KV Manuguru SS to 400 KV Bhadradri Thermal Power Station switch yard (23KM) c)220 kV Bays (2 Nos at 220 kV Manuguru, 2 Nos at BTPS) (4 no.s) | To provide startup supply to Bhadradri Thermal Power Station (4X270 MW) under Black start restoration procedure & alternate evacuation of power from BTPS (4x270 MW) was received from the Executive Engineer/Construction, Khammam as per SLDC studies | GE | T.O.O (CE-Construction) MS. No. 401 Dated: 08.07.2019 | - | CRN No. TST/TS Erection of 400/220 KV 1x315 MVA ICT at BTPS switch yard Manuguru & Erection of 220 KV DC line from 220/132/33 KV Manuguru SS to 400 KV BTPS switch yard Approval/No.06/2019-20 dt:22.11.2019 | 66.56 | - | REC | 59.91 | - | 31.09.2019 | 31.03.2026 | 12.03.2021 | 13.15 | -0.67 | 12.48 | - | -
98 | P-19-02 | Yadadri Thermal Power (5x800MW) Evacuati | a)220KV TMDC line from proposed 400/220KV Damarcherla SS to 220KV Miryalaguda SS and bay extensions at Miryalaguda b)220KV SMDC line from proposed 400/220KV Damarcherla SS to 220KV Huzurnagar SS and bay extensions at Huzurnagar c)LILO of both circuits of 220KV Malkaram-Narketpally DC line to proposed 400/220/132 KV Choutuppal SS on MC towers d)132 KV DC line from proposed 400KV SS Choutuppal to 132 KV SS Choutuppal and 2 No.s 132 KV bays at 132/33 KV SS Choutuppal e)32kV DC line from proposed 400/220/132 KV Choutuppal SS to proposed 132 KV Dandumalkapur SS and 132 KV bay extension at 132 KV SS Dandumalkapur | covered in 400KV Scheme | GE | T.O.O.(CE-400kV) Ms.No.51 , Dt:10.10.2019 | - | Covered in 400KV |  | - | PFC | 1102.26 | - | 15.11.2020 | 31.03.2026 | a)Ckt-I charged on 29.08.2022 and Ckt-II charged on 29.12.2022 b)25.08.2024 c)LILO of Ckt-I charged on 23.03.2023 and LILO of Ckt-II charged on 20.03.2023 d)20.10.2023 | 47.55 | 4.64 | 52.19 | - | -
|  | Total | [14 empty] | 588.57 | 114.3 | 702.87
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please
6 | S-10-02 | ERECTION 132/33 KV SS AT ASIFABAD | a)132/33 kV Substation at Asifabad with 2 x 16 MVA (Released) PTR Capacity (Radial) b)132kV DC/SC line from Sirpurkagaznagar 132/33 kV SS to the proposed 132/33 kV Asifabad Substation c)132 kV Bay extension at Sirpurkagaznagar 132 kV substation. |  | SI | T.O.O (CE-Construction) Ms. No. 267 Dated: 6.10.2010 |  | CRN.No.APT/TS/132 KVSS/ Asifabad/Invest.24/12 | 21.78 |  | REC | 18 |  | 29.11.2012 | 31.03.2025 | 25.11.2015 | 0 | -0.06 | -0.06
7 | S-10-13 | ERECTION OF 132/33KV LGMPET SS | a)132/33 kV Substation at LGM Pet with 1 x 31.5 + 1 x 16 MVA (Released) PTR Capacity Radial b)132kV DC/SC line from 220/132 kV Malkaram to the proposed 132/33 kV LGM Pet Substation c)132 kV Bay extension at 220/132 kV Malkaram substation. |  | SI | T.O.O (CE-Trans) Ms. No. 27 Dated: 17.02.2016 |  | APT/TS/132kv SS- LGM Peta/F-INVST-17/2012 | 35.51 |  | UCO Bank | 14.79 |  | 16.09.2011 | 31.03.2025 | 18.08.2016 | 0 | 0.05 | 0.05
9 | S-10-18 | ERECTION OF 132/33 KV SUBSTATION AT RAIKAL | a) 132/33 kV Substation at Raikal with 1 x 31.5 + 1 x 16 MVA (Released) PTR Capacity (Radial) b) 132kV DC/SC line from Jagityal 220/ 132 kV SS to the proposed 132/33 kV Raikal Substation c)32 kV Bay extension at Jagityal 220/ 132 kV SS No. |  | SI | T.O.O (CE-Construction-I) Ms. No. 394 Dated: 15.12.2010 |  | APT/TS/132 kV SS -Raikal/ F-INVST -20/2013 | 14.12 |  | OBC | 13.8 |  | 01.12.2014 | 31.03.2025 | 07.09.2016 | 0 | -0.03 | -0.03
12 | S-10-28 | 220KVsingle moose DC line from 400KV | - |  | SI | The work is covered in Jaipur Power Transmission Scheme | [10 empty] | 0.01 | 0 | 0.01
17 | S-11-21 | 132KV LINE DHARMAPURI- LUXXETTIPET | a)132 kV DC/SC line from 132/33 kV Dharmapuri SS to 132/33 kV Luxxettipet SS b)132 kV bays at 132 /33 kV SS Dharmapuri and 132/33 kV SS Luxxettipet SS |  | SI | T.O.O (CE-Construction-I) MS. No. 251 Dated: 10.10.2011 |  | APT/TS/132 kV -DC/SC Line- Luxettipet-Dharmapuri/ F-INVST -13/2013 | 10.91 |  | PFC | 10.91 |  | 12.12.2014 | 31.03.2025 | 12.12.2017 | 0.09 | 0.01 | 0.1
19 | S-11-29 | 132/33 KV SUBSTATION AT PADMAJIWADI | a)132/33 kV Substation at Padmajiwadi with 1 x 31.5 + 1 x16 MVA PTR Capacity (LILO) b)132kV LILO line from 132 kV Dichpalli - Kamareddy to the proposed 132/33 kV Padmajiwadi Substation |  | SI | T.O.O (CE-Construction-I) Ms. No. 2, Dated: 6.04.2011 |  | - | 10.39 |  | REC | 7.79 |  | 07.01.2013 | 31.03.2025 | 29.03.2014 | 0 | -0.02 | -0.02
20 | S-11-30 | 220KV SS AT PARIGI IN RR DISTRICT | a)220/132 kV Substation at Parigi with 2*100 MVA PTR’s Capacity with 4 Nos 132 KV out going feeder bays. B)220 kV DC line with single Moose conductor from 400/220 kV Yeddumailram Sub-Station to the proposed 220/132 KV Pargi SS. C)220KV Bay extensions at 400/220 kV Yeddumailram SS |  | SI | T.O.O (CE-Construction–I) MS. No.180 Dated: 09.08.2011 |  | CRN:APT/TS/220/132kV Parigi/ F.INVST-1/2013 Dt:11.05.2012 | 60.35 |  | REC | 54.27 |  | 09.08.2011 | 31.03.2025 | 04.03.2016 | 0 | 0.01 | 0.01
21 | S-11-32 | 132/33 KV SS&LINE PALAMAKULA(RAMPUR) | a)132/33 kV Substation at Rampur with 1 x31.5 + 1 x 16 MVA (Released) PTR Capacity (Radial) b)132kV DC/SC line from 132 kV Husnabad Substation to the proposed 132/33 kV Rampur Sub Station c)132 kV Bay extension at 132 kV Husnabad Substation |  | SI | T.O.O (CE-Construction-I) Ms. No.33 Dated: 27.04.2011 |  | - | 20.14 |  | PFC | 19.71 |  | 21.06.2013 | 31.03.2025 | 28.11.2014 | 0 | 0 | 0
23 | S-12-05 | ERECTION OF 33KV FEATURES AT JANKAMPET | Providing 33 kV features at 132/11 kV Lift Irrigation substation at Jankampet in Nizamabad district with 2*16 MVA PTR Capacity |  | SI | T.O.O (CE-Construction-I) Ms. No. 283 Dated: 20.12.2012 |  | Not Necessary | 4.18 |  | REC | 3.5 |  | 01.11.2016 | 31.03.2025 | 06.12.2018 | 0 | 0.04 | 0.04
24 | S-12-06 | 2NDCKT 220KV LINE 220KV RSS -MANDAMARRI | a)2nd circuit stringing on existing 220 kV DC/SC line from 220 kV Ramagundam SS to 220 kV Mandamarri (Bellampally) SS b)220kV Bay Extensions at 220 kV Ramagundam & Mandamarri Sub-Stations. |  | SI | T.O.O (CE-Construction-I) MS. No. 261 Dated: 28.11.2012 |  | Not Necessary | 10.67 |  | REC | 91.6 |  | 01.10.2014 | 31.03.2025 | 20.10.2015 | 0 | -0.01 | -0.01
26 | S-12-10 | MD PALLY SS& LINE SCHEME | a)132/33 kV Sub-Station at Mylardevpally (Kattedan) with 2 X 50 MVA Power Transformer Capacity - Radial b)132 kV DC line with 630 Sq. MM XLPE UG Cable from 220/132/33 kV Sub-Station, Shivarampally to the proposed 132/33 kV Sub-Station Mylardevpally (Kattedan). c)132 kV Bay Extensions at 220 kV Sub-Station, Shivarampally.(2 No.s) |  | SI | T.O.O (CE-Construction) Ms.No.27 Dated: 12 .02.2015 |  | TST/TS/132kV / MD Pally, Kattedan /F-INVST- 03/2016 | 57.9 |  | PFC | 33.864 |  | 05.08.2015 | 31.03.2025 | 25.09.2017 | 0 | 0.02 | 0.02
27 | S-12-11 | 132/33 KV SUBSTATION AT MUNAGALA | a)132/33 kV Sub-Station at Munagala with 3 X 10/16 (Released) MVA PTRs b) 132 kV DC line (37 KM) from 400 kV Suryapet to existing 132 kV Kodada with 1 circuit LILO (6 KM) to the upcoming 132 kV Munagala SS. TOTAL 37 + 6 = 43 KM |  | SI | T.O.O (CE-Construction) Ms. No.127 Dated: 17.07.2015 |  | TST/TS/132/33kV SS Munagala / F-INVST- 13/2015 | 35.54 |  | REC | 30.947 |  | 20.06.2016 | 31.03.2025 | 22.12.2017 | 0 | -0.01 | -0.01
30 | S-13-04 | Survey for ere. of 1 meter narrow based | Does not pertain to Construction wing | [13 empty] | 0.01 | - | 0.01
43 | S-15-11 | 2ND220 KV RSS-NIRMALDC/SCLINE&RSSTOJGL | a)Stringing of 220 kV 2nd Circuit on existing 220 kV DC/SC line from 220 kV RSS to 220 kV Nirmal SS b)Stringing of 220 kV 2nd Circuiton existing 220kV DC/SC line from 220 kV RSS to 220 kV Jagityal SS c)220 kV Bays (RSS-2Nos, Nirmal-1 No, Jagityal-1 No.) |  | SI | T.O.O (CE-Construction) Ms. No.164 Dated: 06.11.2017 |  | CRN/TS/TST/220 KV2nd Ckt/RSS to Nirmal SS and RSS to Jagityal SS/Invst. App/No.15/2015,dt.17.12.15 | 66.14 |  | PFC | 38.06 |  | 27.11.2015 | 31.03.2025 | RSS- Nirmal - 30.12.2016 RSS-Jagityal-02.11.2018 | 0 | 0.48 | 0.48
44 | S-15-12 | 132/33 kV Sub-Station at Gandimasanipet | a)132/33 kV Sub-Station at Gandimasanipet of Yellareddy Constituency with 3 X 10/16 MVA PTRs (Released) b)132 kV DC line on Galvanised Towers with Panther ACSR for making LILO of 3rd circuit of 132 kV Minpur – Nizamsagar feeder at the proposed 132kV Sub-Station at Gandimasanipet of Yellareddy Constituency. |  | SI | T.O.O (CE-Transmission) MS.No. 179 Dated: 07.09.2015 |  | Not Necessary | 15.89 |  | PFC | 13.4 |  | 25.07.2016 | 31.03.2025 | 30.07.2018 | 0 | 0 | 0
52 | S-16-07 | 33KV Features at Exg 132KVSS KDNDPR NLG | 33 kV features at existing 132 kV Switching Station at Kodandapur with 2 X 31.5 MVA PTRS |  | SI | T.O.O (CE-Transmission) Ms. No.31, Dated: 18.02.2016 |  | Not necessary | 8.91 |  | REC | 8.01 |  | 01.04.2018 | 31.03.2025 | 25.03.2019 | 0 | 0.01 | 0.01
53 | S-16-09 | Erec of 132/33 KV SS at Regonda in Wgl D | a)132/33 kV Sub-Station at Regonda in Warangal District with 3 X 10/16 MVA PTRs (Released) b)132 kV DC/SC line on Galvanised Towers with Panther ACSR from existing 132/33 kV SS Chelpur to the proposed 132kV Sub-Station at Regonda in Warangal District. C)132kV Bay at 132/33kV SS, Chelpur |  | SI | T.O.O (CE-Transmission) Ms. No.49 Dated: 06.04.2016. |  | CRN.No.TST/TS/220/132/33 KV SS, Regonda,Warangal,Dist./Invest.Appl.No.8/17,2016-17 | 22.11 |  | PFC | 19.07 |  | 07.02.2018 | 31.03.2024 | 07.02.2018 | 0 | - | 0
68 | S-17-14 | 33 KV features at 220 KV SS Mahabubabad | Providing of 33 kV Features at upcoming 220/132KV Substation Mahabubabad, in Mahabubabad District with Released 2X10/16 MVA PTRs |  | SI | T.O.O (CE-Construction) Ms. No.170, Dated: 16.11.2017 |  | Not necessary | 8.54 |  | REC | 7.44 |  | 31.10.2018 | 31.03.2025 | 26.05.2021 | 0.02 | 0.05 | 0.07
11 | S-10-21 | 132 KV SS at Toopranpet | - | To meet increased load on 33/11 kV substations and also to reduce 33 kV line losses | SI | Dandumalkapur T.O.O is issued instead of Toopranpet | [10 empty] | 0.01 | 0 | 0.01

## DC works
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2026-27 for Transmission Business filed with TGERC
Scheme-wise details of Capital Expenditure incurred in FY: 2024-25 of 4th control period
(figures in Crores)
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme) | Project Purpose (SI/SE/SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total approved Cost (in Cr) | Source of funds |  |  |  | Project Start Date (DD-MM-YY) | Project Completion Date (DD-MM-YY) | DOC | Opening CWIP as on 31.03.2024 | Actual Expenditure from 01.04.2024 to 31.03.2025 | Cumulative expenditure upto 31.03.2025 | % Capatalisation | Remarks / Balance works , if any.
[9 empty] | TGTransco Funds | Loan source | Loan Amount | Grants, if any
|  | Brought Forward | [13 empty] | 588.57 | 114.3 | 702.87
1 | D-18-05 | shftng of lns B/w manoharbd-Kothapalli n | Shifting/Modification of 132 KV & 220KV lines between Manoharabad and Kothapalli Railway line in Siddipet District | DCW | - | - | - | 21.39 | - | Consumer contribution | - | - | 31.03.2018 | 31.03.2026 | 02.07.2019 | - | 0 | 0 | - | -
2 | D-18-10 | Divrsn of Gajwl-Kndapka etc Komrveli mal | i) Diversion of 220 KV Gajwel-Kondapaka and 220 KV Kamareddy-Kondapaka lines (b/w Loc.No.25/1 to Loc. No.25/15) and 132 KV Doulthabad –Gajwel DC/SC line(b/w Loc.No.62 to Loc.No.69) (7 KM including 1.5 KM Multi circuit towers)1.5 KM Multi circuit towers) (ii) Diversion of old 132 KV Siddipet –Gajwel DC line (13KM) in b/w Loc. No.203 & 227 which are falling under submeregence area of proposed Sri Komaravelli Mallanasagar Reservoir under DC works & (iii) Diversion of 132 KV line (3.5KM) from location no.11 to 25 of 400 KV SS Gajwel to 132 KV SS Thunikibollaram for Pranahita-Chevella Package -14 Kaleswaram LIS in Siddipet District. | DCW | - | - | - | 17.6 | - | Consumer contribution | - | - | 26.09.2018 | 31.03.2026 | 09.12.2020 | 0 | 0.43 | 0.43 | - | -
3 | D-18-12 | Extn of pwr sply 2 RTSS Manoharabad 4m N | Extension of 132 KV Power supply for a CMD of 10MVA to the proposed Railway Traction SS at Manoharabad (V), Toopran(M), Siddipet Circle in Medak District | DCW | - | - | - | 11.35 | - | Consumer contribution | - | - | 15.04.2019 | 31.03.2026 | 25.11.2020 | 0.08 | 0 | 0.08 | - | -
4 | D-18-13 | Pwr sply 2 132KV RTSS Divitipally(RVNL) | Pwr sply 2 132KV RTSS Divitipally(RVNL) | DCW | - | - | - | 9.76 | - | Consumer contribution | - | - | 21.01.2020 | 31.03.2026 | 22.07.2022 | 0.06 | 0.25 | 0.31 | - | -
5 | D-18-15 | Extn of 132 KV lne 4 kamrdy 2 Tlamdla Ra | Extension of 132 KV Radial 2 –phase DC/SC line (8KM) from existing 220/132 KV SS Kamareddy to proposed 132/25 KV Talamadla Railway Traction Substation. | DCW | - | - | - | 14.55 | - | Consumer contribution | - | - | 24.03.2021 | 31.03.2026 | 31.03.2023 | 0.04 | 1.13 | 1.17 | - | -
6 | D-18-16 | Ere of Pwr sply 2 132/25 KV RTS Jankamp | Extension of power supply to proposed 132/25 KV Railway Traction Substation Jankampet by erection of 132 KV radial 2-phase DC/SC line (12KM from proposed 220/132 KV SS Renjal | DCW | - | - | - | 19.05 | - | Consumer contribution | - | - | 25.11.2020 Mbay- 07.10.2022 | 31.03.2026 | 04.11.2024 | 11.19 | 2.86 | 14.05 | - | -
| D-18-17 | 132KV UG at Parigi b/n Transco & Wind po | Erection of metering bay at 132 KV Parigi SS | DCW | - | - | - | 0.41 | - | Consumer contribution | - | - | Supervision work |  | 24.03.2016 | 0.05 | - | 0.05 | - | -
7 | D-18-18 | Extn of 132 KV sply 2 RTSS at Wnaprthy 4 | Extension of 132 KV supply to railway traction SS at Wanaparthy from existing 132/11 KV Kothakota LIS in Mahaboobnagar District. | DCW | - | - | - | 15.6 | - | Consumer contribution | - | - | 06.01.2022 | 31.03.2026 | 04.08.2023 | 0.11 | 0 | 0.11 | - | -
8 | D-18-19 | Extn of HT sply 2 Thimmapr RTSS 4m Shams | Extension of HT supply at 132 KV level for a CMD of 10MVA to Thimmapur RTSS from 220/132 KV Shamshabad SS | DCW | - | - | - | 34.87 | - | Consumer contribution | - | - | 08.11.2018( Line & bay at Shamshabad) 21.01.2019 (Bays at RTSS) | 31.03.2026 | 24.05.2025 | 26.99 | 4.97 | 31.96 | - | -
9 | D-19-01 | Shftng of 132KV Erragadda-Shivarampally | Shifting of existing 132KV Erragadda – Shivarampally SC Feeder between Loc.No. 85 & 86 for GHMC under strategic road development programme Phase-III near Malkaram cheruvu | DCW | - | - | - | 0.94 | - | Consumer contribution | - | - | 07.03.2019 | 31.03.2026 | 11.03.2020 | - | 0.08 | 0.08 | - | -
10 | D-19-02 | Shift Gachibowli-Madapur-I&II DC lines b | Shifting of Gachibowli – madhapur – I & II DC lines crossing at Botonical Garden Junction Hyderabad | DCW | - | - | - | 13.02 | - | Consumer contribution | - | - | 29.11.2019 | 31.03.2026 | 28.05.2020 | 0.77 | 0.79 | 1.56 | - | -
11 | D-19-03 | Sft 220KV Gachibowli-S.nagar-Egadda line | Shifting of 220KV Gachibowli – Shapurnagar – Erragadda – DC line at Kothaguda Junction, Hyderabad under DC Works | DCW | - | - | - | 19.61 | - | Consumer contribution | - | - | 29.11.2019 | 31.03.2026 | 31.08.2021 | 1.11 | 0.13 | 1.24 | - | -
12 | D-19-04 | Sft 132KV lines 4m Roadno.45-Durgam Cher | Shifting of 132KV Jubilee Hills – Chandrayanagutta DC feeder and 132 KV Erragadda – Shivarampally SC feeder at 132KV SS Jubilee Hills for GHMC for construction of elevation corridor from road no.45 to Durgam Cheruvu under DC Work | DCW | - | - | - | 18.8 | - | Consumer contribution | - | - | 30.01.2019 | 31.03.2026 | 13.06.2020 | 2.37 | 0.03 | 2.4 | - | -
13 | D-19-09 | 220KV Monopole from 220 KV Ghanpur-CPRI | 220KV Monopole DC/SC line from 220KV SS Ghanapur to M/s.CPRI | DCW | - | - | - | 55.16 | - | Consumer contribution | - | - | 31.05.2023 | 31.03.2026 | - | 0.38 | - | 0.38 | - | -
14 | D-19-10 | Diversn of 220KV Gachibwli-Err'da-SH.ngr | Diversion of 220KV Gachibowli-Erragadda-Shapurnagar DC line passing through the premises of M/s.DLF Commercial Developers Limited, IT/ITES IT Park, Gachibowli, Hyderabad | DCW | - | - | - | 1.37 | - | Consumer contribution | - | - | 17.09.2019 | 31.03.2026 | 19.10.2020 | 1.59 | -0.06 | 1.53 | - | -
15 | D-20-01 | 132/33 KV SS at E-city Fabcity | 132/33KV Sub-station at Electronic Manufacturing Cluster at E-City Fabcity, (ii) 132 KV line from existing 220/132 KV Fabcity SS to proposed 132/33 KV E-City Fabcity SS for proposed 132/33 KV E-city Fabcity SS in Raviryal Village, Maheshwaram Mandal, Ranga Reddy District | DCW | - | - | - | 47.99 | - | Consumer contribution | - | - | 21.09.2020 (SS & Bays) 22.04.2021 (Line) | 31.03.2026 | 16.09.2023(SS) 31.08.2023 (bays) 31.08.2023 (Line) | 0.1 | 0.75 | 0.85 | - | -
16 | D-20-02 | Extension of 132KV supply to RTSS Manopa | i) 1 No.132 KV bay at existing 132/33 KV Alampur SS for 132 KV RTSS Manopad, (ii) 132 KV DC/SC line from existing 132/33 KV Alampur SS to proposed RTSS Manopad for a length of about 12 KM in Jogulamba District (iii) 1 No.132 KV metering bay at proposed 132 KV RTSS Manopad in Jogulamba District | DCW | - | - | - | 20.14 | - | Consumer contribution | - | - | 25.01.2023 | 31.03.2026 | 19.06.2024 | 8.85 | 2.38 | 11.23 | - | -
17 | D-20-06 | 132 KV DC/SC lne 4m 132/33 KV SS Morthad | (i) Extension of 132 KV radial 2-phase DC/SC line (0.5 KM) from existing 132/33 KV SS Morthad to proposed 132/25 KV Morthad Railway traction substation (CMD of 10 MVA) (ii) 1 No.132 KV Bay extension at 132/33 KV SS Morthad and (iii)1 No.132 KV bay along with metering bay at proposed 132/25KV Morthad Railway Traction Substation in Nizamabad Dsitrict | DCW | - | - | - | 5.81 | - | Consumer contribution | - | - | 15.04.2021 | 31.03.2026 | 29.04.2022 | 0 | -0.01 | -0.01 | - | -
18 | D-20-07 | Modifictn of power lne of Bhadrachalam-S | - | DCW | - | - | - | 61.16 | - | Consumer contribution | - | - | 20.10.2020 | 31.03.2026 | 28.07.2021 | 0.14 | -0.06 | 0.08 | - | -
19 | D-21-23 | 400KV 1000Sqmm XLPE cable etc.-Srisailam | - | DCW | - | - | - | - | - | Consumer contribution | - | - | - |  |  | 1.73 | -0.01 | 1.72 | - | -
20 | D-21-24 | 132kV DC.SC line Ganganpally-RTSS Pandur | (i) Erection of 2Nos 132kV bays at 132/33kV Ganganpally SS (a) for 132kV Pandurangaswamy road RTSS and (b) for 2nd circuit stringinging from 220kV Jurala SS in 132/33kV Ganganpally SS in Jogulamba Dist.Gadwal(Jogulamba) District. (ii) Erection of 132kV DC/SC line to existing 132/33kV Ganganpally SS to proposed RTSS Pandurangaswamy road in Gadwal(Jogulamba) Dist. (iii) Erection of 1No. 132kV Bay at 220/132kV Jurala SS for 132kV Ganganpally SS. (iv) stringing of 2nd circuit from 220/132kV Jurala SS to | DCW | - | - | - | 14.55 | - | Consumer contribution | - | - | 11.10.2021 | 31.03.2026 | 10.04.2022 | 0.41 | 0.67 | 1.08 | - | -
|  | Data centers at TSIIC- M/s. Amazon |  |  | - | - | - |  | - |  | - | - | [6 empty] | - | -
21 | D-21-27 |  | a) 220KV MC/DC line from 220/132 KV Fabcity SS to the proposed site of M/s.Amazon Data Services India Pvt Ltd.at TSIIC industrial park Fabcity(2.5Kms) b) 2 no.s 220KV feeder bays at 220/132KV Fabcity SS c) 2 No.s 220KV bays at Amazon SS | DCW | - | - | - | 40.49 | - | Consumer contribution | - | - | 14.10.2021(bays at Fabcity end) 11.10.2021(line) 14.10.2021(Bays at Amazon end) | 31.03.2026 | 28.06.2023 28.06.2023 13.07.2023 | 21.91 | 6.8 | 28.71 | - | -
|  |  | (a) 2 No.s single circuits with 220KV XLPE UG cable 1000 Sq.mm from 400/220 KV Maheshwaram SS to 220KV Amazon SS (b) 2 No.s 220KV bays at 400/220KV SS Maheshwaram (c) 2 No.s 220KV Bays at Amazon |  | - | - | - | 72.76 | - | Consumer contribution | - | - | 23.11.2021(bays at maheshwaram end) 06.01.2022 (Line) 14.10.2021(Bays at Amazon end) |  | 18.08.2023 18.08.2023 16.09.2023 |  |  |  | - | -
|  |  | a)2 No.s 220KV bays proposed at 220/132/33 KV SS Chandanvally (TSIIC) and (b)220KV single moose DC line from proposed 220/132/33 KV Chandanvally (TSIIC) SS to proposed 220KV M/s.Amazon (Chandanvally) SS on 220KV narrow based towers (c)2 No.s 220KV bays at 220 KV M/s.Amazon(Chandanvally) |  | - | - | - | 34.58 | - | Consumer contribution | - | - | 01.08.2022 |  | Work under progress |  |  |  | - | -
22 | D-21-30 | Industrial park at Chandanavally(V), Sha | (i) 220/132/33 KV at Chandanavally (ii) 220Kv TMDC line from 400/220KV Kethireddypally SS to proposed 220KV Chandanavally (TSIIC) for a length of 12.663 KM (4.663 KM) on 400KV Quad moose MC towers + 8.0 KM on 220KV TMDC towers instead of 220KV SMDC line on normal 220KV DC towers (iii) 2 no.s 220KV feeder bays at 400/220KV Kethireddypally SS for proposed 220KV Chandanavally SS, Shabad Mandal in Ranga Reddy District. | DCW | - | - | - | 108.33 | - | Consumer contribution | - | - | SS-14.10.2021 Line-25.10.2021 Bays-23.11.2021 | 31.03.2026 | SS-16.01.2023 Line-13.01.2023 Bays-10.01.2023 | 1.91 | 4.41 | 6.32 | - | -
23 | D-21-33 | Shiftng of 220KV Shapurnagar-Jangaon SC | - | DCW | - | - | - | - | - | Consumer contribution | - | - | Supervision work |  | 14.06.2022 | 1.29 | - | 1.29 | - | -
24 | D-21-37 | shiftng lne of Regumanugadda-Wanapthy(An | Shifting of 1 No.220KV DC line of Regumanugadda-Wanaparthy & Singotam of length 2KM with ACSR Moose conductor in Kollapur Mandal (Total Length : 5km) due to submerging in Anjangiri proposed package -3 canal in Nagarkurnool District. | DCW | - | - | - | 9.56 | - | Consumer contribution | - | - | 21.09.2022 | 31.03.2026 | 19.08.2022 & 26.08.2022 | 0.01 | -0.01 | 0 | - | -
25 | D-21-38 | Jadcherla 2 boothpur SC line in Mbnr Dis | Shifting of existing 132 KV SC line (9KM) with INVAR HTLS conductor between loc.no.494 and loc.no.521 of 132/33 KV Jadcherla SS to 220/132 KV Boothpur SC line in Mahabubnagar Dist. | DCW | - | - | - | 11.7 | - | Consumer contribution | - | - | 22.12.2021 | 31.03.2026 | 02.07.2023 | 0.73 | -0.58 | 0.15 | - | -
26 | D-21-47 | 220kv SS at Kakatiya Mega Textile park | Extension of power supply to M/s. Kakatiya Mega Textile Park- Erection of (i) 220/132/33 KV SS (2 X 160+ 2 x 50 MVA) including 2 Nos 220KV incoming feeders and 8 Nos 33KV feeder bays at Kakatiya Mega Textile park, Shyampet(V), Geesukonda (M),(ii) 220KV DC line (29KM) from existing 220KV SS Pulukurthy to proposed 220/132/33 KV SS at Kakatiya Mega Textile Park and (iii) 2 No.s 220KV bay extensions at 220KV SS Pulukurthy in Warangal District. | DCW | - | - | - | 189.2 | - | Consumer contribution | - | - | 28.10.2022 | 31.03.2026 | Work under progress | 46.69 | 10.9 | 57.59 | - | -
27 | D-21-48 | M/s.Kitex Garments Limited | Extension of power supply to M/s. Kitex Garments Limited- Erection of (i) 132 KV DC line (3.2 KM) from proposed 220/132/33 KV SS at Kakatiya Mega Textile Park(KMTP) to M/s.Kitex Garments Limited proposed to establish at KMTP(ii) 2 No.s 132 KV bays at proposed 220/132/33 KV KMTP (iii) 2 No.s 132 KV metering bay extensions at M/s.Kitex Garments Limited in Warangal District. | DCW | - | - | - | 19.99 | - | Consumer contribution | - | - | 17.11.2022 | 31.03.2026 | 09.01.2024 | 7.8 | 3.9 | 11.7 | - | -
28 | D-21-50 | Diversion of 132 KV Yacharam-Ibrahimpatn | Diversion of 132 KV Yacharam-Ibrahimpatnam-Bongulur SC line from Loc.No.367 to 372 and LILO Loc No.s 370/1 to 370/3 of Ibrahimpatnam DC line passing through M/s.BEL’s land located at Sy.No.s 254 to 256 of Ibrahimpatnam Khalan Village, Ibrahimpatnam Mandal, Ranga Reddy District | DCW | - | - | - | 8.88 | - | Consumer contribution | - | - | 25.11.2022 | 31.03.2026 | 11.05.2023 | - | 0.04 | 0.04 | - | -
29 | D-22-01 | 132/33 KV SS Chandrugonda-Railway Tracti | Extending power supply at 132KV level to the proposed 132/25KV Railway Traction Sub-station at 132/33 KV SS Chandrugonda in Khammam District. | DCW | - | - | - | 20.7 | - | Consumer contribution | - | - | 10.10.2023 | 31.03.2026 | 10.06.2024 | 5.18 | 1.63 | 6.81 | - | -
30 | D-22-05 | 220KV Mamidipally-Shivarampally-Mamidipl | Diversion of existing 220KV Mamidipally-Shivarampally & 220KV Mamidipally-HIAL to Shivarampally DC line for clearance on Hyderabad-Bengaluru NH-44 near Aramghar- Shamshabad section (ii) Diversion of 132 KV Chandrayangutta-Jubilee Hills DC line for clearance on Hyderabad-Bengaluru NH44 near Aramghar-Shamshabad section. | DCW | - | - | - | 52.82 | - | Consumer contribution | - | - | Supervision work |  | 26.11.2022 | 0.14 | - | 0.14 | - | -
31 | D-22-06 | Shiftng of Shivarampally-Gachibowli -Gir | Shifting of existing 220KV Shivarampally-Gachibowli DC line between Loc.No.66 to Loc.No.68 & 132 KV Chandrayanagutta-Jubilee Hills DC line bbetween Loc.No.86 to Loc.No.89 for M/s.Giridhari | DCW | - | - | - | 1.22 | - | Consumer contribution | - | - | Supervision work |  | 31.12.2022 | 0.01 | - | 0.01 | - | -
32 | D-22-14 | 132 KV DC lne 4m 132/33 KV Makthal SS 2 | (i) 132 KV DC line (10.00 KM) from existing 132/33 KV Makthal SS to proposed 132/25KV Makthal Railway Traction substation (CMD of 10MVA) ii) 2 No.s 132 KV bays extension at 132/33 KV SS Makthal and (iii) 2 No.s 132 KV bays along with Metering arrangement at proposed 132/25KV Makthal Railway Traction Substation in Mahabubnagar District | DCW | - | - | - | 66.14 | - | Consumer contribution | - | - | 07.08.2023 | 31.03.2026 | 04.02.2025 | 12.95 | 5.84 | 18.79 | - | -
33 | D-22-18 | Erection of (i) 1 No.132 KV bay at 220/1 | Extension of 132 KV supply for a CMD of 22.5MVA in a phased manner to M/s.Ester Film Tech Limited, Chandanvally, Shabad,Mandal, Rangareddy District | DCW | - | - | - | 2.49 | - | Consumer contribution | - | - | Supervision work |  | 18.01.2023 | - | 0.21 | 0.21 | - | -
34 | D-22-21 | shifting of132 KV Chandrayanagutta-Shiva | Shifting of 132KV Chandrayanagutta – Shivarampally line passing through National Police Academy (NPA) for construction of 6 lane grade separator (flyover) from Aramghar to Zoo park for M/s. GHMC (Turnkey) | DCW | - | - | - | 29.58 | - | Consumer contribution | - | - | This scheme ID is not operated, as the applicant chosen supervision after wards (vide scheme ID D-23-22) instead of Turnkey. |  | - | - | 0 | 0 | - | -
35 | D-23-02 | raising height siddipet-Durshed-mallaram | Raising of the height of the conductor between (i) Loc.No.154 & Loc.No.155 of 220KV Siddipet to Durshed & 220KV Siddipet-Mallaram lines (ii) Loc.no.35 & 36 of 132 KV Siddipet to Shanigaram & 132 KV Ellanthakunta to Chandulapur lines | DCW | - | - | - | - | - | Consumer contribution | - | - | 04.07.2024 | 31.03.2026 | 24.04.2025 | - | 3.39 | 3.39 | - | -
36 | D-23-08 | M/s.Microsoft Corporation (India)-Chanda | Extension of HT supply for a CMD of 163MVA in phased manner with an initial load of 17MVA to M/s. Microsoft corporation (india) Pvt Ltd, Plot.No.10, Nagarguda, Shamshabad Road, Hayathabad, Chandanvally(V), Shabad (M), R.R Dist., | DCW | - | - | - | 10.9 | - | Consumer contribution | - | - | Supervision work |  | 26.09.2024 | 0.69 | -0.25 | 0.44 | - | -
37 | D-23-09 | Extn.of sply 2 M/s.Microsoft, Mekaguda | Extension of HT supply for a CMD of 160MVA in phased manner to M/s. Microsoft Corporation India Limited at Sy No 859,862,880 & 892, Mekaguda Road, Near NATCO Pharma, RangaReddy District under DC works. | DCW | - | - | - | 26.85 | - | Consumer contribution | - | - | Supervision work |  | 16.12.2024 | - | -3.35 |  | - | -
38 | D-23-10 | Extn.of sply 2 M/s.DL Development Hyd Lt | Extension of HT supply for a CMD of 160MVA in phased manner to M/s. DC Development Hyderabad Limited (100% subsidiary to M/s. Adani group) at Sy No 490-405, 509-511, 529 & 530, Parigi Road, Elikatta, Shadnagar, RangaReddy District under DC works | DCW | - | - | - | 30.29 | - | Consumer contribution | - | - | Supervision work |  | 29.02.2024 | 1.15 | -0.95 |  | - | -
39 | D-23-19 | Shifting of 132/33 KV Kodad SS for road | Shifting of existing 132/33KV Kodad Substation for road widening of Kodad-Khammam section of NH-365 in Suryapet District Kodada | DCW | - | - | - | 0.62 | - | Consumer contribution | - | - | Supervision work |  | 28.03.2024 | - | 0.17 |  | - | -
40 | D-23-22 | Shiftng of 132 KV Chandrayangutta-Shivar | Shifting of 132KV Chandrayanagutta – Shivarampally line passing through National Police Academy (NPA) for construction of 6 lane grade separator (flyover) from Aramghar to Zoo park for M/s. GHMC | DCW | - | - | - | 10.9 | - | Consumer contribution | - | - | Supervision work |  | 26.09.2024 | - | -0.01 |  | - | -
| D-23-23 | Shiftng of 132 KV Shapurnagar-Medchal DC | Shifting of 132 KV Shapurnagar-Medchal DC line between Loc.Nos.32 to 35 passing through the land of J.Santhi and Chirumamilla Deepthi at sy.Nos.19 & others at Gundla Pochampally Village and Sy.nos.202 & others at Kandlakoya Village, Medchal Mandal in Ranga Reddy District | DCW | - | - | - | 2.27 | - | Consumer contribution | - | - | Supervision work |  | 09.07.2025 | - | 1.69 |  | - | -
41 | D-23-98 | Shifting of EHT lines under DC works-220 | - | DCW | - | - | - | - | - | Consumer contribution | - | - | Supervision work |  | - | - | 0.01 | 0.01 | - | -
42 | D-24-02 | 220KV KTPS-Shapurnagar line Dvrsn & Bhon | Diversion of existing 220KV KTPS – Shapurnagar DC/SC Line reach from Loc.No 537 to Loc.No 560 b) Diversion of existing 132KV Bhongiri – Kolanpaka – Shapurnagar DC Line reach from Loc.No 12 to Loc.No 26 which falls in FTL (Full Tank Level) area of proposed Canal and Reservoir for Earth work excavation and formation of Baswapur Reservoir under Kaleshwaram Lift Irrigation Scheme in Yadadri – Bhongir District | DCW | - | - | - | 3.9 | - | Consumer contribution | - | - | supervision work |  | i)220 kV KTPS-Shapurnagar charged on -31.07.2020, ii)132 Bhongir-shapurnagar charged on -10.03.21 & iii) 132 kV Bhongir-Kolanpaka charged on -23.06.23 | - | -0.5 |  | - | -
43 | D-24-03 | Extn.of HT sply -load 80MW to M/s.VITP | Extension of HT supply for a load of 80 MW at 220KV Voltage level to M/s.VITP Pvt. Ltd. at Plot No.17, Survey No. 64/2, Software Units Layout, Madhapur | DCW | - | - | - | Scheme charges of Rs.37.54 Crores were communicated to M/s.VITP (Supervision by TGTRANSCO). Payment of Rs.27.46 Crores was received on 26.05.2023, duly excluding the land charges for Gachibowli SS and its GST amount. Further, Rs.13.92 Crores were communicated towards execution of 220 KV GIS Bay at Raidurg by TGTRANSCO instead of Supervision. Payment of Rs. 13.92 Crores was received on 31.05.2024, for which tenders to be called. | - | Consumer contribution | - | - | Supervision work |  | 31.12.2025 | - | 1.99 |  | - | -
44 | D-24-05 | Diversion of existing 220KV Gachibowli-S | Diversion of Existing 220 KV DC Gachibowli - Shankarpally Circuit - I & II HTLS OH line between Location Nos.70 to 72 at M/s. Ventura Estate Developers, Kollur Village, Sanga Reddy District | DCW | - | - | - | 0.58 | - | Consumer contribution | - | - | Supervision work |  | 28.08.2024 | - | 0.02 |  | - | -
45 | L-12-02 | 2Nos 132kV Bays at Jaipur for SCCL | i) 220 KV LILO (10.80 KM) line from existing 2nd circuit of 220KV RSS-Nagaram DC line to M/s Ramgundam Fertilizers & Chemicals Ltd. (RFCL), Ramgundam ii) 2 Nos. 220 KV Bays along with Metering Arrangements at RFCL, Ramgundam on Turnkey Basis in Peddapally District | DCW | - | - | - | 17.34 | - | Consumer contribution | - | - | 06.12.2017 | 31.03.2026 | 10.04.2019 | 0.06 | 0.67 |  | - | -
|  | Total | [13 empty] | 745.06 | 164.65 | 908.77
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please
1 | D-13-02 | SWICHYARDSTATIONNTPC SOLAR EVACUATION | i) 132 KV switching station for evacuation of power from Solar Power plant at NTPC Ramagundam (ii) 132 KV LILO line from 132 KV RTS-B-Kalwasrirampur line (0.7KM) to proposed 132 KV switching station at NTPC | DCW |  |  |  | 10.17 |  | Consumer contribution |  |  | 13.05.2015 | 31.03.2025 | 05.05.2016 | 0 | 0 | 0
2 | D-17-06 | 220 KV LILO (10.80 KM) line from existin | 220 KV LILO (10.80 KM) line from existing 2nd circuit of 220KV RSS-Nagaram DC line to M/s Ramgundam Fertilizers & Chemicals Ltd. (RFCL), Ramgundam ii) 2 Nos. 220 KV Bays along with Metering Arrangements at RFCL, Ramgundam on Turnkey Basis in Peddapally District | DCW |  |  |  | 2.11 |  | Consumer contribution |  |  | 03.11.2016 | 31.03.2025 | 14.06.2018 | 0 | 0.01 | 0.01
3 | D-17-09 | 220KV Sdipet 2 Drshd DC lne (kaleshwrm) | i)Diversion of existing 220KV Siddipet to Durshed DC line from Loc.No.159 to Loc.No.172 ii) Diversion of existing 132 KV Siddipet to Ellanthakunta DC line from Loc.No.14 to Loc.No.18, falling under submergence area of Ranganayaka Sagar reservoir under proposed Kaleshwaram Lift Irrigation Scheme | DCW |  |  |  | 10.69 |  | Consumer contribution |  |  | 13.08.2017 | 31.03.2024 | 09.08.2018 | 0 | - | 0
4 | D-17-11 | 132 KV lne 4m Miryalaguda to RTSS and cn | i) 132 KV DC/SC line from 220/132/33 KV Miryalaguda SS to 132/33 KV RTSS Miryalaguda and connected bays in Nalgonda District & for supply, erection, testing & commissioning of 132KV DC/SC line from 132/33 KV Ramannapet SS to Ramannapet RTSS (2.2 KM) and connected bays in Yadadri-Bhongiri District. | DCW |  |  |  | 15.41 |  | Consumer contribution |  |  | 02.06.2018 | 31.03.2025 | 27.09.2019 | 0.14 | 0 | 0.14
5 | D-17-12 | Shifting of 220KV kline from veltoor-Thi | Shifting of 220KV kline from veltoor-Thi (1) Shifting of 220KV kline from veltoor-Thimmajipet 2) 220 KV Shifting of Boothpur-Kalwakurthy) | DCW |  |  |  | 11.61 |  | Consumer contribution |  |  | 23.05.2018 | 31.03.2024 | 29.01.2019 06.11.2018 | 0.49 | 0 | 0.49
12 | D-18-17 | 132KV UG at Parigi b/n Transco & Wind po | Erection of metering bay at 132 KV Parigi SS | DCW |  |  |  | 0.41 |  | Consumer contribution |  |  | Supervision work |  | 24.03.2016 | 0.05 | 0 | 0.05
19 | D-19-09 | 220KV Monopole from 220 KV Ghanpur-CPRI | 220KV Monopole DC/SC line from 220KV SS Ghanapur to M/s.CPRI | DCW |  |  |  | 55.16 |  | Consumer contribution |  |  | 31.05.2023 | 31.03.2025 | - | 0.38 | 0 | 0.38
24 | D-20-10 | Extn.of cntrl room bal wrks at 220 KV S | 50MW Solar Power Projects of M/s. Suraj Kiran Renewable Resources Pvt Ltd (SPV of M/s. Sky Power Southeast Asia III Investments Limited) near Mansing Tanda with interconnecting substation at 220/132 KV SS KM Pally in Nalgonda District- Extension of control room and other balance works at 220/132 KV SS KM Pally in Nalgonda District. | DCW |  |  |  | 4.18 |  | Consumer contribution |  |  | Pertains to civil wing |  |  | 0 | 0.14 | 0.14
25 | D-21-18 | Shiftng 220KV Miryalaguda-KTPS SC lne at | Shifting of 220KV Miryalaguda-KTPS SC line at Loc.No.537-538 at Railway Track crossing at Kukkadam Village under DC works on turnkey basis in Nalgonda District | DCW |  |  |  | 1.6 |  | Consumer contribution |  |  | Payment not yet received |  |  | 0 | 0.02 | 0.02
|  |  | a) 220KV MC/DC line from 220/132 KV Fabcity SS to the proposed site of M/s.Amazon Data Services India Pvt Ltd.at TSIIC industrial park Fabcity(2.5Kms) b) 2 no.s 220KV feeder bays at 220/132KV Fabcity SS c) 2 No.s 220KV bays at Amazon SS |  |  |  |  | 40.49 |  |  |  |  | 14.10.2021(bays at Fabcity end) 11.10.2021(line) 14.10.2021(Bays at Amazon end) |  | 28.06.2023 28.06.2023 13.07.2023
38 | D-22-06 | Shiftng of Shivarampally-Gachibowli -Gir | Shifting of existing 220KV Shivarampally-Gachibowli DC line between Loc.No.66 to Loc.No.68 & 132 KV Chandrayanagutta-Jubilee Hills DC line bbetween Loc.No.86 to Loc.No.89 for M/s.Giridhari | DCW |  |  |  | 1.22 |  | Consumer contribution |  |  | Supervision work | 31.03.2025 | 25.12.2022(220KV line) & 31.12.2022 (132KV line) | 0 | 0.01 | 0.01
30 | D-21-33 | Shiftng of 220KV Shapurnagar-Jangaon SC | - | DCW |  |  |  | - |  | Consumer contribution |  |  | Supervision work |  | 14.06.2022 | 1.38 | 0 | 1.38
37 | D-22-05 | 220KV Mamidipally-Shivarampally-Mamidipl | Diversion of existing 220KV Mamidipally-Shivarampally & 220KV Mamidipally-HIAL to Shivarampally DC line for clearance on Hyderabad-Bengaluru NH-44 near Aramghar- Shamshabad section (ii) Diversion of 132 KV Chandrayangutta-Jubilee Hills DC line for clearance on Hyderabad-Bengaluru NH44 near Aramghar-Shamshabad section. | DCW |  |  |  | 52.82 |  | Consumer contribution |  |  |  |  | 28.04.2018 | 0 | -0.01 | -0.01
38 | D-22-06 | Shiftng of Shivarampally-Gachibowli -Gir | Shifting of existing 220KV Shivarampally-Gachibowli DC line between Loc.No.66 to Loc.No.68 & 132 KV Chandrayanagutta-Jubilee Hills DC line bbetween Loc.No.86 to Loc.No.89 for M/s.Giridhari | DCW |  |  |  | 1.22 |  | Consumer contribution |  |  | Supervision work | 31.03.2025 | 25.12.2022(220KV line) & 31.12.2022 (132KV line) | 0 | 0.01 | 0.01
41 | L-12-02 | 2Nos 132kV Bays at Jaipur for SCCL | i) 220 KV LILO (10.80 KM) line from existing 2nd circuit of 220KV RSS-Nagaram DC line to M/s Ramgundam Fertilizers & Chemicals Ltd. (RFCL), Ramgundam ii) 2 Nos. 220 KV Bays along with Metering Arrangements at RFCL, Ramgundam on Turnkey Basis in Peddapally District | DCW |  |  |  | 17.34 |  | Consumer contribution |  |  | 06.12.2017 | 31.03.2025 | 10.04.2019 | 0.01 | 0.88 | 0.89

## Non-Plan works
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2026-27 for Transmission Business filed with TGERC
Scheme-wise details of Capital Expenditure incurred in FY: 2024-25 of 4th control period
(figures in Crores)
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme) | Project Purpose (SI/SE/SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total approved Cost (in Cr) | Source of funds |  |  |  | Project Start Date (DD-MM-YY) | Project Completion Date (DD-MM-YY) | DOC | Opening CWIP as on 31.03.2024 | Actual Expenditure from 01.04.2024 to 31.03.2025 | Cumulative expenditure upto 31.03.2024 | % Capatalisation | Remarks / Balance works , if any.
[9 empty] | TGTransco Funds | Loan source | Loan Amount | Grants, if any
|  | Brought Forward | [13 empty] | 745.06 | 164.65 | 908.77
1
1 | N-18-01 | Other Non Planned Project Str 2018-19 | - | - | - | - | - | - | - | - | - | - | - | - | - | 0.01 | -0.02 | -0.01 | - | -
3 | N-20-01 | Non Planned Capital works for FY 2020-21 | - | - | - | - | - | - | - | - | - | - | - | - | - | 0.12 | 0.17 | 0.29 | - | -
4 | N-21-01 | Non Planned Capital works for FY 2021-22 | - | - | - | - | - | - | - | - | - | - | - | - | - | 0.79 | 0.01 | 0.8 | - | -
5 | N-22-01 | Non Planned Capital works for FY 2022-23 | - | - | - | - | - | - | - | - | - | - | - | - | - | 2.43 | 4.3 | 6.73 | - | -
6 | N-23-01 | Non Planned Capital works for FY 2023-24 | - | - | - | - | - | - | - | - | - | - | - | - | - | 1.57 | 2.33 | 3.9 | - | -
7 | N-24-01 | Non Plan Capital works Exe by Const wing | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 1.92 | 1.92 | - | -
|  | Total | [13 empty] | 749.98 | 173.36 | 922.4
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please