## ARR 25-26
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2026-27 for Transmssion Buisiness filed with TGERC
Scheme wise details of Capital Expenditure proposed for Financial Year 2026-27
Sl.No. | Project Code/Scheme ID(SAP code) | Project Title(SAP Project Title) | Scope of the Work (names of all the substations and Lines included in the scheme given) | Justification | Project Purpose(SI/SE/SR/GE) | Administrative Approval T.O.O Ref | SRPC Approval (if any) | TGERC Investment Approval Ref. | Total TGERC Approved Cost | Source of Funds |  |  |  | Project Start Date (DD-MM-YY) | Project Completion date (DD-MM-YY) | Opening CWIP as on 31.03.2025 | FY 2025-26 |  |  | Projected Expenditure for FY 2026-27 | Spill Over Yearly Caital Expenditure Projected for works taken up in or before 2025-26 (in Cr) |  |  | Total Cumulative Expenditure (in Cr) | Present Status of Work | Whether Approved in Resource Plan
[10 empty] | TGTransco Funds | Loan Source | Loan Amount | Grants if any |  |  |  | 1 st Half (Apr-Sept) Actuals | 2nd Half (Oct-Mar) Projected | Total FY 25-26 Projected |  | 2027-28 | 2028-29 | 2029-30
1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 (17+18) | 20 | 21 | 22 | 23 | 24 | 25 | 26
I. ONGOING SCHEMES AS ON 01.04.2026
1 | D-15-03 L-15-02 L-15-03 L-15-04 L-16-02 L-16-03 L-16-05 | Kaleshwaram Lift Irrigation Project (*) i ) 400KV SUPPLY TO MYADARAM/RAMADUGU/TIPPA ii) 400KV SUPPLY TO TIPPAPUR iii) 400KV SUPPLY TO MYADARAM iv) 400KV SUPPLY TO RAMADUGU MANDAL v)ERECTION OF CHANDULAPUR LISS (KLIS) vi)ERECTION OF TUKKAPUR LISS (KLIS) | i) 400/11 KV Medaram GIS and 400KV QMDC Line from 400KV RAMADUGU SS to the proposed 400KV Medaram SS-42 CKM. ii) 400/13.8/11 kV Ramadugu SS and 400kV QMDC Line for making LILO of both the circuits of 400kV SCCL-Gajwel QMDC line to Ramadugu SS in Karimnagar District (2x18KM) -72 CKM iii) 400/220/11 kV Sundilla SS and 400kV QMDC Line for making LILO of both the circuits of 400kV SCCL – Nirmal QMDC line to proposed Sundilla SS (2x3 KM)-12CKM. iv)400/11 kV Tukkapur SS and 400 KV TMDC line from 400/11 kV Chandlapur Sub-Station to proposed 400/11 KV Tukkapur SS(24.8 KM) and 400 KV TMDC line from proposed 400/11 kV Tukkapur Sub-Station to 400/220 KV Narsapur SS(55.1 KM) v) 400/11 kV Tippapur SS and 400kV QMDC Line from Ramadugu SS to Tippapur 46 KM-92CKM. vi) 400/11 kV Chandulapur SS , 400kV LILO of both the circuits of 400 KV TMDC Gajwel- Bhoopalapally Line-108.36 CKM and 400 KV QMDC Line from Tippapur 400/11 KV SS to proposed Chandulapur 400/13.8/11 KV SS -38.226 CKM. vii)220/11 kV Medigadda SS and 220kV TMDC Line from Sundilla 400/220/11 KV to Medigadda KV SS - 148.76 CKM. viii) 220/11 kV Annaram SS and 220kV TMDC Line from 400/220/11kV Sundilla Pump House SS (Yellampally SS) to proposed 220/11kV SS at Annaram Pump House -58 CKM ix) 132/11 kV Malakpet SS and 132KV DC Line from 220/33 KV Sircilla Substation (Sripada Yellampally SS) to proposed 132/11kV SS at Malakpet -22.7CKM | Works completed. Expenditure was carried over from 4th control period due to delay in disbursement of funds from I&CAD.The Projected Expeniture shall hold good only if the payments are received from I&CAD Department. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(CE-LIS) Ms.No.848, dt:18.09.2020 (BL Works) T.O.O.(CE-LIS) Ms.No.849, dt: 18.09.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 3086.446 | Govt. of TS Grants I&CAD | Aug'16 | Mar'26 | -0.38708 | 0.0039786 | 7 | 7.004 | 0 | 0 | 0 | 0 | 6.6169 | Works completed delay in disbursement of funds from I&CAD | Expenditure was carried over from 4th control period
2 | L-20-01 D-20-08 | KLIS ADDITIONAL 1 TMC-BL KLIS ADDITIONAL 1TMC - DC Works | 1.400/11 kV Velgatoor Sub-station and 400kV QMDC Line from 400kV Kachapur Switching station to 400/11kV Velgatoor SS -49.4 CKM 2.400/11 kV Pegadapally (Namapur) Sub-station and (i) 400kV QMDC Line from 400kV Kachapur Switching station to 400/11kV Namapur SS -30.28 CkM (ii) 400kV QMDC Line from 400kVVelgatoor substation to 400/11kV Namapur SS -43.48 CkM 3.400KV Kachapur Switching Station, (i) LILO of 400kV STPP Jaipur - Ramadugu QMDC line to Nampur SS - 19.14 CkM (ii) 400kV QMDC Line 400kV Kachapur Switching station - 400/220/132kV Gajwel SS -14.456 CkM and (iii)LILO of 400kV QMDC Line from NTPC to 400kV Narsapur SS -7.816 CkM 4.400 /11 kV Veljipur Sub-Station and 400 KV QMDC line 400/11 KV Tippapur SS - 400/11 KV Veljipur SS -10.2 CKM 5.400/11 kV Chinagundavelli (Yellaipally) Sub-Station and 400kV QMDC Line from existing 400/13.8/11kV Chandulapur SS to Proposed 400/11kV Yellaipally SS -19.096 CKM 6.400/11 KV New Tukkapur SS and Bays 7.400/220 kV Annaram Sub-Station and 400 KV QMDC line from STPP(Jaipur) to proposed 400 KV SS at Annaram Works -40.344 CKM 8.400 kV QMDC Line from 765/400kV Nizamabad PGCIL SS to 400/13.8/11kV Chandlapur SS -187.996 CKM 9.220 kV TMDC Line from 220 kv Annram to 220 kV Medgadda -40.494 kM | Works stopped and were carried over from 4 th control period due to delay in disbursement of funds from I&CAD.Projected Expeniture shall hold good only if the payments are received from I&CAD Department. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(CE-LIS) Ms.No.848,dt:18.09.2020 (BL Works) T.O.O.(CE-LIS) Ms.No.849 ,dt:18.09.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 2946.53 | Govt. of TS Grants I&CAD | Oct'21 | Mar`29 | 968.3702 | 27.6133 | 20 | 47.6133 | 386.39 | 495 | 202 | 20 | 2119.3735 | Works stopped due to pending payments from I&CAD | Yes
3 | L-14-02 | Kaleshwaram PKGS-20,21&22(*) 220/11kV Sarangapur, 220/11kV Manichippa, 220/11kV Yacharamthanda | 1.220/11kV Sarangapur SS and 220 kV DC Line from 400/220 kV Ditchpally SS to proposed 220/11 kV Sarangapur SS-65.88 CKM 2. 220/11kV Manchippa SS and 220kV DC line from 400/220 kV Dichpally SS to 220/11 kV Manchippa SS -48.352 CKM 3.220/11kV Yacharam Thanda SS and 220 KV TMDC line 400/220kV Dichpally SS - 220/11 kV Yacharam Thanda SS -53.804 CKM | Works were carried over from 4 th control period due to delay in disbursement of funds from I&CAD. The Projected Expeniture shall hold good only if the payments are received from I&CAD Department. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-LI) Ms.No.02, dt:22-01-2014 (BL Works) T.O.O. (CE-LI) Ms.No. 03, dt:22-01-2014 (DC Works) T.O.O.(ED-LIS) Ms.No.787,dt:23.06.2020 (BL Works) T.O.O.(ED-LIS) Ms.No.788,dt:23.06.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 264.82 | Govt. of TS Grants I&CAD | Jan'19 | Mar'27 | 115.7875 | 0.57161 | 7 | 7.5716 | 15.25 | 0 | 0 | 0 | 138.6091 | Works stopped due to pending payments from I&CAD | Expenditure was carried over from 4th control period
4 | L-19-01 | Kaleshwaram Lift Irrigation Schemes(*) 220/11 kV New Manchippa SS and 220/11 kV New Mentrajpally SS | 1. 220/33KV New Manchippa and 33kV DC line from New Manchippa Substation to proposed 33/11kV Ghadkol Substation- 8 CKM 2. 220/11 kV Mentrajpally SS and 220 KV LILO Line to proposed Mentrajpally from one of the circuit of under construction 220 KV DC Line from 400/220 kV SS Dichpally to 220/11 KV Manchippa SS in Nizamabad Dist.-7.517 CKM | Works were carried over from 4 th control period due to delay in disbursement of funds from I&CAD. The Projected Expeniture shall hold good only if the payments are received from I&CAD Department. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(CE-LIS) Ms.No.415,dt:24.07.2019 (BL Works) T.O.O.(CE-LIS) Ms.No.416,dt:24.07.2019(DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 67.77 | Govt. of TS Grants I&CAD | Mar'20 | Mar`27 | 6.2134 | 0.24596 | 2.75 | 2.996 | 1.1 | 0 | 0 | 0 | 10.3093 | New Manchippa works under progress .delay in disbursement of funds from I&CAD | Expenditure was carried over from 4th control period
5 | L-18-01 | JCR Phase-III 220/11kV Devvanapeta SS(**) 220/11kV Devvanapeta SS | 220/11 kV Devannapeta SS and 220kV Twin Moose DC line from 400/220kV Jangaon Sub-Station to 220/11kV Devannapet Sub-Station -108.519 CKM | Works completed. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(ED-LIS) Ms.No.765,dt:22.05.2020 (BL Works) T.O.O.(ED-LIS) Ms.No.766,dt:22.05.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 138.66 | Govt. of TS Grants I&CAD | Dec'19 | Jun'24 | 0.14435 | -0.0055073 | 0 | -0.0055073 | 0 | 0 | 0 | 0 | 0.14435 | Works completed. | Works completed.
6 | L-15-01 | AMRP LLC Lift Irrigation Project at Puliathanda(*) | 1. 2nd Circuit stringing on 220KV Chalakurthy-Puttamgandi line(18.63 KM) and DC line from location no.9 of Chalakurthy-Puttamgandi 220KV line to the proposed 220KV SS at Puliathanda (2 KM) 2. 220kV DC/SC line from 220KV Chalakurthy-Puttamgandi line (18.63 KM) | Works completed. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | [5 empty] | Govt. of TS Grants I&CAD | 3.37 | Govt. of TS Grants I&CAD | Jan'16 | Nov`16 | 0 | 0 | 0 | 100% Capitalized | 0 | 0 | 0 | 0 | 0 | Works completed. | Works completed.
7 | L-17-04 | Kaleshwaram Lift Irrigation Scheme- Package -14(*) (Akkaram & Markook) | 1. 220/11 kV Akkaram SS and 220kV TMDC line from 400/220/132 KV Gajwel SS to 220/11kV Akkaram SS 2.220/11 kV Markook SS and 220kV DC line from 220/11kV Akkaram SS to 220/11kV Markook SS | Works completed. Supply extended to I&CAD Pump House. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-LIS) Ms.No. 369,dt.28-05-2019 (BL Works) T.O.O. (CE-LIS) Ms.No.370,dt.28-05-2019 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 197.66 | Govt. of TS Grants I&CAD | Apr'18 | Mar'26 | 1.3095 | -0.15151 | 0 | -0.15151 | 0 | 0 | 0 | 0 | 1.158 | Works Completed . | Works completed.
8 | L-18-03 | Thumilla Lift Irrigation (RDS) (*) 132/11kVThumilla | 132/11 kV Thumilla SS ,132 kV LILO line to proposed Tummilla 132/11 kV SS to be tapped from IEEJA to Alampur 132 kV DC line at the point of 15 KM from IEEJA 132/33kV SS-17.384 CKM 2)Stringing of Second circuit 132/33KV SS to Alampur 132/33kV SS under 1st circuit -41.849 CKM | Works completed. Supply extended to I&CAD Pump House. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.985,dt:26.02.2021(BL Works) T.O.O. (CE -LIS) Ms.No.986,dt:26.02.2021(DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 34.3 | Govt. of TS Grants I&CAD | Jun'18 | Mar'26 | 1.7958 | 0.64911 | 0 | 0.64911 | 0 | 0 | 0 | 0 | 2.4449 | Works Completed . | Works completed.
9 | L-17-05 | PRLIS(*) Diversion of 3Nos. 220kV lines due to submerging in the proposed Anjanagiri Project | Diversion of 3Nos. 220kV lines due to submerging in the proposed Anjanagiri Project | Works completed. Supply extended to I&CAD Pump House. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-Projects-II) Ms.No.15 Dt.09-06-2017 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 18.23 | Govt. of TS Grants I&CAD | May'18 | Mar'25 | 0.00073329 | -0.000735 | 0 | 100% Capitalized | 0 | 0 | 0 | 0 | 0.00073329 | Works Completed . | Works completed.
10 | L-05-02 | Godavari LIS (*) (a) (132/11kV Gandiramaram, 132/11kV Bommakuru, 132/11kV Rangaraopalli) | 1. 132/11 kV Gandiramaram SS and 132kV DC/SC line from existing 132/33kV Raghunathpalli SS to the proposed 132/11kV SS at Gandiramaram -16.6 CKM 2. 132/11 kV Bommakur SS and 132KV second circuit stringing from Janagoan to Narmetta- 16.6 CKM and LILO to 132/11 KV Bommakur-6 CKM 3. 132/11 kV Rangaraopally SS and 132kV LILO to the proposed 132/11kV SS Rangaraopally tapping from the existing 132kV Mulugu - chelpur line -0.754CKM | Works completed. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-Projects-I) Ms. No.19,dt:23-05-2016(BL Works) T.O.O. (CE-Projects-I) Ms. No.20,dt:23-05-2016(DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 97 | Govt. of TS Grants I&CAD | Apr'17 | Mar'25 | 1.1252 | 0 | 0 | 100% Capitalized | 0 | 0 | 0 | 0 | 1.1252 | Works completed | Works completed.
11 | L-17-03 | Lift Irrigation Scheme along Flood Flow Cancal(*) 220/11 kV Rampur SS, 220/11kV Rajeswerraopeta SS, 220/11kV Mupkal SS | 1. 220/11 kV Rampur SS, 220 KV Line from Ramadugu to Rampur -70 CKM . 2 No's Bays at Rampur and LILO of 220KV RSS - Bheemgal Feeder to 220/11 KV Rampur SS Under FFC -0.92 CKM 2. 220/11 kV Rajeshwarrao Peta SS and 220kV DC line (36KM) from proposed 220kV Rampur Substation to proposed 220/11kV Rajeshwar Rao Peta Substation-72 CKM 3. 220/11 kV Mupkal SS and 220kV LILO line from 220kV Nirmal – Renjal line to proposed 220/11kV Mupkal Substation-0.676 CKM | Major works completed.(Pump Integration works were pending). Expenditure was carried over from 4th control period due to delay in disbursement of funds from I&CAD.The Projected Expeniture shall hold good only if the payments are received from I&CAD Department. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(ED-LIS ) Ms.No.749,dt:15.04.2020(BL Works) T.O.O.(ED-LIS ) Ms.No.750,dt:15.04.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 186.9 | Govt. of TS Grants I&CAD | Feb'18 | Jun'24 | 0.11753 | 0.35191 | 0.5 | 0.85191 | 0 | 0 | 0 | 0 | 0.96944 | Works completed delay in disbursement of funds from I&CAD | Expenditure was carried over from 4th control period
12 | L-17-01 | Chanaka Korata LIS(*) 132/11kV Hatighat | 132/11 kV Hathigat SS , 132kV DC line from existing132/33kVSS at Adilabad to the proposed 132/11kVSS at Hathigat SS in Adilabad District -30 CKM and 132kV LILO Line to 220/132/33kV SS, Nirmal from 132kV Pochamapad – Adilabad feeder -6.172 CkM | Works completed. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.925, dt:15.12.2020 (BL Works) T.O.O. (CE -LIS) Ms.No.926, dt:15.12.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 43.49 | Govt. of TS Grants I&CAD | Apr'17 | Mar`25 | 0.04221 | 0 | 0 | 100% Capitalized | 0 | 0 | 0 | 0 | 0.04221 | Works Completed . | Works completed.
13 | D-11-05 L-11-01 | Thotapally Reservoir to Gouravelly Reservoir LIS (220/132kV Huzurabad SS and CL)(*) | 1. 132/11 kV Regonda SS and 132kV DC line from 220/132kV Huzurabad Sub-Station to proposed 132/11kV Sub-Station at Regonda (Gouravelly) -63 CKM 2. 220/132 kV Huzurabad SS and 220kV LILO line to Huzurabad from 220 kV Durshed - Oglapur line-20.54 CKM | Works completed. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(CE-LI) Ms.No.384,dt:19.01.2012 T.O.O.(CE-LI) Ms.No.149, dt:11.07.2011 |  |  |  |  | Govt. of TS Grants I&CAD | 69.7031 | Govt. of TS Grants I&CAD | Feb'15 | Mar`25 | 0.0049777 | 0 | 0 | 100% Capitalized | 0 | 0 | 0 | 0 | 0.0049777 | Works Completed . | Works completed.
14 | L-18-02 | PH-III PACKAGE -II JCRDGLIS-220/11 BHEEMG | Augmentation at 220/11kV Bheemghapur SS | Works completed | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (ED -LIS) Ms.No. 10,dt:17.04.2018 (BL&DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 23.55 | Govt. of TS Grants I&CAD | Jun'18 | Mar'25 | 0.051649 | 0 | 0 | 100% Capitalized | 0 | 0 | 0 | 0 | 0.051649 | Works completed | Works completed.
15 | L-16-04 | Dr. BRAPCSS LIS (Kanakapur) 132/11kV Kanakapur | 132/11 kV Kanakapur SS and 132kV DC/SC line from existing 132/11kV Kosli Substation to the proposed 132/11kV Kanakapur LIS Substation -20 CKM | Works completed. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-Projects-I) Ms.No.04,dt:26 -02-2016 (BL Works) T.O.O. (CE-Projects-I) Ms.No.05,dt.26 -02-2016 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 31.74 | Govt. of TS Grants I&CAD | Dec'16 | Nov`18 | 0.014333 | 0 | 0 | 100% Capitalized | 0 | 0 | 0 | 0 | 0.014333 | Works Completed | Works completed.
16 | L-19-02 | Phase – III Godavari Lift Irrigation Sch | Suply Erect 132/33-11 kV RS Ghanpur SS and 132kV LILOLine - RS Ghnpr tap Drsgr-Rgnty | Works completed. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(ED-LIS ) Ms.No.749, dt:15.04.2020(BL Works) T.O.O.(ED-LIS ) Ms.No.750,dt:15.04.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 0 | Govt. of TS Grants I&CAD | Mar'20 | Sep'25 | 0.017278 | 0.0099831 | 0 | 0.0099831 | 0 | 0 | 0 | 0 | 0.027261 | Works Completed | Works completed.
Sub-Total (I) |  |  |  |  | Loan Amount 12: 7210.1691; Grants if any 16: 1094.6075; 1 st Half (Apr-Sept) Actuals 17: 29.2881; 2nd Half (Oct-Mar) Projected 18: 37.25 | 66.5389 | 402.74 | 495 | 202 | 20 | 2280.8919
II. New Schemes taken up during 2026-27
1 | L-21-02 D-21-25 | NELLIKAL LIS 132/11kV Nellikal SS ,Connected Lines and Bays | 132/11KV SS at Nellikal and LILO line from existing Nagarjuna sagar Receiving station to Nagarjuna sagar Left canal SS - -3CKM | These are Deposit contribution works. Already approved vide resource plan for 5th CP.The Projected Expeniture shall hold good only if the payments are received and Works will be taken up as per requirement of I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.1161 & 1162 Dt:16.08.2021 |  |  |  |  | Govt. of TS Grants I&CAD | 21.8 | Govt. of TS Grants I&CAD | Mar'26 | Mar`30 | 0 | 0 | 0 | 0 | 6 | 10.8 | 3 | 2 | 21.8 | Tenders will be called after reciept of payments from I&CAD . | Yes
2 | L-23-01 | Mukteshwara Lift Irrigation Scheme Alternate Route to Medigadda -Lines and Bays | (i) Erection of 132 kV DC line-5.2 CKM from LILO point at Loc.No.83 of 132 kV Kataram-Beersagar line to the existing 220/11 kV Medigadda SS (ii) Stringing of 2nd Corcuit on existing 132 kV DC/SC Kataram-Bersagar Lift Irrigation Substation-18.007 CKM | These are Deposit contribution works. Already approved vide resource plan for 5th CP. The Projected Expeniture shall hold good only if the payments are received and Works will be taken up as per requirement of I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.1557 Dt:21.01.2023 |  |  |  |  | Govt. of TS Grants I&CAD | 64.73 | Govt. of TS Grants I&CAD | Mar'26 | Mar`30 | 0 | 0 | 0 | 0 | 10 | 30 | 20 | 4.73 | 64.73 | Tenders will be called after reciept of payments from I&CAD . | Yes
3 | L-21-01 D-21-01 | CHITYALA & WADAPALLY LIS a)132/11kV Chityala SS,Connected Lines and Bays b)132/11kV Wadapally SS,Connected Lines and Bays | 132/11KV Chityala Sub-station and Line from Chalakurthy Switching Station to Chityala 132/11KV -52 CKM | These are Deposit contribution works. Already approved vide resource plan for 5th CP.The Projected Expeniture shall hold good only if the payments are received and Works will be taken up as per requirement of I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No. 362 & 363 Dt:13.05.2019 |  |  |  |  | Govt. of TS Grants I&CAD | 67.13 | Govt. of TS Grants I&CAD | Mar'26 | Mar`30 | 0 | 0 | 0 | 0 | 2 | 33 | 30.13 | 2 | 67.13 | Tenders will be called after reciept of payments from I&CAD . | Yes
4 | L-21-06 D-21-40 | KAMBALAPALLY LIS 132/11kV Kambalapally SS, Connected Lines and Bays | 132/11KV SS at Kambalapally and DC line from existing 220KV K.M. Pally SS -96 CKM | These are Deposit contribution works. Already approved vide resource plan for 5th CP.The Projected Expeniture shall hold good only if the payments are received and Works will be taken up as per requirement of I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.1234 & 1235 Dt:10.11.2021 |  |  |  |  | Govt. of TS Grants I&CAD | 94.42 | Govt. of TS Grants I&CAD | Mar'26 | Mar`30 | 0 | 0 | 0 | 0 | 5 | 42 | 42.42 | 5 | 94.42 | Tenders will be called after reciept of payments from I&CAD . | Yes
5 | L-21-05 D-21-39 | AMBA BHAVANI LIS 132/11kV Ambabhavani SS,Connected Lines and Bays | 132/11KV SS at Amba Bhavani and LILO line from proposed Kambalapally SS to K.M.Pally SS -2CKM | These are Deposit contribution works. Already approved vide resource plan for 5th CP.The Projected Expeniture shall hold good only if the payments are received and Works will be taken up as per requirement of I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.1234 & 1235 Dt:10.11.2021 |  |  |  |  | Govt. of TS Grants I&CAD | 17.28 | Govt. of TS Grants I&CAD | Mar'26 | Mar`30 | 0 | 0 | 0 | 0 | 2 | 8.28 | 5 | 2 | 17.28 | Tenders will be called after reciept of payments from I&CAD . | Yes
6 | L-22-02 D-22-08 | SANGAMESHWARA LIS (i) 220/132/11 kV Chelmada SS Connected Lines and Bays (ii) 132/11 kV Hotikurd SS,Connected Lines and Bays | (A) 220/11kv LI Sub-Station at Chelmeda Khurd, i) New 220kV DC line from existing 220/132kV Sadasivapet SS to now proposed 220/132/11kV SS at Chelmeda Pump House for a line length of 25 CKM and ii) Replacement of existing 220kV DC line of single Moose conductor from 400/220kV Shankarpally SS to 220/132kV Sadasivapet SS with HTLS Conductor (520mm2 ACCC) for a line length of 38.0KM. (B) 132/11 KV LI SS at Hoti Khurd and 132 kV DC Line from proposed 220/132/11 kV LI SS at Chelmeda Khurd pump house to now proposed 132/11 KV Hoti - Khurd LI SS-56CKM | These are Deposit contribution works. Already approved vide resource plan for 5th CP.The Projected Expeniture shall hold good only if the payments are received and Works will be taken up as per requirement of I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.1418 & 1419 Dt:22.06.2022 |  |  |  |  | Govt. of TS Grants I&CAD | 222.51 | Govt. of TS Grants I&CAD | Mar'26 | Mar`30 | 0 | 0 | 0 | 0 | 2 | 125 | 92.81 | 2.7 | 222.51 | Tenders will be called after reciept of payments from I&CAD . | Yes
7 | L-22-03 D-22-09 | BASAVESHWARA LIS a)132/11 kV Borancha SS b) 132/11 kV Ramrith SS, Connected Lines and Bays | (A) 220/132/11kV LI Sub-Station at Borancha, i)Erection of new 220kV SMDC line from existing 400/220kV Narsapur SS to now proposed 220/132/11kV SS at Borancha Pump House for a line length of 146 CKM ii) Erection of new 220kV SMDC line from proposed 220/132/11kV Chelmeda SS to now proposed 220/132/11kV SS at Borancha for a line length of 80 CKM (B) 132/11kV LI Sub-Station at Ramthirth and 132kV DC line ( 35 KM) to the proposed 132/11KV Ramthirth LI SS from the proposed 220/132/11kV Borancha LI SS. -70CKM | These are Deposit contribution works. Already approved vide resource plan for 5th CP.The Projected Expeniture shall hold good only if the payments are received and Works will be taken up as per requirement of I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.1423 & 1424, Dt:27.06.2022. |  |  |  |  | Govt. of TS Grants I&CAD | 361.72 | Govt. of TS Grants I&CAD | Mar'26 | Mar`30 | 0 | 0 | 0 | 0 | 2 | 198 | 158.91 | 2.81 | 361.72 | Tenders will be called after reciept of payments from I&CAD . | Yes
8 |  | MUKTYALA BRANCH CANAL LIS 132/11 kV Vellatur SS Connected Lines and Bays | 132/11KV Sub-station at Vellatur and 132KV DC Line to the proposed Muktyala Branch Canal LIS from existing 220/132KV SS Sithapuram (15KM) -30CKM | These are Deposit contribution works. Already approved vide resource plan for 5th CP.The Projected Expeniture shall hold good only if the payments are received and Works will be taken up as per requirement of I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | [5 empty] | Govt. of TS Grants I&CAD | 85.25 | Govt. of TS Grants I&CAD | Mar'26 | Mar`30 | 0 | 0 | 0 | 0 | 5 | 40 | 35.25 | 5 | 85.25 | Tenders will be called after reciept of payments from I&CAD . | Yes
9 |  | NALA SOMANADRI (GATTU) LIS 132/11 kV Rayapuram SS Connected Lines and Bays | 132/11 KV LI SS at Rayapuram , LILO line of the proposed 132 kV DC/SC line from 220/132 kV SS Jurala to 132/33 kV SS Ieeja to the proposed 132/11 KV LI SS at Rayapuram -23 CKM and Stringing of 2nd circuit on the existing DC/SC line from 220/132 kV SS Jurala to 132/33 kV SS Ieeja for a line length of 36.27 Ckm | These are Deposit contribution works. Already approved vide resource plan for 5th CP.The Projected Expeniture shall hold good only if the payments are received and Works will be taken up as per requirement of I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | [5 empty] | Govt. of TS Grants I&CAD | 95.25 | Govt. of TS Grants I&CAD | Mar'26 | Mar`30 | 0 | 0 | 0 | 0 | 5 | 35 | 50.25 | 5 | 95.25 | Tenders will be called after reciept of payments from I&CAD . | Yes
10 | L-22-04 D-22-11 | CHENNURU LIS 220/11 kV Pokkuru SS Connected Lines and Bays | 220/11kV LI Sub-Station at Pokkur and 220KV TMDC line from the existing 400/220kV Sundilla SS to 220kV Medigadda LI SS line to execution of 220kV TMDC line-6CKM | These are Deposit contribution works. Already approved vide resource plan for 5th CP.The Projected Expeniture shall hold good only if the payments are received and Works will be taken up as per requirement of I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.1446 &1447, Dt.03.08.2022. |  |  |  |  | Govt. of TS Grants I&CAD | 56.18 | Govt. of TS Grants I&CAD | Mar'26 | Mar`30 | 0 | 0 | 0 | 0 | 2 | 26 | 26.18 | 2 | 56.18 | Tenders will be called after reciept of payments from I&CAD . | Yes
11 |  | MANJEERA LIS 132/33/11 kV Waddepalli SS Connected Lines and Bays | 132/33/11 kV Substation at Waddepally and 132 kV LILO to proposed Waddepally LIS from the existing 132 kV DC Line from 220/132 kV Banswada to 132 kV SS Waddepally -2CKM (PTR :33/11 KV 2X8 MVA,33 kV line-2 KM,33 kV ptlam SS) | These are Deposit contribution works. Already approved vide resource plan for 5th CP.The Projected Expeniture shall hold good only if the payments are received and Works will be taken up as per requirement of I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | [5 empty] | Govt. of TS Grants I&CAD | 43.82 | Govt. of TS Grants I&CAD | Mar'26 | Mar`30 | 0 | 0 | 0 | 0 | 3 | 30 | 8.82 | 2 | 43.82 | Tenders will be called after reciept of payments from I&CAD . | Yes
12 |  | Kodangal LIS 220/11kv LIS substation at Vutkur 220/11kv LIS substation at Bhudpur 220/11kv LIS substation at Jayamma Cheruvu, | (1) 220/11kv LIS substation at Vutkur and 220kV TMDC line from proposed 220/11 kV Budpur substation to proposed 220/11kV Vutkoor pump house for a line length of 56 CKM. (2)220/11kv LIS substation at Bhudpur and 220kV TMDC line from existing 400/220 kV Veltoor Substation to proposed 220/11 kV Budpur pump house for a line length of -78 CKM. (3) 220/11kv LIS substation at Jayamma Cheruvu, 220kV TMDC line from proposed 220/11 kV Utkoor Substation to proposed 220/11 kV Jayamma Cheruvu pump house for a line length of 30 CKM and 220kV TMDC line from proposed 220/11 kV Jayamma cheruvu Substation to existing 220/132 KV Kosigi substation for a line length of 58 CKM | These are Deposit contribution works. Already approved vide resource plan for 5th CP.The Projected Expeniture shall hold good only if the payments are received and Works will be taken up as per requirement of I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | [5 empty] | Govt. of TS Grants I&CAD | 561.54 | Govt. of TS Grants I&CAD | Mar'26 | Mar`30 | 0 | 0 | 0 | 0 | 100 | 250 | 206.54 | 5 | 561.54 | Tenders will be called after reciept of payments from I&CAD . | Yes
Sub-Total(II) |  |  |  |  | Loan Amount 12: 1691.63; Grants if any 16: 0; 1 st Half (Apr-Sept) Actuals 17: 0; 2nd Half (Oct-Mar) Projected 18: 0 | 0 | 144 | 828.08 | 679.31 | 40.24 | 1691.63
III. Non-Plan Schemes during 2026-27 (will be taken up on payment of amounts by Third Parties)
NIL
Sub Total (III) |  |  |  |  | Loan Amount 12: 0; Grants if any 16: 0; 1 st Half (Apr-Sept) Actuals 17: 0; 2nd Half (Oct-Mar) Projected 18: 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Total (I+II+III) |  |  |  |  | Loan Amount 12: 8901.7991; Grants if any 16: 1094.6075; 1 st Half (Apr-Sept) Actuals 17: 29.2881; 2nd Half (Oct-Mar) Projected 18: 37.25 | 66.5389 | 546.74 | 1323.08 | 881.31 | 60.24 | 3972.5219
CHIEF ENGINEER
LIFT IRRIGATION SCHEMES (FAC)

## Financial Abstract
a) Table1: FINANCIAL ABSTRACT(Revised)
Sl.No. | Particulars | FY:2025-26 (1st half-Apr-Sept ) Actuals | FY:2025-26 (2nd half- Oct-Mar ) Projections | FY:2025-26 (Total) Projections | FY:2026-27 projections
1 | Total Cost Of Ongoing Schemes as on 31st March | 29.29 | 37.25 | 66.54 | 402.74
2 | Total Cost Of New Schemes taken up during the year from 1st April | 0 | 0 | 0 | 144
3 | Total Cost of Non-Plan Schemes taken up during the year from 1st April | 0 | 0 | 0 | 0
| Grand Total | 29.29 | 37.25 | 66.54 | 546.74
CHIEF ENGINEER
LIFT IRRIGATION SCHEMES (FAC)