## Actuals 2024-2025
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2026-27 for Transmssion Buisiness filed with TGERC
2.Scheme-wise details of Capital Expenditure incurred in FY: 2024-25 of 4th control period
Sl.No. | Project Details | Project Code/Scheme ID (SAP code) | Project Title(SAP Project Title) | Scope of the Work (names of all the substations and Lines included in the scheme given) | Project Purpose(SI/SE/SR/GE) | Administrative Approval T.O.O Ref | SRPC Approval (if any) | TGERC Investment Approval Ref. | Total TGERC Approved Cost | Source of Funds |  |  |  | Project Start Date (DD-MM-YY) | Project Completion date (DD-MM-YY) | Date of Commissioning | Opening CWIP as on 31.03.2024 | Actual Expenditure from 01.04.2024 to 31.03.2025 | Cumulative expenditure upto 31.03.2025 | % Capatalisation | Remarks / Balance works , if any.
| Project Code* | [8 empty] | TGTransco Funds | Loan Source | Loan Amount | Grants if any
ONGOING SCHEMES AS ON 01.04.2025
1 | Bulk Load/DC Works | D-15-03 L-15-02 L-15-03 L-15-04 L-16-02 L-16-03 L-16-05 | Kaleshwaram Lift Irrigation Project (*) (i) 400KV SUPPLY TO MYADARAM/RAMADUGU/TIPPAPUR (ii) 400KV SUPPLY TO TIPPAPUR (iii) 400KV SUPPLY TO MYADARAM (IV) 400KV SUPPLY TO RAMADUGU MANDAL (V) ERECTION OF CHANDULAPUR LISS (KLIS) (VI)ERECTION OF TUKKAPUR LISS (KLIS) | i) 400/11 KV Medaram GIS and 400KV QMDC Line from 400KV RAMADUGU SS to the proposed 400KV Medaram SS-42 CKM. ii) 400/13.8/11 kV Ramadugu SS and 400kV QMDC Line for making LILO of both the circuits of 400kV SCCL-Gajwel QMDC line to Ramadugu SS in Karimnagar District (2x18KM) -72 CKM iii) 400/220/11 kV Sundilla SS and 400kV QMDC Line for making LILO of both the circuits of 400kV SCCL – Nirmal QMDC line to proposed Sundilla SS (2x3 KM)-12CKM. iv)400/11 kV Tukkapur SS and 400 KV TMDC line from 400/11 kV Chandlapur Sub-Station to proposed 400/11 KV Tukkapur SS(24.8 KM) and 400 KV TMDC line from proposed 400/11 kV Tukkapur Sub-Station to 400/220 KV Narsapur SS(55.1 KM) v) 400/11 kV Tippapur SS and 400kV QMDC Line from Ramadugu SS to Tippapur 46 KM-92CKM. vi) 400/11 kV Chandulapur SS , 400kV LILO of both the circuits of 400 KV TMDC Gajwel- Bhoopalapally Line-108.36 CKM and 400 KV QMDC Line from Tippapur 400/11 KV SS to proposed Chandulapur 400/13.8/11 KV SS -38.226 CKM. vii)220/11 kV Medigadda SS and 220kV TMDC Line from Sundilla 400/220/11 KV to Medigadda KV SS - 148.76 CKM. viii) 220/11 kV Annaram SS and 220kV TMDC Line from 400/220/11kV Sundilla Pump House SS (Yellampally SS) to proposed 220/11kV SS at Annaram Pump House -58 CKM ix) 132/11 kV Malakpet SS and 132KV DC Line from 220/33 KV Sircilla Substation (Sripada Yellampally SS) to proposed 132/11kV SS at Malakpet -22.7CKM. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(CE-LIS) Ms.No.848, dt:18.09.2020 (BL Works) T.O.O.(CE-LIS) Ms.No.849, dt: 18.09.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 3086.446 | Govt. of TS Grants I&CAD | 2016-08-01 | Apr`23 | 29.06.2020 | -0.38708 | 0.40983 | 0.022744 | Part Capitalisation
2 | Bulk Load/DC Works | L-20-01 D-20-08 | KLIS ADDITIONAL 1 TMC-BL KLIS ADDITIONAL 1TMC - DC Works | 1. 400/11 kV Velgatoor Sub-station and 400kV QMDC Line from 400kV Kachapur Switching station to 400/11kV Velgatoor SS -49.4 CKM. 2. 400/11 kV Pegadapally (Namapur) Sub-station and (i) 400kV QMDC Line from 400kV Kachapur Switching station to 400/11kV Namapur SS -30.28 CkM (ii) 400kV QMDC Line from 400kVVelgatoor substation to 400/11kV Namapur SS -43.48 CkM. 3. 400KV Kachapur Switching Station, (i) LILO of 400kV STPP Jaipur - Ramadugu QMDC line to Nampur SS - 19.14 CkM, (ii) 400kV QMDC Line 400kV Kachapur Switching station - 400/220/132kV Gajwel SS -14.456 CkM and (iii)LILO of 400kV QMDC Line from NTPC to 400kV Narsapur SS -7.816 CkM. 4. 400 /11 kV Veljipur Sub-Station and 400 KV QMDC line 400/11 KV Tippapur SS - 400/11 KV Veljipur SS -10.2 CKM. 5. 400/11 kV Chinagundavelli (Yellaipally) Sub-Station and 400kV QMDC Line from existing 400/13.8/11kV Chandulapur SS to Proposed 400/11kV Yellaipally SS -19.096 CKM. 6. 400/11 KV New Tukkapur SS and Bays. 7. 400/220 kV Annaram Sub-Station and 400 KV QMDC line from STPP(Jaipur) to proposed 400 KV SS at Annaram Works -40.344 CKM. 8.400 kV QMDC Line from 765/400kV Nizamabad PGCIL SS to 400/13.8/11kV Chandlapur SS -187.996 CKM. 9.220 kV TMDC Line from 220 kv Annram to 220 kV Medgadda -40.494 kM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(CE-LIS) Ms.No.848,dt:18.09.2020 (BL Works) T.O.O.(CE-LIS) Ms.No.849,dt:18.09.2020(DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 2946.53 | Govt. of TS Grants I&CAD | Oct'21 | Mar`26 |  | 968.3702 | 81.1456 | 1049.5158 | Part Capitalisation
3 | Bulk Load/DC Works | L-14-02 | Kaleshwaram PKGS-20,21&22(*) 220/11kV Sarangapur, 220/11kV Manichippa, 220/11kV Yacharamthanda | 1.220/11kV Sarangapur SS and 220 kV DC Line from 400/220 kV Ditchpally SS to proposed 220/11 kV Sarangapur SS-65.88 CKM 2. 220/11kV Manchippa SS and 220kV DC line from 400/220 kV Dichpally SS to 220/11 kV Manchippa SS -48.352 CKM 3.220/11kV Yacharam Thanda SS and 220 KV TMDC line 400/220kV Dichpally SS - 220/11 kV Yacharam Thanda SS -53.804 CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-LI) Ms.No.02, dt:22-01-2014(BL Works) T.O.O. (CE-LI) Ms.No. 03, dt:22-01-2014(DC Works) T.O.O.(ED-LIS) Ms.No.787,dt:23.06.2020(BL Works) T.O.O.(ED-LIS) Ms.No.788,dt:23.06.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 264.82 | Govt. of TS Grants I&CAD | Jan'19 | Mar'25 |  | 115.7875 | 4.7372 | 120.5247 | Part Capitalisation
4 | Bulk Load/DC Works | L-19-01 | Kaleshwaram Lift Irrigation Schemes(*) 220/11 kV New Manchippa SS and 220/11 kV New Mentrajpally SS | 1. 220/33KV New Manchippa and 33kV DC line from New Manchippa Substation to proposed 33/11kV Ghadkol Substation- 8 CKM 2. 220/11 kV Mentrajpally SS and 220 KV LILO Line to proposed Mentrajpally from one of the circuit of under construction 220 KV DC Line from 400/220 kV SS Dichpally to 220/11 KV Manchippa SS in Nizamabad Dist.-7.517 CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(CE-LIS) Ms.No.415,dt:24.07.2019 (BL Works) T.O.O.(CE-LIS) Ms.No.416,dt:24.07.2019(DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 67.77 | Govt. of TS Grants I&CAD | 2020-03-20 | 2025-03-01 |  | 6.2134 | 1.9691 | 8.1825 | Part Capitalisation
5 | Bulk Load/DC Works | L-18-01 | JCR Phase-III 220/11kV Devvanapeta SS(**) 220/11kV Devvanapeta SS | 220/11 kV Devannapeta SS and 220kV Twin Moose DC line from 400/220kV Jangaon Sub-Station to 220/11kV Devannapet Sub-Station -108.519 CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(ED-LIS) Ms.No.765,dt:22.05.2020 (BL Works) T.O.O.(ED-LIS) Ms.No.766,dt:22.05.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 138.66 | Govt. of TS Grants I&CAD | Dec-19 | Jun`24 | 12.04.2023 | 0.14435 | 6.4657 | 6.6101 | Part Capitalisation
6 | Bulk Load/DC Works | L-13-02 | Kaleshwaram Lift Irrigation Scheme OLD(*) 132/11kV Beersagar(Kannepalli) LIS | 132/11 kV Kannepalli SS and 132 kV DC/SC line from Kataram to Kanepalli and 1 No. 132 kV Bay Extension at Kataram SS-18.007CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.884,dt:19.11.2020 (BL Works) T.O.O. (CE -LIS) Ms.No.885,dt:19.11.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 28.7775 | Govt. of TS Grants I&CAD | 2016-12-01 | Jun`20 | 30.06.2020 | 0 | 0.044251 | 0.044251 | Part Capitalisation
7 | Bulk Load/DC Works | L-15-01 | AMRP LLC Lift Irrigation Project at Puliathanda(*) | 1. 2nd Circuit stringing on 220KV Chalakurthy-Puttamgandi line(18.63 KM) and DC line from location no.9 of Chalakurthy-Puttamgandi 220KV line to the proposed 220KV SS at Puliathanda (2 KM) 2. 220kV DC/SC line from 220KV Chalakurthy-Puttamgandi line (18.63 KM) | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | [5 empty] | Govt. of TS Grants I&CAD | 3.37 | Govt. of TS Grants I&CAD | 2016-01-16 | Nov`16 | 09.11.2016 | 0 | 0.16018 | 0.16018 | Part Capitalisation
8 | Bulk Load/DC Works | L-17-04 | Kaleshwaram Lift Irrigation Scheme- Package -14(*)(Akkaram & Markook) | 1. 220/11 kV Akkaram SS and 220kV TMDC line from 400/220/132 KV Gajwel SS to 220/11kV Akkaram SS 2.220/11 kV Markook SS and 220kV DC line from 220/11kV Akkaram SS to 220/11kV Markook SS | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-LIS) Ms.No. 369,dt.28-05-2019 (BL Works) T.O.O. (CE-LIS) Ms.No.370,dt.28-05-2019 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 197.66 | Govt. of TS Grants I&CAD | 2018-04-01 | Apr`20 | 26.04.2020 | 1.3095 | -1.3668 | -0.057285 | Part Capitalisation
9 | Bulk Load/DC Works | L-18-03 | Thumilla Lift Irrigation (RDS) (*) 132/11kVThumilla | 132/11 kV Thumilla SS ,132 kV LILO line to proposed Tummilla 132/11 kV SS to be tapped from IEEJA to Alampur 132 kV DC line at the point of 15 KM from IEEJA 132/33kV SS-17.384 CKM 2)Stringing of Second circuit 132/33KV SS to Alampur 132/33kV SS under 1st circuit -41.849 CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.985,dt:26.02.2021(BL Works) T.O.O. (CE -LIS) Ms.No.986,dt:26.02.2021(DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 34.3 | Govt. of TS Grants I&CAD | Jun'18 | Aug`17 | 31.08.2019 | 1.7958 | 0.046482 | 1.8423 | Part Capitalisation
10 | Bulk Load/DC Works | L-17-05 | PRLIS(*) Diversion of 3Nos. 220kV lines due to submerging in the proposed Anjanagiri Project | Diversion of 3Nos. 220kV lines due to submerging in the proposed Anjanagiri Project | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-Projects-II) Ms.No.15 Dt.09-06-2017 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 18.23 | Govt. of TS Grants I&CAD | May'18 | Dec`20 | 19.12.2020 | 0.00073329 | 0 | 0.00073329 | Part Capitalisation
11 | Bulk Load/ | L-05-02 | Godavari LIS (*) (a) (132/11kV Gandiramaram, 132/11kV Bommakuru, 132/11kV Rangaraopalli) | 1. 132/11 kV Gandiramaram SS and 132kV DC/SC line from existing 132/33kV Raghunathpalli SS to the proposed 132/11kV SS at Gandiramaram -16.6 CKM 2. 132/11 kV Bommakur SS and 132KV second circuit stringing from Janagoan to Narmetta- 16.6 CKM and LILO to 132/11 KV Bommakur-6 CKM 3. 132/11 kV Rangaraopally SS and 132kV LILO to the proposed 132/11kV SS Rangaraopally tapping from the existing 132kV Mulugu - chelpur line -0.754CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-Projects-I) Ms. No.19,dt:23-05-2016(BL Works) T.O.O. (CE-Projects-I) Ms. No.20,dt:23-05-2016(DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 97 | Govt. of TS Grants I&CAD | 2017-04-01 | Oct`19 | 25.10.2019 | 1.1252 | 0.14422 | 1.2694 | Full Capitalisation
12 | Bulk Load/DC Works | L-17-03 | Lift Irrigation Scheme along Flood Flow Cancal(*) 220/11 kV Rampur SS, 220/11kV Rajeswerraopeta SS, 220/11kV Mupkal SS | 1. 220/11 kV Rampur SS, 220 KV Line from Ramadugu to Rampur -70 CKM . 2 No's Bays at Rampur and LILO of 220KV RSS - Bheemgal Feeder to 220/11 KV Rampur SS Under FFC -0.92 CKM 2. 220/11 kV Rajeshwarrao Peta SS and 220kV DC line (36KM) from proposed 220kV Rampur Substation to proposed 220/11kV Rajeshwar Rao Peta Substation-72 CKM 3. 220/11 kV Mupkal SS and 220kV LILO line from 220kV Nirmal – Renjal line to proposed 220/11kV Mupkal Substation-0.676 CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(ED-LIS ) Ms.No.749,dt:15.04.2020(BL Works) T.O.O.(ED-LIS ) Ms.No.750,dt:15.04.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 186.9 | Govt. of TS Grants I&CAD | Feb-18 | Jun`20 | 18.06.2020 | 0.11753 | 0.027885 | 0.14542 | Part Capitalisation
13 | Bulk Load/DC Works | L-17-01 | Chanaka Korata LIS(*) 132/11kV Hatighat | 132/11 kV Hathigat SS , 132kV DC line from existing132/33kVSS at Adilabad to the proposed 132/11kVSS at Hathigat SS in Adilabad District -30 CKM and 132kV LILO Line to 220/132/33kV SS, Nirmal from 132kV Pochamapad – Adilabad feeder -6.172 CkM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.925, dt:15.12.2020 (BL Works) T.O.O. (CE -LIS) Ms.No.926, dt:15.12.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 43.49 | Govt. of TS Grants I&CAD | Apr-17 | Mar`19 | 01.03.2019 | 0.04221 | 0.2894 | 0.33161 | Part Capitalisation
14 | Bulk Load/DC Works | D-11-05 L-11-01 | Thotapally Reservoir to Gouravelly Reservoir LIS (220/132kV Huzurabad SS and CL)(*) | 1. 132/11 kV Regonda SS and 132kV DC line from 220/132kV Huzurabad Sub-Station to proposed 132/11kV Sub-Station at Regonda (Gouravelly) -63 CKM 2. 220/132 kV Huzurabad SS and 220kV LILO line to Huzurabad from 220 kV Durshed - Oglapur line-20.54 CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(CE-LI) Ms.No.384,dt:19.01.2012 T.O.O.(CE-LI) Ms.No.149, dt:11.07.2011 |  |  |  |  | Govt. of TS Grants I&CAD | 69.7031 | Govt. of TS Grants I&CAD | Feb-15 | Mar'22 |  | 0.0049777 | -0.061907 | -0.056929 | Part Capitalisation
15 | Bulk Load/DC Works | L-18-02 | PH-III PACKAGE -II JCRDGLIS-220/11 BHEEMG | Augmentation at 220/11kV Bheemghapur SS | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (ED -LIS) Ms.No. 10,dt:17.04.2018 (BL&DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 23.55 | Govt. of TS Grants I&CAD | 2018-06-01 | Aug`19 | 14.08.2019 | 0.051649 |  | 0.051649 | Part Capitalisation
16 | Bulk Load/DC Works | L-14-01 | Lift Irrigation Scheme at Jogapur 132/11kV Jogapur SS | 132/11 kV Jogapur SS and 132 kV DC/SC Line from 132/33kV Mallaram SS to Proposed 132kV Jogapur SS (13 KM) | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-Trans&LI) Ms.No.16,dt:01-09-2014 (BL Works) T.O.O. (CE-Trans.&LI) Ms.No.15,dt:01-09-2014 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 45.12 | Govt. of TS Grants I&CAD | 2016-12-16 | May`18 | 30.05.2018 | 0 |  | 0 | Part Capitalisation
17 | Bulk Load/DC Works | L-16-04 | Dr. BRAPCSS LIS (Kanakapur) 132/11kV Kanakapur | 132/11 kV Kanakapur SS and 132kV DC/SC line from existing 132/11kV Kosli Substation to the proposed 132/11kV Kanakapur LIS Substation -20 CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-Projects-I) Ms.No.04,dt:26 -02-2016 (BL Works) T.O.O. (CE-Projects-I) Ms.No.05,dt.26 -02-2016 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 31.74 | Govt. of TS Grants I&CAD | 2016-12-01 | Nov`18 | 26.11.2018 | 0.014333 | -0.027952 | -0.013619 | Part Capitalisation
18 | Bulk Load/ | D-16-03 L-16-01 | Extension of 132 kV Supply to Dubbathanda BRLIS | 132 KV SUBSTATION AT DUBBATHANDA | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | [5 empty] | Govt. of TS Grants I&CAD |  | Govt. of TS Grants I&CAD |  | Dec`16 | 24.12.2016 | 0 | -0.013892 | -0.013892 | Part Capitalisation
19 | DCWoks | L-19-02 | Phase – III Godavari Lift Irrigation Sch | Suply Erect 132/33-11 kV RS Ghanpur SS and 132kV LILOLine - RS Ghnpr tap Drsgr-Rgnty | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(ED-LIS ) Ms.No.749,dt:15.04.2020(BL Works) ,T.O.O.(ED-LIS ) Ms.No.750,dt:15.04.2020 (DC Works) | [7 empty] | 2020-03-01 | 2022-03-01 | 30.03.2022 | 0.017278 | 0.93038 | 0.94766 | Full Capitalisation
Sub-Total(I) | [16 empty] | 1094.6075 | 94.8997 | 1189.5072
II.New Schemes taken up during 2023-24
NIL
Sub-Total(II)
III. Non-Plan Schemes taken up during 2023-24
NIL
Sub-Total(III)
CHIEF ENGINEER
LIFT IRRIGATION SCHEMES(FAC)