## Capitalisation 24-25
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2025-26 for Transmssion Buisiness filed with TGERC
3.Scheme-wise details of Actual Capitalisation for FY 2024-25
Sl.No. | Voltage Level | Project Code/Scheme ID (SAP code) | Project Title(SAP Project Title) | Scope of the Work (names of all the substations and Lines included in the scheme given) | Project Purpose(SI/SE/SR/GE) | Administrative Approval T.O.O Ref | SRPC Approval (if any) | TGERC Investment Approval Ref. with Date | Start Date |  | Completion Date(Charging Date) |  | Date of Capitalisation | Total TGERC Approved Cost | Source of Funds |  |  |  | Capitalisation upto previous year as per Audited Financial Statements | Capital Expenditure during the current year(2024-25) | Capitalisation claimed for the Current Year(FY 2024-2025) (Rs. Crores) | Whether Part Capitalisation (or) Full Capitalisation | Addition to Transmission Network |  |  |  | Physical Completion Certificate | Financial Completion Certificate | Reason for Time/Cost Overrun
[9 empty] | Scheduled Date | Actual | Scheduled Date | Actual |  |  | TGTransco Funds | Loan Source | Loan Amount | Grants if any |  |  |  |  | Substations | Lines (CKT KM) | Capacity (MVA) | Bays (Nos.)
1 | 400 kV ,220 kV & 132 kV | D-15-03 L-15-02 L-15-03 L-15-04 L-16-02 L-16-03 L-16-05 | Kaleshwaram Lift Irrigation Project (*) i)400KV SUPPLY TO MYADARAM/RAMADUGU/TIPPA ii) 400KV SUPPLY TO TIPPAPUR iii) 400KV SUPPLY TO MYADARAM iv) 400KV SUPPLY TO RAMADUGU MANDAL v)ERECTION OF CHANDULAPUR LISS (KLIS) vi)ERECTION OF TUKKAPUR LISS (KLIS) | i)400/11 KV Medaram GIS and 400KV QMDC Line from 400KV RAMADUGU SS to the proposed 400KV MEDARAM SS-42 CKM ii)400/13.8/11 kV Ramadugu SS and 400kV QMDC Line for making LILO of both the circuits of 400kV SCCL-Gajwel QMDC line to Ramadugu SS in Karimnagar District (2x18KM)-72 CKM iii)400/220/11 kV Sundilla SS and 400kV QMDC Line for making LILO of both the circuits of 400kV SCCL – Nirmal QMDC line to proposed Sundilla SS (2x3 KM)-12CKM iv) 400/11 KV Medaram GIS and 400KV QMDC Line from 400KV RAMADUGU SS to the proposed 400KV MEDARAM SS- 21 KM-42CKM v) 400/11 kV Tippapur SS and 400kV QMDC Line from Ramadugu SS to Tippapur 46 KM-92CKM vi)400/11 kV Chandulapur SS , 400kV LILO of both the circuits of 400 KV TMDC Gajwel- Bhoopalapally Line-108.36 CKM and 400 KV QMDC Line from Tippapur 400/11 KV SS to proposed Chandulapur 400/13.8/11 KV SS -38.226 CKM vii)220/11 kV Medigadda SS and 220kV TMDC Line from Sundilla 400/220/11 KV to Medigadda KV SS - 148.76 CKM viii)220/11 kV Annaram SS and 220kV TMDC Line from 400/220/11kV Sundilla Pump House SS (Yellampally SS) to proposed 220/11kV SS at Annaram Pump House -58 CKM viii)132/11 kV Malakpet SS and 132KV DC Line from 220/33 KV Sircilla Substation (Sripada Yellampally SS) to proposed 132/11kV SS at Malakpet -22.7CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(CE-LIS) Ms.No.848, dt:18.09.2020 (BL Works) T.O.O.(CE-LIS) Ms.No.849, dt: 18.09.2020 (DC Works) |  |  | Sep'16 | Jul'19 | Jan'20 | Apr'23 | 31.03.2019 31.03.2020 31.03.2025 |  |  | Govt. of TS Grants I&CAD | 3086.446 | Govt. of TS Grants I&CAD | 2422.03 | 0.40983 | 1.4853 | Part Capitalisation | 0 | 0 | 0 | 0 | 2020000425 2021000363 2019000619 2019000482 2020000450 2019000444 2019000469 2019000472 | 202100370 202001108 202000738 202000755 202000787 202100068 202000766 202000761 202000758
2 | 220 kV | L-14-02 | Kaleshwaram PKGS-20,21&22(*) 220/11kV Sarangapur, 220/11kV Manichippa, 220/11kV Yacharamthanda | 1.220/11kV Sarangapur SS and 220 kV DC Line from 400/220 kV Ditchpally SS to proposed 220/11 kV Sarangapur SS-65.88 CKM 2. 220/11kV Manchippa SS and 220kV DC line from 400/220 kV Dichpally SS to 220/11 kV Manchippa SS -48.352 CKM 3.220/11kV Yacharam Thanda SS and 220 KV TMDC line 400/220kV Dichpally SS - 220/11 kV Yacharam Thanda SS -53.804 CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-LI) Ms.No.02, dt:22-01-2014(BL Works) T.O.O. (CE-LI) Ms.No. 03, dt:22-01-2014(DC Works) T.O.O.(ED-LIS) Ms.No.787,dt:23.06.2020(BL Works) T.O.O.(ED-LIS) Ms.No.788,dt:23.06.2020 (DC Works) |  |  | Apr'19 | Apr'19 | May'22 |  | 31.03.2022 |  |  | Govt. of TS Grants I&CAD | 264.82 | Govt. of TS Grants I&CAD | 67.55 | 4.7372 | 0.26187 | Part Capitalisation | 0 | 0 | 0 | 0 | 2022000390 2022000323 2022000394 | 202200362 202200365 202200363
3 | 220kV | L-19-01 | Kaleshwaram Lift Irrigation Schemes(*) 220/11 kV New Manchippa SS and 220/11 kV New Mentrajpally SS | 1. 220/33KV New Manchippa and 33kV DC line from New Manchippa Substation to proposed 33/11kV Ghadkol Substation- 8 CKM 2. 220/11 kV Mentrajpally SS and 220 KV LILO Line to proposed Mentrajpally from one of the circuit of under construction 220 KV DC Line from 400/220 kV SS Dichpally to 220/11 KV Manchippa SS in Nizamabad Dist.-7.517 CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(CE-LIS) Ms.No.415,dt:24.07.2019 (BL Works) T.O.O.(CE-LIS) Ms.No.416,dt:24.07.2019(DC Works) |  |  | Mar'20 | Mar'20 | Feb'21 | Mar'25 | 31.03.2021 31.03.2023 |  |  | Govt. of TS Grants I&CAD | 67.77 | Govt. of TS Grants I&CAD | 17.42 | 1.9691 | 0.058848 | Part Capitalisation | 0 | 0 | 0 | 0 | 2023001011 2023001024 | 2023001156 2023001157
4 | 220 kV | L-18-01 | JCR Phase-III 220/11kV Devvanapeta SS(**) 220/11kV Devvanapeta SS | 220/11 kV Devannapeta SS and 220kV Twin Moose DC line from 400/220kV Jangaon Sub-Station to 220/11kV Devannapet Sub-Station -108.519 CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(ED-LIS) Ms.No.765,dt:22.05.2020 (BL Works) T.O.O.(ED-LIS) Ms.No.766,dt:22.05.2020 (DC Works) |  |  | Sep'20 | Sep'20 | Sep'21 | Jun'23 | 19.06.2023 09.11.2022 12.04.2023 |  |  | Govt. of TS Grants I&CAD | 138.66 | Govt. of TS Grants I&CAD | 111.53 | 6.4657 | 6.4997 | Full Capitalisation | 0 | 0 | 0 | 0 | 2024000080 2024000078 2024000101 | 2024000101 2024000102 2024000103
5 | 132 kV | L-13-02 | Kaleshwaram Lift Irrigation Scheme OLD(*) 132/11kV Beersagar(Kannepalli) LIS | 132/11 kV Kannepalli SS and 132 kV DC/SC line from Kataram to Kanepalli and 1 No. 132 kV Bay Extension at Kataram SS-18.007CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.884,dt:19.11.2020 (BL Works) T.O.O. (CE -LIS) Ms.No.885,dt:19.11.2020 (DC Works) |  |  | Jan'18 | Jan'18 | Jun'20 | Jun'20 | 31.03.2021 |  |  | Govt. of TS Grants I&CAD | 32.93 | Govt. of TS Grants I&CAD | 17.858 | 0.044251 | 0.044251 | Part Capitalisation | 0 | 0 | 0 | 0 | 2021000351 | 202100086
6 | 220 kV | L-15-01 | AMRP LLC Lift Irrigation Project at Puliathanda(*) | 1. 2nd Circuit stringing on 220KV Chalakurthy-Puttamgandi line(18.63 KM) and DC line from location no.9 of Chalakurthy-Puttamgandi 220KV line to the proposed 220KV SS at Puliathanda (2 KM) 2. 220kV DC/SC line from 220KV Chalakurthy-Puttamgandi line (18.63 KM) | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  |  |  | Jan'16 | Jan'16 | Apr'16 | Jan'18 | 31.03.2025 |  |  | Govt. of TS Grants I&CAD | 3.37 | Govt. of TS Grants I&CAD | 2.455 | 0.16018 | 0.16145 | Part Capitalisation | 0 | 0 | 0 | 0 | 2019000849 | 202000962
7 | 220 kV | L-17-04 | Kaleshwaram Lift Irrigation Scheme- Package -14(*) (Akkaram & Markook) | 1. 220kV TMDC line from 400/220/132 KV Gajwel SS to 220/11kV Akkaram SS 2. 220kV DC line from 220/11kV Akkaram SS to 220/11kV Markook SS | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-LIS) Ms.No. 369,dt.28-05-2019 (BL Works) T.O.O. (CE-LIS) Ms.No.370,dt.28-05-2019 (DC Works) |  |  | Aug'18 | Aug'18 | May'19 | Apr'20 | 31.03.2025 |  |  | Govt. of TS Grants I&CAD | 197.66 | Govt. of TS Grants I&CAD | 119.24 | -1.3668 | 0.07536 | Part Capitalisation | 0 | 0 | 0 | 0 | 2021000361 2021000362 2021000301 2021000360 2021000299 2021000362 | 202100371 202100331 202100368 202100332 202100367 202100371
8 | 132 kV | L-18-03 | Thumilla Lift Irrigation (RDS) (*) 132/11kVThumilla | 132/11 kV Thumilla SS ,132 kV LILO line to proposed Tummilla 132/11 kV SS to be tapped from IEEJA to Alampur 132 kV DC line at the point of 15 KM from IEEJA 132/33kV SS-17.384 CKM 2)Stringing of Second circuit 132/33KV SS to Alampur 132/33kV SS under 1st circuit -41.849 CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.985,dt:26.02.2021(BL Works) T.O.O. (CE -LIS) Ms.No.986,dt:26.02.2021(DC Works) |  |  | Jul'18 | Jul'18 | Dec'18 | Aug'19 | 31.03.2025 |  |  | Govt. of TS Grants I&CAD | 34.3 | Govt. of TS Grants I&CAD | 16.8539 | 0.046482 | 0.0005201 | Part Capitalisation | 0 | 0 | 0 | 0 | 2021000362 | 2021000371
9 | 132 kV | L-05-02 | Godavari LIS (*) (a) (132/11kV Gandiramaram, 132/11kV Bommakuru, 132/11kV Rangaraopalli) | 1. 132/11 kV Gandiramaram SS and 132kV DC/SC line from existing 132/33kV Raghunathpalli SS to the proposed 132/11kV SS at Gandiramaram -16.6 CKM 2. 132/11 kV Bommakur SS and 132KV second circuit stringing from Janagoan to Narmetta- 16.6 CKM and LILO to 132/11 KV Bommakur-6 CKM 3. 132/11 kV Rangaraopally SS and 132kV LILO to the proposed 132/11kV SS Rangaraopally tapping from the existing 132kV Mulugu - chelpur line -0.754CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-Projects-I) Ms. No.19,dt:23-05-2016(BL Works) T.O.O. (CE-Projects-I) Ms. No.20,dt:23-05-2016(DC Works) |  |  | Apr'17 | Apr'17 | Jul'21 | Oct'19 | 10.01.2018 25.10.2019 |  |  | Govt. of TS Grants I&CAD | 97 | Govt. of TS Grants I&CAD | 57.683 | 0.14422 | 0.33492 | Full Capitalisation | 0 | 0 | 0 | 0 | 2019000438 2019000440 2020000528 | 202001461 202000064 202000083
10 | 220 kV | L-17-03 | Lift Irrigation Scheme along Flood Flow Cancal(*) 220/11 kV Rampur SS, 220/11kV Rajeswerraopeta SS, 220/11kV Mupkal SS | 1. 220/11 kV Rampur SS, 220 KV Line from Ramadugu to Rampur -70 CKM . 2 No's Bays at Rampur and LILO of 220KV RSS - Bheemgal Feeder to 220/11 KV Rampur SS Under FFC -0.92 CKM 2. 220/11 kV Rajeshwarrao Peta SS and 220kV DC line (36KM) from proposed 220kV Rampur Substation to proposed 220/11kV Rajeshwar Rao Peta Substation-72 CKM 3. 220/11 kV Mupkal SS and 220kV LILO line from 220kV Nirmal – Renjal line to proposed 220/11kV Mupkal Substation-0.676 CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(ED-LIS ) Ms.No.749,dt:15.04.2020(BL Works) T.O.O.(ED-LIS ) Ms.No.750,dt:15.04.2020 (DC Works) |  |  | Feb'18 | Feb'18 | Nov'18 | Jun'20 | 31.03.2020 31.03.2021 |  |  | Govt. of TS Grants I&CAD | 186.9 | Govt. of TS Grants I&CAD | 101.73 | 0.027885 | 0.0019857 | Part Capitalisation | 0 | 0 | 0 | 0 | 2020000631 2021000044 2020000632 2020000633 2021000073 | 202000695 202100072 202000690 202000688 202100075
11 | 132 kV | L-17-01 | Chanaka Korata LIS(*) 132/11kV Hatighat | 132/11 kV Hathigat SS , 132kV DC line from existing132/33kVSS at Adilabad to the proposed 132/11kVSS at Hathigat SS in Adilabad District -30 CKM and 132kV LILO Line to 220/132/33kV SS, Nirmal from 132kV Pochamapad – Adilabad feeder -6.172 CkM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.925, dt:15.12.2020 (BL Works) T.O.O. (CE -LIS) Ms.No.926, dt:15.12.2020 (DC Works) |  |  | Mar'17 | Mar'17 | Jun'18 | May'19 | 31.03.2019 |  |  | Govt. of TS Grants I&CAD | 43.49 | Govt. of TS Grants I&CAD | 24.69 | 0.2894 | 0.44328 | Part Capitalisation | 0 | 0 | 0 | 0 | 2019000662 2019000660 2020000375 2019000661 | 202000727 202000722 202000716 202000705
12 | 220kV & 132 kV | D-11-05 L-11-01 | Thotapally Reservoir to Gouravelly Reservoir LIS (220/132kV Huzurabad SS and CL)(*) | 1. 132/11 kV Regonda SS and 132kV DC line from 220/132kV Huzurabad Sub-Station to proposed 132/11kV Sub-Station at Regonda (Gouravelly) -63 CKM 2. 220/132 kV Huzurabad SS and 220kV LILO line to Huzurabad from 220 kV Durshed - Oglapur line-20.54 CKM | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(CE-LI) Ms.No.384,dt:19.01.2012 T.O.O.(CE-LI) Ms.No.149, dt:11.07.2011 |  |  | Nov'14 | Nov'14 | Dec'16 | Mar'22 | 31.03.2017 31.03.2020 31.03.2023 |  |  | Govt. of TS Grants I&CAD | 69.7031 | Govt. of TS Grants I&CAD | 57.37 | -0.061907 | 0.0044749 | Part Capitalisation | 0 | 0 | 0 | 0 | 2023000833 2023000720 | 2023000597 202001146
16 | 132 kV | D-16-03 L-16-01 | Extension of 132 kV Supply to Dubbathanda BRLIS | 132 KV SUBSTATION AT DUBBATHANDA | Extension of power supply to Lift Irrigation project taken up by Govt. of TS |  |  |  | July'16 | July'16 | Oct'16 | Dec'16 |  |  |  | Govt. of TS Grants I&CAD |  | Govt. of TS Grants I&CAD | 7.8259 | -0.013892 | -0.013892 | Part Capitalisation | 0 | 0 | 0 | 0 | 2019000491 | 202000022
17 | 132 kV | L-19-02 | Phase – III Godavari Lift Irrigation Sch | Suply Erect 132/33-11 kV RS Ghanpur SS and 132kV LILOLine - RS Ghnpr tap Drsgr-Rgnty | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(ED-LIS ) Ms.No.749,dt:15.04.2020(BL Works) ,T.O.O.(ED-LIS ) Ms.No.750,dt:15.04.2020 (DC Works) |  |  | Mar'20 | Mar'20 | Sep'20 | Mar'22 | 25.05.2022 30.03.2022 07.02.2022 | [5 empty] | 21.382 | 0.93038 | 0.9131 | Full Capitalisation | 0 | 0 | 0 | 0 | 2022000422 2022000421 2022000423 2022000418 | 2023000316 202200367 202200383 202200382
Sub-Total(I) | [18 empty] | 3045.6178 | 13.7821 | 10.2711 |  | 0 | 0 | 0 | 0
II.New Schemes taken up during 2024-25
NIL
Sub-Total(II)
III. Non-Plan Schemes taken up during 2024-25
NIL
Sub-Total(III)
,
CHIEF ENGINEER
LIFT IRRIGATION SCHEMES