## Captlztn 24-25
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2024-25 for Transmission Business filed with TGERC
Scheme wise details of Actual Capitalisation for FY 2024-25
(Figures in Rs Crore)
[9 empty] | Work Period | [5 empty] | Source of Funds | [7 empty] | Additions to Network
Sl No. | Voltage Level | Project Code (SAP Code) / Scheme IDs | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the Scheme) | Project Purpose (SI/SE/SR/GE) | Administrative approval no. with date | SRPC approval no with date (if any) | Investment Approval No. with Date | Start Date |  | Completion Date (Charging date) |  | Date of Capitalization | Approved Cost as per Investment Approval | Transco Funds | Loan Source | Loan Amount | Grants, if any | Capitalisation Upto Previous Year (n-1) (as per Audited Financial Statements) | Capital Expenditure during the current year (2024-25) | Capitalisation claimed for the Current year (2024-25) | Whether Part Capitalization or Full Capitalisation | Sub-stations (Nos) | Lines (CKM) | PTR (MVA) | Bays (Nos) | Physical Completion Certificate Nos. | Financial Completion Certificate Nos. | Remarks / Reasons for Cost & Time overruns (if any)
[9 empty] | Schedule | Actual | Schedule | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
I. Ongoing Schemes as on 01.04.2023
1 | 132KV and Above SS | T-18-01 | Implementation of OPGW based Reliable communication upto 132kV SS and above | Providing OPGW communication at 132kV SS and above | SE | Ms.No:26, Dt:12.02.2018 |  | vide 10/18/2018-19 dt. 04.08.2018 | 2019-04-01 | 2022-07-01 | 2021-04-01 | 2025-03-01 | Not yet | 197.85Crs |  | PFC | 120 | PSDF (79.82)
Sub-total-I
II. New schemes taken up during 2023-24
Sub-total-II
III. Non-plan schemes taken up during 2023-24
Sub-total-III
Grans Total I + II + III
Chief Engineer/Telecom
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please

## CapEx 24-25
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2024-25 for Transmission Business filed with TGERC
Scheme-wise details of Capital Expenditure incurred in FY: 2024-25 of 4th control period
(figures in Crores)
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme) | Project Purpose (SI/SE/SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total approved Cost (in Cr) | Source of funds |  |  |  | Project Start Date (DD-MM-YY) | Project Completion Date (DD-MM-YY) | DOC | Opening CWIP as on 31.03.2024 | Actual Expenditure from 01.04.2024 to 31.03.2025 | Cumulative expenditure upto 31.03.2025 | % Capatalisation | Remarks / Balance works , if any.
[9 empty] | TGTransco Funds | Loan source | Loan Amount | Grants, if any
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
I. Ongoing Schemes as on 01.04.2023
1 | T-18-01 | Implementation of OPGW based Reliable communication upto 132kV SS and above | Providing OPGW communication at 132kV SS and above |  | Ms.No:26, Dt:12.02.2018 |  | vide 10/18/2018-19 dt. 04.08.2018 | 197.85 |  | PFC | 120 Crs | PSDF (79.82Crs) | 2019-04-01 | 2025-03-01 |  | 103.81 Crs | 59.28 Crs | 163.09 Crs | 81.54%
Sub-total-I | [16 empty] | 59.28 | 163.09
II. New schemes taken up during 2023-24
Sub-total-II
III. Non-plan schemes taken up during 2023-24
Sub-total-III
Grans Total I + II + III
Chief Engineer/Telecom
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please

## CapEx 23-24
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2024-25 for Transmission Business filed with TGERC
Scheme-wise details of Capital Expenditure incurred in FY: 2023-24 of 4th control period
(figures in Crores)
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme) | Project Purpose (SI/SE/SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total approved Cost (in Cr) | Source of funds |  |  |  | Project Start Date (DD-MM-YY) | Project Completion Date (DD-MM-YY) | DOC | Opening CWIP as on 31.03.2023 | Actual Expenditure from 01.04.2023 to 31.03.2024 | Cumulative expenditure upto 31.03.2024 | % Capatalisation | Remarks / Balance works , if any.
[9 empty] | TGTransco Funds | Loan source | Loan Amount | Grants, if any
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
I. Ongoing Schemes as on 01.04.2023
1 | T-18-01 | Implementation of OPGW based Reliable communication upto 132kV SS and above | Providing OPGW communication at 132kV SS and above |  | Ms.No:26, Dt:12.02.2018 |  | vide 10/18/2018-19 dt. 04.08.2018 | 197.85 |  | PFC | 120 Crs | PSDF (79.82Crs) | 2019-04-01 | 2025-03-01 |  | 22.664 | 81.146 Crs | 103.81 Crs | 51.9%
Sub-total-I | [16 empty] | 81.146 | 103.81
II. New schemes taken up during 2023-24
Sub-total-II
III. Non-plan schemes taken up during 2023-24
Sub-total-III
Grans Total I + II + III
Chief Engineer/Telecom
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please

## ABSTRACT
ABSTRACT
S.No. | Particulars | FY:2025-26(1st half - Apr- Sept) Actuals ) | FY:2025-26(2nd half - Oct- Mar) Projection | FY:2025-26 (Total) Projections | FY:2026-27 Projections
1 | The cost of Schemes Ongoing as on 31st March | 20.94 | 15.96 | 36.9 | Nil
2 | Total cost of New Schemes taken up during the year from 1st April | 1 | 6.4 | 7.4 | Nil
3 | Total cost of Non-plan schemes taken up during the year from 1st April
4 | Grand Total | 21.94 | 22.36 | 44.3 | Nil
Chief Engineer/Telecom

## CapEx 26-27 (3)
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2024-25 for Transmission Business filed with TGERC
Scheme wise details of Capital Expenditure proposed for Financial Year 2026-27
(In Crores)
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme maybe given) | Project Purpose (SI/SE/SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total TGERC approved Cost (in Cr) | Source of funds |  |  |  | Proposed Project Start Date DD-MM-YY | Proposed Project Completion Date DD-MM-YY | CWIP O.B. | FY:2025-26 |  |  | Projected expenditure for 2026-27 | Spill over Yearly Capital Expenditure projected for works taken up in or before 2025-26 (in Cr) |  |  | Total Cumulative Expenditure (in Cr) | Present Status of work
[9 empty] | TGTransco funds | Loan source | Loan Amount | Grants, if any |  |  |  | 1st Half (Apr-Sept) (Actuals) | 2nd Half (Oct-Mar) (Projections) | Total 25-26 (Projected) |  | 2026-27 | 2027-28 | 2028-29
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  |  |  | 17 | 18 | 19 | 20 | 21 | 22
I. Ongoing Schemes as on 01.04.2025
1 | T-18-01 | Implementation of OPGW based Reliable communication upto 132kV SS and above | Providing OPGW communication at 132kV SS and above |  | Ms.No:26, Dt:12.02.2018 |  | vide 10/18/2018-19 dt. 04.08.2018 | 197.85 |  | PFC | 118.03 | PSDF (79.82) | 2019-04-01 | 2025-03-01 |  | 20.94 | 15.96 | 36.9 | Nil | Nil | Nil | Nil
Sub-total-I | [15 empty] | 20.94 | 15.96 | 36.9
II. New schemes taken up during 2025-26
1 |  | Implementation of UNMS scheme. | [13 empty] | 1 | 4.4 | 5.4 | Nil | Nil | Nil | Nil
2 |  | Implementation of VOIP system. | [14 empty] | 2 | 2 | Nil | Nil
Sub-total-II | [15 empty] | 1 | 6.4 | 7.4
III. Non-plan schemes taken up during 2025-26
Sub-total-III
Grans Total I + II + III | [15 empty] | 21.94 | 22.36 | 44.3
Chief Engineer/Telecom
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please