**TRANSMISSION CORPORATION OF ANDHRA PRADESH LIMITED**

Sub: 2nd circuit stringing of 132kV DC/SC line from tapping point of Nidadavolu –Bhimavaram 132kV line to M/s Ravali Spinners Pvt. Ltd., and erection of 132kV DC/SC line from tapping point of Nidadavolu – Bhimavaram 132kV line to 132kV Tanuku 132kV substation –2ndAmendment to Administrative Approval - Issued.

TOO (CE Construction-II) MS. No.38 Date:27 /12/2013

Read this:

1. TOO (CE Construction-II) MS. No. 478 dated09/03/2012
2. TOO (CE Construction-II) MS. No. 198 dated 28/09/2012

APTRANSCO had approved scheme for extension of additional load of 3.2 MVA to M/s. Ravali Spinners Pvt. Ltd., Khanadavili Post, Tanuku, West Godavari District (Referred to as ‘the company’ henceforth) in addition to the existing CMD of 3.15 MVA total aggregating to CMD of 6.35 MVA at 132 kV Potential by erecting 132kV DC/SC line from Tanuku 132kV SS to the company with 132kV Bays at either ends on 25/02/2010. Accordingly, the works were taken up by the company by paying necessary development and supervision charges to APTRANSCO.

1. After erecting 8kM of 132kV DC/SC line from the Company end and also 132kV bays at the Tanuku 132kV SS and the Company end, erection of balance 2 kM of line is held up due to severe right of way problems. The company has requested APTRANSCO for permission to avail supplyby temporary arrangement.
2. APTRANSCO has accorded approval vide TOO cited above for executing the following works by collecting applicable scheme cost from the Company:

|  |  |  |  |
| --- | --- | --- | --- |
| Sl. No | Name of the work | Qty. | Amount (Rs.) |
| a) | Erection of 132kV DC/SC line from between location No. 74/1 and 75 of Nidadavolu 220 kV SS – Bhimavaram 132 kV SS line to Tanuku 132 kV SS | 2 kM | 7124000.00 |
| b) | 2nd circuit stringing of 132kV DC/SC line from tapping point of 132kV line from Nidadavolu 220 kV SS to Bhimavaram 132 kV SS to M/s Ravali Spinners | 8 kM | 6400000.00 |
|  | Total amount to be paid by M/s Ravali Spinners Pvt. Ltd. For APTRANSCO to take up the works: |  | **13524000.00** |

1. The Company has paid an amount of Rs. 1,35,24,000/- vide Demand Draft drawn on State Bank of India, Yellareddiguda, (Hyderabad) branch, bearing No. “488864” on 02/03/2012.
2. Revised administrative approval was accorded vide reference (2) cited above based on the increase in line length and new scheme approval procedures stipulated by APTRANSCO vide TOO MS. No. 20 dated 23/04/2012. The details of the revised administrative approval are as indicated below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| (i) | Erection of 132kV DC/SC line from crossing point of Nidadavolu –Bhimavaram 132kV line to Tanuku 132kV SS | 3 | kM | **13270000.00** |
| (ii) | 2nd circuit stringing of 132kV DC/SC line from tapping point of 132kV line from 220kV Nidadavolu SS to 132kV Bhimavaram SS to M/s Ravali Spinners | 8 | kM | 6400000.00 |
|  | **Total Estimated cost to be paid by M/s Ravali Spinners** | **19670000.00** |
|  |  |  |  |  |
|  | **Amount already Paid by M/s Ravali Spinners** |  |  | **13524000.00** |
|  |  |  |  |  |
|  | **Balance amount to be paid by M/s Ravali Spinners** |  |  | **6146000.00** |

1. Accordingly, the company was intimated to pay the balance amount of Rs. 61.46 Lakhs. However, the company has requested to communicate the revised amounts to be paid after adjusting the actual expenditure incurred towards the work of 2nd circuit stringing of 132kV DC/SC line indicated at (ii) above.
2. Actual expenditure incurred towards 2nd circuit stringing of 132kV DC/SC line from tapping point of 132kV line from Nidadavolu 220 kV SS to Bhimavaram 132 kV SS to M/s Ravali Spinners is arrived at based on the ERP system and the estimated rates for erection of 132kV DC/SC line are updated with the latest rates. The revised amounts are as indicated below:

|  |
| --- |
| *All financial figures in Rs. Lakhs* |
| Sl. No. | Name of the work | Estimated amount  | Amount paid by company | Actual Expn. incurred | Balance amount |
| (i) | Erection of 132kV DC/SC line from crossing point of Nidadavolu –Bhimavaram 132kV line to Tanuku 132kV SS(Estimate updated with latest material rates and SSR 2013-14 labour rates) | 143.03 | 71.24 | Works to be taken up | 71.79 |
| (ii) | 2ndcircuit stringing of 132kV DC/SC line from tapping point of 132kV line from 220kV Nidadavolu SS to 132kV Bhimavaram SS to M/s Ravali Spinners | 64.00 | 64.00 | 47.27 | -16.73 |
|  | **Net balance amount to be paid by the company for taking up the works** | **55.06** |

1. After careful consideration, APTRANSCO accords approval for erection of 132kV DC/SC line from crossing point of Nidadavolu –Bhimavaram 132kV line to Tanuku 132kV SSfor a total amount of Rs.143.03 Lakhs.
2. ”In exercise of the powers conferred under section 164 of the Electricity Act,2003 Central Act No.36, the Government of Andhra Pradesh, vide G.O.Ms.No.115 dated 07/10/2003, conferred upon the Transmission Corporation of Andhra Pradesh Limited, the Transmission licensee in the State of Andhra Pradesh, the powers for placing of the electric supply lines or electric plant for the transmission of electricity or for the purpose of telephonic or telegraphic communications necessary for the proper co-ordination of works that a telegraphic authority possessed under the provision of the Indian Telegraph Act, 1885 (Central Act 13 of 1885).”
3. The Chief Engineer/Zone/Visakhapatnam is authorised to take up the workutilising the materials available with APTRANSCO and duly following the departmental procedures in vogue. On completion of the works the actual expenditure incurred (including all applicable overheads) towards the erection of 132kV DC/SC line and 2nd circuit stringing indicated at paragraph (6) may be arrived at and the same may be communicated to the headquarters for truing-up with the company.
4. The order is issued with the concurrence of Chairman and Managing Director/ APTRANSCO vide Reg. No. 4433dated20/12/2013

**BY ORDER AND IN THE NAME OF**

**TRANSMISSION CORPORATION OF ANDHRA PRADESH LIMITED**

**s\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

  **Sd/-**

**DIRECTOR/PROJECTS**

To,

The Chief Engineer/Zone/Vizag, Visakhapatnam,

The Chief Engineer/Lift Irrigation, Vidyut Soudha, Hyderabad for arranging necessary materials.

Copy to:

The Executive Director/Planning, RAC & Reforms/Vidyut Soudha/Hyderabad.

The Chief Engineer/Construction-II, Vidyut Soudha, Hyderabad.

The Chief Engineer/Civil/Vidyut Soudha/Hyderabad.

The Chief Engineer/Power Systems/Vidyut Soudha/Hyderabad

The Executive Director (Finance) /Vidyut Soudha/Hyderabad.

The FA&CCA (CF)/Vidyut Soudha/Hyderabad

The Superintending Engineer/TLC/Visakhapatnam.

Personal Secretary to the Chairman & Managing Director.

Personal Secretary to the Joint Managing Director/(HRD &Comml)

DE (T) to the Joint Managing Director/Vigilance & Security.

Personal Secretary to the Director/Finance

Personal Secretary to Director/ Projects.

Personal Secretary to Director/ Transmission.

T.O.O Section.

*// FORWARDED BY ORDER //*

*ASST.DIVISIONAL ENGINEER/Elecl.*